## Clarif
No. | RFP Document Reference / Clause | Query or Clarification Requested by the Applicant | Reply of the Client | Amendment in the RFP Document is Required
1 | Section IV – Proposal Forms / Form EQU – Contractor’s Equipment / Specially Manufactured Equipment | Form EQU allows the Proposer to indicate “Specially Manufactured” as the source of key equipment. For certain specialized equipment that is not currently owned by the Proposer and is intended to be procured specifically for the Project upon award of the Contract, please confirm that a commitment letter issued by the manufacturer/equipment supplier, confirming its commitment to provide and make such equipment available for the execution of the Works, will be acceptable for the purposes of Form EQU. | Please refer to Form EQU. For equipment proposed as “Specially manufactured”, the Proposer shall provide details of the manufacture agreement specific to the Project and demonstrate that the equipment will be available for execution of the Works. A manufacturer/supplier commitment letter may be submitted as supporting evidence only where it evidences a project-specific manufacture/supply arrangement. No amendment is made to the RFP. | No
2 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel / Project Manager | The current requirement for the Project Manager requires experience as Project Manager of two contracts for the construction of railway systems. Considering that the Project mainly comprises major civil works such as tunnels, bridges, viaducts and route infrastructure, similar project management experience is also gained through large-scale transportation infrastructure projects. Accordingly, we kindly request the Employer to revise the requirement as follows: “including as Project Manager of two contracts for construction of transportation infrastructure projects (including railway, metro, motorway, highway, etc.), using FIDIC Yellow or FIDIC Gold Book Conditions of Contract.” | Please refer to Section III, Item 1.4. The requirement shall be applied as stated in the RFP. The Project Manager shall have 10 years of relevant project management experience, including experience as Project Manager of two contracts for construction of railway systems (including metro, light rail, tram, funiculars, etc.) using FIDIC Yellow Book or FIDIC Gold Book Conditions of Contract, and 15 years overall professional experience. Highway/motorway-only experience does not satisfy this specific requirement. No amendment is made to the RFP. | No
3 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities – Lot 4 / Activity 7 / Items 7.3 and 7.4 | In the Price Schedule for Lot 4, NATM Tunnel 19-C is listed twice under Items 7.3 and 7.4 with the same description. We understand that one of these items may have been included by mistake. Please confirm whether this is an error and provide the corrected Price Schedule, if necessary. | Please refer to Addendum No. 2, Amendment No. 1. | Yes
4 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities – Lot 4 / Activity 13 – DAAB | In the Price Schedule for Lot 4, Activity 13 is titled “DAAB”; however, the total row is stated as “TOTAL ACTIVITY 12”. We understand that this may have been written by mistake and should read “TOTAL ACTIVITY 13”. Please revise. | Please refer to Addendum No. 2, Amendment No. 2. | Yes
5 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 1.1.86 and 1.1.95 – Time for Completion and Milestones; Section VII – Employer’s Requirements / Clauses 4.9.4 and 4.26 | According to PCC Sub-Clause 1.1.95, the completion periods specified for Milestones 1 to 4 result in a total duration of 84 months (12 + 36 + 12 + 24 months). However, the overall Time for Completion of the Project is specified as 60 months. (Particular Conditions, Part A – Contract Data, 1.1.86 Time for Completion) Please clarify. | Please refer to Addendum No. 2, Amendments Nos. 3 and 4. Section IX, Contract Data Sub-Clause 1.1.95, read with Section VII, Employer’s Requirements Clauses 4.9.4 and 4.26. The overall Time for Completion remains 1,826 days (60 months) from the Commencement Date. The milestone due dates, measured from the Commencement Date, are: Milestone 1 – Design Completion by Month 12; Milestone 2 – Infrastructure Works Completion by Month 46 (the interval from Milestone 1 to Milestone 2 is 34 months); Milestone 3 – Superstructure Completion by Month 58 (12 months after Milestone 2); and Milestone 4 – Testing and Commissioning Completion by Month 60 (2 months after Milestone 3). The former 12 + 36 + 12 + 24-month sequence is not applicable. Testing of completed sections may begin before Milestone 3. Milestone 4 provides a defined two-month window for integrated system-wide testing, trial running and safety certification. The programme, delay damages under Sub-Clause 8.8 and KPIs under ER Clause 12.4 shall be assessed against these milestone dates. These dates do not extend the overall Time for Completion. The 730-day Defects Notification Period starts after Taking-Over and is separate from the Time for Completion. | Yes
6 | Section VII – Employer’s Requirements / Clause 5.8.2 – Key Works and Structures / Istanbul Airport Station | With reference to the Section VII – Employer’s Requirements/5.8.2. Key Works and Structures /Station Works: Istanbul Airport Station "As-built information relating to the completed station structure shall be made available as part of the tender dossier." We understand that this statement contains a clerical error and that the relevant drawings and documentation are to be developed and submitted by the Contractor during the Detailed Design stage. Please kindly confirm that our understanding is correct. | Please refer to Addendum No. 2, Amendment No. 9. | Yes
7 | Section IV – Proposal Forms / Schedule of Payments | We note that the Schedule of Payments, which is expected to define the payment basis and payment breakdown for the items included in the Lump Sum (LS) Pricing Schedule (Schedule of Priced Activities and Sub-activities), has not been provided in the Tender Dossier. Please clarify the applicable payment basis and provide the completed Schedule of Payments. | Please refer to Addendum No. 2, Amendment No. 12, Section IV, Schedule of Payments and Schedule of Priced Activities and Sub-activities, read with Section IX, Clause 14. The Schedule of Payments states that payment is made upon completion and acceptance of each deliverable/sub-activity specified in the Activity Schedule, including any permitted additional deliverables/sub-activities (up to three per Activity), at the lump-sum price quoted for that item. Statements and Interim Payment Certificates may be processed monthly under Clause 14, but an incomplete deliverable is not payable proportionally based solely on progress or quantities. The Contract remains lump-sum and does not become a remeasurement contract. Physical quantities and progress records may support verification of completion and acceptance, but they do not establish a percentage-based payment for an incomplete deliverable or a remeasurement basis. | Yes
8 | Section I – Instructions to Proposers (ITP) / ITP 4.3; Section II – Proposal Data Sheet (PDS) / ITP 1.1 | "4. Eligible Proposers 4.3 A firm that is a Proposer (either individually or as a JV member) shall not participate in more than one Proposal, except for permitted alternative Proposals. This includes participation as a subcontractor in other Proposals. Such participation shall result in the disqualification of all Proposals in which the firm is involved. A firm that is not an individual Proposer or a JV member in a Proposal may participate as a subcontractor in more than one Proposal." Thus, our question is that a bidder (not a subcontractor) can be included in different Jv structures to give different bids for one or more lots? That is, a bidder or proposer can make a bid for one or more lots under different Jv structures or not? We would be pleased if you could clarify this question. | Please refer to PDS ITP 1.1 and ITP 4.3. A Proposer may submit a Proposal for one or more Lots. However, a firm participating as an individual Proposer or as a JV member shall not participate in more than one Proposal for the same lot. Accordingly, the same firm may not participate in different JV compositions through separate Proposals for the same lot. No amendment is made to the RFP. | No
9 | Section III – Evaluation and Qualification Criteria / Clause 3.2 – Average Annual Construction Turnover | • Regarding the construction turnover requirement, could you please clarify whether the “Construction Revenue” figure presented in the Independent Consolidated Audit Financial Report can be directly utilized to fulfill this criterion, and if so, whether Bidders will subsequently be required to substantiate this amount with certified payments (i.e. invoice) ? • Furthermore, Under applicable inflation accounting rules, the restated 2024 revenue presented in the 2025 Audited Financial Report is updated upwards compared to the figure in the original 2024 report. In this regard, could you please clarify whether Bidders are permitted to utilize the restated 2024 construction revenue figure from the 2025 Audited Financial Report instead of the original 2024 report, and if so, whether this restated figure should be converted into foreign currency using the exchange rate as of December 31, 2024 or December 31, 2025? • In the event that the Independent Audit Financial Report is not accepted and certified payments (i.e. invoice) are required, could you please clarify whether certified payments (i.e. invoice) generated from works executed abroad can be utilized to fulfill the construction turnover requirement? | Please refer to Section III, Item 3.2 and the monetary conversion provisions at the beginning of Section III. Average Annual Construction Turnover shall be calculated on the basis of total certified payments received for contracts in progress and/or completed during 2021–2025, divided by five years. Audited “construction revenue”, including a restated audited revenue figure, does not replace the basis defined under Item 3.2. Amounts for each year shall be converted using the exchange rate prevailing on the last day of the respective calendar year. Certified payments received under eligible construction contracts executed outside Türkiye may be included, subject to satisfactory supporting evidence. No amendment is made to the RFP. | No
10 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Bridge Experience | • Regarding the qualification criteria for bridge experience, could you please clarify whether dual-carriageway highway bridges built as structurally independent structures can be counted separately toward the total required length; specifically, if a 300-meter dual-carriageway bridge consisting of two distinct 300-meter structures (bound and unbound) can be evaluated as a total cumulative length of 600 meters? | Yes. For the purpose of the bridge/viaduct key activity under Section III, Item 4.2(b), the lengths of structurally independent qualifying bridge structures executed under the same qualifying contract may be aggregated. Accordingly, two separate 300 m bridge structures may be considered as a total of 600 m, subject to satisfactory documentary evidence. No amendment is made to the RFP. | No
11 | Section II – Proposal Data Sheet (PDS) / ITP 1.1; Section I – Instructions to Proposers (ITP) / ITP 4.3 | • Could you please clarify whether a Joint Venture structure established to bid for one Lot can be modified when bidding for another Lot—specifically, whether it is permissible to submit a bid for Lot 2 with a 3-member Joint Venture and for Lot 3 with a 2-member | Please refer to Answer No.8. | No
12 | Section II – Proposal Data Sheet (PDS) / ITP 16.1; Section IV – Proposal Forms / Appendix to Proposal – Tables A, B and C | According to ITB 16.1 of the Bid Data Sheet, we understand that the bid currency is Turkish Lira (TRY). However, as Table B – Foreign Currency is also included in the bidding documents, we understand that bidders may submit bids comprising multiple currencies. Could you please confirm whether bids may be submitted in a combination of Turkish Lira and one or more foreign currencies? | Please refer to PDS ITP 16.1. Proposal prices in the Schedules of Priced Activities and Sub-activities shall be quoted entirely in Turkish Lira in accordance with Alternative A. Where foreign-currency expenditure is expected, the Proposer may indicate up to three foreign currencies as payment requirements in Appendix to Proposal – Table C, in accordance with ITP 16.1. No amendment is made to the RFP. | No
13 | Section III – Evaluation and Qualification Criteria / Clauses 4.2(a) and 4.2(b) | With respect to the qualification requirements under Section III, Clause 4.2(a) that the following criteria: “(i) A minimum number of similar contract(s) specified below have been satisfactorily and substantially5 completed as a prime contractor, joint venture member6, management contractor or Subcontractor between 1st January 2011 and bid submission deadline. Similar contracts are defined as contracts for the construction of linear transport projects involving: (a) Infrastructure works — including, inter alia, earthworks, tunneling, bridges, and viaducts — carried out under contracts for light rail, metro, mainline railway, or highway projects; AND (b) Railway superstructure works — including, inter alia, tracklaying, ballasting (or slab construction), rail welding, fastening installation, turnout assembly and electrification— carried out under contracts for light rail, metro, and/or mainline railway projects. Both (a) and (b) must be demonstrated. They may be evidenced by the same contract or by separate contracts, provided that all contracts submitted fall within the value thresholds specified below.” However, we understand that these specific requirements do not apply to Clause 4.2(b), and that, for Clause 4.2(b), it is sufficient to demonstrate experience in a railway project involving tunnelling, provided that the other requirements specified under Clause 4.2(b) are met. Could you kindly confirm whether our understanding is correct? | Confirmed. Please refer to Section III, Items 4.2(a) and 4.2(b). The statement under Item 4.2(a) that both infrastructure works and railway superstructure works must be demonstrated applies to Item 4.2(a). Items 4.2(a) and 4.2(b) are separate qualification criteria. The definition of “similar contracts” under Item 4.2(a) is not an additional requirement under Item 4.2(b); compliance with Item 4.2(b) shall be assessed against the key activities and conditions expressly stated under that Item. No amendment is made to the RFP. | No
14 | Section III – Evaluation and Qualification Criteria / Clauses 4.2(a), 4.2(b) and 4.2(c) / Item 4 – Multiple Contracts; Section I – Instructions to Proposers (ITP) / ITP 40.3 | We understand that the same contract cannot be used to satisfy the qualification requirements of different Lots. However, within a single Lot, we understand that the same contract may be used for each clauses to demonstrate compliance with Clauses 4.2(a), 4.2(b) (Design, Tunnel and Route Length requirements) and 4.2(c), provided that the contract satisfies all applicable qualification criteria. Could you please confirm whether this understanding is correct? For example, for Lot 1, can a single contract be used more than once to satisfy all of the each following requirements ? • Design: Experience in the design of railway systems (including tunnels) with a route length of at least 20 km, under a single contract. • Length: Experience in the construction of railway line with a route length of at least 20km under a single contract. • 4.2(c) Specific Experience in managing ES aspects | Within a single Lot, the same reference contract may be used to demonstrate more than one qualification criterion, provided that the contract independently satisfies each applicable requirement and the required supporting evidence is submitted. For multiple Lots, please refer to Section III, Item 4, which expressly requires the contracts referenced under Item 4.2(a) for each Lot to be different. The remaining cumulative requirements shall be applied as stated in Section III. No amendment is made to the RFP. | No
15 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) | With respect to Item 4.2(b), would a railway rehabilitation project be considered acceptable for demonstrating the required experience? | A railway rehabilitation contract may be considered only for satisfying the design requirement under 4.2.b. only to the extent that the contract demonstrably includes the specific key activity and minimum quantity required under Section III, Item 4.2(b). Rehabilitation or maintenance experience, by itself, does not satisfy a requirement for construction of the specified railway line, tunnel, bridge/viaduct or other key activity. No amendment is made to the RFP. | No
16 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Railway System Design Including Tunnels | Regarding the requirement, “Experience in the design of railway systems (including tunnels) with a route length of at least 20 km, under a single contract,” would a project that includes cut-and-cover tunnels be considered compliant with the requirement for “including tunnels”? | Yes. For the railway-system design criterion under Section III, Item 4.2(b), the expression “including tunnels” does not specify a particular tunnel construction method or a separate minimum tunnel length. A qualifying reference including cut-and-cover tunnel works may therefore satisfy this element, provided that all other requirements of the criterion are met. No amendment is made to the RFP. | No
17 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Railway Line Route Length | We kindly request a clarification regarding the following technical qualification criterion specified in the tender documents: "Experience in the construction of railway line with a route length of at least 20 km under a single contract". Under a single contract, we have successfully completed a project that comprises 10 km of high-speed railway line and 10 km of suburban railway line constructed parallel to each other within the same 10 km geographical corridor (route). While the total length of the constructed physical tracks and infrastructure amounts to 20 km, the total geographical route distance is 10 km. Given this layout, would our work experience certificate be considered compliant and sufficient by the Administration to fulfill the minimum 20 km "route length" requirement? | For Section III, Item 4.2(b), “route length” means the geographical length of the railway alignment, irrespective of the number of tracks. The lengths of parallel tracks within the same corridor shall not be added together. | No
18 | Section III – Evaluation and Qualification Criteria / Item 4 – Multiple Contracts; Section I – Instructions to Proposers (ITP) / ITP 40.3 | We respectfully request clarification regarding the award methodology applicable to Proposers submitting proposals for multiple lots under this procurement, in accordance with Section III, Item 4 (Multiple Contracts) and ITP 40.3. To illustrate the concern with a concrete example: assume a Proposer (or Joint Venture, with a fixed and identical membership structure across all lots) satisfies the individual qualification criteria for two of the four lots under this RFP on a standalone basis, and achieves the highest evaluated score in both of those lots. However, the same Proposer does not meet the cumulative (aggregate) qualification thresholds — under items 3.1 (Financial Capability), 3.2 (Average Annual Construction Turnover), 4.2(a) (Specific Construction & Contract Management Experience), and 4.2(b) (Key Activities) of Section III — that would be required for the combination of those two lots taken together. In such a scenario, where the Proposer achieves the highest evaluated score in more than one lot individually, but does not meet the combined qualification requirements applicable to holding more than one lot simultaneously, we respectfully seek clarification on the following matters: • Will the Proposer be disqualified from the tender in its entirety as a result of not meeting the cumulative qualification thresholds for the combination of lots, or will the Proposer instead only be precluded from being awarded more than one lot, while remaining eligible for the award of a single lot? • In the event that the Proposer is not disqualified from the tender under the above scenario, and is instead limited to the award of a single lot notwithstanding having achieved the highest evaluated score in more than one lot, how will the Employer determine which specific lot shall be awarded to that Proposer? We kindly request the Employer to confirm whether a defined order of priority, methodology, or set of criteria will be applied among the lots in question for this purpose, and if so, to specify such criteria. | Please refer to Section III, Item 4 – Multiple Contracts. A Proposer is not disqualified from the procurement solely because it does not meet the cumulative qualification requirements for a particular combination of Lots. Where a Proposer has the highest evaluated score for individual Lots but is not qualified for the combination, award shall be determined on the basis of the highest total score for a combination of Lots for which the Proposers are qualified. No separate Lot-priority order is established in the RFP. No amendment is made to the RFP. | No
19 | Section II – Proposal Data Sheet (PDS) / ITP 17.5; Section III – Evaluation and Qualification Criteria / Items 3.2, 4.1(a) and 4.2(b) | ITP 17.5 and the corresponding PDS entry list the parts of the Works for which Proposers are permitted to propose Specialized Subcontractors, currently limited to: Line Laying, Ballast Paving, Rail Welding, Cabling, Ground Improvement, Reinforced Concrete Works, Earthworks, and Construction of Bridge. We kindly request the Employer to clarify whether "Design" could also be added to this list of Specialized Subcontractor categories. Given the scale and complexity of the design scope under this Design & Build contract, allowing the specific design experience of a Specialized (Design) Subcontractor to be considered in the assessment of the Proposer's qualifications would enable Proposers to strengthen their technical capacity through specialized design partners while maintaining full responsiveness to the Employer's Requirements. Could the Employer confirm whether this addition is possible, or clarify the rationale for excluding design from the current list? | The design experience cannot be met by a Specialized Subcontractor. . A design consulting firm may participate as a JV member to perform the design services. The revised Section III provisions exempt a JV member proposed for design services from the Average Annual Construction Turnover requirement in Item 3.2 and the 15-year general construction experience requirement in Item 4.1(a); instead, that design JV member must have at least 10 years of experience in design of works under railway projects. Item 4.2(b) continues to apply to the Proposer as a Single Entity or in case of JV to all members combined. The corresponding provisions in Addendum No. 2, Amendment No. 36 and PDS ITP 17.5 shall be read consistently. | Yes
20 | Section III – Evaluation and Qualification Criteria / Clause 3.2 – Average Annual Construction Turnover / Monetary Conversion Provisions | We understand that the Average Annual Construction Turnover requirement under Sub-Factor 3.2 is intended to be evidenced based on invoiced amounts (certified payments received). We would like to note that Proposers (whether domestic or foreign) whose contracts are predominantly executed and invoiced outside Turkiye typically issue invoices directly in USD or other hard currencies, whereas Proposers executing contracts within Turkiye necessarily invoice in Turkish Lira. Given the currency volatility experienced in Turkiye over the reference period (2021-2025), reliance on invoice-based figures converted from TRY may not fairly reflect the actual financial capacity of Proposers operating domestically, and may create an unintended disparity between Proposers based on the currency of invoicing rather than actual turnover performance. We would therefore request the Employer to clarify whether audited construction revenue figures (as reported in the Proposer's audited financial statements, consistent with the audited financial statements already required to be submitted under this same criterion) could be used as the basis for demonstrating Average Annual Construction Turnover, instead of invoice-based figures, in order to ensure a more accurate and equitable comparison across Proposers. Should the Employer confirm that invoice-based figures are to be maintained as the basis for this criterion, we would request the Employer to reconsider the exchange rate conversion methodology. As currently specified, amounts are to be converted using the exchange rate prevailing on the last day of the respective calendar year. We consider that this approach may not accurately reflect the actual USD value of revenue earned throughout the year, particularly in a high-volatility currency environment, since a single year-end rate does not correspond to the rates actually prevailing at the time each invoice was issued and payment was received. We would therefore request the Employer to clarify whether the exchange rate applicable on the date of each invoice could instead be used for currency conversion purposes, as this would more accurately reflect the actual USD-equivalent turnover generated by the Proposer throughout the relevant year. | The request is not accepted. Please refer to Section III, Item 3.2 and the monetary conversion provisions at the beginning of Section III. Average Annual Construction Turnover shall be calculated using certified payments received for contracts in progress and/or completed during 2021–2025. The exchange rate prevailing on the last day of the respective calendar year shall be used for each year. Invoice-date exchange rates shall not be used for this criterion. No amendment is made to the RFP. | No
21 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Lot 1 Railway-System Design | “For Lot 1 requires experience in the design of railway systems（including tunnels）with a route length of at least 20 km under a single contract. ”Please kindly clarify: 1.whether the 20 km may be calculated by aggregating the track-kilometres of both the up and down lines? 2.whether the Proposer may nominate a qualified design company that will not participate as a JV member but will act as a design subcontractor for the Works, and rely on such company’s relevant experience to satisfy this qualification requirement? If permitted, please specify the required subcontracting commitment, contract experience, and supporting documents. 3.Please also confirm whether such design experience must include track, power supply, and electrification system design, or whether railway alignment and civil works design experience,including tunnels are sufficient. | 1. The 20 km route length is the geographical length of the railway alignment; parallel track-kilometres are not added together, irrespective of the number of tracks. 2. Qualification Criteria 4.2(b) continues to remain applicable to the Proposer as a Single Entity or in case of JV to all members combined. A Specialized Subcontractor’s experience cannot be used to satisfy this criterion. A design consulting firm may join the JV; the revised Items 3.2 and 4.1(a) will provide the design-member exception, requiring at least 10 years of railway-project design experience instead of the construction turnover and 15-year general construction experience requirements. 3. Item 4.2(b) does not impose a separate power-supply/electrification experience requirement under the railway-line construction criterion. The reference must demonstrate construction of the required railway line and associated railway infrastructure over the required route length. Please refer to Addendum No. 2, Amendment No. 36. | Yes
22 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Lot 1 TBM Tunnel | For Lot 1 requires experience in the construction of a 20 km of single-bore TBM tunnels for transportation purposes under a single contract. Please kindly clarify: 1. whether, where one contract includes several separate TBM tunnel sections, their respective single-bore excavation lengths may be aggregated to meet the 20 km requirement, or whether one continuous tunnel must independently have a minimum length of 20 km? | The required 20 km need not constitute one physically continuous tunnel, provided that the qualifying single-bore TBM tunnel sections were executed under the same single contract and the total qualifying length under that contract is at least 20 km. No amendment is made to the RFP. | No
23 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Lot 1 Railway Line | For Lot 1 requires experience in the construction of at least 20 km of railway line under a single contract. Please kindly clarify: 1. whether the 20 km may be calculated by aggregating the track-kilometres of both the up and down lines; whether railway line construction experience from light rail projects is acceptable; and whether the referenced experience must include power supply, electrification, and other railway system works, or whether completion of trackwork and associated railway infrastructure works is sufficient to meet the requirement. | 1. No. “Route length” is the geographical length of the railway alignment and is not calculated by adding parallel track-kilometres, regardless of the number of tracks. 2. Mainline railway, metro and light-rail construction experience may be considered, subject to the nature, quantity and single-contract requirements of Section III, Item 4.2(b). 3. Item 4.2(b) does not state a separate power-supply or electrification experience requirement under the railway-line construction criterion. The reference must demonstrate construction of the required railway line and associated railway infrastructure over the required route length. Read consistently with Answers 17 and 865. | No
24 | Section IX – Particular Conditions / Contract Data – Subcontracting Cap; Section I – Instructions to Proposers (ITP) / ITP 17.4 and 17.5 | Provides that the maximum accumulated value of subcontracted work shall not exceed 30% of the Accepted Contract Amount. Please kindly clarify: 1.whether this limit applies to all subcontracted work during contract implementation, including ordinary subcontracting, specialized subcontracting, and design subcontracting, or only to the Specialized Subcontractors listed under ITP 17.5, and whether the value of all such subcontracted work shall be aggregated. 2. In addition, if Employer-instructed variations, changes, or additional works cause the subcontracted value to exceed 30%, Please kindly clarify whether such subcontracted work remains subject to the limit, whether the Contractor may exceed the limit with the prior approval of the Employer or the Engineer, and the applicable approval and handling procedure. | Please refer to PDS ITP 17.4 and Contract Data Sub-Clause 4.4(a). The maximum allowable accumulated value of subcontracted work is 30% of the Accepted Contract Amount. This limit applies to the aggregate subcontracted work and is not limited to the Specialized Subcontractors listed under ITP 17.5. A Variation or additional work does not, by itself, waive the contractual limit; any change to that limit would require a formal amendment of the Contract. No amendment is made to the RFP. | No
25 | Section II – Proposal Data Sheet (PDS) / ITP 1.1; Section III – Evaluation and Qualification Criteria / Item 4 – Multiple Contracts; Section I – Instructions to Proposers (ITP) / ITP 40.3 | Please confirm whether the same independent Proposer (or the same Joint Venture/Consortium) that bids for multiple Lots simultaneously and meets all eligibility and tender requirements may be awarded multiple Lots. If there is any limitation on the number of Lots that can be awarded to a Proposer or Joint Venture, Please kindly provide the relevant provisions and conditions. | Yes. Please refer to PDS ITP 1.1 and Section III, Item 4 – Multiple Contracts. A Proposer may be awarded more than one Lot, provided that it is the Most Advantageous Proposer for the relevant combination and satisfies the cumulative qualification requirements applicable to that combination. The RFP does not specify a maximum number of Lots that may be awarded to one qualified Proposer. No amendment is made to the RFP. | No
26 | Section I – Instructions to Proposers (ITP) / ITP 17.5; Section II – Proposal Data Sheet (PDS) / ITP 17.5; Section III – Evaluation and Qualification Criteria / Clause 4.2(b) | Section III 4.2(b) requires experience in railway system design under a single contract with a route length of no less than 20 km involving tunnels. Nevertheless, design is not included in the scope of Specialized Subcontractor set out in PDS ITP 17.5. Please confirm: 1. Where the Bidder proposes to engage a professional design subcontractor to carry out the design works for Lot 1, whether the relevant past experience of such design subcontractor may be utilised to meet the qualification requirement of Clause 4.2(b). If yes, Please kindly clarify its reporting identity, applicable forms and requirements for supporting documents. | Please refer to Answer No.19. Please refer to Addendum No. 2, Amendment No. 36. | Yes
27 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 1.1.86 and 1.1.95; Section VII – Employer’s Requirements / Chapter 5 / Clause 5.1 | Contract Data 1.1.86 stipulates that the Time for Completion is 1826 days, whereas Clause 1.1.95 sets four milestones at 12 months, followed by 36 months, then 12 months and further 24 months, totalling approximately 84 months in sequence. Please confirm： 1. the correct calculation method for the overall contract period and each milestone of Lot 1, and specify whether subsequent milestone periods shall be calculated cumulatively from the Commencement Date, or run consecutively from the completion date of the preceding milestone. | Please refer to Answer No.5. Please refer to Addendum No. 2, Amendments Nos. 3 and 4. | Yes
28 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 1.1.95; Section VII – Employer’s Requirements / Clause 5.1 and Clause 7.5 – Design Freeze Milestones | Contract Data describes Milestone 1 as “Detailed Design Completion — 12 months from the Commencement Date”. Meanwhile, ER 5.1 provides that the design period shall start from the Effective Date, and the 12-month milestone is mainly defined as completion of construction-ready design and freeze of alignment and principal structures. Please confirm: 1. What is the correct starting point for this milestone? Whether it requires full completion of discipline-wide detailed design together with approvals from the Engineer and relevant third-party authorities, or only the design freeze for alignment, principal structures and work packages sufficient for construction commencement? 2. What are the corresponding acceptance documents and assessment criteria? | Please refer to Addendum No. 2, Amendment No. 3, Contract Data Sub-Clause 1.1.95 and ER Sub-Clause 4.26. Milestone 1 is due 12 months from the Commencement Date. The milestone due dates measured from the Commencement Date are Month 12 (M1), Month 46 (M2), Month 58 (M3) and Month 60 (M4). The separate design period stated in ER Clause 5.1 does not change the contractual milestone calculation. Milestone 1 covers the design deliverables required for the relevant design freeze/completion under the Employer’s Requirements and approved Design Submission Schedule. | Yes
29 | Section VII – Employer’s Requirements / Chapter 4 – Multi-Contract Structure and Interface Management / Clause 4.5; Chapter 5; Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities / Activity 10.6; Section VII – Employer’s Requirements / Annex L – Signaling and Telecommunication System Technical Specification | Lot 2 covers Signaling and Telecommunication works. Nevertheless, the ER and price schedule of Lot 1 still include SCADA, telecommunication works as well as interfaces with Lot 2. Please confirm the design boundary of Lot 1 Contractor for signaling, telecommunication and SCADA systems: 1. which systems shall be subject to detailed design, supply and installation by Lot 1, and which ones only require civil-works reservation, interface data provision and coordination support? Please kindly provide or confirm the applicable interface responsibility matrix. | Please refer to Section VII, Employer’s Requirements, Clauses 5.1 and 5.3.5. Package 2 is a separate contract for Signaling, Telecommunication and Supporting Systems and is not part of this tender. The Contractors under Package 1 remain responsible for the civil provisions, interfaces and the electrification/traction-power/SCADA and other systems expressly included within their respective Lot scope, and shall coordinate with the Package 2 Contractor in accordance with the interface requirements. No amendment is made to the RFP. | No
30 | Section IV – Proposal Forms / Schedule of Payments / Activity 1.1–1.7 | The Schedule of Payments under Section IV does not set out specific payment arrangements, whereas each design item under Activity 1 is priced on the basis of “submission and approval/acceptance”. Please confirm： 1.the measurement and payment mechanism for design costs: whether phased measurement by discipline or work package (upon submission, review and approval) is permitted, or payment shall only be made upon final approval of the entire deliverable. 2. In case of review delays by the Engineer or third-party authorities attributable to causes other than the Contractor’s liability, how shall the completed design outputs be measured? | For each of the activities, the Proposer has the option to add up to 3(three) more sub-activities to the existing sub-activities indicated below. Any entitlement arising from delay in review or approval by the Engineer or third-party authorities shall be governed by the applicable Conditions of Contract. | No
31 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities (Lots 1–4), Activity 1 – Design Completion (As-Built Documentation); relevant Final Acceptance activities | Both Activity 1.7 and 12.2 require submission and acceptance of discipline-wide As-Built Documentation. Please confirm： 1. the differences between these two deliverables in terms of content, submission timing and acceptance criteria, and whether separate pricing shall be included in the bid proposal. | Please refer to Addendum No. 2, Amendment No. 5. | Yes
32 | Section VII – Employer’s Requirements / Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station | The tender documents provide the conceptual-design scheme for Sabiha Airport Station under drawing Annex A3 Architecture folder. Drawing AYGM-INR-ARC-SGA-001 indicates an additional metro line in the vicinity of the station, yet this metro line is not reflected in other cross-section drawings. Relevant data for this metro line, as well as information on surrounding planning, existing utilities and structures around Sabiha Airport Station are missing. 1. Such data gaps impose significant constraints on the development of the station scheme and construction-organisation studies. Could you please supplement and provide the above-mentioned information? | Please refer to Section VII, Employer’s Requirements and the Reference/Conceptual Design documents. The Employer has provided the tender-stage information available for Sabiha Gökçen Airport Station. The Contractor shall verify existing and planned infrastructure, utilities, structures and interfaces and shall carry out the surveys, investigations and coordination required for its Detailed Design and construction methodology. No additional information is issued through this clarification. No amendment is made to the RFP. | No
33 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report; Annex E1 – Design Technical Specification | In the conceptual design furnished in the tender documents, most horizontal-curve radius adopt 1500 m. However, Annex E1-Design Technical Specification specifies that the absolute minimum curve radius for the main line operating at 160 km/h shall be 2000 m. The curve-radius issue shall be further verified combined with the speed-profile calculation. Nevertheless, the tender documents do not contain any train-operation calculation data, hence it is impossible to identify whether section-specific speed-restriction conditions exist. 1. Please kindly provide the relevant train-operation calculation documents, whether alignment-radius adjustments shall be taken into account at the bid-preparation stage. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. The design requirements in the revised Annex E1 govern the relevant geometry; the conceptual alignment shall be verified and developed in accordance with the RFP and its applicable design requirements. Please also refer to the separate amendment to Annex B1 Clause 4.1.4.1 under Amendment No. 31. | Yes
34 | Section VII – Employer’s Requirements / Annex K – Tunnel Electromechanical Works Technical Specification; Annex D – General Technical Specification / EIA Appendix 8 | According to Annex K Tunnel MEP Technical Specification, Lot 1 shall have four shafts in total. However, the excavation-quantity estimation report (Appendix 8 of the EIA document referenced in Annex D) indicates ten shafts. There exists a discrepancy between these two documents. Please kindly clarify which version shall prevail. | Please refer to Section VII, Employer’s Requirements and Annex K. The requirements of Annex K and the Employer’s Requirements shall govern. Quantities stated in the EIA documents and other reference/estimation documents are provided for reference and do not amend the contractual requirements of Annex K. Proposers shall prepare their Proposals accordingly. No amendment is made to the RFP. | No
35 | Section VII – Employer’s Requirements / Annex C – Site Information | ANNEX C – SITE INFORMATION provides very limited hydrogeological information of borehole and test data. Such data constraints impose limitations on structural design and TBM equipment selection studies. 1. Please furnish more detailed geological and hydrogeological data to support equipment selection and relevant design activities adequately. | Please refer to Annex C and Section VII, Employer’s Requirements. The site/geotechnical information provided by the Employer is tender-stage reference information. The Contractor is responsible for reviewing and verifying the available information and for carrying out the additional geological, geotechnical and hydrogeological investigations required for its Detailed Design and equipment selection. No additional data is issued through this clarification. No amendment is made to the RFP. | No
36 | Section VII – Employer’s Requirements / Lot 1 / Site Information and Third-Party Interface Requirements – Military Restricted Zone | According to preliminary site investigation, the section from the starting point of Lot 1 up to the connecting- link junction lies within a military restricted zone. 1. Please kindly provide the exact boundary of this military restricted zone together with permitted working-condition requirements. To verify the constructability of the engineering design and construction scheme, and to assess whether adjustments to design options such as alignment and elevation shall be considered. | Please refer to ITP 7.2 and the Employer’s Requirements. Proposers shall prepare their Proposals on the basis of the tender information made available, the permitted site visit and their own assessment of the Site, while complying with all applicable security and access restrictions imposed by the competent authorities. No amendment is made to the RFP. | No
37 | Section IV – Proposal Forms / Form FIN-3.4 – Current Contract Commitments | Please clarify whether the Proposer is required to provide information of all contracts on current commitments, or the Proposer may at its own discretion, to submit contract information only for those are similar in scale and nature comparable to the present Project？ | Please refer to Form FIN-3.4. The Proposer and each JV member shall provide information on all current commitments described in the Form, including contracts awarded, contracts for which a letter of intent or acceptance has been received, and contracts approaching completion for which an unqualified full completion certificate has not yet been issued. The information is not limited to contracts similar in scale or nature to the Project. No amendment is made to the RFP. | No
38 | Section IV – Proposal Forms / Daywork Schedule | The Section IV Proposal Forms Table of Forms contain daywork schedules, but without corresponding form. Please confirm if its missing or not applicable to this project？ | Please refer to Addendum No. 2, Amendment No. 6. | Yes
39 | Section IV – Proposal Forms / Schedule of Payments | The Section IV Proposal Forms Table of Forms contain Schedule of Payments, but no corresponding form is provided. Please confirm if its missing or not applicable to this project？ | Please refer to Answer No.7. Please refer to Addendum No. 2, Amendment No. 12. | Yes
40 | Section VII – Employer’s Requirements / Annex D – General Technical Specification / Clause A.2.2.40 | Annex D General Technical Specification A.2.2.40 specifies the temporary facilities that the contractor should provide to the Employer and Engineer's Personnel. Is the required number and area of those facilities based on the entire project, or should this applied separately for each Lot ? | Please refer to Annex D, General Technical Specification, Clause A.2.2.40. The requirements for temporary facilities shall apply to each Lot/Contract. Each Contractor shall provide the facilities required for the Employer’s and Engineer’s Personnel for the execution of its respective Contract, unless otherwise instructed or agreed by the Employer. No amendment is made to the RFP. | No
41 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Lot 4 TBM Tunnel | “ For Lot 4 requires -Experience in the constructionof a 10 km (single-bore) TBMtunnel for transportation purposes, under a singlecontract. ” Please kindly clarify: 1. if one contract includes several separate TBM tunnel sections, their respective single-bore excavation lengths may be aggregated to meet the 10 km requirement, or whether one continuous tunnel must independently have a minimum length of 10 km. | The required 10 km need not constitute one physically continuous tunnel, provided that the qualifying single-bore TBM tunnel sections were executed under the same single contract and the total qualifying length under that contract is at least 10 km. No amendment is made to the RFP. | No
42 | Section I – Instructions to Proposers (ITP) / ITP 19.8 and ITP 4.1 – JV Proposal Security | ITP 19.8 stated that，the Proposal Security or the Securing Declaration of a JV shall be in the name of the JV that submits the Proposal. If the JV has not been legally constituted at the time of proposal submission, the Proposal Security or theSecuring Declaration shall be in the names of all future members as named in the letter of intent referred to in ITP 4.1. If the JV has not been legally constituted into a legally enforceable JV at the time of submission of Proposals, Will the Proposal Security can be issued by each party in the JV respectively according to the proportions specified in the JV agreement ? | No. Please refer to ITP 19.8. Where the JV has not been legally constituted at the time of Proposal submission, the Proposal Security shall be in the names of all future JV members as named in the letter of intent. Separate Proposal Securities issued individually by the JV members in proportion to their JV shares do not satisfy ITP 19.8. No amendment is made to the RFP. | No
43 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / Lot 4 Tunnel 19 and Tunnel 19-A | Lot 4's tunnel-19 are divided into three sections: Tunnel 19 (TBM section), Tunnel 19-A (NATM section), and Tunnel 19-B (TBM section), with each section being continuously connected. The existing conceptual design drawings for Tunnel 19-A (NATM) do not show the construction work area layout. Please kindly clarify： 1. whether there are any special design constraints for this section, or if there are any omissions in the drawings. | Please refer to the Employer’s Requirements and the conceptual/reference drawings. The RFP does not prescribe a separate construction work-area layout for Tunnel 19-A. The Contractor shall develop the construction methodology, access arrangements, temporary works and work areas necessary for the NATM section as part of its Design-Build obligations, subject to the Contract requirements and approvals. No amendment is made to the RFP. | No
44 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / TBM Launch and Reception Portals | Please kindly clarify as the current information does not provide conceptual diagrams of the TBM tunnel's starting and arriving portal structures. | Please refer to the Employer’s Requirements. TBM launch/reception portals, shafts and associated temporary works required for the Contractor’s construction methodology shall be developed by the Contractor as part of its Design-Build obligations, unless a permanent structure is expressly defined in the Employer’s Requirements. No additional conceptual drawings are issued through this clarification. No amendment is made to the RFP. | No
45 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings; Annex C – Site Information / Alignment Discipline and Existing Structures | Kindly ask if there are demolition and relocation survey schedule along the alignment and information on the demolition or relocation of major buildings and structures | Please refer to Section VII, Employer’s Requirements, Clause 11.10 and the Resettlement Framework. Statutory expropriation, compensation and preparation/implementation of the RP/LRP remain the responsibility of the Employer. Preliminary lot-based expropriation parcel information is provided in Annex 3 of the Resettlement Framework and is tentative and indicative. The Contractor shall provide the design and construction information required for the Employer to update and implement the applicable land acquisition/resettlement instruments. No separate demolition/relocation survey schedule is issued through this clarification. No amendment is made to the RFP. | No
46 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification; Annex C – Site Information / Hydrological Data | Kindly ask if there are meteorological and hydrological data along the alignment (design flood level, scour depth, flow velocity, etc. at each bridge site) | Please refer to Annex C and the Employer’s Requirements. The Employer has provided the tender-stage meteorological, hydrological and site information available. The Contractor shall carry out the hydrological/hydraulic studies, site-specific investigations and authority coordination required for the Detailed Design. No additional bridge-by-bridge hydrological dataset is issued through this clarification. No amendment is made to the RFP. | No
47 | Section VII – Employer’s Requirements / Annex C – Site Information; Annex F – Civil Works (Infrastructure) Technical Specification / Subgrade and Land Status | Please kindly clarify the land status and attributes along the alignment | Please refer to Section VII, Employer’s Requirements, Clause 11.10 and Annex 3 of the Resettlement Framework. The preliminary lot-based expropriation parcel information is tentative and indicative and may be revised following finalization of the Detailed Design. Statutory expropriation and compensation remain the responsibility of the Employer. Proposers shall prepare their Proposals on the basis of the information made available in the RFP. No amendment is made to the RFP. | No
48 | Section VII – Employer’s Requirements / Annex A – Drawings; Annex H – Architectural and Finishing Works Technical Specification / Station and Yard Discipline | Please kindly provide standard cross-section drawings for stations | Please refer to the Employer’s Requirements and the available Reference/Conceptual Design. The Project is procured on a Design-Build basis and the station layouts and detailed cross-sections shall be developed by the Contractor in accordance with the applicable requirements and interfaces. No additional standard station cross-section drawing is issued through this clarification. No amendment is made to the RFP. | No
49 | Section VII – Employer’s Requirements / Annex C – Site Information / Geological and Topographical Mapping | 1. Please kindly provide a 1:50,000 regional geological map (vector format); 2. Please kindly provide a large-area topographic plan at a scale of 1:10,000 (or a smaller scale), if available | Please refer to Annex C and the Employer’s Requirements. The Employer has provided the tender-stage geological, topographical and survey information available. The Contractor shall obtain, verify and update the geological, topographic and geodetic information required for the Detailed Design. No additional 1:50,000 vector geological map or 1:10,000 topographic plan is issued through this clarification. No amendment is made to the RFP. | No
50 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J – Power Supply and Traction Power System Technical Specification / External Power Connection | Please kindly clarify whether the Works include external power supply works (scope and interface for connection to the external power source) | Yes. Please refer to Section VII, Employer’s Requirements, Clauses 5.3.2 and 5.3.3. The Works include the power-supply and electrification infrastructure within the relevant Lot, including 154 kV energy transmission lines and the interfaces/connections to the TEİAŞ network. The Lot 2 and Lot 4 Contractors shall perform the system-wide power-supply simulations, propose the connection points and obtain the required TEİAŞ/other authority approvals as stated in the RFP. No amendment is made to the RFP. | No
51 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J – Power Supply and Traction Power System Technical Specification / Traction Power Supply Scheme | Please kindly provide the specific traction power supply system scheme, including the power supply arrangement, chainages of substations and posts, traction transformer capacity, redundancy arrangement, etc.; information on the traction power supply scheme of the existing line is also required for reference | Please refer to Section VII, Employer’s Requirements, Clause 5.3.3 and Annex J. The final traction-power supply scheme, including transformer-substation locations, types, capacities, feeding arrangement and connection points, shall be developed through the power-supply design process. The preliminary locations stated in the Employer’s Requirements are planning references only and are subject to confirmation through the required simulations and approvals. No amendment is made to the RFP. | No
52 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J – Power Supply and Traction Power System Technical Specification / Train Operation Data for Power Supply Calculations | Please kindly provide train operation data (rolling stock type, headway, operating pattern, etc.) to verify the traction power supply calculations | Please refer to Section VII, Employer’s Requirements, Clause 5.3.3, Annex E and Annex B2. The Lot 2 and Lot 4 Contractors shall prepare the required train-operation simulations for the whole INRAIL Project using the final alignment geometry, passenger and freight vehicle performance characteristics and the operational requirements stated in the RFP. No additional Employer-prepared train-operation calculation is issued through this clarification. Please refer to Addendum No. 2, Amendment No. 39. | No
53 | Section VII – Employer’s Requirements / Annex J2 – Catenary Systems Technical Specification / Design Speed | Please kindly clarify and confirm the design speed: one statement in Document J2 specifies 250 km/h, whereas other locations indicate 200 km/h; a unified clarification is recommended | Please refer to Addendum No. 2, Amendment No. 7. | Yes
54 | Section VII – Employer’s Requirements / Lot 4 Interface at Çatalca and Existing Ispartakule–Çerkezköy Line; Annex J2 – Catenary Systems Technical Specification | Please kindly provide information on the interface design: Lot 4 has interfaces at both ends. At Çatalca Station, it connects to the existing Ispartakule–Çerkezköy Line, which the documents indicate will open by the end of the year; overhead contact system information for the existing line is therefore required | Please refer to Section VII, Employer’s Requirements, Clauses 5.3.3 and 5.3.4. The Lot 4 Contractor shall design and implement the required interfaces with the Ispartakule–Çerkezköy/Halkalı–Kapıkule line and the existing TCDD network at Çatalca and shall obtain/verify the existing-line data necessary for its Detailed Design in coordination with TCDD and the relevant interface parties. No amendment is made to the RFP. | No
55 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities | Please kindly provide detailed Bills of Quantities (BOQ) or the Method of Measurement that the client accepts. | The Contract is a lump-sum Design-Build contract. No remeasurement Bill of Quantities or separate Method of Measurement will be issued. Proposers shall prepare their prices using the Schedule of Priced Activities and Sub-activities and their own assessment of the design, quantities, construction methodology, Site conditions and risks, in accordance with the RFP. Please also refer to Addendum No. 2, Amendment No. 12, concerning the updated Schedule of Payments. | No
56 | Section III – Evaluation and Qualification Criteria / Clauses 3 and 4 / Clause 4.2(b) and Applicable Footnotes | Section III, Evaluation and Qualification Criteria, Clause 4.2(b), requires several key activity experience criteria to be demonstrated “under a single contract.” However, Footnote 9 under the same clause states:“Volume, number, or rate of production of any key activity can be demonstrated in one or more contracts combined if executed during same time period.” There appears to be an ambiguity regarding the application of these two provisions. please clarify the following: 1. For the key activity experience requirements under Clause 4.2(b) that expressly state “under a single contract”, such as the Lot 1 requirements for 20 km of railway system design, 20 km of single-bore TBM tunnels for transportation purposes, and 20 km of railway line construction, must the full required quantity be independently demonstrated under one single contract, or may the relevant quantities from two or more contracts be aggregated pursuant to Footnote 9 in order to satisfy the respective qualification requirement? 2. If aggregation of multiple contracts is permitted, please clarify the precise meaning of “executed during same time period ” in Footnote 9, including whether: the overall contract periods must overlap; the relevant key activities themselves must have been physically executed concurrently; any partial overlap is sufficient or a minimum concurrent execution period is required; and“same time period” refers to the same calendar year, the same continuous 12-month period, or another defined period. 3. Where multiple concurrent contracts are permitted to be combined, please confirm whether the entire quantity actually performed for the relevant key activity under each contract may be aggregated, or whether only the quantities or production achieved during the overlapping/concurrent period may be combined. Kindly request for the above clarification so that all Proposers may prepare Form EXP-4.2(b) and the supporting experience documentation on a consistent basis. | Please refer to Addendum No. 2, Amendment No. 8. | Yes
57 | Section III – Evaluation and Qualification Criteria / Items 3.2, 4.1(a) and 4.2(b) – Design JV Member Qualifications | Clause 4.2(b) of Section III sets out railway system design experience requirements for each Lot. If the experience of a professional design subcontractor cannot be relied upon to satisfy such requirements, a qualified design company may need to participate as a JV member. However, Clause 3.2 requires each JV member to meet a specified portion of the Average Annual Construction Turnover requirement for the relevant Lot, while Clause 4.1(a) requires each JV member to have more than 15 years of General Construction Experience. These requirements may not be fully applicable to a professional design company whose scope is limited to design. Please kidnly clarify whether a design-only JV member participating to satisfy the design experience requirement under Clause 4.2(b) may be exempted from, or subject to reduced requirements under, Clauses 3.2 and 4.1(a), or be permitted to demonstrate engineering design/consultancy turnover and relevant design experience instead. In addition, for Clause 4.1(a), please confirm whether experience gained by a design company as the designer under EPC, Design-Build or similar works contracts may be considered as satisfying the “ General Construction Experience ” requirement. This clarification is requested to apply to all Lots under the RFP. | Please refer to Answer No.19. Please refer to Addendum No. 2, Amendment No. 36. | Yes
58 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Definition of Railway / Railway Systems / Railway Line | Clause 4.2(b) of Section III, Evaluation and Qualification Criteria, sets out key activity experience requirements relating to the design of railway systems and construction of railway lines; however, the term “Railway” is not specifically defined for the purpose of these requirements. Please clarify whether “Railway / Railway Systems / Railway Line” under Clause 4.2(b), for both design and construction experience, includes Mainline Railway, Metro, Light Rail and Tramway projects. If not all of the above are acceptable, please specify the eligible types of railway systems and any applicable limitations. | Railway / Railway Systems / Railway Line” under Clause 4.2(b), for both design and construction experience, includes Mainline Railway, Metro, Light Rail. | No
59 | Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Requirement for Experience ‘Including Tunnels’ | Clause 4.2(b) of Section III requires, for each Lot, at least 20 km of railway system design experience “ including tunnels ” , while Lot 4 additionally requires at least 25 km of railway line construction experience “including tunnel”. Please clarify whether a minimum tunnel length is required for the above design and construction experience. If so, please specify the minimum length and the applicable method of calculation. If no minimum tunnel length is required, please confirm that the requirement is satisfied provided that the referenced project includes railway tunnel works. | No separate minimum tunnel length is stated for the “including tunnels” element of the railway-system design criteria or for the Lot 4 railway-line construction criterion. Accordingly, the qualifying contract shall include railway tunnel works and shall satisfy the stated route-length and other applicable requirements. This does not affect the separate TBM/NATM key-activity criteria, for which specific minimum lengths are stated. No amendment is made to the RFP. | No
60 | Section II – Proposal Data Sheet (PDS) / ITP 1.1; Section I – Instructions to Proposers (ITP) / ITP 4.2 and 4.3 | With reference to ITP 1.1, Section II – Proposal Data Sheet (PDS) stating that “the Proposer may bid for one or more lots. ” , while, according to Clause 4.3, Section I – Instructions to Proposers stating that “a firm that is a Proposer (either individually or as a JV member) shall not participate in more than one Proposal, except for permitted alternative Proposals.”, as well as other provisions in Clause 4.2, Section I – Instructions to Proposers also conveying a similar meaning, the aforesaid provisions appear to be subject to differing interpretations, therefore, the Employer is kindly requested to answer the following questions: Question 1: Please clarify whether the same individual firm (or the same Joint Venture) who intends to bid for one lot, is allowed to bit more lots under INRAIL Project. Question 2: If a firm, as a member of a Joint Venture, intends to submit a proposal for one lot, would that same firm be allowed to participate as a member of a different Joint Venture in bidding for other lots? | Please refer to Answer No.8. | No
61 | Section II – Proposal Data Sheet (PDS) / ITP 4.1 – Maximum Number of JV Members | ITP 4.1 of the PDS specifies that the maximum number of members in a Joint Venture shall be four (4). Considering the multidisciplinary nature of the Project, including major tunnelling, bridges, railway civil works, track, electrification and system design, Proposers may need to engage specialized partners in different disciplines to satisfy the qualification and execution requirements. Please clarify whether the maximum number of JV members may be increased from four (4) to five (5), allowing Proposers to appropriately integrate specialized design, construction and local capabilities for the successful delivery of the Project. | No. Please refer to PDS ITP 4.1. The maximum number of members in a Joint Venture remains four (4). No amendment is made to the RFP. | No
62 | Section II – Proposal Data Sheet (PDS) / ITP 7.1 and ITP 23.1 – Clarification and Proposal Submission Deadlines | Considering the scale of the Project and the complexity of its technical interfaces, the preparation of the Proposal requires substantial work relating to design development, construction methodology, resource planning, local market assessment, and cost estimation. To allow Proposers sufficient time to thoroughly review the tender documents and site conditions, further develop their technical proposals, conduct more comprehensive market enquiries and supply-chain assessments, and prepare prudent, reliable, and competitive prices. Hence, we are kindly request to extend the Proposal submission deadline by 2(two) months, the clarification extend by 2(two) months. Such an extension would improve the completeness and quality of the Proposals, reduce pricing uncertainties and implementation risks, and support fair and effective competition. | Please refer to Addendum No. 1. | No
63 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(i); Section I – Instructions to Proposers (ITP) / ITP 17.4 – JV Scope Allocation and Subcontracting | Section II – PDS, ITP 12.2(i) stipulates that: “The Joint Venture Agreement should specify the scope and part of the contract to be carried out by each Joint Venture member.” At the same time, all members of the Joint Venture are required to assume joint and several liability for the performance of the entire Contract. In this regard, Please kindly clarify the following: 1. Is it a mandatory requirement that the Joint Venture Agreement specify and allocate the respective scope and parts of the Contract to be performed by each JV member? If so, please clarify to what level of detail such allocation is required to be specified in the Joint Venture Agreement. In particular, is it sufficient to identify the principal work packages or major scopes to be undertaken by each JV member, or is a more detailed allocation of specific activities, quantities and/or contract values required? 2. If the allocation of the scope of work among JV members is mandatory and must be specified in the Joint Venture Agreement, upon award of the Contract, may the Joint Venture subcontract the respective allocated works to its individual JV members for execution? If such subcontracting to JV members is permitted, please clarify whether such subcontracted works would be excluded from the subcontracting limitation specified in ITP 17.4, under which the aggregate value of subcontracted works shall not exceed 30% of the total Contract Price, given that the subcontractors are themselves members of the successful Joint Venture and are jointly and severally liable for the performance of the entire Contract. 3. If the Joint Venture is not permitted to subcontract the respective works to its JV members, or if such subcontracting is permitted but remains subject to the 30% subcontracting limitation under ITP XXX, the works would in substance continue to be performed by the Joint Venture as a whole. In such circumstances, the allocation of specific scopes of work among JV members stipulated in the Joint Venture Agreement could not be fully implemented in practice, and therefore such allocation requirement would appear to have limited substantive effect. Accordingly, the Bidder kindly requests the Employer to clarify whether, in such circumstances, the requirement to specify the respective scope and parts of the Contract to be carried out by each JV member in the Joint Venture Agreement may be removed or otherwise revised to ensure consistency with the applicable subcontracting provisions. | 1. Please refer to ITP 12.2(i) and PDS ITP 12.2(i). The JV Agreement shall identify at least the principal parts of the Works to be carried out by each JV member, and the assigned scope shall correspond to the respective member’s experience and capacity. The RFP does not require a detailed allocation of quantities or contract values unless such detail is otherwise necessary to demonstrate compliance. 2. Performance by a JV member of the scope allocated to that member under the JV Agreement is performance by the JV and is not treated as subcontracting to a third party for the purpose of the 30% limit under ITP 17.4/Contract Data Sub-Clause 4.4(a). Any subcontracting by the JV to third parties remains subject to ITP 17.4 and 17.5. 3. All JV members remain jointly and severally liable for execution of the entire Contract, and the allocation of scope may not be altered without the prior consent of the Employer as stated in PDS ITP 12.2(i). No amendment is made to the RFP. | No
64 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel | For the positions other than the Project Manager and Civil Works Deputy Project Manager, the requirements specify the minimum years of relevant experience but do not clearly state that such experience must be in railway projects. Please confirm whether the relevant experience required for the other positions must also be gained in railway projects, or whether experience in other types of projects such as highway/industrial projects relevant to their respective positions will be acceptable? | Please refer to Section III, Item 1.4. The minimum experience requirement shall be applied separately for each Key Personnel position exactly as stated in the table. Where the RFP expressly requires railway/metro experience, railway-infrastructure experience, large-infrastructure experience or another specified sector/type of experience, that requirement is mandatory. Where a position requires only “relevant experience” without specifying a particular project type, experience from other project types may be accepted provided that it is directly relevant to the duties of the position and satisfies the stated minimum years of relevant and overall professional experience. There is no blanket acceptance of highway/industrial experience for all positions. No amendment is made to the RFP. | No
65 | Section IV – Proposal Forms / Letter of Proposal – Financial Part / Option 2 – Multiple Lots | In the "Letter of Proposal - Financial Part", as Option 2, it is mentioned that “in case of multiple lots: (a) Total price of each lot [insert the total price of each lot in words and figures, indicating the various amounts and the respective currencies]; and (b) Total price of all lots (sum of all lots) [insert the total price of all lots in words and figures, indicating the various amounts and the respective currencies]” In this regard, please clerify if a bidder submits proposals for multiple lots, should both technical and financial proposals be submitted in separate packages/files for each individual lot, or is it sufficient to submit them as a single, combined package covering all lots? | Please refer to ITP 12.1, ITP 22.1, PDS ITP 22.1(b) and the Letter of Proposal – Financial Part, Option 2. A Proposer bidding for multiple Lots may submit one combined Proposal covering the selected Lots, comprising one Technical Part and one Financial Part. Separate Technical and Financial envelopes/packages for each individual Lot are not required. However, all Lot-specific forms, Schedules of Priced Activities and Sub-activities, qualification information, Proposal Securities and other requirements shall be clearly identified and submitted for each Lot as applicable. No amendment is made to the RFP. | No
66 | Section I – Instructions to Proposers (ITP) / ITP 17.5; Section II – Proposal Data Sheet (PDS) / ITP 17.5; Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – Design Specialized Subcontractor | We note that design services are not included among the specialized parts of the Works listed under PDS ITP 17.5. Considering the Design & Build nature of the Contract and the extensive multidisciplinary design scope of the Project, we believe that professional design services should also be included among the specialized parts of the Works under PDS ITP 17.5. We kindly request the Employer to consider including professional design services under PDS ITP 17.5. | Please refer to Answer No.19. Please refer to Addendum No. 2, Amendment No. 36. | Yes
67 | Section I – Instructions to Proposers (ITP) / ITP 17.5; Section II – Proposal Data Sheet (PDS) / ITP 17.5; Section III – Evaluation and Qualification Criteria / Clause 4.2(b) – TBM Specialized Subcontractor | We note that TBM tunnelling works are not included among the specialized parts of the Works listed under PDS ITP 17.5. Considering the highly specialized nature of TBM tunnelling works, requiring dedicated technical expertise, experienced personnel, specialized equipment and proven execution capability, we believe that TBM tunnelling works should also be included among the specialized parts of the Works under PDS ITP 17.5. We kindly request the Employer to consider including TBM tunnelling works under PDS ITP 17.5. | The request is not accepted. Please refer to PDS ITP 17.5. TBM tunnelling is not included among the parts of the Works for which a Specialized Subcontractor may be proposed for qualification purposes. A Proposer may subcontract TBM-related activities in accordance with ITP 17.4 and the Contract, but the experience of an ordinary Subcontractor shall not be used to satisfy the Proposer’s qualification requirements unless expressly permitted by the RFP. No amendment is made to the RFP. | No
68 | Section VII – Employer’s Requirements / Clause 7.2.3 – Utility Records; Section IV – Proposal Forms / Activity 2 – Relocation of Existing Infrastructure and Utilities | Clause 7.2.3 states that the utility information provided in the Tender Documents is indicative, while the Schedule of Prices requires a Lump Sum Price including relocation of existing utilities within the Lot. However, the Bidder could not identify utility drawings, layouts or inventories in the Tender Documents to reasonably assess the type, location and extent of the existing utilities. Please therefore: 1. Provide all available utility information referred to under Clause 7.2.3 and confirm the baseline information to be used for pricing; and 2. Confirm that utilities not identified in the Tender Stage baseline information, or materially differing from such information and not reasonably identifiable before the Proposal Due Date, shall be treated in accordance with the applicable Variation, EOT and Cost provisions of the Contract. | Please refer to Section VII, Employer’s Requirements, Clause 7.2.3 and Section IV, Activity 2. The utility information made available with the RFP is tender-stage information and is indicative. The Contractor shall be responsible for identifying, verifying, surveying and coordinating all existing utilities and for the design and execution of all required protection, diversion and relocation works within its scope. The Contract is a lump-sum Design-Build contract and the Proposer shall include in its Proposal all costs and risks allocated to the Contractor under the RFP. Any entitlement arising from a circumstance encountered during execution shall be determined strictly in accordance with the applicable provisions of the Contract; no advance or blanket confirmation of entitlement to a Variation, Extension of Time or Cost is given. No amendment is made to the RFP. | No
69 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 1.1.95 – Milestone 1 ‘Detailed Design Completion’; Section VII – Employer’s Requirements / Clause 5.1 and Clause 7.5 | Milestone 1 is defined as “Detailed Design Completion”, to be achieved within twelve (12) months from the Commencement Date. However, Section VII – Employer’s Requirements, Clause 5.1 states that, within the same twelve (12) month period, the Contractor is required to achieve substantial completion of the design deliverables necessary for execution of the Works, with the design sufficiently advanced to establish the definitive horizontal and vertical alignment and the extent, configuration and footprint of the major underground structures and crossing infrastructure. It further states that the purpose of this milestone is to enable the Employer to formally freeze the alignment and initiate the Resettlement Action Plan and land expropriation processes. In addition, Section 7.5 – Design Freeze Milestones identifies the twelve (12) month milestone specifically as the deadline for freezing the overall horizontal and vertical alignment and the footprint of all major underground and crossing infrastructure, for the purpose of enabling the Employer to initiate the RAP and land expropriation processes. Based on the above, we understand that Milestone 1 – “Detailed Design Completion” does not require the entire Detailed Design for all disciplines and all construction packages to be fully completed and construction-ready by Month 12. Rather, by Month 12, the design shall have reached sufficient maturity to enable the following elements to be definitively established and frozen: * Horizontal alignment; * Vertical alignment; * Footprint / extent / configuration of major underground structures; * Footprint / extent / configuration of crossing structures; and * Land-take / resettlement / expropriation envelope. Please confirm that the above understanding is correct and that Milestone 1 at Month 12 should therefore be interpreted as substantial completion of the design required to achieve the alignment, major structure footprint and land-take freeze, rather than 100% completion of the Detailed Design for all disciplines and construction packages? | Please refer to Answer 28. | No
70 | Section VII – Employer’s Requirements / Clause 7.1 – Section-Based Commencement of Construction / Early and Temporary Works | Reference is made to Section VII – Employer’s Requirements, Section 7.1, which states that: “For any Section of any Contract (Lot), commencement of construction works within that Section shall be permitted once the Detailed Design has been approved by the Engineer and the PIOC has verified that the applicable Resettlement Plan (RP) has been implemented for that Section.” Considering the above and the critical overall Time for Completion, we understand that the requirement for approval of the Detailed Design prior to commencement of construction applies on a Section basis, rather than requiring completion and approval of the Detailed Design for the entire Lot before any physical works may commence. Accordingly, our programme envisages that certain early and temporary works, including shaft construction and associated enabling/access works, will commence during the twelve (12)-month Detailed Design period, subject to the relevant Detailed Design package for such Section/works being completed and approved by the Engineer and, where applicable, and other statutory/land-access requirements having been satisfied. Please confirm our understanding is correct and that shaft construction and other early/temporary works may commence within the twelve (12)-month Detailed Design period, without waiting for Milestone 1 – Detailed Design Completion for the entire Lot. | Confirmed. Please refer to Section VII, Employer’s Requirements, Clauses 7.1, 7.5, 11.4 and 11.10. Construction may commence on a Section-by-Section or work-package basis once the Detailed Design applicable to that Section/work has received the required review/approval and all applicable land-access, resettlement, E&S, World Bank no-objection and third-party approval conditions have been satisfied. Completion of Milestone 1 for the entire Lot is not, by itself, a condition precedent to commencement of every earlier Section or enabling work. Any additional costs arising from revisions to the design—incurred only after obtaining the shaft's permission and approval—shall be the responsibility of the contractor. No amendment is made to the RFP. | No
71 | Section VII – Employer’s Requirements / Chapter 4 – Multi-Contract Structure and Interface Management / Clause 4.5.3 – Package 2 Interface; Clause 7.5 – Design Freeze Milestones | Package 2 – Signaling and Telecommunication is being procured separately and is not part of the present tender. Nevertheless, Package 1 Civil Works Contractors are required to treat the Package 2 Contractor as a primary interface party from the outset of design. The Civil Works Contractor must provide all civil prerequisites for Package 2, including equipment rooms, cable routes, conduit infrastructure, balise mounting positions and power supply connections. The RFP further provides that post-freeze design changes affecting Package 2 interfaces require notification and the Engineer’s prior written consent. 1. Please provide the anticipated tender, award and appointment programme for the Package 2 Signaling and Telecommunication Contractor, and confirm whether Package 2 is expected to be appointed sufficiently early to review and agree all relevant civil interface requirements before the corresponding Package 1 designs are frozen and/or released for construction. 2. Where the Package 1 Contractor has developed its design in accordance with the RFP, Annex L, the Interface Requirements Schedule and assumptions duly recorded and reviewed by the Engineer, please confirm that any subsequent requirement arising solely from the Package 2 Contractor’s detailed design which could not reasonably have been identified beforehand, including any resulting: - redesign; - demolition or rework; - additional civil provisions; - modification of completed Works; and/or - programme delay, shall not remain at the Package 1 Contractor’s cost and risk and shall be treated in accordance with the applicable Variation, Extension of Time and Cost provisions of the Contract. | Please refer to Answer 29. The Package 1 Contractor shall develop and manage the Package 2 interfaces on the basis of the RFP, Annex L, the Interface Requirements Schedule and the approved interface-control process. The RFP does not establish a separate guaranteed appointment date for the Package 2 Contractor. Any subsequent instruction or change shall be administered in accordance with the Contract. No advance or blanket confirmation of entitlement to a Variation, Extension of Time or Cost is given. | No
72 | Section VII – Employer’s Requirements / Clause 2.4 – Contractor’s Representative and Key Personnel | The Employer's Requirements state that, where a Proposer submits proposals for multiple Lots, separate Key Personnel shall be proposed for each Lot and the same person shall not be proposed for more than one Lot. The Bidder fully understands the Employer's intention to ensure that, during contract execution, each awarded Lot is supported by a dedicated team of Key Personnel. As the final Lot award is not known at proposal stage, providing fully separate teams for all Lots may create a significant practical constraint. Please confirm whether the same Key Personnel may be proposed for more than one Lot at tender stage, provided that, if multiple Lots are awarded to the same Proposer, separate fully compliant Key Personnel shall be nominated for each awarded Lot before Contract signing or commencement, subject to the Employer’s approval. | No. Please refer to Section III, Item 1.4 and the corresponding note for multiple Lots. Where a Proposer submits Proposals for more than one Lot, separate persons shall be proposed for the specified Key Personnel positions for each Lot; the same person shall not be common to multiple Lots. The requirement applies at Proposal stage and is not deferred until award or commencement. No amendment is made to the RFP. | No
73 | Section III – Evaluation and Qualification Criteria / Clause 1.5 – Equipment | The Evaluation and Qualification Criteria require that, where a Proposer submits proposals for multiple Lots, separate equipment shall be proposed for each Lot and that the same equipment shall not be common to multiple Lots. The Bidder fully understands the Employer's intention to ensure that, during execution, each awarded Lot is provided with sufficient and dedicated equipment resources. As the final Lot award is not known at proposal stage, please confirm whether the same equipment may be proposed for more than one Lot for tender evaluation, provided that, if multiple Lots are awarded, separate compliant equipment of equivalent or higher capacity will be secured for each awarded Lot before commencement of the Works. Accordingly, please confirm whether the requirement under Section III, Clause 1.5 may be amended or clarified to allow common equipment to be proposed for multiple Lots for tender evaluation purposes, provided that separate and fully compliant equipment resources are secured and made available for each Lot in the event that multiple Lots are awarded to the same Proposer. | No. Please refer to Section III, Item 1.5. Where a Proposer submits Proposals for more than one Lot, separate equipment shall be proposed for each Lot as required by the RFP; the same equipment shall not be relied upon for more than one Lot. The requirement applies at Proposal stage. No amendment is made to the RFP. | No
74 | Section VII – Employer’s Requirements / Clause 4.9.4 – Contractual Milestones | Please clarify which date shall be assumed as the Project Start / Commencement Date for the preparation of the Tender Stage Level 3 Programme and for determining the proposed target dates of the four Contractual Milestones. Alternatively, please confirm whether the Proposer may adopt a notional Commencement Date (Day 0) for the Tender Stage Programme, with the milestone dates being scheduled relative to Day 0 and subsequently adjusted based on the actual Commencement Date following Contract award. | For preparation of the Tender Stage Level 3 Programme, the Proposer may use a notional Day 0 corresponding to the Commencement Date and show all contractual milestones and activities as durations/target dates measured from Day 0. Following Contract award, the programme shall be updated to the actual Commencement Date in accordance with the Contract. No amendment is made to the RFP. | No
75 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 2.1; Section VII – Employer’s Requirements / Clauses 5.1 and 11.10 – Site Access and Land Acquisition Programme | The Contract Data states that access to the Site shall be provided no later than the Commencement Date, subject to the land access, E&S clearance and World Bank no-objection requirements stipulated in the Employer's Requirements. At the same time, the Employer's Requirements provide that the design deliverables submitted at the twelve (12) month milestone shall enable the Employer to formally freeze the alignment and trigger the Resettlement Action Plan implementation and land expropriation processes. The RFP further provides that construction of a Section may commence only after the relevant Detailed Design has been approved and the applicable land acquisition/resettlement requirements have been completed. In order to enable the Proposer to prepare a realistic Level 3 Programme and construction sequencing, please clarify whether full and unrestricted access to the entire Site is intended to be provided by the Commencement Date or whether Site access will be provided progressively on a sectional basis. If sectional access is envisaged, please provide the planned land acquisition / Site handover schedule identifying the dates by which each principal Section, work front and critical construction area will be made available to the Contractor. Please also confirm that any delay in providing access to a Section beyond the corresponding access date established in the agreed programme, where such delay is not attributable to the Contractor, shall entitle the Contractor to the remedies available under the Contract, including Extension of Time and, where applicable, Cost. | Please refer to Contract Data Sub-Clause 2.1 and Section VII, Employer’s Requirements, Clauses 5.1, 7.1, 11.4 and 11.10. Site access is subject to the applicable land-access, E&S, World Bank no-objection, resettlement and statutory requirements and may therefore become available progressively by Section/work front. No separate guaranteed land-handover schedule beyond the RFP is issued at Proposal stage. The Proposer shall prepare its programme on the basis of the contractual requirements and available tender information. Any entitlement arising from delayed access shall be determined in accordance with the Contract and the facts of the relevant event; no blanket entitlement is confirmed. | No
76 | Section VII – Employer’s Requirements / Clauses 2.1, 9.2.3, 9.2.4 and Chapter 10 – Testing and Commissioning / Designated Body (DeBo) | Clause 2.1 expressly identifies the Contractor's obligations for the engagement of the Notified Body (NoBo), Assessment Body (AsBo) and Independent Safety Assessor (ISA), and states that the associated costs are deemed to be included in the Accepted Contract Amount. However, although the Designated Body (DeBo) is referred to under the Testing and Commissioning requirements as one of the assessment/certification bodies with which the Contractor is required to coordinate and provide information, the RFP Documents do not appear to expressly identify the party responsible for the appointment and engagement of the DeBo. Please clarify: 1. Whether the DeBo is to be appointed and engaged by the Contractor or by the Employer / relevant Authority; 2. If the DeBo is to be engaged by the Contractor, whether all associated DeBo costs shall be deemed included in the Accepted Contract Amount and what appointment/engagement timescale shall apply | The DeBo shall be engaged by the Contractor, where applicable. All associated DeBo costs shall be included in the Contract Price under the relevant Testing and Commissioning / regulatory acceptance activities. The Contractor shall engage the DeBo sufficiently early to meet the design-assessment, authorization, testing and commissioning programme and shall reflect the required review/assessment periods in its Detailed Programme, in coordination with the relevant authorities and the Engineer. No amendment is made to the RFP. | No
77 | Section VII – Employer’s Requirements / Clause 11.4.7 – World Bank No-Objection as a Condition Precedent to Construction | The RFP provides that: “No construction activities of any kind shall commence unless and until the World Bank has issued its written no-objection to the finalized ESIA, finalized ESMP, finalized SEP, C-ESMP, and all applicable sub-management plans.” It further states that World Bank no-objection is a mandatory condition precedent to mobilization to the relevant Site section, establishment of Project Facilities and commencement of physical works. The same Clause then states: “No claim for Extension of Time, additional payment, or compensation shall arise from delays associated with preparation, revision, correction, resubmission or approval of E&S documents.” The Bidder understands that delays arising from incomplete, non-compliant or late E&S submissions attributable to the Contractor shall remain the Contractor’s responsibility. However, please confirm that the above exclusion of entitlement does not apply where the Contractor has submitted complete and compliant documentation within the required timeframe and the delay subsequently arises solely from the review, approval or no-objection process of the Engineer, Employer, PIOC and/or World Bank. Please confirm that such delays, where not attributable to the Contractor, shall be treated in accordance with the Contractor’s applicable entitlement to Extension of Time and Cost under the Contract. | The requested confirmation is not given. Please refer to Section VII, Employer’s Requirements, Clause 11.4.7. The RFP expressly provides that no claim for Extension of Time, additional payment or compensation shall arise from delays associated with the preparation, revision, correction, resubmission or approval of the E&S documents referred to in that Clause. The requirement shall be applied as stated in the RFP. No amendment is made to the RFP. ESMP, LMP,RF, and SEP were updated and disclosed on August 21, 2026. ESIA and the Supplementary Biodiversity Baseline Study, together with the SEA/SH Management Plans, were updated and disclosed on September 3, 2026. All documents have been made publicly available on the AYGM project webpage (aygm.uab.gov.tr/istanbul-kuzey-demiryolu-gecisi-projesi). | No
78 | Section VII – Employer’s Requirements / Clauses 7.5 and 7.6 – Design Freeze and Third-Party Approval Obligations; Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 1.1.95 – Milestones | Milestone 1 is defined as: “Milestone 1 – Detailed Design Completion – 12 months from the Commencement Date.” The RFP also requires third-party approvals from, inter alia, DSİ, TEİAŞ, KGM/YSS Bridge Operator, DHMİ, TCDD and İBB, and expressly provides: “The Engineer's review and consent does not constitute, substitute for, or waive any third-party statutory approval.” , and “Design Freeze for any element subject to a mandatory third-party approval shall not be achieved until that approval has been formally received in writing.” Considering that achievement of certain Design Freeze Milestones is dependent upon approvals from third-party authorities outside the Contractor’s direct control, please clarify how such approval periods are to be treated in relation to Milestone 1 – Detailed Design Completion at Month 12. Where the Contractor has submitted complete and compliant documentation to the relevant authority within the required timeframe, please confirm that delays solely attributable to the review or approval process of such authority shall: not constitute Contractor delay or failure to achieve the relevant Design Freeze Milestone; and entitle the Contractor to the applicable Extension of Time and other contractual relief where such delay affects Milestone 1 or the critical path. | Please refer to Section VII, Employer’s Requirements, Clauses 7.5 and 7.6. The Contractor is responsible for obtaining and coordinating the required third-party approvals and shall allow for the relevant review/approval periods in its programme. Design Freeze is not achieved for an element subject to mandatory third-party approval until the required written approval is received. Any entitlement, if any, shall be determined strictly under the Contract in relation to the specific event; no blanket exclusion of Contractor responsibility or automatic entitlement to Extension of Time or Cost is confirmed. No amendment is made to the RFP. | No
79 | Section VII – Employer’s Requirements / Chapter 10 – Testing and Commissioning / Clause 10.1.6 – Coordination Requirements | The RFP provides that: “Where multiple systems supplied by different organisations require integrated testing, the Contractor shall assume overall responsibility for planning, coordinating and managing the integrated testing activities, irrespective of contractual boundaries.” It further states: “Any failure to adequately coordinate Testing and Commissioning activities that results in delays, disruption, repeated testing, operational restrictions or additional costs shall remain the sole responsibility of the Contractor unless otherwise expressly provided for under the Contract.” The Bidder acknowledges its responsibility for planning and coordinating integrated Testing and Commissioning activities within its contractual scope. However, 1. Please confirm that the Contractor shall not be responsible for delay, repeated testing, disruption or additional cost caused solely by the failure, late completion or lack of readiness of the Package 2 Contractor, an adjacent Lot Contractor, the Railway Operator, Infrastructure Manager or another third party outside the Contractor’s control. 2. Please further confirm that where such circumstances affect Trial Running, Trial Operations, Testing and Commissioning Completion or Taking-Over, the affected Package 1 Contractor shall be entitled to the applicable Extension of Time and Cost. | Please refer to Section VII, Employer’s Requirements, Clause 10.1.6. The Contractor shall assume overall responsibility for planning, coordinating and managing integrated Testing and Commissioning activities irrespective of contractual boundaries. The RFP expressly provides that failures of coordination remain the Contractor’s responsibility unless otherwise expressly provided under the Contract. Any entitlement arising from a specific event caused by another party shall be determined under the Contract; no blanket entitlement to Extension of Time or Cost is confirmed. No amendment is made to the RFP. | No
80 | Section VII – Employer’s Requirements / Chapter 10 – Testing and Commissioning / Clause 10.1.4 – Contractor’s Overall Responsibilities | The Employer’s Requirements state that: “The Contractor shall provide all rolling stock, specialist vehicles, test trains, simulation equipment, portable instrumentation, communication equipment and temporary software necessary to undertake system integration testing and operational demonstrations where such resources are not expressly stated to be provided by the Employer.” However, Rolling Stock is not included within the scope of Package 1 Works, and no corresponding item or allowance for the procurement or provision of rolling stock, test trains or equivalent railway vehicles is identified in the Schedule of Prices for the present tender. Accordingly, the Bidder understands that the above requirement is not intended to impose an obligation on the Package 1 Contractor to procure or supply Rolling Stock or test trains, and that the wording may require clarification in the context of the present Package 1 tender. 1. Please confirm that all Rolling Stock, test trains and other railway vehicles required for dynamic testing, integrated testing, Trial Running and Trial Operations will be provided by the Employer and/or the Railway Operator, at no cost to the Package 1 Contractor. 2. Please also confirm that the simulation equipment required specifically to simulate the operation or performance of Rolling Stock and/or the overall railway system will similarly be provided or arranged by the Employer/Railway Operator. 3. For avoidance of doubt, please confirm that the Package 1 Contractor’s obligations in this respect shall be limited to the testing equipment, instrumentation, temporary systems and resources directly associated with the Works within its own contractual scope, together with the required coordination and technical support for the relevant Testing and Commissioning activities. | The understanding is not correct. Please refer to Section VII, Employer’s Requirements, Clause 10.1.4. The Contractor shall provide all rolling stock, specialist vehicles, test trains, simulation equipment, portable instrumentation, communication equipment, temporary software and other resources necessary for the required Testing and Commissioning activities, except where a resource is expressly stated in the RFP to be provided by the Employer. The absence of a separate item in the Schedule of Priced Activities does not exclude this obligation from the lump-sum Contract Price. No amendment is made to the RFP. | No
81 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Proposal Submission Deadline / Extension Request | We have allocated our resources to ensure the submission of a competitive and well-prepared Proposal for the Project. As part of this effort, we are undertaking various preparatory activities, including obtaining quotations from local and international suppliers and specialist companies, developing the required design solutions, verifying the available geotechnical data and preparing the detailed Technical Proposal. Considering the summer holiday period in Europe, as well as the additional time required to obtain and evaluate competitive quotations, further develop the design and complete the Technical Proposal with the required level of detail, we kindly request an extension of the Proposal Submission Deadline by six (6) weeks. | Please refer to Addendum No. 1. | No
82 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clause 3.2.3.1 – Circular Curves; Annex B1 – Conceptual Design Report / Clause 4.1.4.1 – Circular Curves | “Conceptual design: Rmin = 1,500 m” and “Appendix E1: Normal/absolute minimum horizontal curve radius of 2,500/2,000 m” are contradictory. Please clarify the control standards for the detailed design and the approval process for speed limits. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. For horizontal curve radii and section-specific design speeds, refer to the requirements of the revised Annex E1 and the express amendment to Annex B1 Clause 4.1.4.1 under Amendment No. 31. The superseded text of the original Annex E1, including its former Clause 3.2.3 and Table 3.6, does not apply. The relevant conceptual alignment shall be verified during Detailed Design. | Yes
83 | Section VII – Employer’s Requirements / Annex J – Power Supply and Traction Power System Technical Specification / Clause 1.2 – Scope and Description | To conduct power supply simulations, please provide detailed vehicle performance parameters and operating plans. | Please refer to Answer 52. | No
84 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / AYGM-INR-ALG-PLP-001~044 | At KM40+355 on the LOT 2 section, the route crosses over a canal. Please clarify whether there are any navigability requirements and whether bridge piers may be installed within the river channel. | No specific navigation clearance requirement is prescribed in the RFP for the canal at KM40+355. The bridge/pier arrangement shall be developed during Detailed Design in accordance with the applicable hydraulic and hydrological requirements and the requirements/approvals of the competent authorities. The Contractor shall verify any navigation or waterway restriction applicable to the final design. No amendment is made to the RFP. | No
85 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clauses 9.5.1 and 9.6.2 | The project interface boundary between the tenderer and the municipal water supply network remains undefined. Technical parameters such as location, pipe diameter and water supply pressure of the municipal water supply network are not available, making it impossible to estimate the length and specifications of connecting pipelines. Hence accurate pricing for this scope cannot be made in the BOQ. Please kindly clarify the following items: 1. Define the project interface for connection with the municipal water supply network, and specify whether connecting pipelines and relevant structures are within the scope of this contract; 2. Provide complete technical parameters of the municipal water supply network, including location, pipe diameter and water supply pressure; 3. Specify the exact connection point of the municipal water supply network. | Please refer to Answer 68. | No
86 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clause 9.6.3 | The connection works between sewage inspection chambers and the municipal sewage network are not mentioned in ANNEX F Civil Works (Infrastructure). The project interface boundary between the tenderer and municipal sewage network remains undefined. In addition, technical parameters including location, pipe diameter and burial depth of municipal sewage network are not provided, which makes it impossible to estimate the length and specifications of connecting pipelines. Therefore, accurate pricing cannot be achieved for this part in the BOQ. Please kindly clarify the following: 1. Define the project interface for connection between sewage inspection chambers and municipal sewage network, and specify whether connecting pipelines and related structures are within the scope of this contract; 2. Provide complete technical parameters of municipal sewage network, including location, pipe diameter and burial depth; 3. Specify the exact connection point to the municipal sewage network. | Please refer to Answer 68. | No
87 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clause 9.5.6.6 | Reliable water supply is required for water‑based fire‑fighting systems at tunnel portals and inside tunnels, which can be supplied by municipal water network or natural water sources. At present, basic data of water source is not available, and the water intake source, intake point, water supply connection point and project interface boundary remain undefined. Please kindly clarify the following items: 1. Whether municipal water network or natural water source shall be adopted for the water‑based fire‑fighting system at tunnel portals and inside tunnels; 2. Exact location of water intake point and water supply connection point; 3. Define the project interface boundary from water source to fire‑fighting system, and specify which structures and pipelines fall within the scope of this contract. | The tender-stage RFP does not prescribe a single fixed water source or pre-defined intake/connection point for all tunnel fire-fighting systems. The Contractor shall identify and develop the suitable permanent water source and connection arrangement during Detailed Design, in coordination with the relevant utility/authority and in accordance with Annex K and the applicable fire-safety requirements. From the approved connection point onward, all permanent facilities, piping, storage/pumping equipment and interfaces required to provide the specified fire-fighting performance within the Contract scope shall be included in the Contractor’s design and price. No amendment is made to the RFP. | No
88 | Section VII – Employer’s Requirements / Clause 5.8 – Lot 4 Construction and Electrification Works for the Mithatpaşa–İstanbul Airport–Çatalca Corridor | The civil works of the station have been completed, while it is unclear whether all functional rooms inside the station are finalized. Station architectural drawings and design requirements for each functional room are not available, and requirements for equipment rooms and administration rooms remain unspecified. Since the airport and existing metro station are already in operation, the engineering boundary between the project underground station and existing metro station / airport has not been defined, hence the design scope cannot be confirmed. In addition, loading‑unloading requirements for the station freight platform are unclear. Absence of above information will affect design development and accurate BOQ pricing. Please kindly clarify the following items: 1. Whether completion of station civil works means layout and division of all internal functional rooms are finalized; 2. Provide station architectural drawings together with design requirements for each functional room, and specify technical requirements for equipment rooms and administration rooms; 3. Provide engineering boundary between the project underground station and the operational existing metro station as well as airport, and define the project design scope accordingly; 4. Clarify whether loading‑unloading operation is required for the station freight platform, and provide detailed requirements if applicable. | The station architectural and functional arrangement shall be developed by the Contractor on the basis of the Employer’s Requirements, Annex H, the available architectural/reference drawings and the applicable operational interfaces. The tender-stage completion of existing civil works does not relieve the Contractor from completing the detailed architectural/functional-room design required for its scope. Interfaces with the existing metro facilities and the airport shall be coordinated in accordance with the relevant interface clauses and authority/operator requirements. No additional freight-platform operational requirement is introduced through this clarification beyond the requirements expressly stated in the RFP. No amendment is made to the RFP. | No
89 | Section VII – Employer’s Requirements / Clause 9.3.1 – Governing Standard and Design Basis | The tender document requires submission of mandatory evacuation model. Although the quantity and width of stairs and escalators have been reserved for this station, relevant basic documents of the original design are not available to the tenderer. Please provide fire compartment layout, evacuation routes, evacuation time calculation report, evacuation model files and applicable standards of the original design, as well as documents approved by fire‑safety authority. Please kindly clarify the following items: 1. Provide documents for fire‑compartment division of the original station design; 2. Provide evacuation routes, evacuation time calculation report, evacuation model files and applicable standards adopted in original design; 3. Provide official approval documents issued by fire‑safety review authority. | Please refer to Section VII, Employer’s Requirements, Clauses 9.3.1 and the applicable fire-life-safety requirements. The Contractor shall prepare and substantiate the required evacuation analyses/models as part of Detailed Design using the operating, rolling-stock and station parameters established under the RFP and the approved Detailed Design. The tender-stage information made available by the Employer is the basis for the Proposal; no separate original approved evacuation model is issued by this clarification. No amendment is made to the RFP. | No
90 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clause 1.8.4 | Emergency passenger load is the key basis for evacuation calculation. Key parameters including train passenger capacity, waiting‑passenger volume on platform and maximum passenger volume of trains during peak‑hour operation are not defined in tender documents. Please kindly clarify the following items: 1. Define train passenger capacity for evacuation calculation; 2. Define design value of waiting‑passenger volume on platform; 3. Define maximum passenger volume of trains during peak‑hour operation. | No separate fixed Employer-prescribed passenger-load values are issued through this clarification. The evacuation design shall be developed using the final rolling-stock capacity, operating scenario and peak passenger demand adopted for the Project, in accordance with the Employer’s Requirements and the applicable standards, and shall be subject to the Engineer’s review. Please also refer to Section VII, Clause 5.3.3, Annex E and Annex B2. No amendment is made to the RFP. | No
91 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Clause 4.4.1 – Sleepers; Annex G1 – Superstructure Works Construction Specification / Clause 1.1 | Conflicting requirements exist for ballasted track sleeper spacing in different tender documents: 620 mm is specified in document B1, while 60 cm is stated in document G1. Unclear parameters will affect track design and BOQ pricing. Please kindly clarify the following item: 1. Confirm whether sleeper spacing for ballasted track shall be 620 mm or 60 cm. | Please refer to Annex G1 and the document-precedence provisions of Section VII, Employer’s Requirements. The mandatory Technical Specification shall govern over the Reference/Conceptual Design. Accordingly, the sleeper spacing specified in Annex G1 shall be used for Proposal and Detailed Design purposes, subject to compliance with the complete requirements of the RFP. No amendment is made to the RFP. | No
92 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Clauses 4.4.1 – Sleepers and 4.4.2 – Ballast | According to ANNEX B1‑Conceptual Design Report, the location and scope of USP and UBP shall not be defined at tender stage, and shall be determined during construction phase based on detailed technical justification, site conditions and relevant analysis reports. Without technical conditions for USP / UBP at tender stage, design work cannot be performed. Please kindly clarify the following item: 1. Define technical conditions, triggering boundary and preliminary application scope for USP and UBP for tender‑stage purposes. | The locations and extent of USP/UBP or other vibration/track-resilience measures shall be determined by the Contractor during Detailed Design on the basis of the applicable Technical Specifications, structural interaction, vibration/noise analysis and the approved track design. No separate fixed chainage list is provided at Proposal stage. No amendment is made to the RFP. | No
93 | Section VII – Employer’s Requirements / Annex A – Drawings / Annex A1 – Alignment Drawings / 01_6_Itinerary | The project connects to existing railway lines at start and end points. Basic data of the connected railways are not provided, which will affect design of alignment, track, catenary and other disciplines. Please kindly clarify the following item: 1. Provide complete basic data of existing connecting railways at the start and end of this project. | Please refer to the Employer’s Requirements concerning interfaces with TCDD and existing railway infrastructure. The Contractor shall verify the existing conditions and obtain/coordinate the data, access, approvals and interface information necessary for Detailed Design with TCDD, the Engineer and the relevant parties. The tender-stage information provided with the RFP is the basis for the Proposal. No amendment is made to the RFP. | No
94 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Clause 4.3.1 – Rails; Annex A1 – Alignment Drawings / 01_5_Typical_Sections | The tender document requires guard rails for ballasted track on bridge sections. However, guard rails are not shown on typical cross‑section drawing for ballasted track on bridges, where a 20 cm‑thick protective wall is provided. Discrepancy exists between text requirement and drawing, affecting design work. Please kindly clarify the following items: 1. Whether guard rails shall be installed for ballasted track on bridge sections; 2. Whether guard rails can be omitted if a 20 cm‑thick protective wall is already provided on the bridge. | The omission of guard rails from a Reference/Conceptual drawing does not waive a requirement stated in the applicable specifications. Guard rails shall be provided where required by the RFP and the approved Detailed Design. The Contractor shall coordinate the final arrangement with the relevant bridge/track design and applicable standards. No amendment is made to the RFP. | No
95 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / 01_6_Itinerary and 01_5_Typical_Sections | According to Alignment Drawing‑1, tunnels before and after YSS Bridge are TYPE‑E cut‑and‑cover tunnels. Nevertheless, only TYPE‑1 and TYPE‑2 typical cross‑sections for cut‑and‑cover tunnels are provided, without TYPE‑E drawings and track‑form information, which prevents design work. Please kindly clarify the following items: 1. Provide complete design documents for TYPE‑E cut‑and‑cover tunnel; 2. Specify whether ballasted or ballast‑less track shall be adopted inside TYPE‑E cut‑and‑cover tunnel. | No separate tender-stage Type-E cut-and-cover detailed-design package is issued through this clarification. The Contractor shall develop the detailed Type-E cut-and-cover design in accordance with the Employer’s Requirements, the applicable tunnel/civil Technical Specifications and the alignment/interface requirements. For the applicable ballasted/ballastless track form, please refer to the Ballasted/Ballastless Track Itinerary added by Addendum No. 2, Amendment No. 15. | Yes
96 | Section VII – Employer’s Requirements / Annex A – Drawings / Annex A1 – Alignment Drawings / 01_5_Typical_Sections / AYGM-INR-STR-TCS-001~021 | YSS Bridge has a main span of 1408 m. Only cross‑section drawing is provided in tender documents, without further design information for the bridge. The reserved track form cannot be confirmed, which affects track‑bridge interface design. Please kindly clarify the following item: 1. Whether ballast‑less track or ballasted track is reserved in the design of YSS Bridge. | Please refer to Section VII, Employer’s Requirements, Clause 4.8.1. Lot 3 works within the YSS Bridge corridor shall be designed and executed in coordination with KGM and the YSS Bridge Operator. The Contractor shall use the tender-stage information made available and shall obtain/verify the information required for Detailed Design through the prescribed interface process. No structural modification to the existing YSS Bridge is anticipated under the Contract unless otherwise agreed in writing in accordance with Clause 4.8.1. No amendment is made to the RFP. | No
97 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Chapter 8 – Electromechanical Systems / Clause 8.3 – Emergency Strategy and Fire Fighting | Please kindly clarify the following item: Please confirm which of the following AC power supply connection modes shall be adopted for communication and signal buildings at stations, tunnels and along sections: 1. The local energy supplier provides power connection point and incoming power cables. The interface between the Contractor and local energy supplier is located at the upper terminals of switch‑gear equipment within station, tunnel and section buildings. 2. The local energy supplier only provides the power connection point. All installation works of incoming power cables from such connection point to power‑consuming points of stations, tunnels and section buildings shall be undertaken by the Contractor. | The final AC auxiliary-power connection arrangement shall be developed by the Contractor during Detailed Design in accordance with Annex E1, the power-supply technical requirements, the utility/interface conditions and the approvals of the Engineer and relevant authorities. The RFP does not prescribe one universal connection mode for all locations unless expressly stated in the applicable Technical Specification. No amendment is made to the RFP. | No
98 | Section VII – Employer’s Requirements / Clause 5.2.2 – Contractor’s Deemed Knowledge of Site Conditions | Please kindly clarify the following item: 1. Supplement the detailed investigation reports of adjacent projects listed in Appendix Table 13 of ANNEX C1‑Geological Data Report, or provide occurrence data of bedding planes, joints and fractures for rock layers along the whole alignment. 2. Supplement the detailed investigation reports of adjacent projects listed in Appendix Table 13 of ANNEX C1‑Geological Data Report, or provide the above‑mentioned complete hydro‑geological and karst‑related data. 3. Supplement the detailed investigation reports of adjacent projects listed in Appendix Table 13 of ANNEX C1‑Geological Data Report, or provide the aforesaid aggressivity test reports and aggressivity grade data. | Please refer to Answer 35. | No
99 | Section VII – Employer’s Requirements / Clause 5.4.2 – Special Requirements | ANNEX C1 and ANNEX B1 do not provide hydro‑geological test data for each stratum, together with investigation, test and hazard‑assessment data for karst development in marl and limestone, which restrict waterproof‑drainage design for foundation pits and tunnels. Please kindly clarify the following item: 1. Supplement detailed investigation report of adjacent projects listed in Appendix Table 13 of ANNEX C1, or provide above‑mentioned hydro‑geological and karst‑related investigation, test and hazard‑assessment data. | Please refer to Answer 35. | No
100 | Section VII – Employer’s Requirements / Clause 5.8.3 – Special Requirements | ANNEX C1, ANNEX B1 and Appendix‑D do not provide swelling indexes, swelling grade, development and hazard degree data for swelling rock‑soil of Belgrad and İhsaniye formations. Swelling grade governs design schemes for tunnels, cuttings and bridges. Please kindly clarify the following item: 1. Supplement swelling indexes, swelling grade, development and hazard‑degree data for swelling rock‑soil; or provide detailed geotechnical reports for tunnel, cutting and bridge sites within swelling‑soil zones of adjacent projects in Appendix Table 13 of ANNEX C1. | Please refer to Answer 35. | No
101 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Typical Sections | Cross‑section drawings show track centre‑to‑centre distance of 4.5 m, while this value is not explicitly stated in tender text documents, which affects alignment, subgrade, bridge and tunnel design. Please kindly clarify the following item: 1. Confirm whether 4.5 m shall be adopted as track centre‑to‑centre distance for main line. | The 4.5 m track centre-to-centre distance shown in the Reference/Conceptual Design shall be treated as tender-stage reference information. The final track spacing shall be established during Detailed Design in accordance with the mandatory Employer’s Requirements and applicable standards. No separate fixed 4.5 m requirement is introduced through this clarification. No amendment is made to the RFP. | No
102 | Section VII – Employer’s Requirements / Annex I3 – Stations Escalators, Moving Walkways and Elevators Technical Specification | Clause 7.2.1 and Clause 7.2.12 of tender document specify conflicting material requirements for escalator handrail support plate. Unified technical requirement shall be confirmed. Please kindly clarify the following item: 1. Confirm material requirements for escalator handrail support plate. | Where the two cited provisions prescribe different requirements for the escalator handrail support plate, the more stringent material/performance requirement shall be adopted for Proposal purposes. The final material specification shall be confirmed in the Detailed Design and submitted for approval in accordance with the Employer’s Requirements. No amendment is made to the RFP. | No
103 | Section VII – Employer’s Requirements / Annex I4 – Stations Platform Screen Door System (PSDS) Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station | Clause 9.4 specifies platform‑screen‑door (PSD) height of 2300 mm‑2600 mm. According to layout drawings, PSDs are installed right at platform edge; under corresponding profile conditions, installation height will far exceed 2600 mm. Discrepancy exists between drawing and text. Please kindly clarify the following item: 1. Define controlling height and installation boundary conditions for PSD, and reconcile discrepancy between drawings and text clauses. | Please refer to Annex I4 and the Employer’s Requirements. The PSD system shall comply with the dimensional, functional, safety and interface requirements stated in Annex I4 and shall be finalized during Detailed Design in coordination with the station geometry and rolling-stock/interface requirements. No amendment is made to the RFP. | No
104 | Section VII – Employer’s Requirements / Annex I4 – Stations Platform Screen Door System (PSDS) Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station | Clause 9.11.3 signal interface requires one‑to‑one correspondence and aligned‑isolation between train doors and PSD sliding doors. Both short‑consist and long‑consist trains will operate on this line with different PSD opening patterns. Number of doors, door spacing and vehicle geometric dimensions for both consists are not provided. Hence quantity and position of PSD sliding doors cannot be determined and aligned‑isolation function cannot be guaranteed. Please kindly clarify the following items: 1. Provide number of doors and door‑to‑door spacing for short‑consist and long‑consist trains respectively; 2. Provide complete geometric parameters for all train consists stopping at this station. | The final PSD door arrangement shall be coordinated with the approved rolling-stock and signalling/system interfaces during Detailed Design. No separate Proposal-stage door count, door spacing or additional rolling-stock geometric schedule is issued through this clarification. The Contractor shall provide the station/civil and interface provisions required by the RFP and shall coordinate the final PSD geometry and aligned-isolation functions with the responsible system package and the approved rolling stock. No amendment is made to the RFP. | No
105 | Section VII – Employer’s Requirements / Annex J2 – Catenary Systems Technical Specification | The maximum design speed of the line is 160 km/h, while ANNEX J2 catenary technical specification requires catenary to be designed for 200 km/h. There is inconsistency between the two requirements. Please kindly clarify the following item: 1. Confirm the design speed to be adopted for catenary system. | The maximum design speed of the railway line is 160 km/h. The design speed for the electrification and signalling systems shall be 200 km/h. Please refer to Addendum No. 2, Amendment No. 7. | Yes
106 | Section VII – Employer’s Requirements / Clause 5.3.2 – Infrastructure and Superstructure Railway Works – Scope Common to All Lots | Scope of station communication system, interface boundary with Package 2 communication system and whether station security‑check equipment is within tender scope are not defined. Please kindly clarify the following items: 1. Define scope of station communication system; confirm whether it only covers CCTV, PA, access‑control, AFC, ticket gates, clock system, emergency telephone and help‑point devices; 2. Define engineering interface between station communication system and communication system of Procurement Package 2 (Signaling, Telecommunication and Supporting Systems); 3. Confirm whether station security‑check equipment is within this contract tender scope. | Please refer to Answer 29. | No
107 | Section VII – Employer’s Requirements / Clause 9.3.4 | According to SRT‑TSI Regulation EU 1303/2014 Clause 4.2.1.5.2, cross‑passages between adjacent independent tunnel tubes shall be provided at least every 500 m. Please confirm the spacing for cross‑passages for twin‑tube TBM tunnels of this project. Please kindly clarify the following item: 1. Confirm whether cross‑passages for twin‑tube TBM‑driven tunnels shall be arranged at 500 m or 250 m intervals. | Please refer to Addendum No. 2, Amendment No. 10. | Yes
108 | Section IX – Particular Conditions / Part A – Contract Data | Please clarify scope of works for each milestone. Please kindly clarify the following items: 1. Scope of work for Milestone 2 (Infrastructure Works); 2. Scope of work for Milestone 3 (Superstructure); 3. Whether Milestone 4 is included within the scope of work under this Contract. | Milestone 2 means completion of the Infrastructure Works, Milestone 3 means completion of the Superstructure Works, and Milestone 4 means completion of Testing and Commissioning. Milestone 4 is included within the scope of this Contract. The detailed scope of each Milestone shall be read together with the Employer’s Requirements and the applicable Schedule of Priced Activities and Sub-activities. | No
109 | Section VII – Employer’s Requirements / Clause 11.6.3 – Approvals, Permits and Land Access (Project Facilities) | Responsible party for land approval, permit acquisition, land‑use right and cost‑bearing party for demolition and compensation of above‑ground facilities shall be defined. Please kindly clarify the following items: 1. Whether land approval, permits and acquisition of land‑use right within project boundary are the responsibility of Employer; 2. Whether demolition and compensation costs for above‑ground facilities shall be borne by Employer. | Please refer to Answer 45. ESMP, LMP,RF, and SEP were updated and disclosed on August 21, 2026. ESIA and the Supplementary Biodiversity Baseline Study, together with the SEA/SH Management Plans, were updated and disclosed on September 3, 2026. All documents have been made publicly available on the AYGM project webpage (aygm.uab.gov.tr/istanbul-kuzey-demiryolu-gecisi-projesi). | No
110 | Section VII – Employer’s Requirements / Chapter 7 – Design Requirements and Deliverables; Chapter 8 – Building Information Modelling Requirements; Annex B1 – Conceptual Design Report / Chapter 9 – Standards and Technical Specifications | Deliverable depth for each design phase is not specified. Whether specific software interface is mandatory for 4D‑BIM time‑model link is unclear. Requirements for as‑built model format and data interface towards TCDD asset‑management system are missing. Please kindly clarify the following items: 1. Provide required development depth and level‑of‑information for each design phase (preliminary design, detailed design, construction, as‑built); 2. Whether specific software (e.g. interface between P6 and designated BIM platform) is mandatory for time‑model linking in 4D‑BIM; 3. Deliverable format of as‑built model and technical data‑interface requirements towards TCDD asset‑management system (IBM or equivalent system). | Please refer to Section VII, Employer’s Requirements, Chapter 8 and Annex O. The Contractor shall prepare the BIM Execution Plan and the BIM models/deliverables required by the RFP. The software, data-exchange and 4D-linking solution proposed by the Contractor shall be compatible with the Employer’s specified information requirements and shall be subject to review/acceptance under the Contract. No additional mandatory software platform is prescribed by this clarification. No amendment is made to the RFP. | No
111 | Section VII – Employer’s Requirements / Clause 4.8.1 – Interface with KGM and the YSS Bridge Corridor (Lot 3); Annex B1 – Conceptual Design Report / Clause 5.1 – Yavuz Sultan Selim (YSS) Bridge Crossing | As‑built drawings, structural calculation reports and material performance reports for YSS Bridge are not available. Working‑hour restrictions for railway construction imposed by bridge operator are required. Please kindly clarify the following items: 1. Provide complete as‑built drawings, structural calculation reports and material performance reports for YSS Bridge; 2. Provide detailed working‑time restrictions for railway construction imposed by bridge operator (e.g. night‑work only, peak‑traffic avoidance etc.). | Please refer to Answer 96. | No
112 | Section VII – Employer’s Requirements / Annex B2 – INRAIL Railway Safety Plan / Clauses 3.3 – Project Components and Institutional Arrangements and 4.1 – Institutional Railway Operations | Please kindly clarify the following items: 1. “TCDD operational standards, maintenance procedures and rolling‑stock requirements” are binding design inputs for all sections; please specify the delivery format and delivery timing to contractor; 2. Specify level‑of‑detail and format requirements for operation‑maintenance manuals, comprehensive asset register and training plan; confirm whether Employer‑provided templates are available. | Please refer to the Employer’s Requirements concerning TCDD interfaces. Applicable TCDD operational standards, maintenance requirements and interface constraints are binding to the extent required by the RFP and applicable law/authority requirements. The Contractor shall obtain and coordinate the latest applicable requirements with TCDD during Detailed Design. No separate guaranteed issue date for additional TCDD documents is provided at Proposal stage. No amendment is made to the RFP. | No
113 | Section IV – Proposal Forms / Table A – Local Currency and Table B – Foreign Currency; Section III – Evaluation and Qualification Criteria | Please kindly clarify the following items: 1. Provide list of materials excluded from price adjustment in Table A (Local Currency); 2. Regarding Table B. Foreign Currency (FC), if the national statistical institute or equivalent authority of the foreign‑currency country does not issue cost indices comparable to Turkish Lira local indices A01‑A10, how shall the cost indices K01‑K10 in Table B be filled in? | For Table B (Foreign Currency), where an index for any one or more of the foreign-currency indices K01–K10 is not published by the national statistical institute or equivalent authority of the relevant currency country, the Proposer shall provide supporting documentation demonstrating that the index is not published. The Proposer may then propose a relevant alternative index for Table B, together with supporting justification. Any proposed alternative index shall be subject to the Employer’s review and approval before Contract award, if the Proposal is accepted. The remaining requirements for Table A and Table B shall be applied as stated in the RFP. | No
114 | Section VII – Employer’s Requirements / Schedule of Priced Activities and Sub-activities / Activity 10 – Systems Installation Substantial Completion | Please kindly clarify the following items: 1. Confirm whether our understanding is correct that the referenced SCADA works correspond to scope defined in ANNEX M1‑Mainline SCADA & Control Systems Technical Specification; give explanation if not. 2. Whether telecommunication works under this item fall within Package 2 scope; if not, detail the relevant scope of works. | Please refer to Answer 29. | No
115 | Section VII – Employer’s Requirements / Schedule of Priced Activities and Sub-activities / Activity 10 – Systems Installation Substantial Completion | Please kindly clarify the following items: 1. Specify exact scope of Environmental works under this item and provide relevant technical specifications; 2. Clarify detailed content of dismantling works under this item; confirm whether these dismantling works are excluded from ACTIVITY 2‑RELOCATION OF EXISTING INFRASTRUCTURE. | The Environmental works under Activity 10 comprise the environmental protection, reinstatement and related measures directly associated with the Systems Installation works, in accordance with the Employer’s Requirements and the applicable environmental and social documents. Dismantling under Activity 10 is limited to dismantling/removal directly associated with those system works. Relocation of existing infrastructure remains under Activity 2 and shall not be duplicated under Activity 10. No separate technical specification is issued through this clarification. | No
116 | Section VII – Employer’s Requirements / Clause 2.2 – Key External Stakeholders | Please kindly clarify the following items: 1. Whether “grid connection” undertaken by TEİAŞ refers to transmission lines from TEİAŞ grid up to the incoming gantry of project substation; 2. Whether all costs arising from TEİAŞ‑executed grid connection, protection study, power‑outage coordination, relocation or reinforcement of transmission assets shall be borne by contractor. | Please refer to Answer 50. | No
117 | Section VII – Employer’s Requirements / Clause 5.3.2 – Infrastructure and Superstructure Railway Works – Scope Common to All Lots; Clause 5.3.5 – Package 2: Signaling, Telecommunication and Supporting Systems | Please kindly clarify the following items: 1. Confirm whether the “water‑mist fire‑fighting system” mentioned in tender documents is identical with water‑spray fire‑fighting system in ANNEX I2 clause 6.4.1 and water‑based fire‑fighting facilities in ANNEX K clause 5; if not, provide corresponding technical specification; 2. Clause 5.3.5‑16 of Package 2 covers earthquake early‑warning system. Confirm whether earthquake early‑warning system belongs to this contract or to Package 2. If within this contract scope, provide its technical specification; 3. Provide technical specification for “climate sensor system”. | 1. The fire-fighting requirements shall be read together with Annex I2 and Annex K. No separate water-mist technical specification is issued through this clarification; the Contractor shall comply with the applicable water-based fire-fighting/fire-suppression requirements stated in the RFP. 2. Please refer to Answer 188. Systems expressly allocated to Package 2, including the signalling/telecommunication-related early-warning functions, are outside the present Package 1 scope, except for the required civil, power-supply and interface provisions. 3. The same scope-allocation principle applies to the climate-based limited-operation/climate-sensor functions. Any civil, electrical or interface provisions expressly assigned to the relevant Lot remain within that Lot Contractor’s scope. No amendment is made to the RFP. | No
118 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design – Cross-Lot Obligations; Clause 5.5.1 – Overview | Please kindly clarify the following items: 1. Clarify which Lot contractor shall be responsible for power‑supply simulation work considering conflicting descriptions in Clause 5.3.3 and Clause 5.5.1; 2. Clause 5.5.1 references Clause 5.2.3 and 5.2.4 which contain no power‑supply‑simulation content; confirm whether this is a typographical error and provide correction. | Clause 5.3.3 governs: the Lot 2 and Lot 4 Contractors shall independently prepare the system-wide train-operation/power-supply simulations. The incorrect cross-references in Clause 5.5.1 are corrected through Addendum No. 2, Amendments Nos. 22 and 39. Please refer to ER Clauses 4.6.2–4.6.4 for the Engineer’s reconciliation/direction, the allocation of revision costs to the Contractor(s) responsible for an inconsistency, and the rule that harmonization/reconciliation itself does not entitle the Contractors to additional time or cost. The Engineer shall reconcile the simulations and issue its written direction no later than the end of the Detailed Design phase, as specified in Addendum No. 2, Amendment No. 39. | Yes
119 | Section VII – Employer’s Requirements / Relevant Lot Schedule / Activity 10 – Systems Installation Substantial Completion | Please kindly clarify the following item: 1. Comment on the proposal that Employer shall coordinate and arrange all required third‑party certification by competent authorities, with each Lot contractor providing cooperation. | The proposal is not accepted. Please refer to Section VII, Employer’s Requirements, Chapters 9 and 10. The Contractor is responsible for the certification, assessment, testing and commissioning obligations allocated to it by the RFP, including engagement/coordination with the relevant assessment and certification bodies and competent authorities. No amendment is made to the RFP. | No
120 | Section VII – Employer’s Requirements / Relevant Lot Schedule / Activity 10 – Systems Installation Substantial Completion | Please kindly clarify the following item: 1. Comment on the proposal that Employer shall coordinate and organize Dynamic testing and trial running, with cooperation from each Lot contractor and Package 2 contractor. | The proposal is not accepted. Please refer to Section VII, Employer’s Requirements, Chapter 10. The Contractor has overall responsibility for planning, providing the necessary resources for, coordinating and carrying out the Testing and Commissioning activities within its contractual scope, including dynamic testing and trial-running activities as required by the RFP. No amendment is made to the RFP. | No
121 | Section VII – Employer’s Requirements / Relevant Scope and Technical Requirements (RFP p.229) | Please kindly clarify the following item: 1. Confirm whether SCADA, signaling and communication systems shall be executed by Package 2 contractor. If yes, define detailed scope of SCADA works here; if other responsible party is specified in tender documents, clearly identify the responsible executing entity. | Please refer to Answer 29. | No
122 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification; Annex E1 – Design Technical Specification | ANNEX E4‑3.5.3.2 adopts LM71 train load, but the coefficient for classified vertical loads for this project is not defined. ANNEX E1‑2.1 requires LM71, SW/0 and SW/2 to be applied with maximum axle load of 25 t. SW/2 is designated for heavy‑haul railways while this line is not heavy‑haul. LM71 itself corresponds to maximum axle load of 25 t. Please kindly clarify the following items: 1. Specify coefficient value of classified vertical loads for this project; 2. Confirm whether SW/2 load combination shall be applied to this project; 3. Confirm whether classified vertical loads factor of 1.0 can be adopted given project maximum axle load of 25 t. | Please refer to Annex E4. The bridge design shall include the load models and associated factors expressly required by Annex E4 and the applicable standards. The Contractor shall demonstrate compliance in the Detailed Design and shall obtain any required authority approvals. a factor will be taken as 1.33. No amendment is made to the RFP. | No
123 | Section I – Instructions to Proposers (ITP) / ITP 19.1 and ITP 19.3; Section II – Proposal Data Sheet (PDS) / ITP 19 and ITP 19.3 | In order to prepare a fully compliant submission, we would appreciate your clarification on the following three points: 1.Is a Proposal Security in the form of an unconditional and irrevocable bank guarantee, issued by a reputable commercial bank domiciled outside the Republic of Türkiye (yet within an eligible country), acceptable under the relevant tender requirements? 2.With respect to the definition of "eligible countries" for the purposes of the bank guarantee provisions, are all of the following jurisdictions—namely, France, Spain, China, and Japan—recognized as qualifying eligible countries? 3. The RFP requires “the written letter confirming the validity of the Proposal Security from the issued Bank.” Please confirm: Whether this letter should be a separate document from the issuing bank or not; If yes, what is the requirement for the content and form of this letter? | Please refer to ITP 19.1, ITP 19.3 and the corresponding PDS provisions. A Proposal Security in the form of an unconditional bank guarantee issued by a bank in an eligible country is acceptable provided that it complies with the form and requirements of the RFP. Where the issuer is a non-bank financial institution located outside the Employer’s country, the additional requirements of ITP 19.3 shall apply. Forms of security expressly excluded by the PDS are not acceptable. No amendment is made to the RFP. | No
124 | Section VII – Employer’s Requirements / Annex F – Civil Works (Infrastructure) Technical Specification / Clause 2.21.10.3 – Quality Control | Please kindly clarify the following item: 1. Please clarify the time‑sequence relationship between the initial setting time and the 50 kPa strength requirement. 2. Two different 28‑day compressive strength values for grout are specified in the above clauses: minimum 8 MPa (100 mm cube specimen) and minimum 2.0 MPa. Please confirm which 28‑day compressive strength requirement shall apply to the grouting material. | The requirement for 50 kPa strength can be found in Annex F 2.21.12 Additional Provisions. For 28-day compressive strength of grout material See Addendum No. 2, Amendment No. 11. | Yes
125 | Section VII – Employer’s Requirements / Annex F – Civil Works (Infrastructure) Technical Specification / Clauses 2.21.10.4 – Material and 2.21.10.5 – Grout Mixture | Please clarify whether the grouting material shall comply with the requirements under Clause 2.21.10.5, or the requirements under Clause 2.21.12 Additional provisions. | Please refer to Answer 124 and Addendum No. 2, Amendment No. 11. The cited provisions shall be read together. For the 28-day compressive strength of the grout material, the amended requirement of 2.0 MPa applies; the 50 kPa requirement under Clause 2.21.12 remains unchanged. | Yes
126 | Section VII – Employer’s Requirements / Annex J – Power Supply and Traction Power System Technical Specification / Traction Substation Feeder Configuration | Substations can be configured with either a single feeder or two feeders; please clarify which configuration is required. | The final substation feeder configuration shall be determined during Detailed Design on the basis of the traction-power studies, reliability and operational requirements, system architecture, redundancy criteria and the approvals of the Engineer and the relevant utility/authority. The alternatives illustrated in the tender documents do not constitute a universal requirement for every substation unless expressly stated. No amendment is made to the RFP. | No
127 | Section VII – Employer’s Requirements / Annex J – Power Supply and Traction Power System Technical Specification; Annex L – Signaling and Telecommunication System Technical Specification / Substation CCTV and Remote Monitoring | The substations under this project are designed as unattended substations. Tender documents contain no relevant provisions regarding video‑surveillance system for substations. If such system is required, please confirm whether it shall be connected to the dispatch console, and specify the responsible executing party. Please kindly clarify the following items: 1. Whether video‑surveillance system shall be provided for unattended substations; 2. If video‑surveillance system is required, whether it shall be connected to the dispatch console; 3. If such system is to be implemented, specify the responsible executing entity. | The Contractor shall provide the security, monitoring, communications and SCADA interfaces required for safe and compliant operation of unattended substations in accordance with the Employer’s Requirements and the applicable technical specifications. The detailed CCTV/video-surveillance arrangement, where required, shall be developed during Detailed Design and coordinated with the relevant systems/interface packages. No amendment is made to the RFP. | No
128 | Section VII – Employer’s Requirements / Annex C – Site Information; Annex E1 – Design Technical Specification / Meteorological Design Data | Existing geotechnical and conceptual‑design annexes lack meteorological parameters including annual average precipitation / evaporation, maximum precipitation / evaporation, average wind speed, maximum wind speed, prevailing wind direction, extreme high and low temperatures, which restrict design for drainage, disaster prevention and structural loads. Please kindly clarify the following item: 1. Provide complete above‑mentioned meteorological base data for the whole alignment. | The Employer has provided the tender-stage meteorological and site information available. The Contractor shall obtain, verify and use the official meteorological data necessary for Detailed Design from the competent authorities, including the General Directorate of Meteorology where applicable. No amendment is made to the RFP. | No
129 | Section VII – Employer’s Requirements / Clause 4.8.2 – Interface with Airport Operators (Lots 1 and 4) | The project is adjacent to operational airport. Constraints from airport operator concerning construction working hours, site access, noise limits, height restriction and other restrictions are required for design and construction planning. Please kindly clarify the following item: 1. Provide control requirements issued by the Airport Operator concerning construction working hours, site access, noise limits, height restriction values and other relevant constraints. | Please refer to Section VII, Employer’s Requirements, Clauses 4.8.2 and 7.6. The Contractor shall establish the required interface protocol with the relevant airport operator and DHMİ and shall obtain all required approvals for access, working hours, crane operations, temporary structures, obstacle-limitation surfaces, security, noise and other operational restrictions. Such constraints shall be incorporated into the Contractor’s design, methodology and programme. No separate fixed construction-window schedule is issued at Proposal stage. No amendment is made to the RFP. | No
130 | Section VII – Employer’s Requirements / Clause 7.2.3 – Utility Records; Annex C – Site Information | Information on utilities to be relocated / protected (power, communication, water supply, sewerage, natural gas etc.) and surrounding buildings / structures requiring protection within each section are not available, which affects risk assessment and design work. Please kindly clarify the following item: 1. Provide information on utilities requiring relocation and protection (power, communication, water supply, sewerage, natural gas, etc.) within each contract section, as well as details of surrounding buildings and structures requiring protection. | Please refer to Answer 68. | No
131 | Section VII – Employer’s Requirements / Sabiha Gökçen Airport Station; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station; Annex C – Site Information | Please kindly clarify the following item: Please provide information on existing buildings and structures surrounding Sabiha Station site, to support determination of construction method, excavation sequence and supporting structure type. | Please refer to Answer 32. The Employer has provided the tender-stage information available for Sabiha Gökçen Airport Station. The Contractor shall verify the existing buildings, structures, underground facilities and interfaces necessary for its Detailed Design and construction methodology. No additional information is issued through this clarification. No amendment is made to the RFP. | No
132 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J2 – Catenary Systems Technical Specification / Existing-Line OCS Interface | Train consist configuration, pantograph quantity, pantograph spacing and electrical connection condition directly determine catenary neutral‑section arrangement. Existing‑line catenary drawings at connection point are missing. It is also unclear whether modification works on existing‑line catenary due to line connection fall within this contract scope. Please kindly clarify the following items: 1. Provide train consist configuration, pantograph quantity, pantograph spacing and electrical connection details; 2. Provide existing‑line catenary design drawings and documents at connection point; 3. Confirm whether modification works on existing‑line catenary caused by project connection are within this contract scope. | Please refer to Answers 52 and 54. | No
133 | Section VII – Employer’s Requirements / Clause 4.5 – Civil Infrastructure and Signaling and Telecommunication Interface; Annex L – Signaling and Telecommunication System Technical Specification / Maltepe CTC Interface | It shall be confirmed whether civil‑works expansion of Malpet CTC falls within Procurement Package 1 scope. Please kindly clarify the following item: 1. Whether civil‑works expansion of Malpet CTC is included within Procurement Package 1. | Please refer to Answer 29. | No
134 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification; Annex C – Site Information / Hydrology and Navigation Requirements | The alignment crosses several rivers. It is not specified whether these rivers are navigable. For navigable rivers, navigation clear‑width and clear‑height requirements govern bridge span arrangement. Please kindly clarify the following item: 1. Clarify whether rivers crossed by the alignment are navigable; if yes, provide controlling requirements for navigation clear height and clear width. | No specific navigation clear-height or clear-width values are prescribed in the RFP for the rivers crossed by the alignment. The Contractor shall verify, during Detailed Design, whether any navigation requirements apply at the relevant crossing and shall coordinate with the competent authorities. Any applicable navigation clearance and pier-location requirements shall be incorporated into the final design together with the hydraulic and hydrological requirements. No amendment is made to the RFP. | No
135 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Proposal Submission Deadline / Extension Request | Considering the Design and Build nature of the Contract under the FIDIC Plant and Design-Build Contract (Yellow Book), the preparation of a fully compliant and technically sound Tender requires substantial engineering, design development and coordination activities in addition to the preparation of the commercial proposal. Furthermore, due to the complexity and multidisciplinary nature of the Works, adequate time is required to coordinate the technical inputs, verify quantities and assumptions, assess interface requirements, and ensure that the proposed design and construction methodology are fully aligned with the Employer’s Requirements and the Tender Documents. In this regard, we believe that allowing an additional two (2) months would provide all prospective Tenderers with sufficient time to prepare complete, technically robust and competitive Tenders and would contribute to a more comprehensive and effective tender evaluation process. | Please refer to Addendum No. 1. | No
136 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel / Multiple Lots | We refer to Section III, Subsection 1.4 (Contractor’s Representative and Key Personnel) of the RFP Document, which currently contains the following requirement: “Note: If the Proposer submits proposals for multiple lots, it must propose separate teams of key personnel for each lot. Specifically, for each of the below listed key personnel positions different persons should be proposed for the multiple lots, such that the same person is not common in the multiple lots.” In order to optimize technical efficiency, maintain management consistency, and avoid unnecessarily duplicating key personnel resources across multiple Lots, we kindly request clarification as to whether the Employer would consider allowing Proposers bidding for multiple Lots to propose the same Key Personnel for more than one Lot, provided that the proposed personnel fully meet the qualification requirements for the respective positions and that their availability and capacity are sufficient to adequately perform the required duties for each Lot. | Please refer to Answer 72. | No
137 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel | Does the technical personnel requested to be submitted in the tender need to work within the bidder? Can we procure from external sources? | The RFP does not require proposed Key Personnel to be existing permanent employees of the Proposer/JV at Proposal stage unless expressly stated for a particular position. Personnel sourced externally may be proposed provided that they meet all qualification requirements, are duly committed and available for the relevant Lot, and the required personnel forms and supporting evidence are submitted. No amendment is made to the RFP. | No
138 | Section I – Instructions to Proposers (ITP) / ITP 11.1 – Language of Proposals / Translation | Is it sufficient to have a certified translator for the documents in the tender process or a notarized divorce certificate is also required? | Please refer to ITP 11.1 and the applicable Proposal Forms. Documents forming part of the Proposal shall be in English as required by the RFP. Where supporting documents are issued in another language, the pertinent parts shall be accompanied by an English translation, and the English translation shall govern for interpretation. The RFP does not impose a general requirement that every translation be notarized unless notarization/legalization is expressly required for the underlying document or form. No amendment is made to the RFP. | No
139 | Section IV – Proposal Forms / Letter of Proposal – Financial Part / Option 2 – Multiple Lots | In the "Letter of Proposal - Financial Part", as Option 2, it is mentioned that “in case of multiple lots: (a) Total price of each lot [insert the total price of each lot in words and figures, indicating the various amounts and the respective currencies]; and (b) Total price of all lots (sum of all lots) [insert the total price of all lots in words and figures, indicating the various amounts and the respective currencies]” In this regard, please clarify if a bidder submits proposals for multiple lots, should both technical and financial proposals with qualification documentations to be submitted in separate packages/files for each lots, or is it sufficient to submit them as a single, combined package covering all lots? | Please refer to Answer 65. | No
140 | Section III – Evaluation and Qualification Criteria / Clause 3.2 – Average Annual Construction Turnover | Clause 3.2 requires minimum annual construction turnover for the last 5 years based on certified payments. Our audited financial statements clearly show our annual construction turnover. Could the Employer confirm if we can submit these approved financial statements as supporting evidence? We request to submit them in lieu of individual interim payment certificates or contract payment documents. | Please refer to Answer 9. | No
141 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Proposal Submission Deadline / Extension Request | Due to the comprehensive technical and financial requirements of the tender, we require additional time to prepare our proposal and compile all necessary official documents. In order to prepare a high-quality, competitive, and fully compliant bid, we kindly request the Employer to grant a 2-month extension for the final bid submission deadline. | Please refer to Addendum No. 1 | No
142 | Section IV – Proposal Forms / Schedule of Payments | At “Inrail-RFP” document, page 140, the “Schedule of Payments” section is blank, could you please inform us about how the payments will be executed for the LS prices of sub-activities. For example, the sub-activities such as “Cut and Cover Tunnels Construction Works” or “Bridge-3 Construction Works” or “TBM Tunnel Works”, how the payments will be executed. Will there be any breakdown or percentage for payments of these activities or will the payment of each activity be done after the 100% completion of the activity | Please refer to Answer No. 7 and Addendum No. 2, Amendment No. 12, concerning the Schedule of Payments. | Yes
143 | Section II – Proposal Data Sheet (PDS) / ITP 1.1, ITP 7.1 and ITP 23.1; Section IV – Proposal Forms / Letter of Proposal – Technical Part and Financial Part; Form of Proposal Security – Demand Guarantee | For the purpose of consistently preparing all Proposal Forms and documents to be submitted to the Employer, including the Proposal Securities, for Lot 1, Lot 2, Lot 3 and Lot 4, we kindly request the Employer to confirm the exact Employer/Beneficiary details, Proposal/Contract name and RFP reference(s) to be used, and whether the following information may be used accordingly: Employer / Beneficiary: Ministry of Transport and Infrastructure, Directorate General of Infrastructure Investments Address: Hakkı Turayliç Caddesi No:5/B, Emek, Floor 6, Room 616, Ankara, 06500, Republic of Türkiye Proposal Names: - Design and Construction of Infrastructure & Superstructure Works including electricfication, with four Lots (Lot-1, Lot-2, Lot-3, Lot-4), under İstanbul North Rail Crossing Project - Lot 1- Construction and Electrification Works for Çayırova – Sabiha Gökçen Airport – Kurtdoğmuş Corridor - Design and Construction of Infrastructure & Superstructure Works including electrification, with four Lots (Lot-1, Lot-2, Lot-3, Lot-4), under İstanbul North Rail Crossing Project - Lot 2 - Construction and Electrification Works for Kurtdoğmuş - Alibahadır Corridor - Design and Construction of Infrastructure & Superstructure Works including electrification, with four Lots (Lot-1, Lot-2, Lot-3, Lot-4), under İstanbul North Rail Crossing Project - Lot 3 - Construction and Electrification Works for Alibahadır - YSS Bridge - Mithatpaşa Corridor - Design and Construction of Infrastructure & Superstructure Works including electrification, with four Lots (Lot-1, Lot-2, Lot-3, Lot-4), under İstanbul North Rail Crossing Project - Lot 4 - Construction and Electrification Works for Mithatpaşa - İstanbul Airport - Çatalca Corridor As four separate Proposals will be submitted for Lots 1, 2, 3 and 4, we kindly request the Employer to confirm that, wherever the Proposal/Contract name is required in any Proposal Form or document, including the Proposal Security, each Proposal shall separately refer to the respective Lot and its corresponding Corridor name as stated above. Furthermore, please confirm whether the Request for Proposals No. “AYGM-INRAIL-2025-YAP 01/1-2-3-4” shall be stated in full in all applicable Proposal Forms and documents, or whether a Lot-specific reference shall be used for each Lot (i.e., AYGM-INRAIL-2025-YAP 01/1, 01/2, 01/3 and 01/4 for Lots 1, 2, 3 and 4, respectively). Please also confirm the exact information to be inserted in the separate “RFP No.” and “Request for Proposal No.” fields appearing in the Letter of Proposal Forms. | Please refer to PDS ITP 1.1 and the applicable Proposal Forms. The Employer, Project, Contract title and RFP identification shall be stated as given in the RFP. For a Proposal covering one or more Lots, the Proposer shall identify the relevant Lot(s) consistently in the Proposal Forms and supporting documents. The RFP No. remains AYGM-INRAIL-2025-YAP 01/1-2-3-4; no separate new procurement number is created for each Lot unless expressly indicated by the Employer. No amendment is made to the RFP. | No
144 | Section I – Instructions to Proposers (ITP) / ITP 17.4–17.5; Section II – Proposal Data Sheet (PDS) / ITP 17.4(b) and 17.5; Section III – Evaluation and Qualification Criteria / Item 1.2 and relevant criteria; Section IV – Proposal Forms / Subcontractors and Qualification Forms | PDS ITP 17.5 identifies certain parts of the Works for which Specialized Subcontractors may be proposed. We understand that, for the purposes of ITP 17.5, the specific experience of Specialized Subcontractors proposed for such parts of the Works may be considered in assessing the qualification of the Proposer, while their general experience and financial resources shall not be added to those of the Proposer for qualification purposes. Please confirm our understanding and clarify the qualification requirements applicable to: (i) ordinary Subcontractors proposed under ITP 17.4; and (ii) Specialized Subcontractors proposed under ITP 17.5. In particular, please confirm whether an ordinary Subcontractor is required to demonstrate qualifications only in relation to its proposed subcontracted scope, and please identify the qualification criteria applicable to Specialized Subcontractors. Please also confirm the exact Section IV forms and supporting documents required to be separately completed and submitted by each proposed Specialized Subcontractor, including, as applicable, Forms CON-3, CON-4, FIN-3.1, FIN-3.2, EXP-4.1, EXP-4.2(a), EXP-4.2(b) and EXP-4.2(c). Furthermore, considering that ITP 17.5 provides that the general experience and financial resources of Specialized Subcontractors shall not be added to those of the Proposer for qualification purposes, please clarify whether the financial information requested in Forms FIN-3.1 and FIN-3.2 is nevertheless required to be submitted by Specialized Subcontractors and, if so, for what purpose such information will be evaluated. Please also confirm whether any proposed ordinary Subcontractor or Specialized Subcontractor is required to separately nominate Key Personnel and submit Forms PER-1 and PER-2 or any other personnel documentation, or whether the Key Personnel requirements are assessed solely at Proposer/JV level. | Please refer to ITP 17.4, ITP 17.5, PDS ITP 17.5 and Section III. An ordinary Subcontractor does not contribute its qualifications to the Proposer and shall be qualified by the Contractor for the subcontracted scope in accordance with the Contract. For a Specialized Subcontractor permitted under PDS ITP 17.5, only the specific experience relevant to the designated specialized part may be considered for the Proposer’s qualification; the Specialized Subcontractor’s general experience and financial resources are not added to those of the Proposer. The Section IV forms shall be completed by a Specialized Subcontractor only where the relevant form expressly requires information from a Specialized Subcontractor. Forms PER-1/PER-2 are submitted for the Key Personnel proposed by the Proposer/JV; a Subcontractor is not required to nominate a separate duplicate Key Personnel team unless the RFP expressly requires it. | No
145 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Clause 9.2; Annex B2 – INRAIL Railway Safety Plan; Annex G – Track Works (Superstructure) Technical Specifications; Annex A1 – Tunnel Typical Cross Sections / Drawing AYGM-INR-STR-TCS-007 | Mass-Spring System (MSS) is indicated underneath the precast panels on the drawing name of "TYPE-6 NATM-Double Track Tunnel" and numbered "AYGM-INR-STR-TCS-007" within the "Tunnel Typical Cross Sections". But we noticed that there was not any specific technical specification in term of the material "Mass-Spring System". For us to review and select the most proper material, can you please provide us the required technical specification for "Mass-Spring System" (MSS)? | Please see Addendum No. 2, Amendment No. 13 | Yes
146 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / AYGM-INR-ALG-PLP-001~044 / Tunnel 12 Ground Profile and Portal Chainage | In the alignment profile shared in the bid documents as drawing “AYGM-INR-ALG-PLP-001~044,” it can be seen that the ground profile at the start of Tunnel 12 falls below the tunnel clearance. Please confirm the shared ground profile and the entrance chainage of Tunnel 12. | The tender-stage alignment/profile information shall be used as the reference basis. Any apparent conflict between the shown ground profile and the tunnel clearance/portal arrangement shall be verified by the Contractor through its surveys and investigations and resolved in the Detailed Design in accordance with the Employer’s Requirements. No separate revised Tunnel 12 portal chainage is issued through this clarification. No amendment is made to the RFP. | No
147 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Construction and Ventilation Shafts | Could you please clarify the purpose of the shafts given in the project. | The shafts shown in the Reference/Conceptual Design are indicative facilities associated with the construction, access, ventilation, emergency, operation and/or maintenance requirements of the tunnel works, as applicable. The Contractor shall verify their function, necessity, location and final configuration during Detailed Design and shall provide all shafts and associated works required to satisfy the Employer’s Requirements, safety requirements and its approved construction methodology. No amendment is made to the RFP. | No
148 | Section VII – Employer’s Requirements / Annex A1 – Tunnel Drawings; Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Cross-Passage Tunnels | Could you please provide typical section for Cross Passage Tunnels | Please see Addendum No. 2, Amendment No. 10 | No
149 | Section VII – Employer’s Requirements / Annex A1 – Tunnel Drawings; Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Flare and Cut-and-Cover Structures at Tunnel Portals | Could you please provide typical section for Flaute and cut and cover structures given on tunnel entrance and exits. | No additional tender-stage typical section is issued through this clarification for the referenced flared/cut-and-cover transition structures. The Contractor shall develop the applicable detailed cross-sections during Detailed Design in accordance with the alignment, tunnel/civil Technical Specifications, structural requirements and interfaces shown in the RFP. No amendment is made to the RFP. | No
150 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / AYGM-INR-ALG-PLP-001~044; Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Cut Slopes | Could you please provide cut slope angles/proportions shown in alignment plan drawing “AYGM-INR-ALG-PLP-001~044,” | The cut-slope angles/proportions shown at tender stage are not fixed universal design values. Final cut slopes shall be established by the Contractor during Detailed Design on the basis of the applicable geotechnical parameters, stability analyses, drainage requirements and site-specific ground conditions, and shall be submitted for approval. No amendment is made to the RFP. | No
151 | Section VII – Employer’s Requirements / Annex A1 – Tunnel Drawings; Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Tunnel Portal Face Slopes | Could you please clarify how the tunnel face slopes at the tunnel entrance and exit portals? | Tunnel portal/face slopes shall be determined by the Contractor during Detailed Design on the basis of the site-specific geotechnical conditions, portal geometry, stability analyses, drainage and protection requirements. The tender-stage drawings are reference/conceptual information unless expressly stated otherwise. No amendment is made to the RFP. | No
152 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings / Tunnel 1D-2 End; Annex F – Civil Works (Infrastructure) Technical Specification / Portal Slopes | Could you please clarify why the slopes at the Tunnel 1D-2 END is not shown. | The tender-stage drawings are conceptual and do not define the final portal-slope geometry at Tunnel 1D-2 END. The Contractor shall determine and design the required portal slopes during Detailed Design on the basis of the verified geological and geotechnical conditions, Annex F and the applicable Employer’s Requirements. No additional portal-slope drawing is issued through this clarification. No amendment is made to the RFP. | No
153 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Structural Drawings; Annex B1 – Conceptual Design Report; Annex E4 – Railway Bridge Design Technical Specification / Viaduct Pier Locations and Structural System | When examining the pier locations based on the alignment profile given in the tender documents, some piers or their foundations overlap with the existing railway or road. For instance, the starting piers of Viaduct-2 show this situation. At these locations, we consider that the bridge type and standard 40 m span length given in the tender documents will not be adequate. We kindly ask for your review and comments on this issue. | Please refer to Section VII, Employer’s Requirements and Annex E4. The bridge/viaduct layouts shown in the Reference/Conceptual Design are indicative. The Contractor shall optimize the structural system, span arrangement, foundations and clearances during Detailed Design so as to avoid unacceptable conflicts with existing roads, railways and utilities and to comply with all applicable technical and third-party requirements. No amendment is made to the RFP. | No
154 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Dynamic Analysis Using ‘Real Trains’; Annex J – Power Supply and Traction Power System Technical Specification / Train Data | In ANNEX E4 – Railway Bridge Design Technical Specification, it is specified that "Real Trains" shall be utilized for the dynamic analysis of railway bridges. However, the tender documents lack the necessary technical parameters (e.g., axle loads, axle spacings, vehicle geometry, and train configurations) required to define these "Real Trains". Could the Administration please provide the full technical characteristics and configuration parameters for the required "Real Trains" to be used in the dynamic analyses; or alternatively, confirm that performing the dynamic analysis solely using the standard HSLM (HSLM-A / HSLM-B) models in accordance with TS EN 1991-2 will be deemed sufficient and acceptable? | Please refer to Annex E4 and Answer 52. The Contractor shall carry out the dynamic analyses required by Annex E4 using the applicable standard load models and the project train/operational parameters established under the RFP and Detailed Design. The requirement for analysis with “Real Trains”, where expressly stated in Annex E4, is not waived by this clarification. The necessary train parameters shall be developed/verified through the prescribed railway-system and operator interfaces as part of Detailed Design. No amendment is made to the RFP. | No
155 | Section I – Instructions to Proposers (ITP) / ITP 1.3(b), ITP 4.1 and ITP 21.1–21.2; Section II – Proposal Data Sheet (PDS) / ITP 21.1(c) | ITP 4.1 and PDS ITP 21.1(c) refer to the nomination of “a Representative” of the JV, while ITP 21.1 provides that the Proposal may be signed by a “person or persons” duly authorized to sign on behalf of the Proposer, and ITP 21.2 refers to “an authorized representative of the JV”. ITP 1.3(b) further provides that, where the context so requires, the singular means the plural and vice versa. Please confirm: (i) whether a JV may nominate more than one Representative, each authorized to act for and on behalf of all JV members during the RFP process; and (ii) whether a single Power of Attorney may authorize more than one named person to sign the Proposal on behalf of the JV, with the Proposal being validly signed by any one or more of such authorized persons, as specified in the Power of Attorney. If only one JV Representative and/or one Proposal signatory is permitted, please confirm accordingly. | Please refer to ITP 4.1, ITP 21.1 and PDS ITP 21.1. The JV shall nominate a representative duly authorized to conduct all business for and on behalf of the JV. The Proposal may be signed by the person or persons duly authorized by the Proposer/JV in accordance with the power of attorney. The individual signing the Proposal need not be the same person as the JV Representative, provided that each authorization is valid and compliant with the RFP. No amendment is made to the RFP. | No
156 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(i) – Joint Venture Arrangements / Lead Member Share | With reference to PDS ITP 12.2(i), which states that “the Lead Member shall have the lead/principal share in the Joint Venture”, please confirm the minimum participation/share required for the Lead Member. In particular, please confirm whether a 50%-50% JV structure would be acceptable where one member is expressly designated as the Lead Member, or whether the Lead Member is required to hold a higher participation/share than any other JV member. If the latter applies, please confirm whether a 50.01%-49.99% participation would satisfy this requirement. Please also confirm whether the Lead Member and its lead/principal share are required to be maintained throughout the bidding process and, if awarded, throughout Contract execution. In the event of any subsequent change in the JV participation/shareholding, composition or membership, please confirm whether the prior consent of the Employer referred to in PDS ITP 12.2(i) is sufficient, or whether the World Bank’s no-objection or any other approval is also required. | Please refer to PDS ITP 12.2(i). The Lead Member shall have the lead/principal share in the JV. The RFP does not prescribe a numerical minimum percentage; however, the participation structure shall clearly identify a Lead Member having the principal share and authority contemplated by the RFP. A structure in which no member has a principal share would not demonstrate compliance with this requirement. The Lead Member and the JV participation structure shall be maintained in accordance with PDS ITP 12.2(i). Any subsequent change in the JV participation/shareholding, composition or membership shall be subject to the prior consent of the Employer. Following Contract signature, any such change shall also be subject to the World Bank’s prior no-objection. No amendment is made to the RFP. | No
157 | Section II – Proposal Data Sheet (PDS) / ITP 21.1(b) – Establishment and Legal Status Documents | With reference to PDS – ITP 21.1(b), which requires “Copies of original documents indicating the Proposer's establishment, legal status, place of registration and headquarters,” we understand that documents issued in a language other than English may be submitted together with their English translations, duly notarized in the country where the Sole Participant or respective JV member is registered, without any further legalization or apostille. We understand that the same applies to the Power of Attorney. Please confirm our understanding. | Please refer to Answer 138. | No
158 | Section I – Instructions to Proposers (ITP) / ITP 11.1 – Language of Proposals / Translation | We understand that, for documents issued in a language other than English, an English translation prepared and certified by a certified translator is sufficient. Please confirm our understanding. | Please refer to Answer 138. | No
159 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel; Section IV – Proposal Forms / Forms PER-1 and PER-2 | With reference to Section III – Evaluation and Qualification Criteria, Item 1.4 – Contractor’s Representative and Key Personnel, we understand that the proposed Contractor’s Representative and Key Personnel are not required to be directly employed by or on the payroll of the Proposer or a JV member at the Proposal submission date, and may be personnel of a subcontractor or other external personnel committed to the Project. Please confirm our understanding. Please also confirm that such personnel will be acceptable provided that the applicable qualification, availability and other requirements of the RFP are satisfied. | Please refer to Answer 137. | No
160 | Section VII – Employer’s Requirements / Annex Q – Quality Management / Project Quality Requirements / Clauses 5, 12 and 13 | Clause 12 and Clause 13 both carry the heading “Non-Conformance and Corrective Action Management”, whereas the content of Clause 13 addresses the audit programme. In addition, the heading of Clause 5 reads “PROJECT PROJECT QUALITY PLAN (PQP)”. The Employer is requested to confirm the correct heading of Clause 13 and to confirm that the heading of Clause 5 is to be read as “Project Quality Plan (PQP)”. | Please refer to Addendum No. 2, Amendment No. 18. | Yes
161 | Section VII – Employer’s Requirements / Annex Q – Quality Management / Project Quality Requirements / Clause 14 – References and Applicable Standards | Clause 14 (References and Applicable Standards) is followed directly by sub-clause 14.3 (Priority of Standards). Sub-clauses 14.1 and 14.2 do not appear in the issued document, and the table of reference standards is presented under the Clause 14 heading without a sub-clause number. The Employer is requested to confirm whether sub-clauses 14.1 and 14.2 have been omitted in error and, if so, to issue them; alternatively, to confirm the sub-clause number under which the table of reference standards is to be cited. | Please refer to Addendum No. 2, Amendment No. 19. | Yes
162 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(k); Section VII – Employer’s Requirements / Annex Q – Quality Management / Project Quality Requirements / Clause 5.1 – Project Quality Plan | PDS ITP 12.2(k) requires a Draft Project Quality Plan to be submitted with the Proposal, while Annex Q Clause 5.1 requires the Contractor to prepare and submit the Project Quality Plan within thirty (30) days following the Commencement Date. Please clarify the required level of detail and minimum content of the Draft Project Quality Plan to be submitted at Proposal stage, and confirm that the Project Quality Plan required under Annex Q Clause 5.1 will constitute the subsequent detailed/final development of the Draft Project Quality Plan submitted with the Proposal. | Please refer to PDS ITP 12.2(k) and Annex Q. The Draft Project Quality Plan submitted with the Proposal is a tender-stage document demonstrating the Proposer’s proposed quality-management approach. Following award, the Contractor shall develop, finalize and submit the Project Quality Plan within the period specified in Annex Q, incorporating the Contract requirements, approved design/construction arrangements and the Engineer’s comments. These requirements are complementary and not contradictory. No amendment is made to the RFP. | No
163 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(k); Section VII – Employer’s Requirements / Annex Q – Quality Management / Project Quality Requirements / Quality Submission Forms and Page Limits | The Employer is requested to confirm whether mandatory forms or templates are prescribed for the quality submission, and the page limits applicable to the quality documentation, if any. | No additional mandatory quality-plan template or page limit is prescribed beyond the forms, contents and requirements expressly stated in the RFP. The Proposer may use its own format provided that all information required by PDS ITP 12.2(k), Annex Q and the Technical Proposal Forms is clearly addressed and readily identifiable. No amendment is made to the RFP. | No
164 | Section VII – Employer’s Requirements / Annex Q – Quality Management / Project Quality Requirements / Clause 14 – ISO/IEC 17025 and Testing Laboratory | Clause 14 references ISO/IEC 17025. The Employer is requested to confirm whether the testing laboratory is to be established by the Contractor on Site, whether an accredited external laboratory is acceptable, and whether the Employer will nominate or pre-approve the laboratory. | Please refer to Annex Q. Testing shall be carried out by laboratories meeting the accreditation and competence requirements specified in the RFP, including ISO/IEC 17025 where applicable, and subject to the Engineer’s/Employer’s acceptance as required. The RFP does not require the Contractor to establish a new dedicated laboratory where a compliant accredited laboratory can perform the required tests, unless a specific Contract requirement states otherwise. No amendment is made to the RFP. | No
165 | Section VII – Employer’s Requirements / Annex Q – Quality Management / Project Quality Requirements / Clause 6.4 – Independent Reviewers and Third-Party Verification | Clause 6.4 states that the Employer reserves the right to appoint independent reviewers or third-party verification entities. The Employer is requested to confirm whether the cost of such appointments is to be borne by the Contractor and, if so, whether a provisional sum is included in the Contract for this purpose. | Please refer to Annex Q and the applicable Contract provisions. Where the Employer elects to appoint an independent reviewer or third-party verification entity, the allocation of the associated cost shall be as expressly stated in the Contract. The Contractor shall nevertheless provide all access, information, documentation and cooperation required for such review and shall include in its Contract Price all costs allocated to the Contractor by the RFP. No separate provisional sum is established unless shown in the Schedule of Priced Activities. No amendment is made to the RFP. | No
166 | Section I – Instructions to Proposers (ITP) / ITP 4.2(e), (f) and (g); Section IV – Proposal Forms / Letter of Proposal – Technical Part | The Letter of Proposal – Technical Part requires the Proposer to certify that it, including any subcontractors for any part of the Contract, meets the eligibility requirements and has no conflict of interest in accordance with ITP 4. Please confirm whether the Proposer’s certification in the Letter of Proposal – Technical Part is sufficient for this purpose, or whether each proposed Subcontractor and Specialized Subcontractor is required to submit a separate declaration and/or supporting documentation demonstrating compliance with the eligibility and conflict-of-interest requirements under ITP 4. Please also confirm the applicable documentation requirements for any Subcontractor proposed for appointment after Contract award. | Please refer to ITP 4.2 and the Letter of Proposal – Technical Part. The eligibility and conflict-of-interest declarations apply to the Proposer, each JV member and, where expressly stated in the RFP, relevant Subcontractors/Specialized Subcontractors. The certifications shall be made exactly as required by the prescribed Proposal Forms. No amendment is made to the RFP. | No
167 | Section I – Instructions to Proposers (ITP) / ITP 13.1; Section IV – Proposal Forms / Form Instructions and Notes | Section IV contains various instructional texts, Notes to Proposers, bracketed guidance and template directions. Certain forms expressly require such text to be deleted, while the same instruction is not consistently stated for all forms. Please confirm which instructional notes, bracketed guidance and template directions shall be deleted from the final Proposal and which, if any, shall remain where no express deletion instruction is provided. Please also confirm that deletion of such instructional text in accordance with the Employer’s instruction will not constitute an alteration to the prescribed form. | Please refer to ITP 13.1 and the instructions contained in the prescribed Proposal Forms. Bracketed guidance, notes and instructional text that the form directs the Proposer to delete or replace shall be dealt with in accordance with those instructions. The substantive wording and declarations of the prescribed forms shall not be altered except where the form expressly permits completion or deletion. No amendment is made to the RFP. | No
168 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(k); Section I – Instructions to Proposers (ITP) / ITP 18.2(d); Section IV – Proposal Forms / Local Labour Method Statement | Please confirm whether completion of the Local Labour Method Statement provided in Section IV is sufficient to satisfy the relevant RFP requirement, or whether a separate detailed Local Labour Method Statement and/or supporting annexes are required in addition to the prescribed form. If additional documentation is required, please specify the required contents and submission format. | Please refer to PDS ITP 12.2(k), ITP 18.2(d) and the Local Labour Method Statement in Section IV. Completion of the prescribed form may be supplemented by annexes or supporting narrative where necessary to fully address the required methodology. A separate duplicative document is not required where the submitted Local Labour Method Statement clearly contains all information required by the RFP. No amendment is made to the RFP. | No
169 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(k); Section IV – Proposal Forms / Code of Conduct for Contractor’s Personnel (ES) | Please confirm whether the implementation details required under PDS ITP 12.2(k), including incorporation into conditions of employment/engagement, training, monitoring and handling of breaches, are to be provided as a separate annex to the prescribed Code of Conduct form. Please also confirm whether the Proposer/JV may submit its existing corporate/JV Code of Conduct as supplementary supporting documentation. | Please refer to PDS ITP 12.2(k) and the Code of Conduct form in Section IV. The Proposer shall submit the prescribed Code of Conduct and the required implementation details. The implementation arrangements may be presented in an annex or integrated document provided that all requirements are clearly addressed. A corporate code may be submitted as supplementary information but does not replace the prescribed Contract Code of Conduct. No amendment is made to the RFP. | No
170 | Section I – Instructions to Proposers (ITP) / ITP 15.3–15.5; Section II – Proposal Data Sheet (PDS) / ITP 15.3; Section IV – Proposal Forms / Price Adjustment Forms | PDS ITP 15.3 provides that the prices quoted by the Proposer shall be subject to adjustment during performance of the Contract, while ITP 15.5 provides that a fixed price quotation submitted where Adjustable Price applies will not be rejected but the price adjustment will be treated as zero. However, we could not identify a specific field in the Proposal Forms where the Proposer is required to expressly state that its Proposal is submitted on an Adjustable Price basis. Please confirm that the Proposal is to be submitted on an Adjustable Price basis and specify whether completion of the relevant price adjustment/indexation forms is sufficient to evidence this, or whether a separate statement/declaration is required. If a separate indication is required, please specify the exact form and location where “Adjustable Price” shall be stated. | Please refer to PDS ITP 15.3 and the Price Adjustment Forms in Section IV. Completion of the applicable Table(s) of Adjustment Data in accordance with the RFP is the required tender-stage submission for price adjustment. No separate declaration is required unless expressly requested by a prescribed form. No amendment is made to the RFP. | No
171 | Section II – Proposal Data Sheet (PDS) / ITP 15.1; Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Particular Conditions / Sub-Clauses 14.1 and 14.4 | Please confirm the basis on which monthly progress of lump-sum Activities and Sub-activities will be assessed and certified for payment. In particular, please clarify whether payment will be based on percentage completion, defined milestones, measurable physical progress or another methodology, and identify the supporting records required for such valuation. Please also identify any Activities/Sub-activities or parts of the Works which will be subject to measurement/re-measurement rather than lump-sum progress valuation. | Please refer to Answer No.7. | No
172 | Section I – Instructions to Proposers (ITP) / ITP 22; Section II – Proposal Data Sheet (PDS) / Relevant ITP 22 Provisions – Proposal Packaging | Please confirm the required packaging arrangement for the Proposal. In particular, after separately sealing the Original Technical Part and Original Financial Part, and separately preparing the required copies, please confirm whether all such envelopes are required to be placed inside one additional outer package/envelope and provide the required hierarchy and marking of each envelope/package. | Please refer to ITP 12.1, ITP 22 and the corresponding PDS provisions. The Original Technical Part and Original Financial Part shall be placed in separate sealed envelopes and then enclosed in the outer package marked as required by the RFP. The required copies shall be packaged and identified in accordance with ITP 22 and the PDS. Where one Proposal covers multiple Lots, the Lot-specific information shall be clearly identified within the same Proposal package in accordance with Answer 65. No amendment is made to the RFP. | No
173 | Section I – Instructions to Proposers (ITP) / ITP 22.2(c), ITP 33.1(c) and ITP 34.1; Section II – Proposal Data Sheet (PDS) / ITP 19 and ITP 26.1 – ‘DO NOT OPEN BEFORE’ Marking | Please confirm the exact date, time and wording to be stated after “DO NOT OPEN BEFORE” on the Technical Part, Financial Part, “Proposal - Original” outer envelope and “Proposal - Copies” outer envelope. In particular, please specify the wording to be used for the Financial Part, since its opening date and time will only be notified following completion of the Technical Part evaluation. | Please refer to ITP 22.2 and the corresponding PDS provisions. The Technical Part shall bear the exact opening date/time stated in PDS ITP 26.1. The Financial Part shall be marked in accordance with the RFP for opening at the date/time subsequently notified by the Employer following completion of the Technical Part evaluation, unless the PDS expressly states otherwise. Proposers shall use the wording prescribed by ITP 22.2 and the PDS. No amendment is made to the RFP. | No
174 | Section I – Instructions to Proposers (ITP) / ITP 26.5–26.7 – Opening of Technical Parts | Please confirm whether, at the opening of the Technical Parts, the Employer will prepare a detailed inventory/checklist of the complete contents of each Technical Part, identifying each document, form, statement, methodology, supporting document and other required deliverable as “submitted/present” or “not submitted/absent”, without undertaking any substantive evaluation at that stage. Please further confirm that such inventory/checklist will form part of, or be attached to, the official opening record and will be made available to the relevant Proposer. | Please refer to ITP 26. The Employer will conduct and record the opening of the Technical Parts in accordance with the procedures specified in the RFP. The opening record is not a detailed compliance evaluation or an exhaustive inventory of every document in the Proposal; responsiveness and completeness are determined during evaluation under the applicable ITP provisions. No amendment is made to the RFP. | No
175 | Section I – Instructions to Proposers (ITP) / ITP 32.1–32.2; Section III – Evaluation and Qualification Criteria | Please confirm that the phrase “to its satisfaction” in ITP 32.1 does not permit the Employer to apply any additional or undisclosed qualification criteria, and that the Employer’s determination of the Proposer’s eligibility and qualification will be based solely on the qualification criteria expressly specified in Section III – Evaluation and Qualification Criteria. Please further confirm that any verification or additional supporting documentation requested by the Employer will be solely for the purpose of verifying compliance with such stated criteria and will not introduce any new qualification requirement. | Confirmed. Please refer to ITP 32 and Section III. Qualification will be determined against the criteria and requirements stated in the RFP. The words “to its satisfaction” do not authorize the application of undisclosed qualification criteria. The Employer may, however, verify submitted information and request clarifications in accordance with the RFP. No amendment is made to the RFP. | No
176 | Section II – Proposal Data Sheet (PDS) / ITP 15.8; Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 4.2, 8.8, 14.2 and 14.3 | PDS ITP 15.8 provides that the Proposal Price shall exclude VAT and that the applicable VAT will be added by the Employer and included in the Contract Price. Please confirm whether the Performance Security, ES Performance Security, Advance Payment, Retention Money and Delay Damages, each expressed as a percentage of the Accepted Contract Amount, shall be calculated on a VAT-exclusive or VAT-inclusive basis. | Please refer to PDS ITP 15.8 and the relevant Contract Data. The Proposal Price shall be prepared excluding VAT as stated in the PDS, and VAT shall be dealt with in accordance with the RFP and applicable law. Percentages stated in the Contract Data by reference to the Accepted Contract Amount shall be calculated on the Accepted Contract Amount as defined in the Contract, not on VAT added separately in accordance with PDS ITP 15.8. No amendment is made to the RFP. | No
177 | Section I – Instructions to Proposers (ITP) / ITP 41.1–41.3; Section III – Evaluation and Qualification Criteria / Abnormally Low Proposals | Please clarify the methodology to be used by the Employer to identify a potentially Abnormally Low Proposal under ITP 41. In particular, please confirm whether any numerical threshold, percentage deviation, statistical test, benchmark or comparison with other Proposal prices and/or the Employer’s estimate will be applied. If so, please provide the applicable methodology, parameters and reference data. | Please refer to ITP 41. The RFP does not establish a fixed numerical threshold or formula for identifying an Abnormally Low Proposal. The Employer may identify a Proposal as potentially abnormally low in accordance with the methodology for determination of Abnormally Low Bids/Procurement specified in the World Bank’s Procurement Regulations and Guidance Notes, having regard to its price and the scope, methodology, resources, risks and other relevant aspects, and may request the detailed explanations and evidence specified in ITP 41. | No
178 | Section I – Instructions to Proposers (ITP) / ITP 4.1; Section III – Evaluation and Qualification Criteria / Contractor’s Representative and Key Personnel; Section VII – Employer’s Requirements / Contractor’s Representative | Please confirm whether the JV Representative nominated under ITP 4.1 may be a different individual from the Project Manager (Contractor’s Representative) proposed under Section III and the Employer’s Requirements, or whether these roles are required to be performed by the same individual. | Confirmed. The JV Representative nominated under ITP 4.1 may be a different person from the Project Manager proposed under Section III, provided that each person independently satisfies the role, authorization and qualification requirements applicable to that position. No amendment is made to the RFP. | No
179 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel | Please confirm whether the title “Chief Resident Engineer” imposes any nationality, residence or local residency requirement on the proposed individual. In particular, please confirm whether a foreign individual who otherwise satisfies the required qualifications and experience may be proposed for this position. | The title “Chief Resident Engineer” does not, by itself, impose a nationality or residency requirement. Any nationality, language, registration, professional-licensing or other requirement shall apply only if expressly stated for the relevant Key Personnel position or required by applicable law. No amendment is made to the RFP. | No
180 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel; Section IV – Proposal Forms / Key Personnel Forms | Please confirm the mandatory supporting documentary evidence required at Proposal stage to substantiate the academic qualifications and professional/work experience stated in Forms PER-1 and PER-2. In particular, please confirm whether the completed Forms PER-1 and PER-2 together with copies of relevant diplomas and certificates, where applicable, are sufficient, or whether employer reference certificates, employment/service records, social security/payroll records or other official evidence are also required | Please refer to Section III and Forms PER-1/PER-2. The Proposer shall submit the information and documentary evidence required by the prescribed forms to demonstrate each proposed person’s qualifications and experience, including the applicable academic/professional credentials and experience records. The Employer may verify the information in accordance with the RFP. No additional universal form of employer reference letter is required unless expressly stated. No amendment is made to the RFP. | No
181 | Section III – Evaluation and Qualification Criteria / Item 1.5 – Contractor’s Equipment; Section IV – Proposal Forms / Form EQU | FORM EQU requires the Proposer to provide its strategy for acquiring and maintaining the key equipment and sets out the information to be addressed in such strategy. Please confirm whether completion of FORM EQU, supplemented as necessary to address the stated strategy requirements, constitutes the complete Proposal-stage submission, or whether a separate narrative Equipment Strategy/Methodology document is required | Please refer to Form EQU. The acquisition/availability strategy and the information requested by Form EQU shall be provided in that form; supporting evidence such as ownership records, lease arrangements, purchase/manufacture agreements or commitment letters may be attached as applicable. A separate standalone narrative is not required where Form EQU and its attachments fully address the requirement. No amendment is made to the RFP. | No
182 | Section IV – Proposal Forms / Table of Adjustment Data / Z0–Z1 | Please confirm the official exchange-rate source and the applicable exchange-rate date convention to be used for determining Z0 on the Base Date and Z1 on each Date of Adjustment for the purposes of the Z0/Z1 correction factor. | Please refer to the Table of Adjustment Data and the price-adjustment provisions of the Contract. The source of each index or reference value shall be the source identified in the completed Table and the applicable Contract provisions. Any currency conversion required for the adjustment formula shall be made in accordance with the exchange-rate provisions specified in the Contract. No additional Employer-prescribed exchange-rate source or date convention is introduced by this clarification. No amendment is made to the RFP. | No
183 | Section VII – Employer’s Requirements / Clause 11.10.1 – Land Acquisition and Expropriation; Annex D – General Technical Specification / Clause A.2.2.42; Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 2.1; Section VIII – General Conditions / Sub-Clauses 2.1 and 1.13(a) | ANNEX D – GTS A.2.2.42 provides that the Contractor shall prepare the documentation required for the expropriation process and that the Employer shall complete the statutory expropriation procedures. Please clarify the exact scope of the documentation to be prepared by the Contractor, including whether cadastral and ownership information, parcel plans, surveys and valuation-related documentation are included. Please also clarify the applicable lead time for submission of such documentation, noting the reference in A.2.2.42 to Clause 2.2.44, and specify the period within which the Employer will complete the expropriation process and make the affected land available following receipt of a complete submission. Please also confirm the required lead time for the Contractor’s submission of the complete expropriation documentation and the maximum period within which the Employer will complete the expropriation/land acquisition process and provide access to the affected land following receipt of such complete submission. | Please refer to Answer 45. The Contractor shall prepare and provide the technical, cadastral, survey, parcel and design information necessary for the Employer to carry out the statutory land-acquisition/expropriation procedures, to the extent required by Annex D and the Employer’s Requirements. The timing shall be coordinated with the Detailed Design and land-access programme so that the Employer can progress the statutory procedures. The RFP does not establish a separate guaranteed maximum Employer processing period following each submission. Any entitlement arising from land access shall be dealt with under the Contract. No amendment is made to the RFP. | No
184 | Section VII – Employer’s Requirements / Clause 11.10.1 – Land Acquisition and Allocation Procedures; Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 2.1; Section VIII – General Conditions / Sub-Clauses 2.1 and 1.13(a) | ANNEX D – GTS A.2.2.42 provides that the Contractor shall prepare the documents required for allocation from other institutions and that the Employer shall complete the allocation procedures. Please confirm that this also applies to Treasury-owned, State-owned or other public land required for the Permanent Works, including any necessary allocation, transfer, right-of-use, easement or similar procedures. Please further confirm which Party shall bear any allocation, land-use, easement, permission or similar fees or charges associated with such land. | The allocation/transfer/right-of-use procedures for Treasury-owned, State-owned or other public land required for the Permanent Works shall be processed by the Employer where such procedures form part of the Employer’s statutory land-acquisition/allocation responsibility. The Contractor shall prepare and provide the technical drawings, schedules and supporting documents required for those procedures. Fees and charges directly associated with obtaining the Employer’s permanent land rights shall be borne through the Employer’s land-allocation/acquisition process, whereas permits, temporary land-use arrangements and approvals required for the Contractor’s own construction methods, temporary facilities and means and methods remain the Contractor’s responsibility unless otherwise stated in the Contract. No amendment is made to the RFP. | No
185 | Section I – Instructions to Proposers (ITP) / ITP 17.4; Section II – Proposal Data Sheet (PDS) / ITP 17.4(a)–(b); Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 4.4(a); Section VIII – General Conditions / Sub-Clause 4.4 | Please confirm that the maximum 30% subcontracting limit under PDS ITP 17.4(a) and Contract Data Sub-Clause 4.4(a) applies only to Subcontractors performing a subcontracted part of the Works and does not include suppliers, manufacturers or service providers which do not themselves perform any part of the Works as a Subcontractor. | Please refer to PDS ITP 17.4 and Contract Data Sub-Clause 4.4(a). The 30% limit applies to the accumulated value of work subcontracted to Subcontractors for execution of parts of the Works. The procurement of materials, Plant or Equipment from a supplier that does not execute a part of the Works as a Subcontractor is not, solely by reason of such supply, counted as subcontracted work. Where a supplier also performs installation, construction or another part of the Works, the relevant subcontracted work is subject to the Contract requirements. No amendment is made to the RFP. | No
186 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 1.1.86 and 1.1.95; Section VII – Employer’s Requirements / Clauses 4.9.4 and 5.1 | Time for Completion: 1,826 days calculated from the Commencement Date. ( ~5 years= 60 months) Milestone 1 Detailed Design Completion: 12 months from the Commencement Date. Milestone 2 Infrastructure Works Completion: 36 months from the completion date of Major Milestone 1. Milestone 3 Superstructure Completion: 12 months from the completion date of Major Milestone 2. Milestone 4 Testing and Commissioning Completion: 24 months from the completion date of Major Milestone 3. TOTAL: 12 + 36 + 12 + 24 = 84 MONTHS Please reconcile the overall Time for Completion of 1,826 days (~60 months) under Contract Data Sub-Clause 1.1.86 with the sequential Milestone periods under Contract Data Sub-Clause 1.1.95, which result in a cumulative period of 84 months up to Milestone 4. In this respect, ER Section 5.1 states that the construction period shall be completed within 60 months and that the 24-month Defects Notification Period commences only after Taking-Over, while ER 4.9.4 requires all four contractual Milestones, including Milestone 4 – Testing and Commissioning Completion, to be programmed from the Commencement Date through to Taking-Over. Accordingly, please confirm the correct contractual Time for Completion and the intended cumulative completion period/date of each Milestone from the Commencement Date, and clarify whether the 24-month period stated for Milestone 4 is correct. Please also clarify whether the references to “Major Milestone 1/2/3” are intended to mean Milestone 1/2/3 as defined under Sub-Clause 1.1.95, and whether the references in ER Section 5.1 to the “Effective Date” are intended to refer to the Commencement Date. | Please refer to Answer No.5. Please refer to Addendum No. 2, Amendment No. 3. | Yes
187 | Section VII – Employer’s Requirements / Annex B2 – INRAIL Railway Safety Plan / Land Acquisition and Traction Substation Sites | Based on the information provided in Annex of ANNEX B2 – INRAIL Railway Safety Plan, we understand that land acquisition activities will be undertaken by the Employer. However, in order to clarify the scope, we kindly request confirmation of the following: For the three (3) 154/25 kV Traction Substations to be installed under the Project, will the land acquisition and/or expropriation required for the towers/poles and routes of the 154 kV transmission lines provided from the natural power grid for these substations, as well as for the 34.5 kV distribution lines to be installed for tunnel power supply, be under the scope and responsibility of the Employer or the relevant Contractor? | Please refer to Answer 45. Permanent land required for the Project Works is dealt with under the land-acquisition provisions of the Employer’s Requirements. The Contractor shall provide the design and technical documentation necessary to define such land. Land required solely for Contractor-selected temporary facilities, additional working areas, access arrangements or construction methods outside the Site shall remain the Contractor’s responsibility and cost unless otherwise provided by the Contract. No amendment is made to the RFP. | No
188 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Special Systems; Annex L – Signaling and Telecommunication System Technical Specification | With reference to ANNEX E1 – Design Technical Specification, Section “Special Systems”, the following systems are identified: • Early Earthquake Warning System • Climate-Based Limited Operation System • Mass-Spring System Furthermore, ANNEX L – Signaling, Telecommunication and Support Systems Technical Specification specifically requires the installation and integration of the Seismic Early Warning System with the signalling and train control systems. In this regard, please clarify whether the design, supply, installation, testing and commissioning of the above-mentioned Special Systems shall be included within the Contractor’s scope and Tender Price. If so, please also clarify under which Contract/Lot and discipline each of these systems shall be considered and priced, particularly where interfaces will be exist between signalling/telecommunication/support systems and other relevant disciplines. | The scope shall be allocated as follows. Systems forming part of signalling, telecommunication and supporting systems, including signalling-integrated early-earthquake-warning and climate-based limited-operation functions, are within Package 2, while the Package 1/Lot Contractor shall provide the civil, structural, power/interface and enabling provisions expressly required by the Employer’s Requirements. The Mass-Spring System, where required by the track/civil design, is within the relevant Lot Contractor’s scope; its Technical Specification is added by Addendum No. 2, Amendments Nos. 13 and 44. Each Contractor remains responsible for the design, supply, installation, testing and commissioning of the systems expressly allocated to its own scope and for the required interfaces with the other packages. | Yes
189 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clause 7.10 – Solar Energy System | With reference to ANNEX E1 – Design Technical Specification, Section 7.10 – Solar Energy System, please clarify whether the Solar Energy System (Photovoltaic System) shall be included in the Contractor’s scope and Tender Price, or whether it will be implemented under a separate contract/package. If it is within the Contractor’s scope, please specify the locations/areas where the PV system is required, together with the required or indicative capacity for each location | Where a solar-energy system is required by Annex E1 or another applicable Technical Specification, its design, supply, installation, testing and commissioning are included in the Contractor’s scope and lump-sum Contract Price for the relevant Lot. The final capacity, location, configuration and interfaces shall be developed during Detailed Design subject to the requirements of the RFP and the Engineer’s approval. No amendment is made to the RFP. | No
190 | Section VII – Employer’s Requirements / Clauses 11.13.1–11.13.2 – Archaeology and Cultural Heritage; Section IX – Particular Conditions / Sub-Clause 4.23; Section VIII – General Conditions / Sub-Clause 1.13 | Please confirm whether any archaeological surveys, geophysical investigations, trial trenching, rescue excavations or other cultural heritage investigations are required to be completed before commencement of construction in any part of the Site. If so, please identify the relevant locations/sections and confirm which Party shall be responsible for carrying out such investigations or works, obtaining the required permits and approvals, and bearing the associated costs. | Please refer to Section VII, Employer’s Requirements, Clause 11.13 and the applicable Particular Conditions. The Contractor shall comply with the archaeological and cultural-heritage requirements of the Contract, including any surveys, investigations, monitoring, protection and chance-find procedures required by the competent authority or the approved E&S documents. Costs allocated to the Contractor by those requirements shall be included in the Contract Price. No amendment is made to the RFP. | No
191 | Section VII – Employer’s Requirements / Clauses 11.13.1–11.13.2 – Archaeology and Cultural Heritage; Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 2.1 and Sub-Clause 8.1; Section VIII – General Conditions / Sub-Clause 2.1 | Please confirm whether any sections of the alignment/Site are expected to be inaccessible to the Contractor or handed over at a later stage due to archaeological/cultural heritage investigations, protection measures or rescue works. If so, please identify the affected sections and the anticipated dates on which each section will be made available to the Contractor in a condition suitable for the planned Works. | Please refer to Section VII, Employer’s Requirements, Clauses 11.10 and 11.13 and Contract Data Sub-Clause 2.1. The Contractor shall programme the Works taking account of land-access, E&S, archaeological and statutory constraints. The RFP does not identify a separate guaranteed schedule of archaeological hold areas at Proposal stage. Any actual restriction or delayed access shall be administered in accordance with the Contract. No amendment is made to the RFP. | No
192 | Section VIII – General Conditions / Sub-Clause 1.13(b), Sub-Clause 8.6 and Sub-Clause 20.2; Section VII – Employer’s Requirements / Clause 7.6 – Third-Party Approval Obligations | Please confirm whether the Contractor will also be responsible for approvals, permits, no-objections and authorisations required by authorities or asset owners not identified in the RFP Documents. If so, please confirm the Contractor’s entitlement to additional time and/or Cost where such requirements could not reasonably have been foreseen at the Proposal submission date. | Please refer to Section VII, Employer’s Requirements, Clause 7.6. The Contractor is responsible for identifying, obtaining and maintaining all approvals, permits, no-objections and authorisations allocated to it by the Contract, including those that become necessary as the Detailed Design develops. The fact that a particular approval is not individually listed does not automatically create an entitlement to additional time or payment. Any entitlement shall be determined under the Contract in relation to the specific event. No amendment is made to the RFP. | No
193 | Section I – Instructions to Proposers (ITP) / ITP 17.4; Section II – Proposal Data Sheet (PDS) / ITP 17.4(a); Section VIII – General Conditions / Sub-Clause 4.4; Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 4.4(a) and Sub-Clause 4.24 | Please confirm that the maximum 30% subcontracting limit under PDS ITP 17.4(a) and Contract Data Sub-Clause 4.4(a) applies only to Subcontractors performing a subcontracted part of the Works and does not include suppliers, manufacturers or service providers which do not themselves perform any part of the Works as a Subcontractor. | Please refer to Answer 185. | No
194 | Section I – Instructions to Proposers (ITP) / ITP 12.2(j) and ITP 17.4–17.5; Section IV – Proposal Forms / Subcontractors Form; Section VIII – General Conditions / Sub-Clause 4.4 | Please confirm that, where the Proposer does not propose any Subcontractor or Specialized Subcontractor at Proposal stage, the “Subcontractors” form in Section IV may be completed as “N/A – No subcontractor proposed at Proposal Stage”, and that the Contractor may subsequently propose and appoint Subcontractors during Contract execution in accordance with Sub-Clause 4.4 and the applicable requirements of the Contract. | Where no Subcontractor or Specialized Subcontractor is proposed at Proposal stage, the relevant form may be completed accordingly, including by stating “None” or “Not Applicable” as appropriate. Subsequent appointment of Subcontractors shall be subject to the Contract and the Engineer’s approval requirements. A Subcontractor appointed after Proposal submission may not be used retrospectively to cure a failure of the Proposer to meet a qualification requirement at Proposal stage. No amendment is made to the RFP. | No
195 | Section II – Proposal Data Sheet (PDS) / ITP 17.4(a); Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 4.4(a); Section VIII – General Conditions / Sub-Clause 1.1.1 – Accepted Contract Amount; Section VIII/IX – General/Particular Conditions / Sub-Clauses 13.3 and 13.7 | Please confirm that the “total contract amount” referred to in PDS ITP 17.4(a) is intended to mean the Accepted Contract Amount, consistent with Contract Data Sub-Clause 4.4(a), and that the 30% subcontracting limit is calculated by reference to the Accepted Contract Amount. Please also confirm whether the 30% limit remains based on the original Accepted Contract Amount and is unaffected by Price Adjustments under Sub-Clause 13.7, and whether Variations have any effect on the calculation of this limit. | Please refer to PDS ITP 17.4(a) and Contract Data Sub-Clause 4.4(a). The 30% limit is calculated by reference to the Accepted Contract Amount as defined in the Contract. Price Adjustments under Sub-Clause 13.7 do not change the original Accepted Contract Amount for this purpose. The treatment of Variations that change the scope of subcontracted work shall be determined under the Contract and, where necessary, by the Engineer/Employer in administering the subcontracting limit; no automatic increase of the percentage limit is created by a Variation. No amendment is made to the RFP. | No
196 | Section VII – Employer’s Requirements / Clause 11.2 – Applicable Legal, Policy and Contractual Framework; Annex D – General Technical Specification / Clause A.2.13 | The Particular Conditions and the Employer’s Requirements / World Bank ES provisions require all subcontracts relating to the Works to include flow-down obligations, including compliance with relevant ES requirements. Given the potentially large number of minor, low-value or ancillary subcontracts, please confirm whether a materiality/value/criticality threshold may be applied so that full flow-down obligations are required only for subcontractors performing material, safety-critical, ES-sensitive or otherwise significant parts of the Works. For minor or low-risk subcontracts, please confirm whether a proportionate set of core compliance obligations would be acceptable. | The request for a general materiality threshold is not accepted. Please refer to the Employer’s Requirements and Annex D. Contractual and E&S obligations shall be flowed down to Subcontractors, suppliers and service providers to the extent applicable to their respective activities and risks. The form and level of implementation may be proportionate to the scope and risk, but this shall not reduce or exclude any mandatory Contract, legal or World Bank E&S obligation applicable to that party. No amendment is made to the RFP. | No
197 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities, Activity 13 – DAAB; Section IX – Particular Conditions / Sub-Clause 21.1 – Constitution of the DAAB | Please provide the indicative monthly fee, daily fee, home location and travel basis of the Employer-proposed DAAB candidates, or confirm the pricing assumptions to be adopted by Proposers for Activity 13 – DAAB. | Please refer to Section IV, Schedule of Priced Activities and Sub-activities (Activity 13 – DAAB), and Section IX, Sub-Clause 21.1. No amendment to the DAAB fee and payment provisions is made under Addendum No. 2. | No
198 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 21.1 and 21.6; Section IX – Particular Conditions / Sub-Clauses 21.1 and 21.6 | Please clarify, for the purposes of PC Sub-Clause 21.6, how a Joint Venture comprising both domestic and foreign members will be classified as a “foreign Contractor” or a “domestic Contractor”. In particular, please confirm whether the presence of at least one foreign JV member is sufficient for the Contract to be treated as a contract with a foreign Contractor, irrespective of the JV members’ participation percentages, the JV Leader or the nationality of the majority member. Please also clarify the corresponding impact on the DAAB nationality requirements under PC Sub-Clause 21.1. If such mixed-nationality JV is treated as a foreign Contractor, please confirm whether the Employer-proposed DAAB candidates of Turkish nationality would be inapplicable, given that DAAB members must not have the same nationality as the Employer or the Contractor, and how replacement DAAB candidates would be identified in that case. | Please refer to Addendum No. 2, Amendment No. 20. | Yes
199 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 21.6(a); Section IX – Particular Conditions / Sub-Clause 21.6(a) | For foreign contractors, the Contract Data states that the place of arbitration will be indicated at the time of award in accordance with the origin of the Contractor. Please consider specifying a neutral place of arbitration in the RFP/Contract Data at this stage, such as Paris, France or Geneva, Switzerland, rather than leaving it to be determined at award. If the selected Contractor is incorporated in, or otherwise has the same nationality as, the specified place of arbitration, the Parties may agree an alternative neutral place at that time. Please also confirm that the Contractor will have the right to object to any proposed place of arbitration that is not neutral. | The request is not accepted. Please refer to Contract Data Sub-Clause 21.6. For a foreign Contractor, the place of arbitration shall be indicated at the time of award in accordance with the origin of the Contractor, as stated in the RFP. The RFP does not provide a separate unilateral right for the Contractor to reject the place determined under that provision. No amendment is made to the RFP. | No
200 | Section II – Proposal Data Sheet (PDS) / ITP 1.1; Section I – Instructions to Proposers (ITP) / ITP 4.3 – Participation in Multiple Lots / Different JV Structures | ITP 1.1. states that “proposers may bid for one or more lots. Evaluation of bids and contract award will be lot-wise”. We are also aware that qualification criteria for application to more than one lot will be the cumulative sum of minimum requirement for respective lots as specified under items 3.1, 3.2, 4.2(a) and 4.2(b) (Key Activities) of Section III. In order to ensure that the Contractor can best fulfil the technical requirements of the Works, secure the cash flow required for the successful implementation of the Project, and effectively utilize local experience through strong partnerships, we are considering submitting competitive bids for different Lots under different partnership structures. In this regard, could you please clarify whether a company is permitted to participate in different Lots through different bidding arrangements? For example, would it be permissible for the same company (Company A) to: • submit a bid for Lot 1 as a Single Entity; • submit a bid for Lot 2 as part of a Joint Venture/partnership between Companies A and B; • submit a bid for Lot 3 as part of a Joint Venture/partnership between Companies A and C? In other words, would a bidder be considered eligible to participate in multiple Lots through different consortium/JV structures, provided that all applicable qualification, eligibility, and participation requirements are satisfied cumulatively? | Please refer to Answer No.8. | No
201 | Section VII – Employer’s Requirements / Annex G10 – Ballastless Railway Line Construction Specification / Slab Track Design | Upon review of the typical cross-sections included in the Conceptual Design drawings forming part of the Tender Documents, it is observed that ballastless track (slab track) is envisaged for all tunnel sections, while ballasted track is envisaged for all bridge and viaduct sections. On the other hand, ANNEX G10 – Technical Specification for the Construction of a Ballastless Railway Line states that the construction of ballastless track on bridges and viaducts is subject to the Employer’s approval. Furthermore, based on the protocol decision signed between TCDD and AYGM, it is understood that ballastless track is adopted for tunnels with a length of 2,000 m or more and, on the other hand, for bridges/viaducts with a length of 200 m or more. In view of the above, it is kindly requested that the criteria for selecting ballastless/ballasted track for tunnels, bridges, and viaducts within the scope of this Project, as well as the applicable structure length thresholds, be clearly defined. | The Ballasted/Ballastless Track Itinerary has been added to the RFP Documents regarding the application of ballasted and slab track. Please refer to Addendum No. 2, Amendment No. 15. | Yes
202 | Section VII – Employer’s Requirements / Environmental and Social Impact Assessment (ESIA) Report / Annex 2.8 – Hydrology 1 / Ömerli Dam Protection Zone | Based on the joint review of Environmental and Social Impact Assessment (ESIA) Report – Annex 2.8 Hydrology 1 and the alignment corridor included in the Tender Documents, it is observed that, within Lot 2, the railway alignment at approximately Km 29+000 passes through the absolute protection zone of Ömerli Dam. In this regard, the Employer is kindly requested to provide its opinion on whether the railway alignment passing through the absolute protection zone is acceptable and whether the alignment should be revised to avoid this area. Should it be deemed necessary to relocate the alignment outside the absolute protection zone, the Employer is also kindly requested to clarify whether an alternative alignment located within the short-distance protection zone would be acceptable in terms of the applicable regulations and Project requirements, and to communicate its decision accordingly. | Please refer to the ESIA, the Employer’s Requirements and the applicable reservoir/water-authority requirements. The Reference/Conceptual alignment is indicative and the Contractor shall develop the Detailed Design so as to comply with the applicable environmental, water-protection, drainage and permitting requirements. Any alignment modification shall be subject to the Engineer’s and relevant authority approvals under the Contract. No amendment is made to the RFP. ESMP, LMP,RF, and SEP were updated and disclosed on August 21, 2026. ESIA and the Supplementary Biodiversity Baseline Study, together with the SEA/SH Management Plans, were updated and disclosed on September 3, 2026. All documents have been made publicly available on the AYGM project webpage (aygm.uab.gov.tr/istanbul-kuzey-demiryolu-gecisi-projesi). | No
203 | Section VII – Employer’s Requirements / Annex G3 – Ballast Technical Specification / Clauses 1, 2.1, 2.2.1, 2.2.2, 3.2 and 4.1.1; Annex B1 – Conceptual Design Report; Annex E1 – Design Technical Specification | Documents concerned: ANNEX G3, Ballast Technical Specification, being one of the Technical Specifications comprised in Annexes D through Q. ANNEX G3 provides, at clause 2.2.1 (page 4): "Following the collection of samples from the quarry, the Bidders shall deliver the relevant ballast samples to the laboratory prior to the tender date and shall submit the delivery records for the samples they have delivered, together with receipts confirming payment of the testing fees, along with their tenders." The delivery records and the testing-fee receipts are accordingly required by ANNEX G3 to be submitted with the Proposal, and the sampling upon which they depend must be completed before the tender date. The sequence prescribed by ANNEX G3 comprises: selection of the quarry; the taking of a sample of not less than 150 kg of ballast, together with a sample of approximately 5 kg for petrographic analysis, in the presence of the Control officer and the Sampling Committee, the same clause providing that test results on samples not taken under that supervision "shall not be accepted by the Employer and shall not be binding"; the sealing of the samples and the drawing up of the Sample Collection Record in triplicate; delivery to the laboratory; and the issue of the receipt confirming payment of the testing fees. The definitive quarry and sample selection within that sequence cannot be completed until the applicable acceptance category is known, because the category determines which quarry can be selected with confidence for compliance purposes. ANNEX G3 states, at clause 1, that it sets out the characteristics of the ballast to be purchased for "HT/YHT, conventional, connecting and shunting lines". Each of its acceptance tables, however, is set out in two columns only — for HT/YHT lines and for conventional lines — and is expressed for main lines. The specification does not state which column applies to a line of the design speed of the present Works, nor which applies to the single-track connection lines, or to the sidings, station tracks and depot and maintenance yard lines, forming part of the Works. The two columns differ materially in the mandatory physical properties of clause 3.2, which are those determined upon the quarry sample: Los Angeles abrasion not exceeding 14 per cent as against 20 per cent (clause 3.2.1, page 11); water absorption not exceeding 1.5 per cent as against 2 per cent (clause 3.2.2, page 11); particle density of not less than 2.60 Mg/m³ as against 2.50 Mg/m³ (clause 3.2.3, page 12); magnesium sulphate mass loss not exceeding 3 per cent as against 5 per cent (clause 3.2.4, page 12); and Micro-Deval abrasion not exceeding 12 per cent as against 14 per cent (clause 3.2.5, page 12). These thresholds do not merely alter the price. They determine which quarries in the region are eligible at all, and therefore which sample a Proposer is to deliver. A Proposer who selects a quarry against the conventional criteria and is later held to the HT/YHT criteria will have delivered a sample which cannot pass, with no opportunity to remedy the position before the tender date. We note that the RFP Document is not uniform in its description of the line. ANNEX B1 and ANNEX E1 record a design speed of 160 km/h with a control speed of 176 km/h, while ANNEX B1 also describes the line as a "high-speed line section" with a maximum train operating speed of 200 km/h in the context of the electrical and mechanical systems, and classifies high-speed trains as those operating between 160 and 250 km/h. ANNEX B1 states of itself that its values, "including ... ballast specifications", are "indicative" and subject to confirmation, and that the report "does not constitute part of the formal contractual engagement". It is for this reason that a determination by the Employer is required before quarry selection can begin. Clarification Request : Which acceptance category of ANNEX G3 applies to the Works — that for HT/YHT lines, or that for conventional lines? Does the same category apply to the connection lines and to the sidings, station tracks and depot and maintenance yard lines, for which ANNEX G3 declares itself applicable at clause 1 but provides no separate column? The expression "tender date", used at clause 2.2.1, is not a defined term of the RFP Document. Kindly confirm that it is to be read as the deadline for submission of Proposals fixed by PDS ITP 23.1, namely 14 October 2026 at 14:30 Ankara time, and not as any earlier date. ANNEX G3 requires, at clause 2.2.1 (page 4), that the delivery records and the testing-fee receipts be submitted with the tender, and provides at clauses 2.1 (page 3) and 2.2.2 (page 5) that the report there variously described as the "Material Quarry Survey Report", the "Material Quarry Research Report" and the "Material Quarry Investigation Report" is to be prepared prior to the commencement of quarry production operations. We accordingly understand the documents to be submitted with the Proposal in this respect to be limited to the delivery records and the testing-fee receipts, and kindly request the Employer's confirmation. Kindly also advise at what stage the reports and documents relating to the operation of the quarry — the quarry licence, drilling studies, EIA reports and reserve calculations referred to at clause 4.1.1 — are to be submitted, that clause requiring their submission "by the Tenderers" while the sentence immediately preceding it addresses the Contractor. Should the Employer's determination be issued at a date which leaves insufficient time for the sequence described above, we respectfully request that the Employer consider, pursuant to ITP 8.3 and ITP 23.2, whether prospective Proposers require reasonable additional time in which to take the resulting addendum into account.For the avoidance of doubt, pending the Employer's determination, the Proposer intends, solely as a provisional planning and risk-mitigation measure, to proceed on the basis of the acceptance criteria for HT/YHT lines, being the more onerous of the two sets contained in ANNEX G3. The tests to be carried out upon the quarry sample under clause 2.2.1 are the same for both categories, the categories differing only in the limit values applied to the results, so that a sample satisfying the HT/YHT limit values also satisfies the conventional limit values. This provisional approach is stated so that the Employer's record may be complete; it is without prejudice to the clarification requested above and shall not constitute acceptance by the Proposer of an otherwise undefined requirement of the RFP Document. No confirmation is requested in respect of this paragraph. | HT/YHT acceptance criteria shall apply. Please refer to Addendum No. 2, Amendment No. 16. The pre-tender ballast sample delivery and testing-fee receipt requirement under Annex G3, Clause 2.2.1 is deleted; accordingly, those documents are not required to be submitted with the Proposal. Quarry-related source-approval and operational documents, including the quarry licence, drilling studies, EIA documents and reserve calculations, shall be submitted during Contract execution at the stage required by Annex G3 and before commencement of production/use of the proposed source, as applicable. | Yes
204 | Section VII – Employer’s Requirements / Annex G3 – Ballast Technical Specification / Clause 2.2.1 – Sampling, Laboratory and Testing Requirements | ANNEX G3 defines "Laboratory" as the "Laboratory to be Approved by the Employer", and directs at clause 2.2.1 (page 4) that the sample taken for petrographic analysis be delivered to the Construction Materials Laboratory Branch Directorate, while requiring the ballast sample of not less than 150 kg to be delivered to "the laboratory" and to "the relevant Branch Directorate" without further identification; and it contemplates that samples may be sent onward to external laboratories or institutions where the Employer's laboratory is unable to carry out the tests. To which laboratory is the ballast sample of not less than 150 kg to be delivered before the tender date, and what are its name, unit and postal address? Will a list of laboratories approved for this purpose be issued to Proposers? ANNEX G3 requires the sample to be taken in the presence of the Control officer and the Sampling Committee, and provides that results on samples not so taken shall not be accepted. To which unit, by what form of application, and with what period of notice is a Proposer to request their attendance at the quarry? Kindly also advise the schedule of testing fees, the manner in which they are to be paid, and the form of the receipt to be submitted with the Proposal, ANNEX G3 requiring the receipt but not prescribing its form. The RFP Document requires, for each Lot, a separate Proposal Security, separate key personnel, separate equipment and separate referenced contracts, but contains no corresponding provision as regards material sources; and the "Sample Collection and Quarry Site Determination Report" at Appendix 1 of ANNEX G3, being the form to be completed by firms participating in the tender, is keyed to the quarry, the Lot number appearing only upon the form used for samples taken from production. Kindly confirm that a single quarry's sample set may serve Proposals submitted for more than one Lot. | Please refer to Answer 203. Since the pre-tender ballast sample delivery and testing-fee receipt requirement has been deleted, the requested pre-tender laboratory address, Sampling Committee attendance procedure, testing-fee schedule and payment receipt are not applicable to Proposal submission. During Contract execution, sampling, testing and material-source approval shall be carried out in accordance with Annex G3 under the applicable Employer/Engineer coordination and approval process. A common quarry may be proposed for more than one Lot, provided that the applicable quality, sampling, testing and approval requirements are satisfied for each relevant Lot. Please refer to Addendum No. 2, Amendment No. 16. | Yes
205 | Section VII – Employer’s Requirements / Annex G10 – Ballastless Railway Line Construction Specification; Annex E1 – Design Technical Specification / Mass-Spring System | We refer to the above Request for Proposals. In preparing our Proposal we are presently engaged upon the ballastless track sections of the Works. ANNEX G10 requires the Contractor to select one of the prefabricated ballastless track construction methods and to submit the method so selected for the Employer's approval; that selection shapes the design, the quantities and the warranty structure of a substantial part of the Works, and therefore the basis of the Proposal itself. In working through the RFP Document to establish that method and those quantities, we have found ourselves in need of the Employer's guidance on four matters, each set out with its basis in the sections below: the identity of the technical specification governing mass-spring systems; the limit values by which vibration and noise are to be judged; the operation of the approval to be given to the construction method on bridges and viaducts; and the arrangement of turnout zones on ballastless sections. All four arise from one and the same need — that all Proposals be prepared, and be capable of comparison, upon one and the same basis. This request is made without prejudice to, and shall not be construed as a waiver of, any right of any Proposer under the RFP Document. We are mindful that a response given under ITP 7.1 does not of itself amend the RFP Document: ITP 7.1 provides that any amendment which the Employer deems necessary as a result of a request for clarification is to be made following the procedure under ITP 8. Accordingly, insofar as the Employer's response to the matters below supplies a document or a value not presently contained in the RFP Document, we respectfully request that it be issued as an addendum pursuant to ITP 8.1, so that under ITP 8.2 it forms part of the RFP Document for all Proposers alike. ANNEX G10, Ballastless Railway Line Construction Specification, requires, among the matters to be defined in detail for embedded rail construction, the specifications of the rail-under mat "to comply with the mass spring system technical specifications", thereby referring to a distinct technical specification governing mass-spring systems. The same Annex requires, among the documents to be submitted for the Employer's approval: "Connection systems, mass spring systems, transition zone systems and prefabricated element manufacturers’ declarations of conformity stating that they will provide the required warranty periods for the combined system to be implemented, along with repair and maintenance manuals." ANNEX E1, Design Technical Specification, provides under the heading Mass-Spring System: "The use of mass-spring systems will be assessed based on the need for vibration and noise reduction, limiting structure-track interaction, and improving passenger comfort." We have not been able to identify the mass spring system technical specifications so referred to among the documents comprised in the RFP package. None of the twenty Technical Specifications of the ANNEX G series is a mass-spring system specification, and no other Annex could be found to contain one. In the absence of that specification, the design requirements, the acceptance criteria and the warranty basis of the mass-spring layer cannot be established from the RFP Document. Kindly identify, by Annex number and title, the document constituting the mass spring system technical specifications referred to in ANNEX G10. Should that specification not form part of the present RFP package, we kindly request that it be issued to all Proposers as an addendum pursuant to ITP 8.1. Pending its issue, kindly confirm whether the requirements applicable to mass-spring systems are limited to those set out in ANNEX E1 and ANNEX G10. | Please refer to Answer 145 and Addendum No. 2, Amendment No. 13. The Mass-Spring System Technical Specification is added to the RFP Documents and shall govern together with Annex E1 and Annex G10. | Yes
206 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Vibration, Noise and Mass-Spring System Requirements | ANNEX E1 provides, under the heading VIBRATION and NOISE: "Vibration and noise levels that may occur along the station and track will be analysed. The effects of the values obtained from the analysis on structures, the environment and sensitive equipment will be assessed. Where vibration levels exceed acceptable limits in terms of human comfort and structural safety, vibration damping systems will be implemented." ANNEX E1 further provides, of the parameters of mass-spring systems: "System parameters shall be determined taking into account train loads, operating speeds, ground conditions and the vibration sensitivity of surrounding structures." The obligation to implement vibration damping systems is thus made dependent upon an analysis against "acceptable limits". ANNEX E1 does not specify the limit values against which acceptability is to be assessed for the track alignment, nor the standard or regulation from which they are to be taken; and the parameters upon which the assessment depends include the vibration sensitivity of surrounding structures, which is information peculiarly within the Employer's knowledge of the corridor. Kindly advise the vibration and noise limit values, and the standards or regulations by reference to which acceptability is to be assessed, for the purposes of the analysis required by ANNEX E1. Kindly advise whether the Employer has identified sections of the alignment on which mass-spring systems or other vibration damping measures are envisaged or required and, if so, their locations and extents; or kindly confirm that the identification of such sections is left to the Contractor's analysis at the detailed design stage. | The Contractor shall carry out the vibration and noise analyses required by Annex E1 using the applicable Turkish legislation, TS/EN standards, relevant TSI requirements and other standards stated in the RFP. The need, location and extent of mass-spring or other vibration-mitigation measures shall be established by the Contractor’s analyses during Detailed Design and submitted for approval. No predetermined chainage list is issued by this clarification. No amendment is made to the RFP. | No
207 | Section VII – Employer’s Requirements / Annex G10 – Ballastless Railway Line Construction Specification; Annex B1 – Conceptual Design Report / YSS Bridge | ANNEX G10 defines the "Track Construction Method Using Prefabricated Elements on a Concrete Slab with Individual Supports" and lists among its fields of application bridges and viaducts "subject to approval by the Employer based on the structural design". ANNEX B1, Conceptual Design Report, records of the existing YSS bridge: "Railway works, slab track, rails connections, rail expansions joints, catenary system, signaling system, will be designed and constructed, in accordance with the existing bridge structural design, reserves and application points left for the railway." Kindly advise the criteria, and the content of the submission, by reference to which the approval contemplated by ANNEX G10 for bridges and viaducts — that is, the Employer's approval, at the contract stage, of the construction method selected and submitted by the Contractor — will be assessed; and kindly confirm whether that approval is to be sought structure by structure or once for the Works as a whole.For the existing YSS bridge, kindly confirm that the existing bridge structural design, together with the reserves and application points left for the railway, will be made available to the Contractor, and kindly advise at what stage this information will be provided. The provision of the referenced YSS Bridge drawings to Proposers at the tender stage is the subject of a separate request for clarification submitted by us; the present request is made without prejudice to that request and concerns the stage at which the information will be made available to the Contractor. | Please refer to Annex G10 and Section VII, Employer’s Requirements. The selected ballastless-track construction method shall be demonstrated by the Contractor as suitable for each relevant structure and submitted for approval with the structural design and interface details. Approval may be given by design package/structure as appropriate to the Contractor’s design sequence; no single Works-wide approval is implied where structure-specific verification is required. For the YSS Bridge, please also refer to Answer 96. | No
208 | Section VII – Employer’s Requirements / Annex G10 – Ballastless Railway Line Construction Specification; Annex G11 – Switch Technical Specification / Turnout Zones | ANNEX G10 provides, of the selection of the ballastless construction method: "The Contractor shall select one of the ballast-free track construction methods using prefabricated elements employed on railway lines and submit it for approval by the Employer." ANNEX G11, Switch Technical Specification, provides, of the support arrangement beneath turnouts: "The elastomer pads to be used beneath the steel plates or slabs shall be 10 mm thick and have a static stiffness of Cstat = 30 kN/mm." The geometry of a turnout zone is variable and does not conform to a standard prefabricated panel module, and the arrangement contemplated by ANNEX G11 — steel plates or slabs upon elastomer pads — presupposes a support formed to the turnout's own geometry. We accordingly understand the obligation to select one construction method under ANNEX G10 to relate to the running line, the turnout zones being detailed in accordance with ANNEX G11. Kindly confirm that, on ballastless sections, turnout zones may be constructed as a cast-in-place slab arrangement complying with ANNEX G11, as a detail of the construction method selected under ANNEX G10, and that the obligation to select one method does not preclude such turnout-specific detailing. Should the Employer require a particular arrangement for turnout zones on ballastless sections beyond the requirements of ANNEX G11, kindly advise the applicable requirement. | Confirmed, subject to compliance with the RFP. The turnout-zone arrangement on ballastless sections may be detailed specifically for the turnout geometry, including a cast-in-place slab solution, provided that the complete arrangement complies with Annex G11, Annex G10, the applicable track/structural requirements and receives the required approval. No amendment is made to the RFP. | No
209 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification; Annex K – Tunnel Electromechanical Works Technical Specification / Escape Tunnels | The lengths of Tunnel-6 (L=1 100m), Tunnel-15 (L=1 050m) and Tunnel-17 (L=1 020m) are greater than 1 000 m. Furthermore, these tunnel lengths have been taken into account excluding the Cut&Cover structures to be constructed at the tunnel entrances and exits. According to international specifications, an escape tunnel must be constructed in tunnels longer than 1 000 metres. Please specify whether an emergency escape tunnel should be constructed for these three tunnels. | Please refer to Addendum No. 2, Amendment No. 10. | Yes
210 | Section VII – Employer’s Requirements / Annex A1 – Tunnel Drawings; Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Safety Tunnel Alignment and Gradient | The vertical gradient to be applied in terms of the dimensioning and alignment geometry of the safety tunnels will directly affect the total length of the safety tunnel and, consequently, the location of the connection points with main tunnels. In this regard, please confirm the maximum allowable longitudinal/vertical gradient (%) for the safety tunnels under this project. | The safety/escape tunnel geometry, including longitudinal gradient, shall be developed during Detailed Design in accordance with the applicable fire-life-safety, evacuation, accessibility, operational and structural requirements of the RFP and relevant standards. No separate project-specific maximum gradient is introduced by this clarification. No amendment is made to the RFP. | No
211 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Shaft Requirements | No explanation or design rationale regarding the purpose and necessity of the shafts planned at Km: 2+300, Km: 8+700, Km: 20+900 and Km: 22+300 has been found in the tender annex documents. Please clarify the function of the shafts in question (emergency access, ventilation, operation/maintenance, construction method, etc.) and the rationale for their inclusion in the project, as well as the requirements on which the design is to be based. | Please refer to Answer 147. | No
212 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / Additional Shaft Locations and Land Requirements | Who is going to pay the expropriation charges for any other additional shaft locations required for the retrieval of the TBM machines to the surface or for the execution of NATM works, other then shaft locations identified by the Client | Please refer to Answer 45. Expropriation and compensation costs for the land required for shaft locations (e.g., ventilation shafts, emergency shafts, etc) will be borne by the Employer, in line with its statutory land acquisition and RP/LRP obligations under Law No. 2942 and ESS5. | No
213 | Section VII – Employer’s Requirements / Annex A1 – Tunnel Typical Cross Sections; Annex E1 – Design Technical Specification / TBM Tunnel Internal Diameter | The internal diameter of the TBM tunnel is specified as 8.60 m in the tender drawings. However, the internal diameters of the TBM tunnels used in the ongoing high-speed rail projects (Halkalı–Kapıkule, Bursa–Yenişehir etc.) are 7.40 m. Could a tunnel cross-section with an internal diameter of 7.40 m also be used in this project? | The request to use a 7.40 m inner diameter is not accepted. The required TBM tunnel inner ring diameter is 8.60 m, as specified in the revised Annex E1 – Design Technical Specification and the applicable tender drawings. Please refer to Addendum No. 2, Amendments Nos. 14 and 31. | Yes
214 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Clause 6.2 – Bridges; Annex E4 – Railway Bridge Design Technical Specification / Structural System Selection | Please confirm whether the Contractor is free to select and optimise the structural system of each bridge/viaduct, including precast prestressed girders, cast-in-situ post-tensioned box sections, steel-composite decks, or other technically equivalent structural systems. It is noted that “Conceptual Report – Section 6.2. Bridges of Istanbul North Railway” states that the bridge system shall consist of precast girders with a 40 m span and a 2.40 m depth. Please confirm whether the above requirement is mandatory or whether alternative technically equivalent structural systems may be proposed by the Contractor. | Confirmed in principle. Please refer to the Employer’s Requirements and Annex E4. The Contract is Design-Build and the Contractor may optimize the bridge/viaduct structural system, subject to compliance with all mandatory design criteria, clearances, loads, durability, constructability, interfaces, third-party requirements and approvals. Reference/Conceptual Design structural forms and span arrangements are indicative unless expressly stated as mandatory. No amendment is made to the RFP. | No
215 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Bridges; Annex E4 – Railway Bridge Design Technical Specification / Span Arrangement | Please confirm whether the number and lengths of spans, and consequently the number and locations of piers, may be modified by the Contractor, provided that railway geometry, required clearances, environmental conditions, and third-party requirements are fully satisfied. | Please refer to Answer 214. | No
216 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Bearing Concept and Longitudinal Restraint | Please confirm whether the Employer/TCDD has a preferred bearing arrangement and system for longitudinal restraint and horizontal force transfer in long viaducts. If no specific system is prescribed, please confirm whether the bearing and restraint system may be determined by the Designer based on the results of seismic, braking, and track–bridge interaction analyses. | Please refer to Answer 214. | No
217 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / STU-LUD, Seismic Isolators and Dampers | Please confirm whether the use of STU/LUD devices, shock transmission units, seismic isolation bearings, dampers, or similar devices is permitted, provided that their application is technically justified by the structural analysis and design. | Please refer to Answer 214. | No
218 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Modular Viaduct System | Please confirm whether there are any Employer/TCDD restrictions on dividing long viaducts into structurally independent continuous modules, for example, modules comprising 3 or 4 spans separated by expansion joints. | Please refer to Answer 214. | No
219 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Inspection and Maintenance Access | Please confirm the minimum inspection and maintenance access requirements applicable to the deck, bearings, expansion joints, pier caps, and other structural elements. Please also confirm whether such requirements are to be considered in the quantity take-off. | Inspection and maintenance access shall be provided as required by the Employer’s Requirements, the applicable design standards and the approved Detailed Design. Any access provisions necessary for inspection and maintenance of decks, bearings, expansion joints, pier caps and other structural elements shall be taken into account by the Contractor in its design and pricing. No separate measurement or payment is introduced through this clarification. | No
220 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Bearing Replacement and Jacking Points | Please confirm whether all bearings are required to be replaceable without a complete interruption of railway operations. Please also confirm whether permanent jacking points required for bearing replacement shall be included in the quantity take-off. | Bearings shall be designed so that inspection, maintenance and replacement can be carried out with the minimum practicable disruption to railway operations and in accordance with the applicable bridge Technical Specifications and approved maintenance strategy. Permanent jacking points or other permanent provisions required for safe bearing replacement shall be included in the Contractor’s design and Contract Price where required by the selected bearing/structural system. No amendment is made to the RFP. | No
221 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / SW/2 Load Model | Please confirm whether SW/2 shall be applied to the design of INRAIL bridges. The basic operating scenario for INRAIL is understood to be mixed traffic comprising passenger and heavy freight trains. Annex E4 defines SW/2 as a load model for heavy railway traffic; however, it also states that “SW/2 shall only be taken into account at the request of the Authority” (Table 3.5.6.2.1 – Train Load Groups). As the Authority’s decision regarding the application of SW/2 is not specified, please confirm whether SW/2 is mandatory for INRAIL bridges. | Please refer to Annex E4. SW/2 shall be applied where required by the load-model provisions of Annex E4 and the applicable standards for the relevant structure/design case. The Contractor shall demonstrate the adopted load cases and combinations in the Detailed Design. No amendment is made to the RFP. | No
222 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Clause 3.5.3.2 – α Classification Factor | Please confirm the applicable α classification factor to be adopted for INRAIL. Section 3.5.3.2 of ANNEX E4 – Railway Bridge Design Technical Specification specifies the following possible α factor values: 0.75, 0.83, 0.91, 1.00, 1.10, 1.21, 1.33, and 1.46. As the α factor is applied as a multiplier to LM71, SW/0, and braking forces and directly affects the structural design, please confirm the specific α classification factor to be used for INRAIL bridges. | The applicable α classification factor for INRAIL bridges shall be 1.33. Please refer to Addendum No. 2, Amendment No. 23. | Yes
223 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification; Annex D – General Technical Specification / Design Standard Hierarchy and Load Combinations | Please confirm the applicable hierarchy of design standards and load combination methodology among EN, AASHTO, and TKDY. Based on our review of Annex E4 and Annex D, it is understood that the design of bridges and related structures is not governed by a single family of standards. Annex E4 refers to different national and international standards for different design aspects, including TS EN 1991-2 for certain load cases, AASHTO LRFD for certain load and load combination provisions and steel design, and the Turkish Seismic Design Code (TKDY) for seismic design. Annex D also refers to various standards and reference documents, including TS, EN, DIN, ANSI, ASTM, ACI, AREA, AASHTO, BS, and UIC. In this regard, please clarify which standard shall take precedence in the event of any discrepancy or conflict between the requirements, provisions, or methodologies of different standards. Furthermore, please confirm whether a Code Hierarchy / Design Basis Matrix will be established for the project. If so, please provide or confirm the applicable primary standard, secondary/reference standards, and order of precedence for each design discipline, including loads, load combinations, seismic design, reinforced concrete, steel structures, geotechnical design, etc. | Please refer to Section VII, Employer’s Requirements, the document-precedence provisions and Annex E4. The Contractor shall apply the design standards and combinations expressly required by the RFP. Where several standards are referenced, they shall be used consistently for the subject matter for which they are prescribed and shall not be selectively combined so as to reduce the required safety or performance level. Any conflict shall be referred to the Engineer in accordance with the Contract. No amendment is made to the RFP. | No
224 | Section VII – Employer’s Requirements / Annex K – Tunnel Electromechanical Works Technical Specification / Clauses 2.2 and 5.9 – Tunnel E&M and Fire-Fighting Systems | Of the specifications provided with the tender documents, Clause 2.2 of ANNEX K – Tunnel Electromechanical Works Technical Specification states that: "For tunnels 1,000 meters or longer, tunnel fire ventilation, fire detection, and fire suppression systems shall be installed." Additionally, Clause 5.9 requires: "To enable firefighting operations from outside the tunnel, one hydrant shall be installed at each tunnel entrance and exit portal." Are these hydrants to be installed only in tunnels longer than 1,000 meters, or in all tunnels? Is there a specified minimum tunnel length for the installation of hydrants? If hydrants are also required at the portals of tunnels shorter than 1,000 meters, will a fire water tank or pump station be installed within the tunnel structure to supply water to these hydrants? | The requirement in Annex K for one hydrant at each tunnel entrance and exit portal applies to tunnels for which the portal fire-fighting provisions of Annex K are required; it is not limited solely by the 1,000 m threshold stated for the complete tunnel fire-ventilation/fire-detection/fire-suppression system. The Contractor shall provide the water-storage, pumping and distribution arrangement necessary to satisfy the required hydrant performance where the available external water supply is insufficient, as established during Detailed Design. No amendment is made to the RFP. | No
225 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J – Power Supply and Traction Power System Technical Specification / Traction Substation Grid Connection | It is understood that there are 3 traction power supply substations that will supply the catenary system. It is kindly requested to provide the connection points of the said traction power supply substations to the energy transmission line, together with the approximate distances to the existing/planned energy transmission lines. | Please refer to Answers 50 and 51. | No
226 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J – Power Supply and Traction Power System Technical Specification; Annex K – Tunnel Electromechanical Works Technical Specification / Auxiliary Power Supply | It is understood that there are numerous tunnels located intermittently along the railway line and that these tunnels will require power supply for their auxiliary systems. Is it planned to supply the tunnels from the 3 x 154/25 kV traction power supply substations envisaged for the traction system, with 154/34.5 kV step-down transformers installed at the same locations? Alternatively, is it possible to obtain power at 34.5 kV level from distribution substations/overhead lines belonging to the Distribution Company and located near the tunnels? If so, it is kindly requested to provide the number, locations, and available capacities of the relevant distribution substations. | The auxiliary-power system shall be designed by the Contractor in accordance with Annex E1, the applicable power-supply Technical Specifications and the approved system studies. The final supply points, transformer/feeder arrangement, redundancy and interfaces shall be determined during Detailed Design in coordination with the relevant utilities and authorities. No amendment is made to the RFP. | No
227 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clause 7.6.13.5.5; Annex J – Power Supply and Traction Power System Technical Specification; Annex K – Tunnel Electromechanical Works Technical Specification / Tunnel Power Supply | Within the scope of Annex-E – Design Technical Specification, Clause 7.6.13.5.5, it is understood that electrical buildings are envisaged to be installed at both ends of the tunnels. However, particularly for long tunnels (e.g., tunnels approximately 12 km in length), it is considered that supplying power at LV level may not be a technically and economically efficient solution in terms of voltage drop and cable costs. In this context, it is kindly requested to clarify whether the solution of installing electrical buildings at both ends of the tunnels, as specified in the relevant clause, is also applicable to long tunnels. Alternatively, for long tunnels, could it be considered an appropriate solution to provide power supply at MV level and install MV equipment rooms and step-down transformer rooms at approximately 2 km intervals? | Please refer to Answer 226. | No
228 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification; Annex K – Tunnel Electromechanical Works Technical Specification / Tunnel Technical Buildings | It is considered that the tunnel technical buildings should include an MV room, transformer room, LV room, GSM-R room, and generator room. However, no tunnel technical building incorporating these functions can be seen in the drawings submitted as part of the tender. It is kindly requested to clarify whether such technical buildings are envisaged within the scope of the project and to provide an explanation regarding the relevant layout/configuration. | The Contractor shall provide all tunnel technical buildings/rooms and associated systems necessary to satisfy the Employer’s Requirements and applicable Technical Specifications. Their final number, locations, room arrangement and equipment interfaces shall be developed during Detailed Design. The absence of a separate tender-stage layout does not exclude required facilities from the lump-sum scope. No amendment is made to the RFP. | No
229 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | ANNEX H – Architectural and Finishing Works Technical Specification: Only the cover page of the relevant document is available, and the technical specification content could not be accessed. Could you please share the complete document with us? | ANNEX H – Architectural and Finishing Works Technical Specification has been provided in the shared RFP documents and shall be read together with the architectural drawings and Room Schedules. No additional Annex H document is issued through this clarification. No amendment is made to the RFP. | No
230 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Partition Walls: The available documents do not provide any information regarding the materials or technical specifications of the partition walls. Therefore, it is proposed that the partition walls be considered as aerated concrete block walls. Is this assumption acceptable? | Partition-wall materials and performance shall comply with Annex H and the applicable fire, acoustic, durability and operational requirements. Aerated concrete blockwork shall not be deemed automatically accepted solely on the basis of this clarification; any proposed wall system shall be demonstrated as compliant in the Detailed Design and submitted for approval. No amendment is made to the RFP. | No
231 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Floor Finishes: The Room Data Sheets do not provide any information regarding the underlying layers beneath the finished floor coverings or their technical specifications. Could you please provide the relevant details and technical information for these layers? Otherwise, the related works will be developed based on assumptions established in accordance with standard engineering and architectural practices and professional experience. Kindly confirm whether this approach is acceptable. | The complete floor build-up, including screeds, levelling layers, waterproofing/insulation and other necessary substrate layers, shall be developed by the Contractor in accordance with Annex H, the Room Schedule, the structural substrate and the intended use of each space. All layers necessary to achieve the specified final finish and performance shall be included in the Contract Price. No amendment is made to the RFP. | No
232 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Scope of Works: The note “CONSTRUCTION ELEMENTS IN SCOPE ARE SHOWN AS BOLD.” is included in the title blocks of the Architectural Concept Design drawings. Based on our review of the architectural drawings for Sabiha Gökçen Station, it is understood that the station structure associated with the SHT Line is excluded from the scope of works and quantity take-off, and that only the station structure associated with the YSS Line is included. Accordingly, kindly confirm that our assumption is correct that the station structure associated with the SHT Line will be excluded from the quantity take-off and only the station structure associated with the YSS Line will be considered. | The scope shall be determined from the Employer’s Requirements together with the architectural/reference drawings and their drawing conventions. Elements expressly shown as existing/outside the Contract scope are not to be included as new construction; however, all interface, protection, modification and completion works required to deliver the contracted YSS Line station works remain within the Contractor’s scope. No additional exclusion of SHT-related interface works is confirmed through this clarification. No amendment is made to the RFP. | No
233 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Entrance and Exit Façades: The available drawings and documents do not provide any material descriptions or technical specifications for the façades of the entrance and exit structures of Sabiha Gökçen Station. Therefore, it is proposed that these façades be considered as curtain wall systems. Kindly confirm whether it is acceptable to prepare the quantity take-off based on the dimensions indicated in the plans and sections, assuming the use of a curtain wall system. | The façade system for the entrance/exit structures shall be developed during Detailed Design in accordance with Annex H, the architectural intent, fire/thermal/acoustic requirements and the applicable airport/station interfaces. A curtain-wall solution may be proposed where compliant, but is not deemed pre-approved by this clarification. No amendment is made to the RFP. | No
234 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Staircases Providing Access to the Intermediate Level: The staircases providing access to the Intermediate Level in the SHT direction are shown in halftone as excluded from the scope on the relevant drawings, apparently due to a drafting or presentation inconsistency. However, the same staircases are shown as included in the scope on the Concourse Level Plan. This discrepancy is considered to be a drawing/representation error. Therefore, kindly clarify and confirm whether these staircases are included in the scope of works and which drawing should be taken as the basis. | The staircases and other vertical-circulation elements required to provide a complete, safe and code-compliant station circulation arrangement shall be included where required by the Employer’s Requirements and the coordinated architectural design. A halftone/graphic inconsistency on one drawing shall not by itself be used to omit an element shown as required elsewhere. The final arrangement shall be resolved in the Detailed Design. No amendment is made to the RFP. | No
235 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Open Car Park: The Ground Floor Plan does not include any layout, arrangement, or detailed drawings for the open car park. Therefore, for the quantity take-off, the required areas and associated works will be estimated based on the open car park capacity of 101 vehicles specified in the Room Schedule. Kindly confirm whether this approach is acceptable. | The open-car-park design shall satisfy the capacity and functional requirements stated in the RFP, including the stated 101-vehicle capacity where applicable. The final layout, circulation, dimensions, drainage, markings, accessibility and related works shall be developed during Detailed Design and included in the Contract Price. No amendment is made to the RFP. | No
236 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Tactile Walking Surface Indicators: The architectural drawings and the Room Schedule do not include any indication or description of tactile guiding and warning surfaces. However, in accordance with the relevant accessibility standards and guidelines (TS 9111, TS ISO 23599, and the Accessibility Guidelines), tactile surfaces should be provided in the required areas to ensure safe and independent access for visually impaired users. Accordingly, tactile guiding and warning surfaces are proposed to be included in the quantity take-off. Kindly confirm whether this approach is acceptable. | Tactile guiding and warning surfaces shall be provided wherever required by the applicable accessibility legislation/standards and the approved station design. The Contractor shall include the necessary tactile surfaces in the Detailed Design and Contract Price even where they are not individually indicated on the tender-stage drawings. No amendment is made to the RFP. | No
237 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Floor Finishes at Concourse Level: In the Room Schedule, the floor finish for some rooms at the Concourse Level is specified as “Epoxy Coating,” while for others it is specified as “Leveling Concrete + Screed + Epoxy Coating.” However, the available drawings and documents do not provide sufficient explanation for the use of different subfloor layers beneath the same final finish. Is there a specific technical reason for this difference? Kindly provide clarification. | The floor build-ups shown in the Room Schedule shall be treated as room-specific requirements. Where the same final finish is shown with different substrate/build-up layers, the applicable Room Schedule requirement for the relevant room shall be followed and completed during Detailed Design to suit the structural substrate and operational requirements. No amendment is made to the RFP. | No
238 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Textured Paint Application: It is proposed to apply textured paint to the internal tunnel surfaces on the track side at Platform Level. However, the current Room Schedule does not specify textured paint for these surfaces. Kindly advise and confirm whether the textured paint application should be included in the Room Schedule and the quantity take-off. | No blanket addition of textured paint to all track-side tunnel surfaces is approved through this clarification. Finishes shall be provided where required by Annex H, the Room Schedule, the architectural drawings and the applicable fire/durability/maintenance requirements. Any alternative or additional finish proposed by the Contractor shall be justified in the Detailed Design and submitted for approval. No amendment is made to the RFP. | No
239 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Wall Finishes in Passenger Areas: “Paint on Exposed Concrete” or “Textured Paint on Exposed Concrete” is specified, particularly for the internal faces of reinforced-concrete walls in passenger areas. However, applying paint directly onto exposed concrete surfaces is not considered technically advisable. In underground structures, potential water or moisture infiltration may cause staining, paint deterioration, and visual defects over time. Therefore, mechanically fixed cladding systems are recommended for these surfaces to minimise the impact of potential water and moisture on the finished surface, facilitate maintenance and replacement, and provide a more controlled architectural appearance in passenger areas. Kindly confirm whether this proposed approach is acceptable. | The tender-stage requirement for painted/exposed-concrete finishes shall not be replaced automatically by a mechanically fixed cladding system through this clarification. The Contractor may propose a technically equivalent or improved finish during Detailed Design, provided that fire, durability, moisture, maintenance, architectural and operational requirements are satisfied and the proposal is approved. No amendment is made to the RFP. | No
240 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Floor Finishes in Technical Areas: It has been noted that the floor finishes for certain technical areas outside the platform area are not specified in the Room Schedule. Considering the operational conditions and durability requirements, a surface hardener finish is recommended for these areas. However, this finish is not currently included in the Room Schedule. Accordingly, it is proposed that the surface hardener application be added to the Room Schedule and included in the quantity take-off. If this finish is not preferred, an epoxy floor coating is recommended as an alternative. Kindly provide your comments and confirm the floor finish to be applied. | For technical areas where a finish is not expressly stated, the Contractor shall propose a durable floor-finish system appropriate to the room function, loading, maintenance, fire and operational requirements, taking Annex H and comparable rooms as the basis. The proposed system shall be submitted for approval during Detailed Design. No amendment is made to the RFP. | No
241 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Precast U-Channel Application: Skirting is specified along the internal faces of the external reinforced-concrete walls on all levels. However, considering the detailing and construction requirements in these areas, a precast U-channel is considered more appropriate than conventional skirting. Accordingly, it is proposed that the existing skirting specification be revised and that the precast U-channel application be included in the Room Schedule and quantity take-off. Kindly provide your comments and confirmation regarding this proposal. | The specified skirting requirement shall remain the tender basis. A precast U-channel or other alternative detail may be proposed during Detailed Design where it provides equal or better performance and is compatible with drainage, waterproofing, cleaning and maintenance requirements, subject to approval. No amendment is made to the RFP. | No
242 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Unspecified Finishes: It has been noted that the floor, wall, and/or ceiling finishes for certain rooms are not specified in the Room Schedule. Kindly advise whether the relevant material information will be provided separately. If no additional material specifications will be issued, kindly confirm whether it would be acceptable for us to propose appropriate materials based on the intended use of each room, applicable technical requirements, and finishes specified for similar rooms, and to use these proposals as the basis for the quantity take-off. | Where a room finish is not expressly identified, the Contractor shall develop and propose an appropriate finish based on the room function, Annex H, applicable technical requirements and the finishes of comparable spaces. The proposed finishes shall be submitted for approval and all necessary works shall be included in the Contract Price. No amendment is made to the RFP. | No
243 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Proposed Revisions to Finishes at Platform Level: It is proposed that the finishes specified in the Room Schedule for certain technical rooms at Platform Level be revised as follows, considering their intended use and technical requirements: Ventilation Connection Tunnel, Tunnel Ventilation Fan Room, and Exhaust Fan Room: Replace the specified granite flooring with surface-hardened concrete, which is considered a more suitable and economical solution for technical areas. Drainage Room: Replace the specified terrazzo flooring with ceramic tiles. Electrical Rooms: The Room Schedule specifies terrazzo flooring for some electrical rooms and epoxy flooring for others. To ensure consistency and meet the technical requirements of electrical rooms, antistatic epoxy flooring is proposed for all electrical rooms. Ventilation Connection Tunnel: Replace the specified baffle ceiling with silicone-based paint, considering the operational conditions of the technical area. Kindly provide your comments and confirm whether the above revisions may be incorporated into the Room Schedule and used as the basis for the quantity take-off. | The proposed finish substitutions are not approved automatically through this clarification. The Contractor may propose technically equivalent or improved finishes during Detailed Design, provided that the applicable fire, durability, slip-resistance, electrical-room, hygiene, maintenance and architectural requirements are satisfied and the proposal is approved. No amendment is made to the RFP. | No
244 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | Door Types and Specifications: It has been noted that the door types and specifications are not defined for every room in the Room Schedule. For doors that have not been specified, it is proposed that appropriate types and technical specifications be determined and incorporated into the design, considering the intended use of the rooms, fire safety, accessibility, operational requirements, and relevant architectural and engineering criteria. Kindly confirm whether this approach is acceptable. | For rooms where the door type is not expressly identified, the Contractor shall determine the appropriate door type and specification during Detailed Design based on room use, fire-rating, smoke control, security, accessibility, acoustic, durability and operational requirements, and shall submit the design for approval. No amendment is made to the RFP. | No
245 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification; Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Architectural Concept Design, Room Schedule and Finishes | WC Doors: The Room Schedule does not provide any material or technical specifications for the WC doors. Based on the indications in the architectural drawings, these doors are understood to be compact laminate doors. Accordingly, the quantity take-off will be prepared on the assumption that compact laminate doors will be used for the WCs. Kindly confirm whether this assumption is acceptable. | WC doors shall comply with Annex H, the architectural requirements and the applicable hygiene, moisture-resistance, durability and accessibility criteria. Compact-laminate doors may be proposed where compliant, but are not deemed pre-approved solely by this clarification. No amendment is made to the RFP. | No
246 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | ANNEX H – Architectural and Finishing Works Technical Specification: Only the cover page of the relevant document is available, and the technical specification content could not be accessed. Could you please share the complete document with us? | Please refer to Answer 229. | No
247 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Partition Walls: The available documents do not provide any information regarding the materials or technical specifications of the partition walls. Therefore, it is proposed that the partition walls be considered as aerated concrete block walls. Is this assumption acceptable? | Please refer to Answer 230. | No
248 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Floor Finishes: The Room Schedule does not provide any information regarding the underlying layers beneath the finished floor coverings or their technical specifications. Could you please provide the relevant details and technical information for these layers? Otherwise, the related works will be developed based on assumptions established in accordance with standard engineering and architectural practices and professional experience. Kindly confirm whether this approach is acceptable. | Please refer to Answer 231. | No
249 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Scope of Quantity Take-Off: The note “NEW CONSTRUCTIONS ARE SHOWN WITH FOCUSED COLORS (SHOWN AS BOLD)” is included in the title blocks of the Architectural Concept Design drawings. Based on this drawing convention and the relevant note, kindly confirm that our assumption is correct that only the Platform Level, Concourse Level, and the completed car park structure at elevation +75.80 (CAR PARK LEVEL) are included in the quantity take-off, excluding façade works. | The quantity take-off and Proposal Price shall cover the complete contractual station scope identified in the Employer’s Requirements and coordinated architectural/reference drawings. The drawing colour/bold convention shall be used together with the written scope; no façade or other element shall be excluded solely on the basis of an assumption unless it is expressly outside the Contract scope. No amendment is made to the RFP. | No
250 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Tactile Walking Surface Indicators: The architectural drawings and the Room Schedule do not include any indication or specification for tactile guiding and warning surfaces. However, in accordance with the relevant accessibility standards and guidelines—TS 9111, TS ISO 23599, and the Accessibility Guidelines—tactile surfaces should be provided in the required areas to ensure safe and independent access for visually impaired users. Accordingly, tactile guiding and warning surfaces are proposed to be included in the quantity take-off. Kindly confirm whether this approach is acceptable. | Please refer to Answer 236. | No
251 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Textured Paint Application: It is proposed to apply textured paint to the internal tunnel surfaces on the track side at Platform Level. However, the current Room Schedule does not specify any textured paint finish for these surfaces. Kindly provide your comments and confirm whether the textured paint application should be added to the Room Schedule and included in the quantity take-off. | Please refer to Answer 238. | No
252 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Precast U-Channel Application: Skirting is specified along the internal faces of the external reinforced-concrete walls on all levels. However, considering the relevant detailing and construction requirements, a precast U-channel is considered more appropriate for these areas than conventional skirting. Accordingly, it is proposed that the existing skirting specification be revised and that the precast U-channel application be added to the Room Schedule and included in the quantity take-off. Kindly provide your comments and confirmation regarding this proposal. | Please refer to Answer 241. | No
253 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Door Types and Specifications: It has been noted that door types and specifications are not defined for every room in the Room Schedule. For unspecified doors, it is proposed that appropriate door types and technical specifications be determined and incorporated into the design, considering the intended use of the rooms, fire safety, accessibility, operational requirements, and relevant architectural and engineering criteria. Kindly confirm whether this approach is acceptable. | Please refer to Answer 244. | No
254 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Discrepancies Between the Room Schedule and Architectural Floor Plans: Discrepancies have been identified between the Room Schedule and the architectural floor plans: Platform Level: Some rooms shown on the Platform Level Plan are not included in the Room Schedule. Likewise, some rooms listed in the Room Schedule are not shown on the Platform Level Plan. Ticket Hall Level: Some rooms shown on the Ticket Hall Level Plan are not included in the Room Schedule, while some rooms listed in the Room Schedule are not shown on the Ticket Hall Level Plan. Kindly clarify which document should take precedence for the quantity take-off and how these discrepancies should be addressed. Unless otherwise instructed, kindly confirm our assumption that the floor plans will be taken as the basis for the quantity take-off, with the relevant assessments made in accordance with our professional engineering and architectural experience. | Where the Room Schedule and architectural floor plans are inconsistent, the discrepancy shall be resolved through the document-precedence/interpretation provisions and the coordinated Detailed Design. Neither document shall be used in isolation to omit a room or required function. For Proposal purposes, the Contractor shall include the works necessary to provide a complete and operational station in accordance with the Employer’s Requirements. No amendment is made to the RFP. | No
255 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Discrepancies in Vertical Circulation Elements: Certain inconsistencies have been identified within the floor plans. The staircase and lift groups located on gridlines O2A and O4A at the Ticket Hall Level are shown as providing access from the Platform Level to the Ticket Hall Level. However, the same vertical circulation elements do not appear to continue to the First Car Park Level. Therefore, kindly confirm our assumption that these staircase and lift groups should be excluded from the quantity take-off. | The staircase/lift groups shall not be excluded solely because continuation is not shown on one tender-stage floor plan. The final vertical-circulation arrangement shall be coordinated during Detailed Design to provide all required connections, accessibility, fire/egress and operational functions. All elements required for the compliant final design shall be included in the Contract Price. No amendment is made to the RFP. | No
256 | Section VII – Employer’s Requirements / Annex H – Architectural and Finishing Works Technical Specification / Istanbul Airport Station Architectural Concept Design, Room Schedule and Finishes | Under-Platform Level Room Schedule: No Room Schedule has been provided for the Under-Platform Level. Kindly confirm whether the Room Schedule for this level will be issued. If it will not be provided, kindly confirm whether it is acceptable to prepare the quantity take-off for the relevant rooms based on the available design information and our professional engineering and architectural experience. | Please refer to Answer 229. | No
257 | Section IX – Particular Conditions / Sub-Clauses 13.6 and 13.7 – Price Adjustment; Section IV – Proposal Forms / Price Adjustment and Daywork Provisions | PDS ITP 15.3 / ITP 15.5 and Section IX Part A — Contract Data. PDS ITP 15.3 states: "The prices quoted by the Proposer shall be subject to adjustment during the performance of the Contracts." By contrast, the opening sentence of the Schedule of Cost Indexation is conditional: "If in accordance with GC 13.7, prices shall be adjustable…", and the Contract Data contains no entry for GC 13.7 (entries for 13.3.1(a) and 13.4(b)(ii) are present). At the same time, the Table of Adjustment Data is provided complete with coefficient ranges, the Employer's Requirements state that "the RFP includes defined price adjustment and escalation mechanisms prepared by the Employer", and PCC Sub-Clause 13.6 expressly refers to "Sub-Clause 13.7 [Adjustments for Changes in Cost]". It is therefore clear that price adjustment is intended, and that what is missing is only the Contract Data entry. Kindly confirm whether a line item for GC 13.7 will be added to the Contract Data by addendum, or whether the price adjustment regime is intended to operate through ITP 15.3 and the Schedule of Cost Indexation without a separate Contract Data entry. | Please refer to PDS ITP 15.3 and the applicable Contract price-adjustment provisions. Price adjustment shall be applied in accordance with the RFP and the completed Table(s) of Adjustment Data. The absence of a separate Contract Data entry does not disapply the express price-adjustment provisions incorporated in the Contract. No amendment is made to the RFP. | No
258 | Section IV – Proposal Forms / Daywork Schedule and Price Adjustment Forms; Section IX – Particular Conditions / Part A – Contract Data | Section IV — Daywork Schedule; ITP 40.1(a). ITP 40.1(a) brings Daywork into the evaluation with the words "but including Daywork items, where priced competitively". However, in the table of contents of Section IV every Daywork Schedule / Schedule of Daywork Rates entry is listed with a broken bookmark reference ("Hata! Yer işareti tanımlanmamış." — "Error! Bookmark not defined."), and the tables themselves are not present in the document package. We consider that the tables may have been omitted inadvertently. Will the Daywork Schedule tables be issued by addendum, or will Daywork not be applied under this Contract? If applicable, kindly advise the date on which the tables will be provided. | Daywork is not applicable under the RFP as issued following Addendum No. 2, Amendment No. 6. The Daywork Schedule entries are deleted from the Table of Forms; no Daywork Schedule tables will be issued. | Yes
259 | Section VII – Employer’s Requirements / Annex B2 – INRAIL Railway Safety Plan; Annex G1 – Superstructure Works Construction Specification / Design Speed | ANNEX B2 — Operational speeds; ANNEX G1; Safety Plan. ANNEX B2 states: "The operational design speeds are 160 km/h for passenger services and operational speed of 120 km/h for freight services." By contrast, ANNEX G1 refers to 250/200 km/h and the Safety Plan to 250 km/h. Kindly confirm whether the design speed governing the track superstructure design and acceptance criteria is 160 km/h (passenger) / 120 km/h (freight) as per ANNEX B2, or 250/200 km/h as per ANNEX G1 / the Safety Plan. Noting that ANNEX B2 defines the operational design speeds specifically for this Project, kindly also clarify whether the 250/200 km/h values in ANNEX G1 / the Safety Plan are project-specific or of generic/template origin. | Please refer to Annex B2, Annex G1 and the Employer’s Requirements. The Project operational design speeds for the railway alignment and track are 160 km/h for passenger services and 120 km/h for freight services. The track superstructure shall be designed accordingly and in compliance with the applicable Technical Specifications. The electrification and signalling systems shall be designed for a maximum speed of 200 km/h. References to 250 km/h in the RFP shall not be construed as establishing a 250 km/h Project design speed for the track superstructure. No amendment is made to the RFP. | No
260 | Section VII – Employer’s Requirements / Annex G14 – Technical Specification for Railway Machinery / Clauses 1.3 and 9.2 | ANNEX G14 — Technical Specification for Railway Machinery, clause 1.3 and clause 9.2. Clause 9.2 provides that, if necessary, the Employer may request a machine group (ballast machine, regulator machine, and dynamic track stabilizer) at each construction site ("if necessary, the Employer may request a machine group (ballast machine, regulator machine, and dynamic track stabilizer) at each construction site."); clause 1.3, in turn, contains a conditional flexibility: "If the machine is approved by the Employer…". Kindly clarify whether the machine-group obligation under clause 9.2 requires a separate group for each concurrently operating worksite within a Lot, or whether, subject to Employer approval under clause 1.3, a single group serving multiple worksites is acceptable. | Please refer to Annex G14. The Contractor shall provide sufficient railway machinery and on-track equipment to achieve the approved programme, quality and production requirements. Unless Annex G14 expressly requires a dedicated machine group for each individual work front, the Contractor may propose an optimized allocation subject to demonstrating availability and compliance and to the Engineer’s acceptance. No amendment is made to the RFP. | No
261 | Section VII – Employer’s Requirements / Annex G15 – Welding Specification / Clauses 5.3 and 5.4; Annex G19 – Rail Weld Inspection / Testing Specification | ANNEX G15 — Welding Specification, clause 5.3 and clause 5.4; ANNEX G19. G15 clause 5.3 defines a sampling-based regime: "the first 300 joints … one joint out of every subsequent 100 will be tested"; the immediately following clause 5.4 states: "All welded joints will be inspected using ultrasonic testing." ANNEX G19 likewise states: "Welds and HAZs will be inspected at a rate of 100%." The conflict lies between two consecutive clauses of the same document. Kindly confirm whether ultrasonic inspection of welds shall be performed at 100% as per G15 clause 5.4 and ANNEX G19, or on the sampling basis of G15 clause 5.3 (first 300 joints, thereafter one in every 100). | Ultrasonic inspection of welded joints shall be performed at 100% in accordance with Annex G15 Clause 5.4 and Annex G19. The sampling provision in Annex G15 Clause 5.3 shall not be interpreted as reducing the 100% ultrasonic inspection requirement; it applies only to the specific additional/destructive or other testing regime addressed by that clause. No amendment is made to the RFP. | No
262 | Section I – Instructions to Proposers (ITP) / ITP 17.5; Section II – Proposal Data Sheet (PDS) / ITP 17.5 – Specialized Subcontractor Parts | ITP 17.5; Section III-A, Criterion 4.2(a), sub-paragraph (b). ITP 17.5 lists the permitted specialized subcontracting parts under eight headings: Line Laying · Ballast Paving · Rail Welding · Cabling · Ground Improvement · Reinforced Concrete Works · Earthworks · Construction of Bridge. By contrast, Section III-A, Criterion 4.2(a), sub-paragraph (b) describes the superstructure as "tracklaying, ballasting (or slab construction), rail welding, fastening installation, turnout assembly and electrification"; ballastless (slab track) construction and turnout assembly are not named in the ITP 17.5 list. The fact that Contract Data 4.4(b) is stated as "N/A" indicates that no specific part of the Works is separately prohibited from subcontracting, while the approval, notification, responsibility and percentage limitations otherwise applicable under the GC/PCC are understood to continue in force; the question below is directed solely at the scope to be taken into account in the QUALIFICATION ASSESSMENT under ITP 17.5/18. We note that Contract Data 4.4(b) is stated as "N/A", which we understand to mean that no specific part of the Works is separately prohibited from subcontracting, without prejudice to the approval, notification, responsibility and percentage limitations otherwise applicable under the GC/PCC. On that basis, kindly confirm (i) whether the parts listed in ITP 17.5 — (a) Line Laying, (b) Ballast Paving, (c) Rail Welding — encompass slab track construction and turnout assembly as described under Section III-A, Criterion 4.2(a), sub-paragraph (b), that is, whether the specific experience of a Specialized Subcontractor proposed for those two works may be taken into account in the assessment of the Proposer's qualifications; and (ii) whether works to be executed by Specialized Subcontractors proposed under ITP 17.5 count towards the 30% maximum accumulated subcontracting value in Contract Data 4.4(a). | Please refer to PDS ITP 17.5. The listed specialized parts shall be interpreted according to the actual scope of the relevant specialized activity. A Specialized Subcontractor’s specific experience may be relied upon only for a part expressly permitted by PDS ITP 17.5 and only to the extent allowed by Section III. The list is not expanded by this clarification. | No
263 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Subgrade and Formation Handover | ANNEX E1 — UIC 719 ballast + sub-ballast thickness formula; ANNEX F. In E1 the thickness formula is given together with its parameters ("E = 0.45 m P3: good foundation"; "d = + 0.12 Maximum axle load of loaded vehicle < 250 kN"; "f = 0 V ≤ 160 km/h or high-speed trains on P3 track bed"), while ANNEX F states "(All fills and cut faces shall be designed according to P3 bearing capacity)". Kindly confirm (i) whether the Contractor's detailed design is required to achieve a P3 prepared subgrade throughout the route — that is, whether sections where the natural subgrade proves to be P2 or lower are to be improved to P3, or whether the correspondingly thicker superstructure layers under the UIC 719 formula are to be adopted instead; (ii) that parameters d and f of the UIC 719 formula in ANNEX E1 are to be applied with a 250 kN axle load and V ≤ 160 km/h (or high-speed on P3) respectively. This confirmation has a direct quantitative effect: on a P3 basis the formula yields e ≈ 0.52 m, whereas on a P2 basis it yields e ≈ 0.67 m, the difference corresponding to a significant volume of granular works over the route length. Further, the difference between the UIC 719 parameter list in ANNEX E1 and the selected-material table in ANNEX F as the basis of the thickness formula is a discrepancy between documents of equal rank. ER 1.2 requires such discrepancies to be referred for the Engineer's written determination and precludes the Contractor from resolving them unilaterally; as the matter directly affects the proposal price, kindly clarify it at Proposal stage pursuant to ITP 7.1. | The prepared subgrade/formation shall be designed to achieve P3 bearing-capacity class in accordance with Annex F and Annex E1. Where the natural subgrade is below P3, the Contractor shall provide the improvement/replacement measures necessary to achieve P3 rather than pricing the permanent track formation on a lower prepared-subgrade class. For the UIC 719 thickness calculation, the parameters stated in Annex E1 shall be applied, including d = +0.12 for maximum axle load below 250 kN and f = 0 for V ≤ 160 km/h (or high-speed operation on P3), as applicable. No amendment is made to the RFP. | No
264 | Section VII – Employer’s Requirements / Annex D – General Technical Specification; Annex E2 – Discipline-Specific Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Subgrade and Formation Requirements | Employer's Requirements — Site investigations; ANNEX D; ANNEX E2. The Employer's Requirements state: "The Contractor shall, at its own cost and responsibility, carry out all additional site investigations"; ANNEX D states: "The Contractor shall not be entitled to a time extension or additional payment as a result of additional geotechnical investigations…"; and ANNEX E2 provides for "additional drillings (quantity-meterage) … The Supervision Engineer/Employer may … change the locations, depths, measurement intervals". ANNEX F further prescribes advanced ground improvement methods ("Preloading, Surcharge, Staged Loading, Vertical Band Drain Method, Use of Geotextiles, Jet Grouting and Construction of Gabions shall be carried out in accordance with the KGM Specification…"), yet the chainages at which they are to be applied are given in no document. In the interest of comparable Proposals, kindly advise whether the Employer will define a minimum number and total metreage of additional boreholes and the scope of the geophysical investigation works; and (ii) will a chainage list of sections anticipated to require ground improvement be provided — and if not, on what common basis Proposals will be rendered comparable in respect of this item? | No predetermined chainage list for ground improvement and the metreage of additional boreholes will be provided. Tenderers shall make all necessary assessments and allowances in their lump-sum Proposal. All risks, quantities and costs associated with additional investigations, ground conditions and any required ground improvement shall be borne by the Contractor. No additional payment or extension of time shall arise in this respect. No amendment is made to the RFP. | No
265 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report; Annex E1 – Design Technical Specification; Annex G10 – Ballastless Railway Line Construction Specification / Formation-to-Track Interface | ANNEX E1 — Table 5.2 (Construction Tolerances); ANNEX G10; ANNEX B1. ANNEX E1 lists the applicable construction tolerances as "the applicable TSI, EN 13848 series, relevant UIC recommendations and the tolerances specified herein", and provides that where a conflict exists the more stringent requirement shall apply. For the main line, Table 5.2 gives "3 mm between rail centres over a 16 m rail length" (along the track), "1435 mm ± 3 mm" (gauge), "± 3 mm over 50 m" (longitudinal level) and "± 2 mm" (cross level), and characterises these as the "maximum permitted construction deviations at the time of acceptance". These four figures are STATIC construction tolerances, whereas EN 13848 defines track geometry QUALITY by means of limit classes that depend on line speed and on the measurement wavelength band. The two are not quantities of the same kind, and the rule that "the more stringent requirement shall apply" therefore cannot be operated at acceptance without knowing which part of EN 13848, which limit class and which speed are to be applied. Furthermore, ANNEX G10 requires track geometry to be achieved and reported in accordance with the "TCDD/Turkish State Railways Superstructure Works Acceptance Conditions Technical Specifications", and ANNEX B1 likewise cites that document in its list of specifications; however, that document is not included in the tender package. Kindly advise (i) the part of EN 13848, the limit class and the measurement wavelength band to be applied at acceptance; (ii) how the rule that "the more stringent requirement shall apply" is to be operated at acceptance as between the static construction tolerances of Table 5.2 and the geometry-quality limits of EN 13848, the two not being quantities of the same kind; (iii) the speed on which acceptance is based; and (iv) whether the "Superstructure Works Acceptance Conditions" document referred to in ANNEX G10 will be issued by addendum. | Please refer to Annex E1 and Annex G10. The static construction tolerances stated in Annex E1, Table 5.2 shall apply at acceptance together with the applicable EN 13848 requirements. Each requirement shall be applied according to its own measurement basis, and the 'more stringent requirement' rule shall apply where the criteria are directly comparable. The applicable EN 13848 measurement parameters and acceptance regime shall be established in the Detailed Design for the applicable design/operating speed and shall be subject to the Engineer’s review. No additional TCDD Superstructure Works Acceptance Conditions document is issued through this clarification. No amendment is made to the RFP. | No
266 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 1.1.95; Section VII – Employer’s Requirements / Annex E3 – Discipline-Specific Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification; Section IX – Particular Conditions / Sub-Clause 4.26 | ANNEX F — Fill over structures; ANNEX E3 — Settlement monitoring. ANNEX F states: "Construction of the fill over the structural works shall not commence until 21 days have elapsed from the completion of the construction of these works…"; ANNEX E3 states: "In fills where the height exceeds 3 m and which rest on compressible soils … assessments regarding settlement levels and the time required for settlement to complete will be made based on the results of in-situ settlement measurements." These provisions make completion of fills and works over structures dependent on measurement outcomes, and settlement duration cannot be committed in advance. The milestone chain (M1 12 months + M2 36 months + M3 12 months + M4 24 months) meanwhile exceeds the Time for Completion in aggregate. Kindly clarify (i) noting that the Milestone table under Contract Data Sub-Clause 1.1.95 defines each Milestone as running from the completion date of the preceding one — i.e. a consecutive chain totalling 84 months — whereas PCC Sub-Clause 4.26 [Milestones] requires the time for completion of each Milestone to be "calculated from the Commencement Date", the Time for Completion is 1,826 days (≈60 months) and the ER states "sixty (60) months from the Effective Date": how these four provisions are to be reconciled and which document will be corrected by addendum; (ii) whether settlement-driven waiting periods are deemed included WITHIN the Milestone durations; and (iii) for programming purposes, the anticipated settlement observation durations for fill sections (or the upper-bound values to be adopted for design). | Please refer to Answer 5 and Addendum No. 2, Amendment No. 3 for the Milestone dates. Settlement-related waiting and observation periods shall be accommodated within the Contractor’s contractual programme and the applicable Milestone/Time for Completion requirements, unless an entitlement to Extension of Time arises under the Contract. No fixed Employer-prescribed settlement observation duration or upper-bound value is issued through this clarification; the required duration shall be determined from the Contractor’s investigations, Detailed Design and monitoring results, subject to the Engineer’s review. | Yes
267 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification; Annex F – Civil Works (Infrastructure) Technical Specification / Formation Acceptance Criteria | ANNEX E1 — UIC 719 "g" parameter and Table 5.1; ANNEX F — selected material. ANNEX E1 ties the geotextile directly to the subgrade class: "g = + : If the sub-base material is QS1 or QS2, geotextile will be used in the superstructure. / g = 0 : If the prepared subgrade is QS3, geotextile is not required". However, the distribution of the QS1/QS2/QS3 classes by chainage along the route is not given in the tender documents. Furthermore, ANNEX E1 Table 5.1 and ANNEX F differ on the selected-material thickness for a QS3 subgrade with a P3 prepared formation. Kindly (i) advise the chainage-based distribution of prepared-subgrade QS classes along the route — this information governs both the geotextile laying area and the sub-base thickness; and if it will not be provided, advise on what common basis Proposals will be rendered comparable in respect of this item; and (ii) clarify whether, for QS3 subgrade with a P3 prepared formation, the selected-material thickness is nil per ANNEX E1 Table 5.1 or 20 cm per ANNEX F. | The distribution of QS1/QS2/QS3 subgrade classes along the route shall be determined by the Contractor on the basis of the available Site Data, its own investigations and detailed design. No chainage-based QS classification will be issued by the Employer. The Contractor shall include in its lump-sum Proposal all geotextile, selected material and associated works necessary to comply with the Employer’s Requirements. With respect to QS3 subgrade and P3 prepared formation, ANNEX F shall govern and a 20 cm selected-material layer shall be provided. ANNEX E1 Table 5.1 shall be read accordingly. No amendment is made to the RFP. | No
268 | Section VII – Employer’s Requirements / Annex B2 – INRAIL Railway Safety Plan / Depot and Siding Scope | ANNEX B2 — SAW and IST stations. ANNEX B2 states: "Construction of a new underground railway station for the project line at SAW, with siding tracks to be incorporated in separate parallel tunnels to segregate freight and passenger trains…" and, for IST, "incorporating siding tracks with structural separation". No information on the length or geometry of these siding tracks could be found in the tender documents. Kindly advise the total lengths, number of tracks and superstructure system (ballasted/ballastless) of the siding tracks at SAW (Lot 1) and IST (Lot 4) stations, and confirm that these tracks fall within the scope of this Contract. | The siding tracks at SAW (Lot 1) and IST (Lot 4) referred to in ANNEX B2 are within the scope of the respective Lots. Their final number, lengths, geometry and superstructure system shall be determined by the Contractor as part of the Detailed Design, in accordance with Section VII – Employer’s Requirements, the applicable Lot requirements, Technical Specifications, operational requirements and Project interfaces. The Contractor shall make all necessary allowances in its lump-sum Proposal for the complete design and construction of such siding tracks. No prescribed quantities or dimensions additional to those stated in the RFP will be provided. No amendment is made to the RFP. | No
269 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Depot and Siding Scope | ANNEX E1 — Design family for depot/workshop tracks; pre-bending provision. ANNEX E1 defines a separate design family for depot tracks (15 km/h, R min 90 m) and contains the provision "Rails intended for use on curves with a radius of 150 m or less shall be pre-bent or pre-curved using standard workshop methods or other approved methods."; given the minimum radius of the main line, these provisions become meaningful only in depot/siding geometry. Kindly confirm whether depot, maintenance-yard or stabling tracks are included in the scope of this Contract; if so, please advise their locations, lengths and sleeper/fastening types. | For the avoidance of doubt, no depot, maintenance yard, workshop or stabling facility is included within the scope of this Contract; references to such facilities or associated track design criteria in Annex E1 shall not be construed as establishing any such facility within the Contract scope. No amendment is made to the RFP. | No
270 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Depot and Siding Layout | ANNEX A1 — Itinerary drawing (AYGM-INR-ALG-ITN-001) and typical cross-sections (AYGM-INR-ALG-TCS-003). On the itinerary drawing the connection lines CONNECTION-1 (KM 0+000.000 – 0+915.860, single track) and CONNECTION-2 (KM 0+000.000 – 1+305.920, double track) on the Anatolian side are shown as included in the LOT-1 length (L = 28,692.00 m); CONNECTION-2 connects to the existing line. As the ER Lot 1 scope section expressly includes the triangular connection and its turnout structures, no scope confirmation is needed; kindly advise (i) the works limit of CONNECTION-2 at the tie-in to the existing line (including the turnout zone); and (ii) the sleeper/fastening family to be applied on the connection lines — the main-line B07 sleeper with W21 fastening, or the family shown on the single-track typical cross-section TCS-003. | Please refer to Section VII, Employer’s Requirements, the Lot 1 scope, Annex A1 and the applicable Technical Specifications. CONNECTION-1 and CONNECTION-2, including the complete tie-in of CONNECTION-2 to the existing railway and all associated turnout and interface works required for a complete and operational connection, are included within the Contractor’s scope. The final works limits, tie-in arrangement and extent of the turnout/interface zone shall be established by the Contractor during Detailed Design, taking into account the existing railway conditions and the applicable interface requirements. The sleeper and fastening system for the connection lines shall be determined in accordance with the applicable track category, design criteria and Technical Specifications and submitted as part of the Detailed Design for approval. No amendment is made to the RFP. | No
271 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Track Superstructure on Bridges, Viaducts and YSS Bridge | ANNEX B1 — Track system on bridges. The sentence in ANNEX B1 has been left without its threshold length value: "Along the Inrail line; on bridges, longer than ballast less infrastructure system will be applied." Kindly advise the threshold length missing from this sentence (i.e. bridges longer than what value are to receive ballastless track), and whether the criterion applies by structure type (viaduct/bridge) or by length. | Please refer to Answer 201 and Addendum No. 2, Amendment No. 15. The Ballasted/Ballastless Track Itinerary added to the RFP shall govern the application of ballasted and ballastless track on bridges/viaducts; the incomplete threshold sentence in Annex B1 shall not be used as a separate basis for pricing. | Yes
272 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification; Annex G6 – Track Technical Specification / Track Superstructure on Structures | ANNEX E4 — Rail stress criteria on bridges; ANNEX G6. ANNEX E4 states: "UIC 60 type rails with a minimum tensile strength of 900 N/mm²", and continues: "Where the above criteria cannot be met, special works must be carried out or additional measures taken."; ANNEX G6, by contrast, defines the main-line rail as "the 60E1/60E2 profile and R260 grade rails" (R260 nominal Rm ≥ 880 MPa). ANNEX E4 provides for special works or additional measures where the stated criteria cannot be met; however, it is not clear whether the minimum rail tensile-strength requirement and additional rail–bridge interaction measures are intended to satisfy the same acceptance criterion. Kindly confirm the rail grade to be used on bridge/viaduct sections and whether the 900 N/mm² requirement may be satisfied using R260 rail together with rail expansion joints, additional analysis or other measures; if not, please state the required rail grade. | Please refer to Annex E4 and Annex G6. The rail grade and mechanical properties stated in the mandatory Technical Specifications shall be satisfied. Any reference to alternative grades or heat treatment shall be applied only in accordance with the criteria expressly stated in the RFP and the approved rail-stress/track-structure interaction design. No amendment is made to the RFP. | No
273 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report; Annex E4 – Railway Bridge Design Technical Specification / Track–Bridge Interaction | ANNEX B1 — List of specifications; ANNEX E4 — rail expansion joint (REJ) provisions. The ANNEX B1 list of specifications refers to the "AYGM Rail Expansion Gasket (REG) Technical Specification", but that document is not included in the tender package. ANNEX E4 contains the threshold "…with an LT expansion length of up to 40 m…" and, for ballastless track, the note "NOTE: For ballastless tracks, these conditions shall be determined by the Authority." Kindly (i) issue the AYGM Rail Expansion Gasket (REG) Technical Specification by addendum; and (ii) advise when and in which document the Authority will determine the REJ requirement conditions for ballastless track sections. | Please refer to Addendum No. 2, Amendment No. 17. The AYGM Rail Expansion Gasket (REG) Technical Specification is added to the RFP Documents. For ballastless-track sections, the applicable rail-expansion-joint requirements shall be established during Detailed Design in accordance with Annex E4 and the added REG Technical Specification and submitted through the applicable Authority/Employer review and approval process. No separate pre-bid determination is issued through this clarification. | Yes
274 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / YSS Bridge Track Superstructure | ANNEX B1 — YSS Bridge; Employer's Requirements KPI R2. ANNEX B1 states: "Only the expansion joints are addressed to be changed to railway expansion joints as stated in YSS Bridge drawings." and "Railway works, slab track, rails connections, rail expansions joints, catenary system, signaling system, will be designed and constructed, in accordance with the existing bridge structural design, reserves and application points left for the railway."; the Employer's Requirements refer to "and KGM interface for the YSS Bridge (Lot 3)". Kindly (i) provide Proposers with the referenced YSS Bridge drawings (existing structural design, reserves and application points, expansion-joint layout); (ii) advise the number of expansion joints to be replaced; (iii) define the working regime on the live bridge (possession windows, lane/traffic restrictions); and (iv) clarify which party bears the ICD approval responsibility and schedule risk at the KGM interface. | Please refer to Answer 96. | No
275 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Structural Drawings / Track Superstructure on Structures | ANNEX A1 — PLP-021; alignment chainage. Drawing PLP-021 carries the label "YAVUZ SULTAN SELİM BRIDGE L=2923.980m"; by contrast, the corridor gap between the end of the Anatolian Section (58+808.876) and the start of European Section-1 (−0+452.560) is 3,009.62 m (Δ 85.64 m). Kindly confirm the basis of measurement for the superstructure works on the YSS Bridge (structural length 2,923.98 m per PLP-021, or corridor length 3,009.62 m between section chainages), and under which item the ~85.6 m approach/transition sections are to be considered. | For the YSS Bridge itself, the structural bridge length shown on drawing PLP-021, L = 2,923.980 m, shall be used as the bridge structural reference. The remaining approach/transition length between the adjacent section chainages is part of the adjoining approach/track/civil works rather than an extension of the YSS Bridge structural length. The Contract remains lump sum and the Contractor shall include all transition/interface works required for a complete railway alignment in the relevant Activities/sub-activities. No amendment is made to the RFP. | No
276 | Section VII – Employer’s Requirements / Clause 5.8.3 – Special Requirements; Annex A1 – Alignment and Structural Drawings / YSS Bridge | ANNEX A1 — ITN-001, INF-003/004; Tunnel-20-D. On the itinerary and information drawings the label for TUNNEL-20-D reads "TYPE-1 TUNNEL-20-D (TBM) L= 825.154m.", whereas the chainage labels on the same drawings (START KM=2+935.019 / END KM=3+639.159) yield 704.140 m; the inconsistency is internal to the drawing itself. The same inconsistency also appears in the Employer's Requirements' own structure list (Section VII, clause 5.8.3, Lot 4): the TUNNEL-20-D row states the chainage 2+935 – 3+639 together with a length of 825 m, whereas the chainage difference is 704 m. In addition, an inconsistency of sign and value is observed between the PLP-022 title chainage "0+453.361" and the start of European Section-1 at −0+452.560. Kindly advise the governing length of Tunnel-20-D (825.154 m or 704.140 m as per the START/END chainages on the same drawings), and the corrected value for the PLP-022 title chainage sign inconsistency; kindly also issue a revised official structure-by-structure axis/portal chainage schedule (with start–end chainages). | Please refer to alignment detailed drawing AYGM-INR-ALG-PLP-034 for Tunnel-20-D. The governing stated tunnel length is L = 825.154 m, representing the average of the right- and left-track tunnel lengths. The European Section starts at chainage -0+452.560. No separate revised structure-by-structure chainage schedule is issued through this clarification; final structure/portal chainages shall be confirmed and coordinated in the Detailed Design on the basis of the governing alignment drawings. No amendment is made to the RFP. | No
277 | Section VII – Employer’s Requirements / Annex G1 – Superstructure Works Construction Specification / Ballasted Tracklaying Method | ANNEX G1 — Laying methods. ANNEX G1 states: "Ballasted track construction is carried out using two different methods. 1- Conventional method (on-site assembly method) 2- Panel laying method (pre-assembled track laying) / Unless specified in the tender documents, the method to be used for laying the track shall be determined by the Employer." No separate provision determining the method could be identified in the tender documents. Kindly confirm whether the ballasted track laying method (on-site assembly or panel laying) is at the Contractor's discretion, or will be determined by the Employer at contract stage; and if the latter, whether the selected method will be communicated before proposal submission. | Please refer to Annex G1. The Contractor may select and develop the ballasted-track construction method permitted by the RFP, subject to its proposed methodology, programme, equipment, quality requirements and the Engineer’s approval. No amendment is made to the RFP. | No
278 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification; Annex G8 – Track Technical Specification / Ballastless Rail Support Spacing | ANNEX G8 — Ballastless track; ANNEX E1 — Fastening spacing. ANNEX G8 states: "Distance between rail supports: ≤ 65 cm / Type of concrete track: Precast Panel"; ANNEX E1, by contrast, states: "Unless otherwise specified in the detailed design, in directly fixed track sections, the spacing of fasteners shall not exceed 0.650 m on curved tracks, 0.750 m on straight tracks, and 1.0 m on workshop tracks." ANNEX G8 sets a limit of ≤0.65 m for ballastless track, whereas ANNEX E1 permits spacing up to 0.750 m on straight track through the detailed design. In view of ER 10.1.10(b), under which the more stringent requirement applies, we understand that the Proposal basis should be a maximum support spacing of 0.65 m unless otherwise instructed in writing by the Employer. If spacing up to 0.750 m on straight ballastless track is intended to be permitted, kindly confirm this by addendum or an express written determination binding on all Proposers | Please refer to the document-precedence and interpretation provisions of the Employer’s Requirements. The Contractor shall comply with the mandatory Technical Specifications and shall not use an inconsistency to adopt a less stringent rail-support spacing. Where the stated limits cannot be reconciled, the matter shall be referred to the Engineer during Detailed Design. No amendment is made to the RFP. | No
279 | Section VII – Employer’s Requirements / Clause 4.5 – Civil Infrastructure and Signaling and Telecommunication Interface; Annex L – Signaling and Telecommunication System Technical Specification | Employer's Requirements — S&T civil provisions. The Employer's Requirements state: "Balise mounting … Construct balise sleeper housings and associated cable draw-pits" and "The civil Contractor shall not wait for the appointment of the Signaling and Telecommunication contractor before developing its civil provisions…". Kindly (i) provide quantities, spacing and locations (or typical arrangement principles) for balise sleeper housings, cable draw-pits/troughing and rail/structure earthing-bonding items; and (ii) noting that under ER 4.5.2 the more detailed/stringent provisions of ANNEX L prevail, advise the layout basis (including the relevant sections of ANNEX L) on which these provisions are to be positioned at Proposal stage, and the procedure to apply should their locations change after appointment of the S&T contractor. | Please refer to Answer 29. | No
280 | Section VII – Employer’s Requirements / Clause 4.5 – Civil Infrastructure and Signaling and Telecommunication Interface; Annex E1 – Design Technical Specification | ANNEX E1 — Movable frog; signalling interface. ANNEX E1 states: "Movable frog (swing nose crossing) technology shall be considered where required…". A movable (swing nose) crossing installation requires an additional drive, locking and detection circuit. Kindly confirm whether the supply and installation of the frog actuation mechanism, locking and detection circuits for swing nose crossings falls within the scope of this Contract (the Contractor) or of the separately procured signalling contractor. | The turnout and track mechanical components within the Package 1 track scope shall be provided by the Package 1 Contractor in accordance with the track Technical Specifications. Signalling actuation, detection, interlocking and control functions allocated to Package 2 shall remain within Package 2, with the civil/mechanical and electrical interfaces coordinated in accordance with Annex L and the Employer’s Requirements. No amendment is made to the RFP. | No
281 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Rail and Turnout Types | ANNEX B1 — Turnout types. The narrative part of ANNEX B1 states: "On the main line, S-type turnouts with a ratio of 1/24,5 and a radius of R = 1500 m, typically used by TCDD for speeds between 120–160 km/h, are used."; the quantity breakdown in the same document, however, states: "In the design, a total of 24 turnouts of 1/24 R = 1500 m, 6 turnouts of 1/18.5 with R = 1200 m, 10 turnouts of 1/12 with R = 500 m, and 1 turnout of 1/9 with R = 300 m have been applied." Kindly confirm whether the main-line turnouts are 1/24 or 1/24.5, and provide the definitive turnout schedule (type, radius, quantity, distribution by Lot) to govern procurement and installation, including the definitive breakdown by type in the same schedule. (Note: the RFP documents show differing counts of R=1500 main-line turnouts between individual documents, which is the reason for our request for a definitive schedule.) | For Proposal purposes, the main-line turnout geometry shall be 1/24.5 with R = 1,500 m. References to 1/24 with R = 1,500 m in the Conceptual Design shall be read as 1/24.5 with R = 1,500 m. The final quantities, locations and distribution by Lot shall be confirmed through the Contractor’s Detailed Design. Please refer to Addendum No. 2, Amendment No. 24. | Yes
282 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Rail and Turnout Types | ANNEX E1 — Rail grade; internal consistency of the line classification. ANNEX E1 states: "the use of heat-treated R350HT grade rail shall be considered as the preferred option not only in curved sections but also in areas subject to high axle loads, steep gradients, or frequent braking, such as station approach zones and depot connections. Contractor shall justify in the design submission any decision to revert to R260 grade in such locations." In the same document, the geometry section gives metro characteristics ("…750 V DC supplied via the third rail, or 750 or 1500 V DC supplied via the pantograph…"), while the turnout section describes the same line as "…S&C … for the High-Speed Railway system…". Kindly (i) define numerically the sections where R350HT is mandatory (curve radius threshold, gradient threshold, definition of station approach zones), or confirm that R260 is acceptable subject to a justified design submission; and (ii) advise which of the metro and High-Speed Railway provisions within ANNEX E1 apply to this project. | Please refer to the applicable rail Technical Specifications. The use and location of R350HT or other specified rail grades shall be determined in accordance with the mandatory criteria and the approved rail-wear/stress/track design. The absence of a tender-stage chainage list does not waive the stated technical criteria. No amendment is made to the RFP. | No
283 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Rail Type Requirements | ANNEX E1 — Movable frog requirement. ANNEX E1 states: "Movable frog (swing nose crossing) technology shall be considered where required to reduce wheel impact loads, vibration and maintenance requirements, particularly for diverging routes with elevated operational speeds." Kindly confirm whether swing nose crossings are mandatory for the R1500-1/24 main-line turnouts, or whether fixed (rigid) crossings are also acceptable subject to a justified design. | Please refer to Annex E1 and Annex G11. A movable frog/swing-nose crossing shall be provided where required by the mandatory technical and operational criteria and the approved turnout design. Where the RFP states that it is to be considered, the Contractor shall justify the selected solution in Detailed Design for approval. No amendment is made to the RFP. | No
284 | Section VII – Employer’s Requirements / Annex G11 – Switch Technical Specification / Turnout Type Requirements | ANNEX G11 — Payment route for intermediate turnout sections. ANNEX G11 states: "Where the distance between switch crossings … is 40 meters or less, continuous switch crossings shall be laid. The cost of laying this intermediate section shall be charged by the ballasted railway construction item." Since intermediate sections between turnouts 40 m or less apart are to be paid under the ballasted track item while built to turnout-grade materials and workmanship, kindly confirm whether Proposers are expected to reflect this difference in the ballasted track unit rate, or whether a separate pay item will be defined for such sections. | Please refer to Answers 55 and 142. The Contract is lump-sum and the price allocation in the Schedule of Priced Activities does not change the technical scope or required track form. The Proposer shall include the cost of the compliant turnout/intermediate track arrangement in the applicable lump-sum Activity/sub-activity. No amendment is made to the RFP. | No
285 | Section VII – Employer’s Requirements / Chapter 8 – Building Information Modelling Requirements; Annex O – BIM Technical Specification; Section IV – Proposal Forms / Lump-Sum Payment Schedules | ANNEX O — BIM Requirements. ANNEX O states: "Tunnel excavation shall be modelled. Quantity take-offs for excavation, concrete and support elements shall be obtainable parametrically according to tunnel type and support system."; it further requires that every modelled element be linked to a unit price item ("…each modelled element belongs to a unit price item and that no element without a parameter related to a unit price item is included in the model") and that the quantity tables serve as the basis for payment ("…shall serve as the basis for interim payment/progress payment applications"). ANNEX O requires every modelled element to be linked to a unit price item and the model take-off schedules to serve as the basis for interim payment. The Activity items, however, are lump sum, and payment under a lump sum is tied to progress percentage rather than measured quantity. Kindly clarify (i) how BIM take-off schedules are to form the basis of payment for lump-sum activities — as a progress measurement tool, or as the measurement determining the payment amount; and (ii) whether the mapping table between the model element breakdown and the lump-sum activity breakdown will be issued by the Employer or proposed by the Contractor in its BIM Execution Plan. | Please refer to Addendum No. 2, Amendment No. 12. | Yes
286 | Section VII – Employer’s Requirements / Section-Based Commencement Conditions, Resettlement Plan Hold Points and S&T Close-Out Requirements / Programme Hold Points | Employer's Requirements — Section-based commencement conditions (RP hold point, S&T close-out, C-ESMP). The Employer's Requirements state: "commencement of construction works within that Section shall be permitted once the Detailed Design has been approved by the Engineer and the PIOC has verified that the applicable Resettlement Plan (RP) has been implemented for that Section." In addition, "track formation" is listed among the items covered by the S&T close-out approval. Kindly advise whether a section/work-front release schedule will be provided showing the anticipated dates of RP verification, C-ESMP/spoil-area pre-approvals and related close-out approvals for each section of the route; and if not, on what assumed section release dates Proposers are expected to build their programmes. | Please refer to Answer 75. | No
287 | Section VII – Employer’s Requirements / Clause 7.6 – Third-Party Approval Obligations; Section IX – Particular Conditions / Part B / Sub-Clause 14.6.3 – Critical KPI Grace Period | Employer's Requirements 7.6 (Third-Party Approval Obligations); PCC Part B 14.6.3. ER 7.6 states: "The Contractor is fully responsible for identifying, pursuing, and obtaining all approvals… Design Freeze for any element subject to a mandatory third-party approval shall not be achieved until that approval has been formally received in writing."; PCC Part B states: "For Critical KPIs, the grace period in Sub-Clause 14.6.3 shall not apply". In respect of third-party authority approvals (e.g. KGM, defence authorities, municipalities), kindly (i) advise the standard review durations envisaged for each authority and any existing protocols/framework agreements between the Employer and those authorities; (ii) share, for programming purposes, the schedule assumptions the Employer has adopted for these approval processes; and (iii) explain how the Critical KPI target dates have been related to these third-party approval timelines. | Please refer to Section VII, Employer’s Requirements, Clause 7.6. The Contractor shall identify, plan for and obtain the required third-party approvals and shall include realistic authority review periods in its programme. The RFP does not prescribe standard approval durations for each authority. No amendment is made to the RFP. | No
288 | Section VIII – General Conditions / Sub-Clause 14.5 – Plant and Materials Intended for the Works; Section IX – Particular Conditions / Part A – Contract Data | Kindly advise whether a Contract Data entry for GC 14.5 (with the list of Plant and Materials and the applicable percentage) will be added by addendum; and if not, advise accordingly. | No Contract Data entry is added for GC 14.5 through this clarification. Accordingly, the mechanism under GC 14.5 for payment for Plant and Materials intended for the Works applies only to the extent expressly activated by the Contract Data; no separate list of Plant/Materials or percentage is prescribed for this Contract. No amendment is made to the RFP. | No
289 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification; Annex G5 – Sleeper Technical Specification; Annex G – Track Works (Superstructure) Technical Specifications / Track Gauge, Sleepers and Fastenings | Kindly confirm (i) whether the nominal gauge governing sleeper manufacture is 1435 mm or 1436 mm, and whether the 1437 mm in ANNEX G5 is the corresponding mould dimension; and (ii) which sleeper–fastening pair applies on the ballasted main line — B07 with W21, or B70 with W14. These value differences between ANNEX E1 and the ANNEX G series are referred for your interpretation pursuant to ER 1.2 as discrepancies between documents of equal rank; as sleeper production is tooled to a single mould geometry and the nominal gauge cannot be altered once manufacture of the order of two hundred thousand units has commenced, your early clarification is of particular importance. | The nominal track gauge governing the Works is 1,435 mm. The 1,437 mm dimension stated in Annex G5 is the applicable sleeper/mould manufacturing dimension and does not change the nominal track gauge. For the ballasted main line, the B07 sleeper with W21 fastening system shall apply. Please refer to Addendum No. 2, Amendment No. 25. | Yes
290 | Section VII – Employer’s Requirements / Annex G6 – Rail Technical Specification; Annex G15 – Welding Specification; Annex G16 – Track / Rail Stress Adjustment Specification / Rail Delivery Length and Welding | ANNEX G6 — Rail lengths; ANNEX G15; ANNEX G16. ANNEX G6 states: "The standard rail length shall be at least 36 m. Rails shall be supplied without holes." The words "at least" set a lower bound; they do not establish the delivery length on which the Proposal is to be based. The delivery length does not determine the total number of welds but determines whether welding is carried out ON SITE or IN THE PLANT: since the rolled rail length is fixed, longer delivery lengths are produced by plant welding. For the rail quantity of this Project, the difference between a 36 m and a 108 m delivery length means that welds of the order of nine thousand are made in the plant rather than on site; this directly changes the distribution of site welding, ultrasonic inspection and fine grinding labour, and therefore the site team structure and the construction programme Kindly advise (i) the standard rail delivery length to be adopted for Proposal purposes (36 m, 72 m, 108 m or 120 m); and (ii) whether the Contractor is free to select a longer delivery length, and if so whether welding is to be priced on the selected length or on the 36 m minimum. We note that the delivery length governs the site-versus-factory distribution of welds rather than the total number of welds. | Please refer to Annex G6, Annex G15 and Annex G16. Rails shall be procured and delivered in lengths complying with the minimum/standard requirements stated in the Technical Specifications, and the Contractor shall develop the welding plan so as to minimize joints and satisfy the complete welding and CWR requirements. No additional project-specific delivery length is prescribed by this clarification. No amendment is made to the RFP. | No
291 | Section VII – Employer’s Requirements / Annex G16 – Track / Rail Stress Adjustment Specification / Stress-Free (Neutral) Temperature | ANNEX G16 — Stress adjustment. ANNEX G16 defines the neutral temperature as "The rail temperature at which the rail is the same length as when it is in a stress-free state. It is calculated as T(average) + 5 °C." and makes the whole stress-adjustment operation dependent on it. The specification refers to a table of province and district values, and provides that for places not listed in the table, data will be obtained from the General Directorate of Meteorology. The table referred to is not included in the package, and "Istanbul" appears nowhere in ANNEX G16. The neutral temperature governs the rail heating, tensioning and clip-tightening working window over the entire CWR line, and therefore the works programme Kindly (i) provide the stress-free temperature table referred to in ANNEX G16; and (ii) if the provinces traversed by the route do not appear in that table, state the numerical stress-free temperature values or mandatory design assumption to be adopted for Proposal purposes in each section of the route, so that all Proposals are prepared on a common and comparable basis. | The relevant table is available in Annex G16 and İstanbul is included. No amendment is made to the RFP. | No
292 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 1.1.27 and Sub-Clause 19.2.3; Section VII – Employer’s Requirements / Annex D – General Technical Specification / Warranty, Maintenance and Repair; Clause 10.6.4 – Defects Liability Period | Particular Conditions Part A — Contract Data 1.1.27; ANNEX D — Warranty, maintenance and repair. The Contract Data gives the Defects Notification Period as 730 days, and the Employer's Requirements support this with the words "DNP … twenty-four (24) months from Taking-Over". ANNEX D, however, states "Warranty Period shall be 60 (sixty) months starting from the date of Final Acceptance.", requires at least one fully authorised member of staff to be maintained at the operating site throughout that period, and expressly lists the track among the covered installations. The difference between the two periods exceeds three years. Furthermore, the term used in the "Period of insurance required for liability for breach of professional duty" row of the Contract Data (Sub-Clause 19.2.3) — "Until end of Defects Liability Period" — is not among the Contract Data definitions. ER 10.6.4 defines the DLP as "The Defects Liability Period (DLP) shall commence upon issuance of the Taking-Over Certificate and shall continue for the period defined in the Contract.", yet the Contract contains no defined duration for the DLP; meanwhile both the end of the professional-indemnity insurance (Contract Data 19.2.3) and Final Acceptance (ER 10.10.10: "Completion of the Defects Liability Period") are tied to this undefined period — and the start of the 60-month period under ANNEX D, being the date of Final Acceptance, is thereby chained to the same uncertainty. Without prejudice to our understanding that the 730-day period in the Contract Data governs the Defects Notification Period by virtue of the ER 1.2 order of precedence, kindly advise (i) whether the 60-month "Warranty Period" in ANNEX D is intended as a separate and additional obligation beyond the Defects Notification Period; (ii) if so, under which item of the Schedule of Prices this obligation (including the fully authorised personnel to be maintained on site) is to be priced; and (iii) whether the term "Defects Liability Period" used in the insurance requirements (Contract Data, row 19.2.3) refers to the DLP defined in Employer's Requirements 10.6.4 or to the 730-day Defects Notification Period under Contract Data 1.1.27; and (iv) given that no duration is defined in the Contract for the "Defects Liability Period", the period by reference to which the professional-indemnity insurance end date under Contract Data 19.2.3 and the Final Acceptance precondition under ER 10.10.10 ("Completion of the Defects Liability Period") are to be operated. | Please refer to Addendum No. 2, Amendment No. 21. | Yes
293 | Section VII – Employer’s Requirements / Annex A1 – Tunnel Typical Cross Sections / Drawings AYGM-INR-STR-TCS-001…021 / Ballastless Track Plinths and Support Blocks | Typical cross-section drawings AYGM-INR-STR-TCS-001…021. The typical cross-sections state the concrete class for all tunnel elements (precast segment C45, shotcrete C25, final lining C30, invert beam C30, invert C30, levelling C25, and fill and slab concrete C20). By contrast, no class is given for the plinths and support blocks of the ballastless track. We have not assumed a class for these elements. Kindly advise the design concrete class for the plinths and support blocks of the ballastless track. | The concrete class for ballastless-track plinths/support blocks shall be established by the Contractor’s Detailed Design to satisfy the structural, fatigue, durability, fire, environmental and track-system requirements of Annex G10 and the applicable structural Technical Specifications. The class shall be submitted for approval with the relevant design calculations. No amendment is made to the RFP. | No
294 | Section VII – Employer’s Requirements / Employer’s Requirements and Annexes A, B, E, F and G; Section IV – Proposal Forms / Price Schedules / Project Information Affecting Quantities | The following information directly determines quantities. The Employer's Requirements, the ANNEX A drawing and inventory files, ANNEX B, E, F and G and the Price Schedules have been reviewed; this information could not be derived from them. Assignment of structures to chainage sections. The Project comprises several independent chainage sections, some of which start from their own 0+000. The lot structure lists at Section VII, clauses 5.5.3–5.8.3 of the Employer's Requirements bind each structure to its Lot and to a start–end chainage, but the location column records only "Asian Side" or "European Side"; two different chainage frames may sit side by side within the same list — in the Lot 4 list, Tunnel-19 begins at 26+330 as "European Side" and Tunnel-20-A likewise begins at 0+631 as "European Side". The 01_List_of_Structures file does not carry that distinction either, recording only "Anadolu / Anatolia" or "Avrupa / Europe"; a structure therefore cannot be placed unambiguously along the route. By way of example: Tunnel-19-C ends at 31+551.770 (the end of European Section-1) and Tunnel-20-A begins immediately thereafter at 0+630.852 (European Section-2) — both are recorded under a single "Europe" label. We note that the 04_Turnout_Information file carries the section for each turnout, so that the information does exist in the Employer's records. Kindly provide the section attribution for each structure, or a structure-to-section mapping list | The structure chainages and section assignments shown in the Reference/Conceptual Design shall be verified and coordinated by the Contractor during Detailed Design. The Contractor shall use the Lot limits, alignment data and structure inventories collectively and shall resolve chainage-frame transitions in the approved design model. No separate structure-to-section mapping list is issued by this clarification. No amendment is made to the RFP. | No
295 | Section VII – Employer’s Requirements / Annex G1 – Superstructure Works Construction Specification / Clause 8.1; Annex G10 – Ballastless Railway Line Construction Specification; Annex G20 – Track Technical Specification / Ballastless Sections | Chainage list of the ballastless sections. ANNEX G1 clause 8.1 treats tunnels, viaducts and station tracks designated by the Employer as ballastless; ANNEX G10 makes the precast system on viaducts and bridges subject to structural design approval; while ANNEX G20 describes the under-ballast mat for ballasted cross-sections and thereby assumes ballasted viaducts and tunnels. Kindly provide a Lot-by-Lot chainage list of the sections to be built as ballastless track, and confirm the regime applicable to bridges, which are not enumerated in ANNEX G1 clause 8.1, and to cut-and-cover structures, for which no provision has been found | Please refer to Answer 201 and Addendum No. 2, Amendment No. 15. The Ballasted/Ballastless Track Itinerary added to the RFP provides the tender-stage basis for the sections to be constructed as ballastless/ballasted track. Final detailed limits and transitions shall be coordinated in the Contractor’s Detailed Design. | Yes
296 | Section VII – Employer’s Requirements / Annex G1 – Superstructure Works Construction Specification / Asphaltic Concrete Binder in Station Areas | Asphaltic concrete binder in station areas. ANNEX G1 requires the asphaltic concrete binder layer to be applied over the whole of the station area at all stations. We understand that the Project contains two passenger stations, both of which are underground. Kindly advise the area to which the binder course and its sub-base are to be applied at each station, or confirm that this requirement does not apply within underground station boxes. | The asphaltic concrete binder/sub-base requirement in Annex G1 shall be applied to the areas for which it is technically required by the approved station/track design. The final limits within underground station boxes shall be developed in Detailed Design; the requirement is not deemed inapplicable solely because a station is underground. No amendment is made to the RFP. | No
297 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities / Rail Expansion Joints; Section VII – Employer’s Requirements / Annex G17 – Track Technical Specification / Insulated and Rail Expansion Joints | Insulated joints and rail expansion joints. Item 9.5 of the Price Schedule (8.5 in Lots 2 and 3) provides for rail expansion joints "at all locations" on a lump-sum basis; however, no technical specification for these devices could be found in the package, and neither quantities nor locations are given for them or for the insulated joints specified in ANNEX G17. Kindly advise the technical specification, quantity and location of both | Please refer to Answer 273 and Addendum No. 2, Amendment No. 17. The AYGM Rail Expansion Gasket (REG) Technical Specification is added to the RFP Documents. The final quantity and location of rail expansion joints and insulated joints shall be determined by the Contractor during Detailed Design in accordance with the added REG specification, Annex G17, the track-structure interaction requirements and the approved signalling/track interfaces. | Yes
298 | Section VII – Employer’s Requirements / Annex J – Power Supply and Traction Power System Technical Specification / Track–Catenary–Earthing Interface | ANNEX J (Power Supply and Traction Power System Technical Specification) — interface touching the superstructure. The Employer's Requirements refer to this annex in three separate places (in the interface-management, catenary and earthing/bonding contexts), but the annex is not present in the package. So far as the superstructure works are concerned, the matters governed by this annex are the positioning of catenary (OLE) mast foundations relative to the track axis and their effect on the laying fronts, cable-duct crossings, and the rail/structure earthing–equipotential bonding interface. Kindly provide the documents, or advise the interface requirements of the traction power and catenary systems as they affect the trackworks. | Please refer to Annex E and Section VII, Employer’s Requirements. The mandatory design criteria and performance requirements of the RFP shall govern. The Contractor is responsible for the final catenary/traction-power interface design, including coordination of catenary foundations, mast positions, cable crossings, earthing/equipotential bonding and the railway infrastructure interfaces within its scope. No amendment is made to the RFP. | No
299 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities / Activity 2 – Relocation of Existing Infrastructure | SECTION IV Proposal Forms - ACTIVITY 2 - RELOCATION OF EXISTING INFRASTRUCTURE Since it is a Lump Sum item, please kindly provide the type, locations and preliminary design information for the Relocation of Infrastructures | Please refer to Answer 68. | No
300 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 19.2.3(a) – Professional Indemnity Insurance Cover Amount and Period | Section IX Part A — Contract Data: the row "amount of insurance required for liability for breach of professional duty" (Sub-Clause 19.2.3(a)) and the row "Period of insurance required for liability for breach of professional duty" (Sub-Clause 19.2.3). The Contract Data provides for the professional indemnity insurance cover as "Not less than 20% of the Accepted Contract Amount" and, in a separate row, for its period as "Until end of Defects Liability Period". Kindly advise (i) noting that the "Permitted deductible limits" row of the Contract Data (Sub-Clause 19.1), at sub-paragraph (c), sets the professional indemnity deductible on a "per claim" basis, whether the cover amount is likewise required per claim or in the aggregate for the policy period; and (ii) whether, should cover at this level prove unobtainable on reasonable terms in the international insurance market, the Employer will accept the maximum cover reasonably obtainable on market terms and, if so, whether that modification will be issued by addendum for equal application to all Proposers. | Please refer to Contract Data Sub-Clause 19.2.3. The Contractor shall maintain professional indemnity insurance with the minimum cover stated in the Contract Data and subject to the deductible requirements stated in the Contract. The request to reduce the required cover by reference to market availability is not accepted. The Contractor shall obtain compliant insurance and include the cost in its Proposal. No amendment is made to the RFP. | No
301 | Section VII – Employer’s Requirements / Annex C1 – Geological Data Report (GDR) / Table 12 – Excavation Waste Storage Areas | ANNEX C1 Geological Data Report.docx, Table 12- Excavation Waste Storage Areas Kindly advise coordinates of the locations given in Table 12 - Excavation Waste Storage Areas | Please refer to Annex C1 and the Employer’s Requirements concerning disposal and waste management. The locations listed in the tender-stage information are indicative. The Contractor shall identify, verify, obtain approval for and use lawful disposal/storage areas in accordance with the approved C-ESMP, permits and applicable legislation. No separate coordinates are issued by this clarification. No amendment is made to the RFP. | No
302 | Section VII – Employer’s Requirements / Clause 4.8.2 – Interface with Airport Operators (Lot 4); Annex A1 – Alignment and Tunnel Drawings / Lot 4 Tunnel 19 Start and Airport Runway Interface | Lot 4, European section 1, 26+330 TYPE-1 TUNNEL-19 START，the The tunnel entrance is on the extension cord of the new cargo runway. During the TBM launching or reception, large cranes will be used. Will the crane affect the normal operation of the runway? Please provide the runway end elevation for assessment. | Please refer to Section VII, Employer’s Requirements, Clauses 4.8.2 and 7.6. Any crane operation or temporary works within the airport obstacle-limitation/airspace influence zone shall be coordinated with İGA and DHMİ and shall not proceed without the required approvals. The Contractor shall obtain/verify the airport operational and elevation data required for its construction methodology through that interface process. No separate runway-end elevation is issued by this clarification. No amendment is made to the RFP. | No
303 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / Lot 4 Tunnel 19-A / TBM Launch and Reception Shaft | Lot 4, European section 1, 29+718.529-30+090.995- TYPE-2A TUNNEL -19-A (NATM)，the section shall be allowed for TBM launch shaft and receiving shaft for material entry into tunnel？ | The use of the referenced NATM section as a TBM launch/receiving or material-access location is a matter for the Contractor’s construction methodology and Detailed Design, subject to compliance with the permanent Works requirements, geotechnical/structural design, airport restrictions, land access and all required approvals. The RFP does not prescribe that this section shall be used for that purpose. No amendment is made to the RFP. | No
304 | Section VII – Employer’s Requirements / Clause 4.8.2 – Interface with Airport Operators (Lot 4); Annex A1 – Alignment and Tunnel Drawings / Airport Apron Construction Area | Lot 4 European section 1, This section is located within the airport apron, as shown in the figure below. The TBM shall be received here, and the NATM tunnel, the material entry and exit the tunnel, also needs to be set up losed area. Will the airport authority shall allow the contractor to set up a closed area for construction? | Please refer to Answer 129. | No
305 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / Lot 4 Tunnel 19-C / Existing Bridge Pile Foundations | Lot 4 European section 1, 31+299.587-31+551.770 TYPE-5 TUNNEL -19-C The tunnel passes through the bridge pile foundation. Please provide the technical parameters of the bridge piles here, especially the depth of the piles. See the figure below： | The Contractor shall verify all existing structures and foundations that may affect its Detailed Design and construction methodology and shall coordinate with the relevant owner/operator and authorities. The tender-stage information made available by the Employer is the basis for the Proposal. No additional bridge-pile parameters are issued by this clarification. No amendment is made to the RFP. | No
306 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / Lot 4 Tunnel 19-C / Existing Bridge Pile Foundations | 6、Lot 4 European section 2，0+600-0+640 TYPE-5 TUNNEL -19-C (NATM)，The tunnel passes through the bridge pile foundation. Please provide the technical parameters of the bridge piles here, especially the depth of the piles. See the figure below： | Please refer to Answer 305. | No
307 | Section VII – Employer’s Requirements / Clause 4.8.2 – Interface with Airport Operators (Lot 4); Annex A1 – Alignment and Tunnel Drawings / Tunnel 20-A and Airport Apron Construction Area | 7、Lot 4 European section 2, 0+630.852-0+803.549 TYPE-5 TUNNEL -20-A (NATM)，This section is located within the airport apron, as shown in the figure below. The TBM shall be received here, and the NATM tunnel, the material entry and exit the tunnel, also needs to be set up losed area. Will the airport authority shall allow the contractor to set up a closed area for construction ? | Please refer to Answer 304. | No
308 | Section VII – Employer’s Requirements / Clause 5.8.2 – Istanbul Airport Station; Annex H – Architectural and Finishing Works Technical Specification / Existing Metro Station Retaining Walls | Lot 4 European section 2, ISTANBUL AIRPORT STATION，As shown in the picture, part sections of the ground retaining walls of hign speed train are proposed using the subway station's retaining walls, please provide the drawings of the subway station's retaining walls， | The Contractor shall verify all existing structures, retaining walls and foundations that may affect its Detailed Design and construction methodology and shall coordinate with the relevant owner/operator and authorities. The tender-stage information made available by the Employer is the basis for the Proposal. No additional drawings or design information for the existing metro station retaining walls are issued by this clarification. No amendment is made to the RFP. | No
309 | Section VII – Employer’s Requirements / Clause 5.8 – Lot 4 Scope; Annex B1 – Conceptual Design Report / Cargo Terminal Tail Tracks | Lot 4, In Design Report, page 35, In designing the alignment, tail tracks for the cargo terminal have also been planned. Please confirm the tail tracks and the cargo terminal are not not included in scope of tender. | The contractual scope is defined by Section VII, Employer’s Requirements and the applicable Lot description, not by an isolated statement in the Reference/Conceptual Design Report. Tail tracks and cargo-terminal-related works shall be included only to the extent they form part of the Works expressly required for Lot 4 and the approved Detailed Design/interfaces. Reference-design concepts do not independently expand or reduce the contractual scope. No amendment is made to the RFP. | No
310 | Section VII – Employer’s Requirements / Clause 4.8.1 – Interface with KGM and the YSS Bridge Corridor (Lot 3); Annex B1 – Conceptual Design Report / Existing Cut-and-Cover Sections | Lot 3, In Design Report, page 33&34, the report mentioned that at the entrance and end of the Yavuz Sultan Selim Bridge, cut-and-cover structure had been completed. Please confirm the sections of cut-and-cover structure sections with 58+542.5-58+808.876 in part of Asia side and -0+452.56-0+000, had been completed and not included in scope of tender. | Please refer to Section VII, Employer’s Requirements, Clause 4.8.1 and the Lot 3 scope. Existing completed structures within the YSS corridor are not to be reconstructed unless the RFP expressly includes completion, modification, interface or railway works on those structures. The Contractor shall verify the existing condition and provide all works required by the Employer’s Requirements and approved Detailed Design. No amendment is made to the RFP. | No
311 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / Lot 1 Shaft Design | Lot 1, 4 shafts had been designed with long distance of TBM section, please comfirm that 4 shafts are sufficient for the TBM section. | Please refer to Answer 147. | No
312 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / Lot 2 Tunnel 1B-3 and Existing Airport Bridge Pile Foundations | Lot 2, Sabiha Gökcen Station, TYPE-4 TUNNEL-1B-3, NATM, 14+339.607-M=14+451.150, across the bridge which connect parking area and terminal of the airport. Please provide the pile foundation details for the bridge, especially for the depth of the piles. | Please refer to Answer 305. | No
313 | Section VII – Employer’s Requirements / Sabiha Gökçen Airport Station; Clause 4.8.2 – Interface with Airport Operators (Lot 1); Annex A3 – Architectural Drawings; Annex H – Architectural and Finishing Works Technical Specification | The station has only completed the conceptual design phase, and the contractor must complete the detailed design of all buildings, structures, mechanical and electrical systems. Is the preliminary design information provided by the owner (geological, structural, mechanical and electrical) complete? Are there any undisclosed constraints? Has the layout of 4 lines (2 passenger lines passing through platforms and 2 freight lines passing through independent TBM tunnels) below the station been agreed upon with TAV Airports? If there is a conflict between the freight line tunnel and the station structure, will the responsibility be changed? The upper level (B2 level) of the station will serve both INRAIL and the Super High Speed Railway Line - who is responsible for the design interface of this super high speed railway line? | Please refer to Answers 32 and 48. The Sabiha Gökçen Airport Station Reference/Conceptual Design is tender-stage information. The Contractor is responsible for completing the Detailed Design and for managing the interfaces with TAV, DHMİ, the Super High Speed Railway Line and other relevant parties in accordance with the Employer’s Requirements. Any design conflict shall be resolved through the prescribed interface and design-review process; the Contractor’s Design-Build responsibility is not transferred by this clarification. No amendment is made to the RFP. | No
314 | Section VII – Employer’s Requirements / Clause 4.8.2 – Interface with Airport Operators (Lot 1); Clause 7.6 – Third-Party Approval Obligations / TAV and DHMİ Approvals and Construction Restrictions | Lot 1 must establish an interface protocol with TAV Airports, and the station fire protection design must be confirmed in writing by TAV. Has the approval process and timeline for TAV Airports been clearly defined? If the approval delay of TAV leads to the obstruction of detailed design, can we claim the construction period? Specific restrictions on construction sites, lifting equipment, and material stacking in airport safety zones (such as height limits, no fly zones, and noise periods) - the owner must provide a written list of restrictions confirmed by TAV During the construction period of the station, the airport operation will not be interrupted. What are the specific construction windows and access channel conditions? | Please refer to Answer 129. | No
315 | Section VII – Employer’s Requirements / Clause 5.2 – Geotechnical Risk Allocation Statement; Annex C1 – Geological Data Report (GDR); Annex A1 – Alignment Drawings / Lot 1 TBM Geology and Ömerli Reservoir Interface | The total length of the tunnel is approximately 26.042 km (double tunnel), of which the TBM section is about 24.3 km and the NATM section is about 1.7 km. Are there any adverse geological conditions such as karst, cavities, and fault zones along the route? The bidding documents only explicitly mention Karstification and Void Risk for Lot 2, but is there a similar risk for Lot 1 tunnel crossing through geological layers? Does the Ö merli Reservoir Protection Area have an impact on Lot 1? Is the construction drainage, settlement control, and material stacking of Lot 1 adjacent to the reservoir area in the conceptual design drawing restricted by reservoir protection? Do the settlement control standards and existing structural protection schemes need to be clearly defined by the owner when TBM crosses the D-100 and North Marmara highways? | The geotechnical baseline for Proposal purposes is the information included in the GDR, the Employer’s Requirements and the tender-stage geological/reference information. No additional Lot 1 karst/cavity/fault-zone baseline is issued through this clarification beyond that information. The Contractor shall investigate and design for the actual ground conditions in accordance with the geotechnical-risk allocation of the Contract. Works affecting or located near the Ömerli Reservoir protection area shall comply with the applicable environmental, water-protection and authority requirements, including restrictions on drainage, discharge, storage and construction activities. For TBM crossings beneath/adjacent to the D-100 and Northern Marmara highways, the Contractor shall establish the settlement-control, monitoring and structural-protection measures in the Detailed Design and obtain the required third-party approvals. No amendment is made to the RFP. | No
316 | Section VII – Employer’s Requirements / Clause 5.2 – Geotechnical Risk Allocation Statement; Annex C1 – Geological Data Report (GDR); Annex F – Civil Works (Infrastructure) Technical Specification / TBM Selection and Launch-Reception Strategy | Require at least 2 TBMs with EPB mode capability The bidding documents require that TBM can be converted to EPB mode, but does the geological condition of the entire line need to operate in a mixed mode (such as alternating hard rock and soft soil)? Can the owner provide a more detailed geological profile map? Do TBMs need to be disassembled and transferred multiple times between 5 sections of TBM tunnels (1A-1 → 12km, 1A-3 → 919m, 1B-2 → 617m, 1C-2 → 2.7km, 1D-2 → 8km)? Can it still be excavated continuously from the first section to the endpoint? The minimum plane spacing requirement for tunnels is 60 meters (when double tunnels are excavated simultaneously). Does the minimum spacing for the parallel section of 4 lines near Sabiha G ö k ç en station meet the requirement? | Please refer to the applicable tunnel Technical Specifications and the Employer’s Requirements. The Contractor shall select and operate TBMs meeting the specified performance and mode requirements and shall develop the launch/reception, transfer and excavation sequence on the basis of its Detailed Design, verified geology and approved construction methodology. Reference-design sectioning does not prescribe a mandatory repeated disassembly sequence where a compliant continuous construction solution is feasible. All minimum tunnel-spacing and safety requirements of the RFP shall be satisfied. No amendment is made to the RFP. | No
317 | Section VII – Employer’s Requirements / Annex A1 – Alignment and Tunnel Drawings; Annex F – Civil Works (Infrastructure) Technical Specification / Lot 1 TBM–NATM Transition Sections | Lot 1 includes 11 sections of NATM transition sections (with a total length of 1.7 km), as well as NATM switch tunnels and platform tunnels in the Sabiha G ö k ç en station area Construction plan for interface/transition section between TBM and NATM tunnel - does TBM need to receive/depart at NATM section? Has the owner considered the corresponding construction period if multiple launches and receptions are required? | The TBM/NATM transition, launch and reception strategy is part of the Contractor’s Detailed Design and construction methodology. The Contractor shall allow for all interfaces, temporary works, launch/reception operations and associated durations necessary to complete the Works within the contractual Time for Completion. No separate Employer allowance is introduced by this clarification. No amendment is made to the RFP. | No
318 | Section VII – Employer’s Requirements / Clause 4.5 – Civil Infrastructure and Signaling and Telecommunication Interface; Annex L – Signaling and Telecommunication System Technical Specification / TCDD Maltepe CTC and Package 2 Interface | Lot 1 contractor is responsible for connecting the INRAIL data transmission system to the TCDD Maltepe CTC center and utilizing TCDD's existing fiber optic infrastructure Is it necessary to build or lease the available bandwidth, physical status, and ownership of TCDD's existing fiber optic cables from Ç ay ı rova to Maltepe? How to divide the interface with Package 2 (signal communication independent contract)? To what extent is Lot 1 responsible, and to what extent is Pkg2 responsible? If the integration of CTC system requires the renovation of existing facilities of TCDD, has the approval and work window of TCDD been clearly defined? | Please refer to Answers 29 and 133. | No
319 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J – Power Supply and Traction Power System Technical Specification / System-Wide Power Supply Simulation | Lot 1 contractor undertakes the obligation of system wide power supply simulation Does the simulation scope of the entire system cover all four sections? If the design changes of Lot 2/3/4 affect the simulation results, how should the responsibilities be divided? Does the owner provide basic data on TCDD's existing power grid (short-circuit capacity, harmonics, power supply reliability, etc.)? | Please refer to Answer No.118. | No
320 | Section VII – Employer’s Requirements / Clause 4.5 – Civil Infrastructure and Signaling and Telecommunication Interface; Annex L – Signaling and Telecommunication System Technical Specification / Reserved Civil Interfaces | The signal and communication are the responsibility of an independent Package 2 contractor, and the civil engineering contractor must reserve interfaces The reserved holes/brackets/space standards for signal equipment, communication cables, and GSM-R antennas in the tunnel - Package 2 has not yet been tendered, how does the civil design of Lot 1 match it? Does the owner have clear reserved size requirements for the installation space of ERTMS/ETCS Level 1/2 trackside equipment required by the signal system? | Please refer to Answer 29. | No
321 | Section VII – Employer’s Requirements / Clause 5.1.1 – Design and Build Disclaimer; Clause 5.2 – Geotechnical Risk Allocation Statement; Section IV – Proposal Forms / Lump-Sum Schedule of Priced Activities and Sub-activities | All quantities, dimensions, and parameters are indicative, and the owner does not guarantee their constructability, completeness, or accuracy If it is found after detailed design that the actual engineering quantity deviates from the conceptual design by more than ± X% (such as changes in tunnel length or geological conditions), will it trigger price adjustment or project extension? | Please refer to Answer 55. | No
322 | Section VII – Employer’s Requirements / Clause 4.8 – Third-Party Interface Obligations / Airport and Highway Construction Windows and Restrictions | Has the construction time window (night/day?) for the airport area been determined? Is it allowed to interrupt traffic construction or must non excavation methods be used when crossing the highway section? | Please refer to Answer 129. | No
323 | Section VII – Employer’s Requirements / Annex A1 – Tunnel Typical Cross Sections and Drawings; Annex E1 – Design Technical Specification / TBM Tunnel Diameter and Segment Requirements | The diameter size of the TBM tunnel in the drawings provided for bidding is inconsistent with the content in ANNEX E1. Please clarify tunnel size and update the characteristic requirements of the segment of Structure. | Please refer to Addendum No. 2, Amendments Nos. 14 and 31, and the revised Annex E1 – Design Technical Specification, which replaces the original Annex E1. The TBM tunnel inner ring diameter is 8.60 m, consistent with the applicable tender drawings. | Yes
324 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Particular Conditions / Sub-Clause 14.4 – Status of Bidder-Added Sub-Activities | Please confirm whether the sub-activities added by the Proposer under the Schedule of Priced Activities and Sub-activities will automatically constitute Milestones for payment purposes, or whether they will constitute lump-sum payment components against which the Engineer may assess the percentage of completed and accepted work for interim payment purposes. | No. Proposer-added sub-activities, within the maximum permitted by the RFP, do not automatically become contractual Milestones. They are separately priced deliverables/sub-activities in the Schedule of Priced Activities and Sub-activities and are payable at their quoted lump-sum prices upon completion and acceptance. An incomplete added sub-activity is not payable proportionally merely because a portion is measurable or physically complete. Please refer to Addendum No. 2, Amendment No. 12. | Yes
325 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Particular Conditions / Sub-Clause 14.4 – Eligibility for Partial / Interim Payment | Please confirm that, where a bidder-added sub-activity is only partially completed, but the completed portion is measurable, independently identifiable, inspected and accepted by the Engineer, such completed portion will be eligible for inclusion in the Contractor's Interim Payment Application, notwithstanding that the relevant sub-activity as a whole has not yet been fully completed. | Please refer to Answer No.324. | No
326 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Particular Conditions / Sub-Clause 14.4 – Tunnel Example / Interim Payment | For example, for a 3,610 m long tunnel, if 200 m of excavation, rock bolting and primary support have been fully completed, inspected and accepted, while waterproofing and secondary lining have not yet commenced: may the Contractor claim interim payment for the completed and accepted 200 m of excavation and primary support; and may such payment be made notwithstanding that the complete Excavation and Primary Support sub-activity for the 3,610 m tunnel has not yet been completed? | For the 3,610 m tunnel example, completion and acceptance of 200 m does not entitle the Contractor to a separate payment calculated as 200 m divided by the total tunnel length if the priced sub-activity covers the entire 3,610 m. Payment is due when the relevant priced deliverable/sub-activity is completed and accepted. A 200 m portion may be paid separately only if it was separately identified and priced as a distinct deliverable/sub-activity in the Schedule and is itself complete and accepted. Please refer to Addendum No. 2, Amendment No. 12, and Clause 14. | Yes
327 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Particular Conditions / Sub-Clause 14.4 – Valuation of Partial Completion | If the Employer confirms that partial/interim payment is permissible, please clarify whether the value of the completed portion will be determined: based on the proportion of physical quantities completed and accepted; based on the Engineer-assessed percentage of completion of the relevant lump-sum sub-activity; or according to another valuation/payment mechanism specified by the Employer. | Please refer to Answer No.324. | No
328 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Particular Conditions / Sub-Clause 14.4 – Payment Mechanism | For the avoidance of doubt, we kindly request the Employer to expressly confirm that, except where a particular Activity or sub-activity is expressly designated as a payment Milestone, partial/interim payment is permissible for measurable, independently identifiable, completed and accepted portions of lump-sum Activities and sub-activities under the Schedule of Priced Activities and Sub-activities, including bidder-added sub-activities, based on the actual percentage of completion, without the requirement to complete the entire Activity or sub-activity. | Please refer to Answer No.324. | No
329 | Section I – Instructions to Proposers (ITP) / ITP 31 – Evaluation of Technical Part / Factor 3: Similar Works; Section III – Evaluation and Qualification Criteria | We understand that the evaluation of 'Factor 3: Similar Works' specified under ITP 31 (Evaluation of Technical Part) will be conducted based on the information and support documents submitted via Form 4.2(a) and Form 4.2(b). Please confirm. | Confirmed. The information and supporting documents submitted under Forms EXP-4.2(a) and EXP-4.2(b), together with any other supporting evidence required by the RFP, will be used in evaluating the relevant Similar Works / experience aspects of the Technical Proposal. The evaluation will be conducted in accordance with ITP 31 and the criteria stated in Section III. No amendment is made to the RFP. | No
330 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(k); Section IV – Proposal Forms / Technical Proposal Forms – Work Program and Construction Schedule | Could you please clarify whether the 'Work Program' requested within the Technical Proposal Forms and the 'Construction Schedule' required under ITP 12.2(k) refer to the same document? If they differ, what are the specific content requirements for each report? | The Work Program requested in the Technical Proposal Forms and the Construction Schedule required under PDS ITP 12.2(k) are closely related but serve complementary purposes. The Construction Schedule shall present the proposed sequence, timing, logic, milestones, critical activities and interfaces for execution of the Works, while the Work Program shall address the programme-related technical information required by the Technical Proposal/evaluation criteria. The Proposer may submit one integrated programme package provided that it clearly and separately addresses all requirements of both the Work Program form/evaluation criteria and PDS ITP 12.2(k). No duplicate document is required solely because both terms are used. No amendment is made to the RFP. | No
331 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(k); Section IV – Proposal Forms / Technical Proposal Forms – Method Statements for Construction Activities and Method Statement | Could you please clarify whether the ‘Method Statements for Construction Activities’ requested in the Technical Proposal Forms and the ‘Method Statement’ required under ITP Section 12.2(k) refer to the same document? If they are different, what are the specific content requirements for each report? | The ‘Method Statements for Construction Activities’ in the Technical Proposal Forms and the ‘Method Statement’ required under PDS ITP 12.2(k) form part of the same tender-stage methodology submission. The Proposer may submit a consolidated Method Statement comprising the required activity/discipline-specific method statements, provided that all matters requested by the Technical Proposal Forms and PDS ITP 12.2(k) are clearly and fully addressed. No duplicate document is required solely because the singular and plural expressions are used. No amendment is made to the RFP. | No
332 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 1.1.86 and 1.1.95 – Time for Completion and Major Milestones; Section VII – Employer’s Requirements / Chapter 5 – Programme | 1. Time for Completion and Milestone Programme Sub-Clause 1.1.86 of Section IX specifies a Time for Completion of 1,826 days, while Sub-Clause 1.1.95 specifies the duration of Major Milestone 4, “Testing and Commissioning Completion”, as 24 months from completion of Major Milestone 3. Based on the durations indicated for the Major Milestones, the overall programme appears to extend beyond the stated 1,826-day Time for Completion. We therefore kindly request the Employer to clarify: a. whether the contractual Time for Completion is 1,826 days or the overall duration resulting from the Major Milestone programme; b. which contractual date will be used for determining the Contractor's completion obligation and any applicable delay damages; and c. whether the 1,826-day Time for Completion includes the complete Testing and Commissioning period under Major Milestone 4. | Please refer to Addendum No. 2, Amendment No. 3, Contract Data Sub-Clause 1.1.95 and ER Clauses 4.9.4 and 4.26. The overall Time for Completion is 1,826 days (60 months). Milestone 4 – Testing and Commissioning Completion is due by Month 60, providing a two-month period after Milestone 3 (due by Month 58), not a separate 24-month period. Testing of completed sections may begin before Milestone 3; the defined Milestone 4 window is for integrated system-wide testing, trial running and safety certification. The programme, delay damages under Sub-Clause 8.8 and KPIs under ER Clause 12.4 shall be read against the amended milestone dates. | Yes
333 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 1.1.95 – Major Milestone 4; Section VII – Employer’s Requirements / Chapter 10 / Clauses 10.1 and 10.6.2 – Testing, Commissioning and Taking-Over | 2. Major Milestone 4 and Taking-Over Sub-Clause 10.6.2 of Section VII sets out a number of conditions for issuance of the Taking-Over Certificate, including Trial Operations, operational readiness, RAMS performance demonstration, safety validation, ISA endorsement where applicable, trained personnel and approved O&M procedures. Please clarify the contractual relationship between completion of Major Milestone 4 and issuance of the Taking-Over Certificate, in particular: a. whether completion of Major Milestone 4 means that all conditions required under Sub-Clause 10.6.2 for Taking-Over have been satisfied; b. whether the Taking-Over Certificate is expected to be issued upon completion of Major Milestone 4; and c. if any additional activities or acceptance procedures remain after Major Milestone 4, please clarify the applicable requirements and expected time allowance. | Completion of Major Milestone 4 means completion of the Testing and Commissioning scope applicable to that Milestone. Issuance of the Taking-Over Certificate remains subject to satisfaction of all conditions stated in Section VII, Employer’s Requirements, Clause 10.6.2 and the applicable Conditions of Contract. The Taking-Over Certificate is therefore not issued merely by expiry of the Milestone period. Where all Taking-Over conditions are satisfied concurrently with completion of Major Milestone 4, the Taking-Over Certificate may be issued in accordance with the Contract. Any outstanding Taking-Over requirement shall be completed before issuance of the Taking-Over Certificate. No separate additional time allowance is created by this clarification. No amendment is made to the RFP. | No
334 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 1.1.27 and Sub-Clause 19.2.3; Section VII – Employer’s Requirements / Chapter 10 / Clause 10.6.4 – Defects Liability Period; Annex D – Warranty | 3. Defects Notification Period Sub-Clause 1.1.27 of Section IX specifies a Defects Notification Period of 730 days, while Sub-Clause 10.6.4 of Section VII refers to the commencement of the Defects Liability Period upon issuance of the Taking-Over Certificate. Please confirm: a. whether the 730-day Defects Notification Period is the same contractual period referred to as the Defects Liability Period; b. whether this period commences upon issuance of the Taking-Over Certificate; and c. whether separate Taking-Over Certificates and/or separate Defects Notification Periods are envisaged for different packages, sections or systems. | Please refer to Answer 292 and Addendum No. 2, Amendment No. 21. | Yes
335 | Section VII – Employer’s Requirements / Chapter 4 – Multi-Contract Structure and Interface Management; Chapter 9 – System Integration, RAMS and Safety; Chapter 10 – Testing, Commissioning and Trial Operations | 4. Package Interface and Testing & Commissioning Responsibilities The Employer's Requirements include extensive requirements concerning system integration, testing, commissioning, verification and validation, RAMS, safety assurance, cybersecurity, Trial Operations, training and O&M readiness. As the project is divided into separate packages, we kindly request the Employer to clarify the scope and responsibility boundaries between the relevant packages, particularly in relation to: a. system integration and interoperability; b. testing, verification and validation; c. RAMS and safety validation; d. ISA endorsement and cybersecurity requirements where applicable; e. Trial Operations and final commissioning; and f. preparation of O&M documentation and training. | Each package Contractor is responsible for the design assurance, verification/validation, RAMS/safety evidence, testing, commissioning, O&M documentation and training for the systems and works within its own contractual scope. Package 1/Lot Contractors shall provide the civil, structural, electrification/power and other enabling/interface provisions expressly allocated to them; Package 2 shall be responsible for the signalling, telecommunication and supporting systems allocated to Package 2, including the system-specific assurance/cybersecurity/ISA inputs applicable to those systems. Integrated testing, interoperability demonstration, Trial Operations and final commissioning shall be planned and coordinated in accordance with Chapters 4, 9 and 10 and the approved interface/test programmes. Each Contractor shall provide the information, access, resources and participation required for the integrated activities. No amendment is made to the RFP. | No
336 | Section VII – Employer’s Requirements / Chapter 4 / Clauses 4.1 and 4.5 – Multi-Contract Structure and Civil Infrastructure / Signaling and Telecommunication Interface; Chapter 10 – Testing and Commissioning | 5. Package 1 Enabling Works and Interface Obligations For works and systems to be delivered by another package, please clarify the corresponding responsibilities of the infrastructure/civil works package. In particular, please confirm which party will be responsible for providing and maintaining the necessary installation readiness and enabling conditions, such as access, equipment rooms, cable routes, ducts, power supply, interfaces, work fronts and other facilities required for subsequent system installation, testing and commissioning. Please also clarify the allocation of responsibility for any delay, disruption or additional cost arising from late access, incomplete enabling works or interface requirements attributable to another package. | For systems supplied under another package, the Package 1/Lot Contractor shall provide and maintain the enabling works expressly required by the RFP within its scope, including the relevant access/work fronts, equipment rooms and spaces, civil openings, foundations, ducts/routes, power/earthing provisions and physical interfaces up to the defined package interface points. The system-package Contractor is responsible for its own equipment, system-specific installation and works beyond those interface points, subject to the RFP allocation. Any delay, disruption or additional-cost entitlement arising from an interface event shall be determined in accordance with the Contract on the facts of that event; no blanket transfer of liability or entitlement is established by this clarification. No amendment is made to the RFP. | No
337 | Section VII – Employer’s Requirements / Chapter 4 – Multi-Contract Structure and Interface Management / Interface Register, Interface Requirements Schedule and Lot-to-Lot Interfaces | 6. Interface Matrix To ensure a clear allocation of responsibilities and avoid contractual ambiguity during implementation, we kindly request the Employer to provide, or confirm whether a detailed Package Interface Matrix will be established, identifying: scope and responsibility of each package; interface deliverables and required dates; access and work-front handover requirements; testing and commissioning interfaces; responsibility for interface defects and non-conformities; and responsibility for delays arising from package interfaces. | A detailed Interface Register/Matrix shall be developed, maintained and updated during Contract implementation in accordance with the interface-management requirements of Chapter 4. It shall identify the responsible package/party, interface deliverables, required dates, access/work-front handovers, testing and commissioning interfaces and the management of defects/non-conformities. The matrix will be coordinated among the relevant Contractors and reviewed through the Employer/Engineer interface-management process. No separate final Interface Matrix is issued at Proposal stage. Contractual responsibility for delay or defects remains governed by the respective Contracts. No amendment is made to the RFP. | No
338 | Section I – Instructions to Proposers (ITP) / ITP 18.2(d) – Local Labour; Section IV – Proposal Forms / Local Labour Method Statement; Section IX – Particular Conditions / Sub-Clause 6.23 – Employment Records of Workers | 1. Labour Cost / FTE Calculation Reference: RFP – Schedule of Labour / FTE Requirements and relevant Proposal Forms The RFP refers to the calculation of labour requirements and labour costs by skill category. Considering the large number and diversity of labour positions that may be required throughout the Contract period, it may not be practical to provide a separate FTE calculation for each individual trade or job title. We therefore kindly request the Employer to confirm whether, for the purpose of the FTE and labour cost calculation, it would be sufficient to classify the workforce under the following three main skill categories only: 1. Skilled Labour 2. Semi-Skilled Labour 3. Unskilled Labour Please confirm whether no further breakdown by individual trade, occupation or skill type is required for the FTE calculation, provided that the total FTE and corresponding labour cost are properly demonstrated for each of the above three categories over the Contract period. | Confirmed. For the Local Labour Method Statement, FTE shall be calculated for the three skill categories stated in Section IV, Proposal Forms: Skilled Labour, Semi-skilled Labour and Unskilled Labour. No further breakdown by individual trade or occupation is required for the FTE calculation. The Proposer shall provide the total FTE and the percentage of total FTE to be filled by local labour for each of these three skill categories, together with the other information required by the Local Labour Method Statement. As expressly stated in the form, the Local Labour Method Statement shall not include financial information such as wages in dollar terms. No amendment is made to the RFP. | No
339 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Particular Conditions / Sub-Clause 14.4 – Schedule of Payments | 2. Schedule of Priced Activities and Sub-Activities – Number of Sub-Activities and Partial Payment Reference: Section IV – Proposal Forms, Schedule of Priced Activities and Sub-activities, and Section IX – Particular Conditions, Sub-Clause 14.4 The RFP allows the Proposer to add up to three (3) additional sub-activities under the relevant Activities. However, for certain major and technically complex lump-sum Activities, particularly tunnels, bridges, stations and other major civil works, a maximum of three additional sub-activities may not always be sufficient to adequately reflect the actual construction sequence and to establish a practical payment structure. We therefore kindly request the Employer to clarify and confirm the following: a) Whether the Proposer may include more than three (3) additional sub-activities where reasonably necessary to reflect the construction sequence and establish an appropriate breakdown of the relevant lump-sum Activity; and b) Whether the sub-activities included in the Schedule of Priced Activities and Sub-activities, including any additional sub-activities proposed by the Bidder, may be used as payment components for Interim Payments, such that measurable, independently identifiable, completed and accepted portions of the relevant sub-activity may be valued and paid on a percentage-of-completion basis, without waiting for completion of the entire Activity or sub-activity, unless the relevant item is expressly designated as a Milestone under the Schedule of Payments in accordance with Sub-Clause 14.4 of the Particular Conditions. We would appreciate the Employer's explicit confirmation of both points, as they are important for establishing a practical and contractually clear payment structure. | (a) No. The Proposer may add up to three (3) additional sub-activities under each relevant Activity, as provided in the Schedule of Priced Activities and Sub-activities. (b) Proposer-added sub-activities do not automatically constitute contractual Milestones. Each separately priced additional deliverable/sub-activity is payable at its quoted lump-sum price upon completion and acceptance. A partially completed item is not payable proportionally merely on the basis of progress or quantities. Please refer to Addendum No. 2, Amendment No. 12 (as revised), and Clause 14. | Yes
340 | Section VII – Employer’s Requirements / Clause 5.5.2 – Key Structures and Works – Sabiha Gökçen Airport Station; Chapter 4, Clause 4.8.2 – Interface with Airport Operators (Lot 1); Annex A3 – Architectural Drawings – Sabiha Gökçen Airport Station / Drawing AYGM-INR-ARC-SGA-001; Annex C – Site Information | It has been observed from drawing AYGM-INR-ARC-SGA-001, included in the Annex A Drawings – Annex A3 Architectural folder of the tender documents for Sabiha Gökçen Airport, that the existing metro alignment intersects with the proposed new station. In view of the potential impact of the existing station structure and associated infrastructure on the design and construction of the proposed new station, we consider it essential to obtain accurate as-built information to enable the necessary interface coordination and verification of the proposed works. Accordingly, we kindly request that the following information be provided: - As-built levels and elevations of the existing station structure, including relevant structural and architectural datum levels; - As-built levels, coordinates, and exact locations of all existing infrastructure and installations that may be affected by the proposed works; - Survey records, as-built drawings, and other relevant technical documentation necessary to establish the precise location and configuration of the existing facilities. This information is required to assess the potential constraints arising from the existing station and to ensure that the design and construction of the proposed new station are properly coordinated with the existing infrastructure. We would appreciate it if the above information could be provided at your earliest convenience. | Please refer to Answer 32. | No
341 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Deadline for Submission of Proposals | As stated in your announcement, bidders must submit their proposals by October 14, 2026, at the latest. However, given the scale of the project, this timeframe is quite limited for the technical work to be carried out; furthermore, since this is a design-and-build project, it requires coordination with design firms throughout the design processes. This situation has directly impacted our ability to complete all necessary documentation within the current timeframe. We would greatly appreciate it if the deadline could be extended by at least 1 (one) month to allow bidders to prepare and submit comprehensive bids that fully comply with the project specifications and the employer’s criteria. | Please refer to the Addendum No.1 | No
342 | Section IX – Particular Conditions / Page 389 | An inconsistency has been identified between the total duration of the milestone chain (84 months) and the Time for Completion (1826 days/60 months). Which one should be taken as the basis? | Please refer to Answer No.5. | No
343 | Section VII – Employer’s Requirements / Annex E1 and Annex E4 | Reinforced concrete calculations and load factors are based on LRFD, train loads on UIC standards, and seismic requirements on TKDY-2020. Can you confirm this? | Confirmed in principle, subject to the specific provisions of the applicable discipline specification. Railway bridge loading and design shall comply with Annex E4 and the standards expressly referenced therein; seismic design shall comply with the applicable Turkish seismic regulations identified in the RFP. Where a discipline-specific Annex provides a more specific requirement, it shall govern that subject matter, subject to the Contract order of precedence. | No
344 | Section VII – Employer’s Requirements / Annex C1- Geological Data Report | Borehole logs, core photographs, and laboratory test results for the 70 boreholes coded AS- (ranging from AS-2 to approximately AS-125)—which were drilled as part of the Northern Marmara Motorway Section 3 and are understood to also cover the Inrail Project Lot-2 section—are not included in the tender documents. Can the data for these boreholes be provided? | The Employer has provided the geological and geotechnical information forming part of the RFP and available for tender purposes. Such information is tender-stage information and shall be read together with Annex C and the other Site Information. The Contractor remains responsible for carrying out the additional investigations and verification necessary for its Detailed Design and construction methodology. No additional geotechnical information is issued by this clarification. | No
345 | Section VII – Employer’s Requirements / Clauses 4.5 and 4.6 | The Employer's Requirements stipulate coordination between the signaling and telecommunication works and the designs of adjacent Lots. Could the submission dates for design-related information and interface details be clarified? | The Contractor shall establish and maintain the Design Submission Schedule, Interface Register and interface deliverable dates in accordance with Chapters 4 and 7 of the Employer’s Requirements. The detailed dates shall be coordinated with the adjacent Lot Contractors, the Package 2 Contractor and the Engineer and incorporated into the approved programme. No additional fixed tender-stage submission dates are prescribed by this clarification. | No
346 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Part 5 | Regarding the bridge types, the typical cross-sections are shown with ballast, except for the YSS bridge. Furthermore, the span length is indicated as 40 m, and the girder type as 240 cm. Within Annex E4, references are made to steel and integral bridges as distinct bridge types; however, their specific designs are not included in the drawing attachments. Could the typical drawings be shared? | The Employer has provided the tender-stage reference/conceptual information available for preparation of the Proposal. The Project is Design-Build and the Contractor shall verify the information, carry out the necessary surveys/investigations and develop the Detailed Design in accordance with the mandatory Employer’s Requirements. No additional document is issued by this clarification unless subsequently transmitted through an Addendum. | No
347 | Section VII – Employer’s Requirements / UIC Code | The specification stipulates a design speed of 160 km/h for the main line. The relationship between the assumed minimum speed—particularly for freight trains—and operational conditions needs to be clarified. Can a minimum speed of 40 km/h be adopted, or should a different value be used? | Please refer to Answer 259. | No
348 | Section IX – Particular Conditions | Clause 4.26 of the Particular Conditions links the milestones to the provisions of FIDIC Sub-Clauses 8.3 (Programme) and 8.5 (Extension of Time). Could the separate indication of the timeframes for the initial submission, review, and resubmission within the delivery schedule be reconsidered? | The request is not accepted. The programme, milestone and design-submission requirements shall be applied as stated in the Contract, including the applicable periods for submission, review and resubmission. | No
349 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Part 4 | The map provided as an attachment to the tender is in 2D format. Is the 3D version available? | The Employer has provided the tender-stage drawings and digital information available for preparation of the Proposal. No separate 3D alignment model is issued under this clarification. The Contractor shall develop the coordinated 3D/BIM model and verify levels, geometry and quantities as part of its Design-Build obligations. | No
350 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification, Cl. 5.12.1 “Bridges – Viaducts and Engineering Structures”; Annex E1, Cl. 2.1 “Design Speed, Clearance, Axle Load, Load Classes”; Annex E4 – Railway Bridge Design Technical Specification, Cl. 3.5; Employer’s Requirements, Chapter 3 | Which clause governs the design of bridges and viaducts under this Contract — Annex E1 Cl. 5.12.1, or Annex E1 Cl. 2.1 read together with Annex E4 Cl. 3.5? Please confirm that Annex E4, as the discipline-specific Technical Specification, prevails over Annex E1 Cl. 5.12.1 in accordance with Chapter 3 of the Employer’s Requirements. | For railway bridges and viaducts, Annex E4 governs the railway-bridge-specific design requirements. Please refer to Addendum No. 2, Amendments Nos. 31 and 40, and the revised Annex E1 – Design Technical Specification attached to the Addendum. The original Annex E1 Clause 5.12.1 has been superseded by the revised Annex E1; the applicable contract order-of-precedence provisions remain unchanged. | Yes
351 | Section VII – Employer’s Requirements / Annex E4, Cl. 3.5.3.2 (classification factor α); Annex E1, Cl. 2.1 (25 t axle load; TSI line category E4) | Please confirm the value of the classification factor α to be applied to LM71, SW/0 and SW/2. Given the stated 25 t maximum axle load and TSI line category E4, is α = 1.00 or α = 1.21 to be adopted? | Please refer to Answer 122. | No
352 | Section VII – Employer’s Requirements / Annex E4, Cl. 3.5.3 (LM71, SW/0, SW/2) | Please confirm whether SW/2 is to be applied over the full extent of all lots' alignment or only at designated locations, and whether SW/2 governs the design of continuous structures. | SW/2 shall be applied where required by Annex E4 and the applicable EN 1991-2 provisions for the structure and traffic arrangement concerned. The Contractor shall identify the applicable load models in the Design Basis and demonstrate compliance for each relevant structure. | No
353 | Section VII – Employer’s Requirements / Annex E4, Cl. 3.5.4.5 (dynamic factor Φ) | Please confirm which dynamic factor is to be applied — Φ2 (carefully maintained track) or Φ3 (track with standard maintenance) — for main-line structures. | Please refer to Addendum No. 2, Amendment No. 28. | Yes
354 | Section VII – Employer’s Requirements / Annex E1, Cl. 2.1 (design speed 160 km/h); Annex E1, Cl. 5.6 “Switches” (reference to “High-Speed Railway system”); Annex E4, Cl. 3.5.4 “Dynamic Effects (Including Resonance)” | Annex E1 Cl. 2.1 states a design speed of 160 km/h, while Annex E1 Cl. 5.6 refers to a “High-Speed Railway system”. Please confirm the design speed governing structural design, and confirm whether the dynamic / resonance analysis of Annex E4 Cl. 3.5.4 is mandatory for all Lots' structures at that speed, or whether the EN 1991-2 Cl. 6.4.4 flowchart may be used to demonstrate that a dynamic analysis is not required. | The governing railway alignment/structural design speed is 160 km/h. Please also refer to Answer 105 regarding electrification and signalling design speed. Dynamic/resonance analysis shall be carried out where required by Annex E4 and the applicable EN 1991-2 criteria; where the applicable standard permits demonstration that a full dynamic analysis is not required, that demonstration shall be submitted as part of the Detailed Design for the Engineer’s review. | No
355 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification, Cl. 3.2 “Bridge Importance Classes” (TKDY-2020) | Please confirm that all bridges and viaducts within all lots are to be designed as KÖS = 1 (Important Bridges) under TKDY-2020. | The Bridge Importance Class shall be determined in accordance with TKDY-2020 and Annex E4 for the relevant structure and operational function. The Contractor shall demonstrate the adopted classification in the Design Basis and Detailed Design submissions. No additional blanket classification is introduced by this clarification unless expressly stated in Annex E4. | No
356 | Section VII – Employer’s Requirements / Annex E4, Cl. 3.1 “Earthquake Ground Motion and Earthquake Effects”; TKDY-2020 Annex 1, Section 3; TBDY-2018 | Please confirm the seismic performance targets required for each ground motion level (DD-1, DD-2, DD-3) for KÖS = 1 railway bridges, and confirm whether the Employer requires performance verification beyond the minimum prescribed by TKDY-2020. | The Bridge Importance Class shall be determined in accordance with TKDY-2020 and Annex E4 for the relevant structure and operational function. The Contractor shall demonstrate the adopted classification in the Design Basis and Detailed Design submissions. No additional blanket classification is introduced by this clarification unless expressly stated in Annex E4. | No
357 | Section VII – Employer’s Requirements / Annex E4, Cl. 3.1; TBDY-2018 Cl. 2.4 (site-specific seismic hazard analysis) | Is a Site-Specific Seismic Hazard Analysis (SSHA) mandatory for ALL Lots' structures, or only for those structures for which TBDY-2018 Cl. 2.4 makes it obligatory (e.g. sites within 15 km of an active fault, or ZF-class soil profiles)? If mandatory for all structures, please confirm that the SSHA is to be produced by the Contractor and identify the review / approval body. | Please refer to Section VII, Clause 9.4 and Annexes E and F. Site-specific seismic hazard assessment and soil classification are part of the Contractor’s design investigation obligations. The resulting design parameters shall be established and verified by the Contractor and submitted through the Design Management process for the Engineer’s review/consent and any statutory review required by the applicable Turkish seismic regulations. | No
358 | Section VII – Employer’s Requirements / Türkiye Deprem Yönetmeliği 2020 – “Principles for the Design of Highway and Railway Tunnels and Other Buried Structures Under Seismic Effect”; Annex E1, Cl. 5.12.2 “Tunnels” | Please confirm the design ground motion levels applicable to tunnels and cut-and-cover structures, and whether these are to be derived from the same SSHA as the bridges. | Please refer to Section VII, Clause 9.4 and Annexes E and F. Site-specific seismic hazard assessment and soil classification are part of the Contractor’s design investigation obligations. The resulting design parameters shall be established and verified by the Contractor and submitted through the Design Management process for the Engineer’s review/consent and any statutory review required by the applicable Turkish seismic regulations. | No
359 | Section VII – Employer’s Requirements / Annex E4, Cl. 3.1 (TKDY-2020 / TYSKVDY-2020); Employer’s Requirements, Cl. 5.1.2 “Design Responsibilities” | Is the selection of the seismic design strategy — conventional ductile design under TKDY-2020 versus seismic isolation and/or supplemental damping under TYSKVDY-2020 — left to the Contractor’s Detailed Design, or does the Employer mandate isolation for any structure or structure type within all lots? | Please refer to Section VII – Employer’s Requirements / Annex E4, Cl. 3.1 (TKDY-2020 / TYSKVDY-2020); Employer’s Requirements, Cl. 5.1.2 “Design Responsibilities”. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and where relevant, submit for the Engineer’s review/approval during Detailed Design. | No
360 | Section VII – Employer’s Requirements / Annex E4, Cl. 4 “Design Criteria” / “Advanced Analysis Methods” (Design Supervision and Control); Employer’s Requirements, Chapter 7 “Design Management”; Section IV – Schedule of Priced Activities | Where TGD service is triggered (isolated / damped bridges, special bridges, or the use of advanced analysis methods), please confirm: (a) whether the TGD body is appointed by the Employer or by the Contractor; (b) the qualification criteria the TGD body must satisfy, and whether an Employer-approved list exists; (c) which Activity or sub-activity of the Schedule of Priced Activities the TGD fee is to be priced under, given that no dedicated item is provided; and (d) whether the Engineer’s review under Chapter 7 of the Employer’s Requirements is additional to, or a substitute for, the statutory TGD review. | Where statutory Design Supervision and Control (TGD) is required by the applicable Turkish legislation/technical regulations, the Contractor shall arrange and bear the cost of the required TGD service through a suitably qualified and authorized body. No Employer-approved exclusive list is provided. The cost shall be deemed included in the relevant design/structural Works lump-sum Activities. The Engineer’s review under Chapter 7 is additional to, and does not replace, any mandatory statutory TGD review. | No
361 | Section VII – Employer’s Requirements / EN 15129 (anti-seismic devices); Annex D – General Technical Specification (factory acceptance test attendance, up to 8 persons per visit) | Are isolation and damping devices required to be prototype- and production-tested in accordance with EN 15129, and if so, is a witnessed test at the manufacturer’s facility a condition of acceptance? Please confirm that the associated Employer / Engineer attendance costs fall under the Annex D provision covering factory acceptance test attendance for up to eight persons per visit. | Where isolation or damping devices are adopted, the devices shall comply with EN 15129 and the applicable product/acceptance-testing requirements, including prototype/type and production testing as applicable. Witnessing requirements shall be coordinated with the Engineer. Employer/Engineer attendance costs shall be dealt with in accordance with the factory acceptance test attendance provisions of Annex D. | No
362 | Section VII – Employer’s Requirements / Annex E1, Cl. 5.12.1 | Please confirm whether this requirement applies to EVERY bridge and viaduct in all lots having any span of 10 m or greater — i.e. to all structures in the indicative structure lists(Employer Requirements) — or only to structures individually designated by the Engineer. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. The original Annex E1 Clause 5.12.1 has been superseded. Any bridge or viaduct load-test obligation shall be determined under Annex E4 and the other applicable RFP testing provisions; the superseded Annex E1 provision does not independently impose a test requirement. | Yes
363 | Section VII – Employer’s Requirements / Annex E1, Cl. 5.12.1; UIC 776-1; DIN 1076; TCDD / AYGM acceptance protocols | Please confirm the governing test standard and acceptance criteria, including the required test load intensity as a proportion of the design live load, load positions, hold durations and permissible residual deflection. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. The original Clause 5.12.1 is superseded. Where loading tests are required by the applicable RFP provisions, the Contractor shall submit the testing procedure, loading arrangements and acceptance criteria for the required approvals, in accordance with the applicable specifications. | Yes
364 | Section VII – Employer’s Requirements / Annex E1, Cl. 5.12.1; Employer’s Requirements, Chapter 4 (interface management, TCDD interfaces) | Please confirm which party supplies the test loading. If test trains are required, will the Employer / TCDD provide the locomotives, wagons and ballast, and will TCDD grant the necessary line possession and traction power? If the Contractor is to provide the loading, please confirm that alternative loading arrangements (e.g. kentledge, ballasted vehicles) are acceptable. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. The original Annex E1 Clause 5.12.1 is superseded. Where testing is required under the applicable RFP provisions, the Contractor remains responsible for the necessary arrangements, including coordination for operational access. The availability of Employer/TCDD resources shall not be assumed without prior agreement. | Yes
365 | Section IV – Proposal Forms – Schedule of Priced Activities (Lot 1&2&3&4), Activity 6, Activity 10 and Activity 11; Conditions of Contract, Sub-Clause 10.1 | Please confirm the point in the programme at which testing is to be carried out relative to track laying, OCS energisation and the Taking-Over Certificate, and whether the tests form part of Activity 10 & Activity 11 (Testing and Commissioning) or of Activity 6 (Structural works: Crossing obligations). | Structural and system testing shall be sequenced in the Contractor’s approved Testing and Commissioning programme after the relevant construction/installation prerequisites are complete and before Taking-Over. Tests forming part of structural completion remain within the relevant structural Activity, while integrated railway-system Testing and Commissioning shall be priced under the applicable Testing and Commissioning Activities. Taking-Over remains subject to completion of all applicable testing and acceptance requirements. | No
366 | Section VII – Employer’s Requirements / Cl. 5.6.2 “Key Structures and Works”; Annex E1, Cl. 5.2.1 “Ballastless Track” / Cl. 5.2.2 “Ballasted Track” | Is the selection of track form on viaducts, in NATM tunnels and in cut-and-cover structures a Contractor’s design decision subject to the Engineer’s consent, or does the Employer mandate a specific track form by structure type (for example, ballastless in all tunnels, or ballastless on viaducts exceeding a defined length)? | Please refer to Answer 201. | No
367 | Section VII – Employer’s Requirements / Annex E1, Cl. 5.2; Annex E4; Annex G1 – Superstructure Works Construction Specification | If the selection is the Contractor’s, please confirm that the Employer will accept a fully ballasted solution on all Lot 1&2&3&4 structures, provided that all performance, deflection, noise, vibration and maintainability requirements of Annexes E1, E4 and G are demonstrably satisfied. | Please refer to Answer 201. | No
368 | Section VII – Employer’s Requirements / Annex G20 – Under-Ballast Mat; Annex G4 – Under-Sleeper Pad; Annex E1, Cl. 1.18.3 “Mass-Spring System” | Please confirm the locations or performance triggers at which Under-Ballast Mat, Under-Sleeper Pad and mass-spring systems become mandatory, or confirm that their use is determined solely by the Contractor’s vibration and noise assessment. | The use and extent of Under-Ballast Mats, Under-Sleeper Pads and Mass-Spring Systems shall comply with the locations and requirements expressly identified in the RFP and, where not expressly fixed, shall be determined through the Contractor’s detailed noise and vibration assessment and Detailed Design, subject to the Engineer’s consent. Please also refer to the Mass-Spring System Technical Specification added by Addendum No. 2, Amendment No. 13. No further amendment is made to the RFP. | Yes
369 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification; UIC 774-3; EN 1991-2 Cl. 6.5.4 | Please confirm that track–structure interaction analysis is to be carried out in accordance with UIC 774-3 / EN 1991-2 Cl. 6.5.4, and confirm the limiting criteria to be adopted for additional rail stress (compression and tension), relative displacement at deck ends under braking / traction, and relative displacement due to deck end rotation. | Track–structure interaction analysis shall be carried out in accordance with Annex E4 and the applicable UIC 774-3 / EN 1991-2 provisions. The limiting criteria for additional rail stresses and relative displacements shall be those stated in the applicable standards and the RFP; the Contractor shall identify the adopted limits in the Design Basis and demonstrate compliance in the Detailed Design. | No
370 | Section VII – Employer’s Requirements / Cl. 5.6.2 (supply and installation of railway turnouts and rail expansion joints); Annex G1 | Are rail expansion devices permitted on the main running lines of Lot 1&2&3&4? If permitted, is there a maximum permissible number per structure or per kilometre, and is a maximum permissible expansion length (L_T) imposed on continuous decks? | Rail expansion devices are permitted where demonstrated as necessary by the approved Detailed Design and track–structure interaction analysis. Please refer to Addendum No. 2, Amendment No. 17 and the AYGM Rail Expansion Gasket (REG) Technical Specification. The RFP does not prescribe a fixed maximum number per structure or kilometre; the Contractor shall minimize their use consistent with safety, performance and maintainability requirements. | Yes
371 | Section VII – Employer’s Requirements / UIC 774-3; EN 1991-2 Cl. 6.5.4; Employer’s Requirements, Cl. 5.6.2 | If rail expansion devices are NOT permitted on continuously welded main-line track, please confirm the maximum expansion length that the Contractor’s structural design must respect, so that span arrangements can be priced on a consistent basis by all Proposers. | No separate universal maximum expansion length is prescribed by this clarification. The permissible expansion length shall be established by the Contractor through the track–structure interaction analysis in accordance with UIC 774-3 / EN 1991-2 and the applicable RFP requirements. Where the analysis requires a rail expansion device, it shall be designed in accordance with the applicable specification. | No
372 | Section VII – Employer’s Requirements / UIC 776-3 “Deformation of Bridges”; EN 1990 Annex A2; Annex E4, Cl. 2.4 (deflection criteria for traffic safety and passenger comfort) | Please confirm the deformation and deflection limits governing structural design — specifically which criteria of UIC 776-3 and EN 1990 Annex A2 apply (vertical deflection limit, deck twist, deck-end rotation, deck acceleration) and at which comfort level (very good / good / acceptable). | The deformation and deflection criteria stated in Annex E4 and the referenced UIC/EN standards shall govern. The Contractor shall demonstrate compliance with all applicable limits for vertical deflection, twist, end rotation, acceleration and passenger comfort for the relevant structure and design speed. No alternative comfort category is prescribed by this clarification. | No
373 | Section VII – Employer’s Requirements / Annex E4, Cl. 3.1 (TKDY-2020 / TBDY-2018); EN 1998-2; Annex Q, Cl. 14.3 | Where TKDY-2020 / TBDY-2018 and EN 1998-2 give conflicting requirements for the same verification, which governs? | The applicable Turkish seismic regulations identified in the RFP shall govern seismic design in Türkiye. EN 1998-2 shall be applied where referenced and to the extent it is compatible with the governing Turkish requirements. Any irreconcilable conflict shall be referred to the Engineer in accordance with the order-of-precedence provisions and shall not be resolved unilaterally. | No
374 | Section VII – Employer’s Requirements / Annex E1, Cl. 5.12.1 (KGM Technical Specifications for Road Bridges / AASHTO LRFD); Annex E4 – Railway Bridge Design Technical Specification | Please confirm whether AASHTO LRFD may be applied to railway bridges under this Contract, or whether Annex E1 Cl. 5.12.1’s reference to KGM / AASHTO is to be read as applicable only to highway overpasses and grade-separation structures carrying road traffic. | For railway bridges and viaducts, Annex E4 and its railway-specific loading and structural-design provisions shall apply; the applicable road-structure provisions remain subject to the relevant RFP requirements. Please refer to Addendum No. 2, Amendments Nos. 31 and 40, and the revised Annex E1 which replaces the original Annex E1. | Yes
375 | Section VII – Employer’s Requirements / Annex E1, Cl. 5.12.1 (“the standard that yields the most favourable results”) | Please clarify the phrase directing design in accordance with the standard yielding the most favourable results. Is this to be understood as requiring the MORE CONSERVATIVE of the two outcomes in every verification? | For railway bridges and viaducts, applicable wind actions and related structural verifications shall be determined in accordance with Annex E4 and the standards referred to therein. Please refer to Addendum No. 2, Amendments Nos. 31 and 40, and the revised Annex E1. The superseded original Annex E1 Clause 5.12.1 wording shall not be used. | Yes
376 | Section VII – Employer’s Requirements / Chapter 7, Cl. 7.2.2 “Design Management System” and Cl. 7.3 “Design Submission Schedule and Design Register”; Annex D – Design Management Plan (list of applicable design codes, regulations and standards) | Will the Employer establish, as a contractual mechanism, a single consolidated “Design Basis / Design Criteria Document”, to be prepared by the Contractor and approved by the Engineer within a defined period after the Commencement Date, which resolves all such conflicts and thereafter governs? If so, please confirm that a conflict resolved in the approved Design Basis Document will not subsequently be reopened by the Engineer during design review. | The Contractor shall prepare and maintain the Design Basis/Design Criteria and the Design Management documentation required by Chapter 7, including the applicable codes, standards, assumptions and resolved interfaces. The Engineer’s consent to such documents does not amend the Contract or prevent subsequent correction where non-compliance with the Contract is identified. | No
377 | Section IV – Proposal Forms, Schedule of Priced Activities and Sub-activities (Lot 2), Activity 6 “Structural works: Crossing obligations (Engineering Structures – Bridges and Viaducts)”; Employer’s Requirements, Cl. 5.1.1 “Design and Build Disclaimer” | If the Contractor’s approved Detailed Design results in a DIFFERENT NUMBER of bridges / viaducts than the twelve structures in the indicative list — for example, two adjacent bridges combined into one continuous viaduct, or a bridge replaced by an embankment or a cut-and-cover structure — please confirm how the Activity 6 lump sum is administered. Specifically: does the total Activity 6 lump sum remain unchanged irrespective of the final structure count? | The Contract is lump-sum Design-Build. The indicative structure list does not constitute a remeasurement basis. Subject to compliance with the Employer’s Requirements and approval of the Detailed Design, a change in the final number/configuration of structures resulting from the Contractor’s design development does not of itself change the Activity lump sum or the Contract Price, unless the change constitutes a Variation under the Contract. | No
378 | Section IV – Proposal Forms – Schedule of Priced Activities (Lot 2), Activities 3, 5 and 6; Conditions of Contract, Sub-Clause 14.3 | If a structure migrates between Activities as a consequence of the Detailed Design — for example, a bridge in Activity 6 replaced by a cut-and-cover structure falling under Activity 5, or a viaduct replaced by embankment and slope stabilisation under Activity 3 — please confirm whether the corresponding lump sums are transferred between Activities, and if so on what basis, given that interim payment is certified by Activity. | The Schedule of Priced Activities is the payment breakdown of the lump-sum Contract and is not a remeasurement BOQ. Where the Contractor’s approved Detailed Design changes the allocation of work between Activities without a Variation, the total Contract Price remains unchanged and the payment breakdown shall be administered through an agreed revised allocation/weighting consistent with the approved design and Clause 14. Any Employer-instructed change shall be dealt with under Clause 13. | No
379 | Section VII – Employer’s Requirements / 3D Drawing | In the Tender documentation, ANNEX A - Drawings\ANNEX A1 - Alignment\01_4_Plan_Profile_Drawings\DWG\ Map.dwg file supposed to have 3d coordinates, however the file has only 2d coordinates. (Z coordinates are only text format and the drawing is not based on the Z coordinates.) That drawing is not allowing bidders to model the allingnment and calculate the earth works for a competative offer. Therefore, we kindly request the same document as 3d including elevation information. | The Employer has provided the tender-stage drawings and digital information available for preparation of the Proposal. No separate 3D alignment model is issued under this clarification. The Contractor shall develop the coordinated 3D/BIM model and verify levels, geometry and quantities as part of its Design-Build obligations. | No
380 | Section III – Evaluation and Qualification Criteria /Contractor’s Representative and Key Personnel | Ref: Section III-A-1.4 – Evaluation and Qualification Criteria /Contractor’s Representative and Key Personnel We understand that the proposed Project Manager is required to demonstrate experience under the FIDIC Yellow or Gold Conditions of Contract. We respectfully request the Employer’s consideration of relevant experience gained on comparable railway projects in Türkiye procured under Public Procurement Law No. 4734 and executed under contracts governed by Public Procurement Contracts Law No. 4735. These laws establish the statutory framework for the relevant public procurement procedures and the preparation and implementation of the contracts, respectively. Although this framework differs from the FIDIC Conditions of Contract, managing major railway projects under such contracts requires substantial competence in contract administration, programme and cost control, multidisciplinary coordination, subcontractor management, quality assurance, and compliance with contractual obligations. We fully acknowledge the importance of appointing a suitably qualified Project Manager and the relevance of familiarity with the contractual framework applicable to the Project. Accordingly, please confirm whether such experience would be accepted as an alternative to the specified experience under the FIDIC Yellow or Gold Conditions of Contract, provided that all other qualification requirements are satisfied and the candidate’s responsibilities and relevant experience are supported by appropriate documentary evidence. | The request is not accepted. Please refer to Section III, Item 1.4. The specified FIDIC Yellow Book or Gold Book experience for the Project Manager is a mandatory qualification requirement and experience solely under Turkish Public Procurement Contracts Law No. 4735 is not an alternative to that requirement. | No
381 | Section VII – Employer’s Requirements / PSD requirements for underground stations | The tender documents do not specify the number of cars per train set. This information is required to determine the number and arrangement of PSD doors. We kindly request, Employer's planned number of cars per train set, train length and passenger door arrangement. | The rolling-stock and operational parameters to be used for Detailed Design shall be those stated in Annex B2 and the other applicable Employer’s Requirements. The Contractor shall coordinate the final PSD door arrangement with the rolling-stock/interface parameters confirmed through the Design Management process. No additional rolling-stock configuration is issued by this clarification. | No
382 | Section VII – Employer’s Requirements / YSS Bridge – Track Superstructure Type | The tender drawings does not include a typical cross-section indicating the track superstructure system to be adopted on the Yavuz Sultan Selim (YSS) Bridge. Please provide the typical cross-section and relevant technical details for the railway track system to be implemented on the YSS Bridge and clarify whether the track shall be ballasted track, slab track, or another specific track system (e.g. a system incorporating timber sleepers or other special bridge-track solutions)? | Please refer to Answer 201. | No
383 | Section VII – Employer’s Requirements / Annex C – Site Information / Annex C1 – Geological Data Report; INRAIL Geological Plan / Appendix A – Borehole Logs | The INRAIL Geological Plan indicates more than 300 borehole locations, whereas Appendix A – Borehole Logs provides detailed logs for only approximately 60 boreholes. Furthermore, no borehole logs have been provided for Lot 2, while only a limited number are available for the other Lots. Considering that no project-specific ground investigation has been carried out by the Employer, while the RFP documents repeatedly highlight significant geotechnical risks and ground-related uncertainties, including groundwater, swelling clay, karstification/voids and variable ground conditions, access to the available subsurface investigation data is essential for the proper assessment and pricing of the Works. In view of the Design & Build and lump-sum nature of the Contract, we kindly request the Employer to provide all available borehole logs and associated investigation data for the borehole locations identified in the INRAIL Geological Plan, including laboratory and in-situ test results, groundwater observations and core photograph. | Please refer to Answer 344. | No
384 | Section VII – Employer’s Requirements / Design and Operating Speeds | It has been identified that different design, control/test and operating speeds are specified in different parts of the Tender Documents, as summarized below: - ANNEX E1 – Design Technical Specification, Clause 3.1.1 / Table GEOMETRIC DESIGN.3: Main Line Design Speed: 160 km/h, Control Speed: 176 km/h. - ANNEX E1 – Design Technical Specification, Clause 5.13.3: OCS Design Speed: 160 km/h, Control Speed: 176 km/h. - ANNEX L – Signaling, Telecommunication and Support Systems Technical Specification, Purpose: Maximum Train Operating Speed: 200 km/h. - ANNEX G1 – Superstructure Works Construction Specification, Clause 1.1: High-Speed Train Line Maximum Speed: 250 km/h, while Fast Train Line Maximum Speed is stated as 200 km/h. Considering the above discrepancies, we kindly request to clarification regarding the governing design speed, maximum operating and control/test speed to be adopted for the Project, separately for: (i) open/at-grade sections, (ii) bridges and viaducts, and (iii) tunnels. | The applicable design, control/testing and operating speeds shall be determined from the relevant section-specific requirements stated in the RFP and the revised Annex E1 issued under Addendum No. 2, Amendment No. 31, together with the governing Annex B1 alignment data and applicable system-specific technical specifications. Different speed designations shall not be treated as interchangeable. | Yes
385 | Section VII – Employer’s Requirements / Annex G1 – Superstructure Works Construction Specification, Clause 8.1.1 – Ballastless Track Construction | According to Clause 8.1.1 of ANNEX G1 – Superstructure Works Construction Specification, “Tunnels, viaducts and station tracks designated by the Employer shall be ballastless tracks.” However, the “BRIDGE TYPICAL CROSS SECTIONS TYPE-S SINGLE TRACK BRIDGE (CONCEPTUAL DRAWING)” and “BRIDGE TYPICAL CROSS SECTIONS TYPE-D DOUBLE TRACK BRIDGE (CONCEPTUAL DRAWING)” and "CUT&COVER TUNNEL TYPICAL CROSS SECTIONS TYPE-1 DOUBLE TRACK CUT&COVER" clearly indicate a ballasted track arrangement, which appears to be inconsistent with the above requirement. The Employer is kindly requested to clarify and confirm whether the track system to be adopted on tunnels, bridges, viaducts and station shall be ballastless track or ballasted track. In case different track systems are intended for different tunnels, bridges, viaducts and station structures or locations, please specify the applicable track type for each case. | Please refer to Answer 201. | No
386 | Section VII – Employer’s Requirements / Existing Cut & Cover Structures at the Bridge Approaches | During the site visit conducted on [01.09.2026], it was stated that the following structures located at the entrance and exit approaches of the Bridge have already been constructed and their construction works have been completed: Cut & Cover-4Aand Cut & Cover-5A. The Employer is kindly requested to confirm in writing that the above-mentioned structures have been completed. In order to assess the existing structures, identify any outstanding/incomplete works, if any, and evaluate the interface and connection details between the existing structures and the works to be constructed under the present Contract, the Employer is kindly requested to provide the As-Built drawings and relevant available technical documentation of Cut & Cover-4A and Cut & Cover-5A to Bidders. | The Employer has provided the tender-stage reference/conceptual information available for preparation of the Proposal. The Project is Design-Build and the Contractor shall verify the information, carry out the necessary surveys/investigations and develop the Detailed Design in accordance with the mandatory Employer’s Requirements. No additional document is issued by this clarification unless subsequently transmitted through an Addendum. | No
387 | Section VII – Employer’s Requirements / Vibration Mitigation Measures – Under-Ballast Mats and Mass-Spring Systems | Under-Ballast Mats (UBM) and Mass-Spring Systems (MSS) are specialized and high-cost vibration mitigation measures, the necessity, type and extent of which are normally determined based on the results of detailed noise and vibration analyses and the specific vibration sensitivity requirements along the alignment. In the absence of such analyses and corresponding design criteria within the Tender Documents, it is not possible for the Proposers to reliably determine the required locations, extent and technical characteristics of these systems and consequently to establish a consistent basis for pricing. The Employer is therefore kindly requested to identify and specify any particular locations/sections where Under-Ballast Mats, Mass-Spring Systems or other specific vibration mitigation measures are required. | Please refer to Section VII – Employer’s Requirements / Vibration Mitigation Measures – Under-Ballast Mats and Mass-Spring Systems. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, submit for the Engineer’s review/approval during Detailed Design. | No
388 | Section III – Evaluation and Qualification Criteria – Lot 3 Key Equipment / Structural Health Monitoring System | It is understood from the RFP Documents that one (1) Structural Health Monitoring System is required as key equipment under Lot 3. Considering that the Yavuz Sultan Selim (YSS) Bridge is an existing structure currently in operation, and that the Lot 3 Works involve the integration of the new railway infrastructure into the existing bridge structure, the Employer is kindly requested to clarify whether a Structural Health Monitoring (SHM) System is currently installed and operational on the YSS Bridge and, if so, whether the SHM System required under Lot 3 is intended to supplement, extend, interface with, or operate independently from the existing system. In this respect, the Employer is kindly requested to provide all available information and technical requirements relating to the SHM System envisaged under Lot 3, including, as applicable, the required monitoring parameters, sensor types and quantities, monitoring locations, data acquisition and communication architecture, software/platform requirements, integration/interface requirements with the existing bridge monitoring system, data storage and reporting requirements, and any requirements of Employer and/or the Bridge Operator, in order to enable all Proposers to establish a clear and consistent technical and commercial basis for their Proposals. | The Contractor shall provide the SHM System required for Lot 3 in accordance with the RFP and shall verify and coordinate any necessary interfaces with the existing bridge monitoring arrangements and the Bridge Operator during Detailed Design. The Contractor shall develop the monitoring parameters, sensor arrangement, data acquisition/communication architecture, software, storage and reporting provisions required to satisfy the Employer’s Requirements and obtain the necessary review/consent. | No
389 | Section I - Instructions to Proposers (ITP); 19. Securing the Proposal | Please confirm that the Proposers will furnish only Proposal Security as part of their Proposal, and confirm that Proposal-Securing Declaration is not applicable. | The Proposer shall submit only Proposal Security as specified in Section II – Proposal Data Sheet, ITP 19.3 and 19.3(d). A Proposal-Securing Declaration is not acceptable. | No
390 | Section VII – Employer’s Requirements / Annex G10 | "Is there a criterion with respect to applying balastless track for tunnels such as tunnel length? For which tunnels apart from tbm tunnels does the Client demand balastless track method?" | Please refer to Section VII – Employer’s Requirements / Annex G10. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
391 | Section VII – Employer’s Requirements / Annex G10 | " Is there a preliminary vibration noise analysis report of the track to determine in which tunnels mass spring system have to be applied?" | Please refer to Section VII – Employer’s Requirements / Annex G10. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
392 | Section VII – Employer’s Requirements / Annex G6, Annex G1, Annex G5, Annex G7 | "Could you clarify rail, sleeper and rail fastener types for ballasted tracks?" | Please refer to Addendum No. 2, Amendment No. 25 and ANNEXG. The nominal track gauge governing the Works is 1,435 mm and, for the ballasted main line, the B07 sleeper with W21 fastening system shall apply. | Yes
393 | Section VII – Employer’s Requirements / Annex B1 | "Could you kindly share layout plan and detailed cross sections of railway deck of YSS bridge?" | The Employer has provided the tender-stage reference/conceptual information available for preparation of the Proposal. The Project is Design-Build and the Contractor shall verify the information, carry out the necessary surveys/investigations and develop the Detailed Design in accordance with the mandatory Employer’s Requirements. No additional document is issued by this clarification unless subsequently transmitted through an Addendum. | No
394 | Section VII – Employer’s Requirements / Annex B1 | " Could you clarify numbers and locations of rail expansion joints that shall be installed on YSS bridge?" | Please refer to Addendum No. 2, Amendment No. 17, including the AYGM Rail Expansion Gasket (REG) Technical Specification added to the RFP Documents. The final need, locations and detailed arrangement of rail expansion devices shall be established through the Contractor’s Detailed Design in accordance with the applicable track–structure interaction requirements and shall be subject to the Engineer’s consent. | Yes
395 | Section IX – Particular Conditions, Contract Data – Sub-Clause 19.2.3(a) | The required Professional Indemnity Insurance limit is stated as not less than 20% of the Accepted Contract Amount. Considering the size and nature of the Project, such a requirement would result in an exceptionally high Professional Indemnity limit which is not commercially available in the international insurance/reinsurance market. Professional Indemnity capacity is subject to specific insurer and reinsurer capacity limitations and does not increase proportionally with the Contract Price. Therefore, we kindly request that the requirement be revised to a fixed limit of USD 50.000.000, which would provide a more reasonable and commercially insurable level of cover for the Project. | Please refer to Answer 300. | No
396 | Section IX – Particular Conditions, Contract Data – Sub-Clause 19.2.1(iv) | The wording “including but not limited to” under Sub-Clause 19.2.1(iv) creates an open-ended insurance obligation and should be deleted. This wording may extend the insurance obligation beyond the risks expressly listed under Sub-Clause 19.2.1(iv) to other Exceptional Events referred to under Sub-Clause 18.1, such as war, hostilities, rebellion, munitions of war and ionising radiation/radioactive contamination. These risks are excluded from CAR insurance and cannot be commercially insured. The risks listed under Subparagraph 18.1 are not covered by the insurance. This needs to be reiterated in this section. Accordingly, we kindly request the removal of the phrase “including but not limited to” in Sub-Clause 19.2.1(iv) . | Please refer to Section IX – Particular Conditions, Contract Data – Sub-Clause 19.2.1(iv). The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
397 | Section IX – Particular Conditions, Contract Data – Sub-Clause 19.2.1(iv) | Pursuant to Clause 19.2.1(iv), earthquake is listed among the risks that may not be excluded from coverage. In addition, Clause 19.2.1(a) requires that the insurance be arranged on a full replacement value basis. However, the tender documentation does not contain any provision regarding whether an earthquake coverage sub-limit/first loss limit may be applied. Considering both the seismic characteristics of the project location and the magnitude of the project value, it does not appear feasible under international insurance market practices to obtain earthquake coverage on a full replacement value basis without any sub-limit. For projects of this nature, earthquake coverage is customarily provided on a first loss basis with a specified sub-limit in line with prevailing market practice. In accordance with current market conditions and underwriting capacity, we consider an earthquake sub-limit of USD 500,000,000 to be reasonable and appropriate. Accordingly, we kindly request confirmation that earthquake coverage may be arranged subject to a sub-limit of USD 500.000.000. | Please refer to Section IX – Particular Conditions, Contract Data – Sub-Clause 19.2.1(iv). The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
398 | Section IX – Particular Conditions, Contract Data – Sub-Clause 19.2.1(iv) | Terrorism is expressly listed under Sub-Clause 19.2.1(iv)(g) and is generally subject to separate insurance/reinsurance market capacity and may require a separate Terrorism / Political Violence insurance placement. Please clarify whether a stand-alone Terrorism Insurance policy is required under the Contract. If so, please specify the required limit, scope of cover and deductible, taking into consideration commercially available insurance/reinsurance market capacity. | Terrorism is listed as a risk to be covered under Contract Data Sub-Clause 19.2.1(iv)(g). The Contractor shall provide the coverage required by the RFP and comply with the applicable permitted deductible limits under Sub-Clause 19.1. The RFP does not prescribe a separate standalone Terrorism/Political Violence policy or an additional separate limit or deductible through this clarification. | No
399 | Section IX – Particular Conditions, Contract Data – Sub-Clause 19.1, Permitted Deductible Limits | Pursuant to Clause 19.1, the maximum deductible applicable to the Works Insurance has been established at USD 1,000,000 per occurrence, and any deductible exceeding this amount is subject to the Employer's prior approval. The deductible levels demanded by the market for earthquake risk differ from the general deductible, and a certain percentage of the damage amount is applied along with a minimum amount. Is it possible to apply the generally accepted earthquake deductible in Türkiye, which is also included in the general specifications for construction works and the Turkish insurance tariff, as a co-insured deductible of 80%-20% and 2% with a deduction? | The RFP does not automatically permit the proposed 80/20 co-insurance arrangement or a 2% earthquake deductible. The maximum deductible for Works Insurance is USD 1,000,000 per occurrence; any deductible exceeding that amount requires the Employer’s prior approval under Contract Data Sub-Clause 19.1. Any proposed deductible structure must comply with the Contract and obtain prior approval where required. | No
400 | Section VII – Employer’s Requirements – Sections 4.7, 4.8.1 and 4.8.2; Section IX – Clause 19 | The Works interface with significant existing and operational assets, including the Yavuz Sultan Selim Bridge and Northern Marmara Motorway, operational TCDD infrastructure and airport facilities. Please confirm whether the property insurers of the Employer and/or the relevant asset owners will provide a waiver of subrogation in favour of the Employer and Contractor/JV and its Subcontractors in respect of such existing property and operational assets. In other words, please confirm whether the insurers of the existing operational assets will waive their rights of subrogation against the Employer, the Contractor/JV and its Subcontractors in respect of losses arising from activities carried out during the construction works. | Please refer to Section VII – Employer’s Requirements – Sections 4.7, 4.8.1 and 4.8.2; Section IX – Clause 19. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
401 | Section VII – Employer’s Requirements – Section 4.1 Multi-Contract Structure and Interface Management; Section VIII – General Conditions – Sub-Clause 17.2 | The Project comprises four separate civil Works Lots and a separate Signalling and Telecommunication package, with extensive interfaces between contractors. Sub-Clause 19.2.4 already requires a cross-liability clause between the Employer and the Contractor. Please confirm whether the insurance arrangements will also provide appropriate cross-liability / severability of interests provisions, where applicable, in respect of JV members and Subcontractors, and whether waiver of subrogation will apply among the Employer, Lot Contractors, Package 2 Contractor and other relevant project participants. | Sub-Clause 19.2.4 and the other applicable provisions of Clause 19 shall apply as stated. No additional cross-liability/severability-of-interests arrangement or waiver-of-subrogation requirement among JV members, Subcontractors, other Lot Contractors or the Package 2 Contractor is introduced through this clarification. No amendment is made to the RFP. | No
402 | Section IX – Particular Conditions, Contract Data – Sub-Clause 1.1.86 (Time for Completion) and Sub-Clause 1.1.95 (Milestones); Section VII – Employer’s Requirements – Section 4.9.4 Contractual Milestones | The Time for Completion is stated as 1826 days (60 months) from the Commencement Date. However, the Milestones under Sub-Clause 1.1.95 appear to be sequential: Milestone 1 – 12 months from the Commencement Date; Milestone 2 – 36 months from completion of Milestone 1; Milestone 3 – 12 months from completion of Milestone 2; and Milestone 4 – 24 months from completion of Milestone 3. This results in a cumulative period of approximately 84 months, which appears inconsistent with the overall Time for Completion of 1826 days. Please clarify this discrepancy and revise the Milestone durations accordingly so that all Milestones, including Testing and Commissioning Completion, fall within the contractual Time for Completion. This clarification is also required to determine the applicable insurance period and the premium to be calculated.. | Please refer to Answer 5. | No
403 | Section VII – Employer’s Requirements / Section 4.9.4 | Kindly confirm whether blasting is permitted for the excavation of the NATM tunnels within each Lot. If permitted, please also clarify whether any specific restrictions, requirements, or approval procedures shall apply to the blasting works. | Please refer to Section VII – Employer’s Requirements / Section 4.9.4. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
404 | Section VII – Employer’s Requirements / Clause 4.9.4 – Contractual Milestones; Section IX – Contract Data / Sub-Clause 1.1.95 – Milestones | Kindly confirm the following understanding of the contractual milestones: Milestone 2: Completion of tunnels, bridges, earthworks, cut&covers&,overpasses, underpasses, and culverts. Milestone 3: Commencement/completion of truckworks/ roadworks starting from subgrade level, including overpass pavement works, bridge waterproofing, and electrification works. Please confirm whether the above interpretation is correct. | Please refer to Addendum No. 2, Amendment No. 3, Contract Data Sub-Clause 1.1.95 and ER Clause 4.9.4. Milestone 2 is Infrastructure Works Completion, due by Month 46; Milestone 3 is Superstructure Completion, due by Month 58; and Milestone 4 is Testing and Commissioning Completion, due by Month 60 from the Commencement Date. The detailed scope of each Milestone is determined by ER Clause 4.9.4 and the applicable contractual requirements and priced Activities. | Yes
405 | Sections VIII–IX – Conditions of Contract / Particular Condition Part A Milestones & Time for Completion | We have noted an inconsistency between the stated Project Completion Period of 1,826 days and the durations of the contractual milestones. As the milestones are sequentially linked, Milestone 4, with a duration of 84 months from the Commencement Date, extends beyond the stated Project Completion Date of 1,826 days. Kindly clarify the applicable contractual completion date and confirm whether the duration of Milestone 4 or the overall Project Completion Period is to be revised. | Please refer to Answer 5. | No
406 | Section VII – Employer’s Requirements / Section 14.2 | We note that Section 14.2 provides provisions for the submission of alternative proposals, whereas ITP Clause 14.1 states that alternative proposals shall not be considered. Kindly clarify whether alternative proposals are permitted or not. | Please refer to ITP 14.1 and the PDS. Alternative Proposals are not permitted. Any generic provision elsewhere in the RFP relating to alternatives shall not override the PDS. | No
407 | Section VII – Employer’s Requirements / Annex K - Tunnel Electromechanical Works Technical Specification Reference; TSI SRT 2014 | Compliance with TSI requirements are mentioned in RFP documents, however, the rolling stock category is not clearly mentioned. If the rolling stock will be Category A (which is the case for other TCDD tunnels), then emergency rescue points will be required, which are not indicated in the design. | Please refer to Section VII – Employer’s Requirements / Annex K - Tunnel Electromechanical Works Technical Specification Reference, Annex B2 - railway Operation Plan; TSI SRT 2014. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
408 | Section VII – Employer’s Requirements / Request for Proposals Works. Design and Build Disclaimer — YSS Bridge: Information relating to the existing Yavuz Sultan Selim Bridge structure; made available within the Tender Documents is provided for reference only and represents the Employer’s; available information at the time of tender. The Employer does not warrant that such information is complete,; accurate, or sufficient for design purposes. The Contractor shall independently verify all structural, geometric,; operational, and loading parameters as part of its design investigation and assessment programme and shall; satisfy itself as to the suitability of the existing structure for the proposed Works | The RFP documents include a requirement for verification of the YSS Bridge. However, undertaking such verification at tender stage requires additional information and technical inputs from the Contractor/Client in order to properly assess the existing structure and evaluate any associated cost implications. Please confirm that, should sufficient information not be made available to enable verification of the existing superstructure during the tender stage, the Contractor shall not be responsible for any subsequent strengthening, modification, or remedial measures that may be identified as necessary for the YSS Bridge. | Please refer to Section VII – Employer’s Requirements / Request for Proposals Works. Design and Build Disclaimer — YSS Bridge: Information relating to the existing Yavuz Sultan Selim Bridge structure; made available within the Tender Documents is provided for reference only and represents the Employer’s; available information at the time of tender. The Employer does not warrant that such information is complete,; accurate, or sufficient for design purposes. The Contractor shall independently verify all structural, geometric,; operational, and loading parameters as part of its design investigation and assessment programme and shall; satisfy itself as to the suitability of the existing structure for the proposed Works. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
409 | Section VII – Employer’s Requirements / Annex A1 - 03_Cut_Fill_Inventory | In Cut and Fill Inventory «Dolgu» is written as Cut and «Yarma» As Fill which is not correct, We think English ones are correct. Please confirm | Confirmed. the English text shall prevail. | No
410 | Section VII – Employer’s Requirements / Input Data Required for GIR | Could you please provide kmz file for existing GI Points? Could you please provide seismic hazard report along the alignment ? Please provide the co-ordinate system and datum references to be followed for the project. | Please refer to Section VII, Clause 9.4 and Annexes C, E and F. Site-specific seismic hazard assessment and soil classification are part of the Contractor’s design investigation obligations. The resulting design parameters shall be established and verified by the Contractor and submitted through the Design Management process for the Engineer’s review/consent and any statutory review required by the applicable Turkish seismic regulations. | No
411 | Section VII – Employer’s Requirements / AYGM-INR-ALG-PLP-014 Type D- Bridge 5 & Bridge 6 plan & profile | Is there a specific reason why is Bridge 5 not connected with Bridge 6? Abutments in between are very high - almost 10m for start of Bridge 6. | Please refer to Section VII – Employer’s Requirements / AYGM-INR-ALG-PLP-014 Type D- Bridge 5 & Bridge 6 plan & profile. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
412 | Section VII – Employer’s Requirements / Input Data Required for Bridge Design | Is there any locations when piers are not allowed except on roads? Rivers? | Please refer to Section VII – Employer’s Requirements / Input Data Required for Bridge Design. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
413 | Section VII – Employer’s Requirements / Input Data Required for Cut & Cover | Is there a specific reason to backfill after 30m excavation? Environmental concerns. | Please refer to relevant requirements of Annex F and ESIA documents of the project. | No
414 | Section VII – Employer’s Requirements / Input Data Required for Passenger Capacity / Design Load Annex B1, §4.7, printed page 39; Annex B1, §4.8, printed page 40; Annex B2 – Railway Operation Plan, Table 10, printed page 37 | The RFP documents indicate different passenger capacities (584 passengers/train in Annex B1 and 400 passengers/trainset in Annex B2). Please confirm the governing rolling stock capacity and passenger design load to be adopted for station sizing and evacuation calculations. | Please refer to Answer 90. | No
415 | Section VII – Employer’s Requirements / Inconsitency for Cross Passage Distance; ; Annex B1- Conceptual Design Report; Annex B2 - INRAIL Railway Operation Plan Section VII of 9.3.4 pg.27; Annex B1, printed page 32; Annex B2, printed page 69 | As per INRAIL_RFP maximum 250 meter between cross passages mentioned in Section VII of 9.3.4 pg.272, on the other hand Annex B1 and Annex B2 pg.32 and pg.69 respectively, the passenger escape connections were denoted as 500 meters, which is line with conceptual design drawings. Please confirm which one to follow. | Please refer to Addendum No. 2, Amendment No. 10. | Yes
416 | Section VII – Employer’s Requirements / Part-2 Employer Requirements 5.7.3 Special Requirements | With reference to the requirement for coordination with the Bridge Authority regarding the planned maintenance regime, kindly provide the available bridge maintenance and operation schedule, including planned maintenance periods, possessions, operational restrictions, and any anticipated cable/hanger replacement activities. | The Employer has provided the tender-stage reference/conceptual information available for preparation of the Proposal. No additional bridge maintenance or operation schedule is issued by this clarification. The Contractor shall coordinate with the relevant Bridge Authority/Operator and obtain and verify the applicable maintenance schedules, operational restrictions, access requirements, planned maintenance periods and other relevant information necessary for the execution of the Works. Such requirements shall be taken into account in the Contractor’s planning, coordination and Detailed Design in accordance with the Employer’s Requirements. | No
417 | Section VII – Employer’s Requirements | Kindly confirm whether shaft construction is permitted at the Sabiha Gökçen Airport and Istanbul Grand Airport locations. If permitted, please clarify whether any specific permits, approvals, or special requirements are applicable to the shaft construction works within the airport premises. | Any proposed shaft works within the Sabiha Gökçen Airport or İstanbul Airport premises shall be subject to the Contractor’s Detailed Design and all applicable approvals and operational restrictions of DHMİ and the relevant airport operator, including access, security, obstacle-limitation, crane/temporary-works and working-hour requirements. No blanket approval for additional shaft construction is given through this clarification. No amendment is made to the RFP. | No
418 | Section III – Evaluation and Qualification Criteria | With respect to the requirement under Clause 4.2(b) of the Eligibility and Qualification Criteria, which requires “Experience in the construction of railway line with a route length of at least 20 km under a single contract” for each Lot, we kindly request the Employer to clarify what scope of works shall be considered as constituting “construction of railway line” for the purpose of this criterion. | For purposes of Section III, Item 4.2(b), “construction of railway line” shall be demonstrated by experience in the construction of a railway line (mainline railway/metro/tram) including infrastructure and superstructure under a qualifying contract, meeting the stated route-length and any other express requirements of the relevant Lot. | No
419 | Section III – Evaluation and Qualification Criteria | With respect to the requirement under Clause 4.2(b) concerning “Experience in the design of railway systems (including tunnels) with a route length of at least 20 km, under a single contract”, we kindly request the Employer to clarify the scope of systems that shall be considered as “railway systems” for the purpose of this criterion. | For the purpose of Item 4.2(b), the reference shall demonstrate experience in the design of a railway system, including tunnels, over the required route length. The criterion does not prescribe a separate exhaustive list of railway subsystems that must be included beyond the wording stated in Section III. No amendment is made to the RFP. | No
420 | Section III – Evaluation and Qualification Criteria / Item 4.2(b) – Key Activities and Applicable Footnotes | Clause 4.2(b) specifies that the relevant experience shall be demonstrated “under a single contract.” However, the relevant footnote states that “Volume, number, or rate of production of any key activity can be demonstrated in one or more contracts combined if executed during same time period. In this regard, we kindly request the Employer to clarify whether the experience requirement may be satisfied by combining the relevant quantities from two separate contracts executed during same time periods, notwithstanding the reference to a single contract in the respective criterion. | Please refer to Addendum No. 2, Amendment No. 8. | Yes
421 | Section VII – Employer’s Requirements | We kindly request the Employer to clarify whether a firm may participate in different joint ventures for different Lots under this RFP. | Please refer to Answer 60. | No
422 | Section III – Evaluation and Qualification Criteria | With respect to the EXP forms to be submitted for demonstrating the required experience, we kindly request the Employer to clarify whether the Proposer is required to indicate the specific Lot(s) for which each project reference is being submitted. If so, please clarify where and in what format such Lot identification should be provided in the EXP forms. | The Contractor/Proposer shall demonstrate the specific Lot(s) for which each project reference is being submitted by flling "RFP No. and title:" information in EXP forms. | No
423 | Section VII – Employer’s Requirements / Annex B1 | Regarding the statement in Annex B1 (Conceptual Design Report) - "Energy needs will be provided from nearby 154 kV lines of Türkiye Electricity Transmission Inc. with the train operation simulation studies, numbers, capacities and locations of traction transformers will be finalized" - could you please clarify if the contractor is responsible for the MV feeder lines? If so, kindly provide further information regarding the potential energy supply points along the project alignment. | Please refer to Section VII – Employer’s Requirements / Annex B1. The requirement shall be applied as stated in the relevant sections of RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design.The Contractor/Proposer shall be responsible for carrying out the necessary investigations and identifying the required MV feeder lines and potential energy supply points in coordination with the relevant utility authorities. | No
424 | Section VII – Employer’s Requirements / Annex B1 | Regarding the statement in Annex B1 (Conceptual Design Report) - "With providing escape tunnels, longitudinal mechanical ventilation for the tunnels longer than 1000m are required. Additionally, fire extinguishing will be established." - could you please provide further technical details on the fire extinguishing requirements? Specifically, is an automatic fire suppression system required for tunnels exceeding 1000m, or will a standard fire hydrant system be sufficient? | Please refer to Section VII – Employer’s Requirements / Annex B1. The requirement shall be applied as stated in the in the relevant sections of RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
425 | Section VII – Employer’s Requirements / Annex B1 | Regarding the statement in Annex B1 (Conceptual Design Report) - "Simulation programs (CFD, and similar) will be required to be used by the contractors for the emergency ventilation calculations at the stations and at the tunnels" - could you please confirm that this simulation study (CFD and similar) is not required as part of the contractor's tender submission package? | Please refer to Section VII – Employer’s Requirements / Annex B1. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
426 | Section VII – Employer’s Requirements | Could you please provide further technical information regarding the CCTV system's storage capacity requirements specifically for the tunnels and stations? | Please refer to Section VII – Employer’s Requirements. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, submit for the Engineer’s review/approval during Detailed Design. | No
427 | Section VII – Employer’s Requirements | Could you please provide further details regarding the water supply points required for both the tunnels and stations? | Please refer to Section VII – Employer’s Requirements. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
428 | Sections VIII–IX – Conditions of Contract | Could you please confirm that the Lot 1 Contractor will be responsible only for the CCTV, fire alarm and public announce systems within the stations and tunnels. Additionally, Lot 2 Signalling and Telecommunications Contractor will be responsible for the Camera-Based Security and Surveillance System along the trackworks, as well as the Passenger Pass Control (Fee Collection) System, Access Control System, Phone System, Radio System, Passenger Information System and SCADA System? | Please refer to Answer 29. | No
429 | Section VII – Employer’s Requirements | Kindly provide further technical details (spesific brand choice, communication protocol) if integration is required for the Lot 1 CCTV, PA systems to the Lot 2 SCADA system? | Please refer to Section VII – Employer’s Requirements. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
430 | Section VII – Employer’s Requirements | Please provide all available utility survey information, drawings, and GIS data showing existing Dry and Wet Utilities (including OHL utilities and transmission/distribution networks) within the Project corridor. Please also identify all known utility conflicts and indicate which utilities are expected to be relocated, diverted, protected, or modified as part of the Project scope. Any existing utility relocation/diversion studies and utility owners' information should also be shared. | Please refer to Answer 68. | No
431 | Section VII – Employer’s Requirements | Could you please confirm whether the Type E cut-and-cover structures starting at chainages 58+808 and 0+452 have already been constructed and are ready for use? | Please refer to Section VII – Employer’s Requirements. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
432 | Section VII – Employer’s Requirements / Annex K - Tunnel Electromechanical Works Technical Specification Reference; TSI SRT 2014 | Compliance with TSI requirements are mentioned in RFP documents, however, the rolling stock category is not clearly mentioned. If the rolling stock will be Category A (which is the case for other TCDD tunnels), then emergency rescue points will be required, which are not indicated in the design. | Please refer to Answer 407. | No
433 | Section VII – Employer’s Requirements / Request for Proposals Works / Design and Build Disclaimer — YSS Bridge: Information relating to the existing Yavuz Sultan Selim Bridge structure; made available within the Tender Documents is provided for reference only and represents the Employer’s; available information at the time of tender. The Employer does not warrant that such information is complete,; accurate, or sufficient for design purposes. The Contractor shall independently verify all structural, geometric,; operational, and loading parameters as part of its design investigation and assessment programme and shall; satisfy itself as to the suitability of the existing structure for the proposed Works | The RFP documents include a requirement for verification of the YSS Bridge. However, undertaking such verification at tender stage requires additional information and technical inputs from the Contractor/Client in order to properly assess the existing structure and evaluate any associated cost implications. Please confirm that, should sufficient information not be made available to enable verification of the existing superstructure during the tender stage, the Contractor shall not be responsible for any subsequent strengthening, modification, or remedial measures that may be identified as necessary for the YSS Bridge. | Please refer to Answer 408. | No
434 | Section VII – Employer’s Requirements / Annex A1 - 03_Cut_Fill_Inventory | In Cut and Fill Inventory «Dolgu» is written as Cut and «Yarma» As Fill which is not correct, We think English ones are correct. Please confirm | Please refer to Answer 409. | No
435 | Section VII – Employer’s Requirements / Input Data Required for GIR / NA | Could you please provide kmz file for existing GI Points? Could you please provide seismic hazard report along the alignment ? Please provide the co-ordinate system and datum references to be followed for the project. | Please refer to Answer 410. | No
436 | Section VII – Employer’s Requirements / AYGM-INR-ALG-PLP-014 / Type D- Bridge 5 & Bridge 6 plan & profile | Is there a specific reason why is Bridge 5 not connected with Bridge 6? Abutments in between are very high - almost 10m for start of Bridge 6. | Please refer to Answer 411. | No
437 | Section VII – Employer’s Requirements / Input Data Required for Bridge Design / NA | Is there any locations when piers are not allowed except on roads? Rivers? | Please refer to Answer 412. | No
438 | Section VII – Employer’s Requirements / Input Data Required for Cut & Cover / NA | Is there a specific reason to backfill after 30m excavation? Environmental concerns. | Please refer to Answer 413. | No
439 | Section VII – Employer’s Requirements / Input Data Required for Passenger Capacity / Design Load / Annex B1, §4.7, printed page 39; Annex B1, §4.8, printed page 40; Annex B2 – Railway Operation Plan, Table 10, printed page 37 | The RFP documents indicate different passenger capacities (584 passengers/train in Annex B1 and 400 passengers/trainset in Annex B2). Please confirm the governing rolling stock capacity and passenger design load to be adopted for station sizing and evacuation calculations. | Please refer to Answer 90. | No
440 | Section VII – Employer’s Requirements / Inconsitency for Cross Passage Distance; ; Annex B1- Conceptual Design Report; Annex B2 - INRAIL Railway Operation Plan / Section VII of 9.3.4 pg.27; Annex B1, printed page 32; Annex B2, printed page 69 | As per INRAIL_RFP maximum 250 meter between cross passages mentioned in Section VII of 9.3.4 pg.272, on the other hand Annex B1 and Annex B2 pg.32 and pg.69 respectively, the passenger escape connections were denoted as 500 meters, which is line with conceptual design drawings. Please confirm which one to follow. | Please refer to Answer 415. | No
441 | Section VII – Employer’s Requirements / INRAIL RFP – Section IV, Design Proposal, Item (g), p.145; Section VII, Clauses 11.2 and 11.4.1–11.4.2 / The Design Proposal requires a strategy for gathering baseline ES information in time to inform design development. Section VII identifies the ESIA, ESMP, ESCP, SEP, LMP, RF/RP/LRP and other E&S instruments as part of the applicable E&S framework. The ESIA and ESMP are identified as baseline documents prepared prior to final design. | Please provide the latest available versions/revisions of the Project ESIA, ESMP and associated E&S baseline studies, and confirm which documents and datasets shall be adopted as the reference E&S baseline for preparation of the tender design and the Environmental & Sustainability Strategy Report. | Please refer to Section VII – Employer’s Requirements / INRAIL RFP – Section IV, Design Proposal, Item (g), p.145; Section VII, Clauses 11.2 and 11.4.1–11.4.2 / The Design Proposal requires a strategy for gathering baseline ES information in time to inform design development. Section VII identifies the ESIA, ESMP, ESCP, SEP, LMP, RF/RP/LRP and other E&S instruments as part of the applicable E&S framework. The ESIA and ESMP are identified as baseline documents prepared prior to final design.. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
442 | Section VII – Employer’s Requirements / INRAIL RFP – Section IV, Design Proposal, Items (g) and (h), p.145; Section VII, Clause 11.5; Section VII – Site Information / Environmental and Social Baseline Data / The Proposer is required to describe how baseline E&S information will be gathered and incorporated into design development. The RFP also refers to existing E&S baseline information and additional surveys/studies that may subsequently be required. | Please provide all available GIS/KMZ/shapefile or equivalent spatial environmental datasets supporting the ESIA and related studies, including, where available, sensitive receptors, biodiversity/ecological constraints, protected or sensitive areas, watercourses, cultural heritage constraints, land-use information and existing environmental survey/monitoring locations, to support integration of E&S constraints into the tender design. | The RFP provides the tender-stage environmental and social information disclosed with the Project documents, including the applicable ESIA and related instruments. No additional GIS/KMZ/shapefile dataset is issued through this clarification. Proposers shall use the information formally disclosed with the RFP and undertake any further surveys or investigations required by the Employer’s Requirements and their proposed design. Any additional information subsequently issued by the Employer will be communicated to all Proposers in accordance with the RFP. | No
443 | Section VII – Employer’s Requirements / INRAIL RFP – Section IV, Design Proposal, Item (g), p.145; Section VII, Clauses 11.5.1–11.5.3 / Item (g) requires the Proposer to provide a “strategy for gathering baseline ES information in time to inform design development.” Section 11.5 subsequently requires the D&B Contractor to identify and undertake additional E&S studies and surveys during design finalisation and Project implementation where required. | Please confirm that, for the tender design stage, the requirement is to define the proposed baseline data-gathering methodology, data-gap assessment, future investigation/survey requirements and programme, and that no new environmental field surveys, sampling or monitoring are required to be undertaken during the tender period. | Please refer to Section VII – Employer’s Requirements / INRAIL RFP – Section IV, Design Proposal, Item (g), p.145; Section VII, Clauses 11.5.1–11.5.3 / Item (g) requires the Proposer to provide a “strategy for gathering baseline ES information in time to inform design development.” Section 11.5 subsequently requires the D&B Contractor to identify and undertake additional E&S studies and surveys during design finalisation and Project implementation where required.. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
444 | Section VII – Employer’s Requirements / INRAIL RFP – Section IV, Design Proposal, Item (f), p.145; Section IV, Sustainable Procurement Proposal, p.148 / The Design Proposal requires the Proposer to demonstrate its approach to Sustainable Procurement, including energy efficiency, reduction of wastage, material reduction and sources of materials. A separate Sustainable Procurement Proposal is also identified within the Technical Proposal Forms. | Please confirm whether any project-specific mandatory quantitative sustainability or sustainable procurement targets are applicable to the tender design, including targets or minimum requirements relating to energy efficiency, embodied carbon, material efficiency/reduction, recycled content, responsible sourcing, excavated-material reuse, waste reduction or other sustainability KPIs. Where applicable, please provide the relevant targets, standards and assessment criteria. | Proposers shall address the requirements and evidence specified in the RFP and may describe the project-specific targets and monitoring approach proposed for their Sustainable Procurement Proposal. No additional numerical thresholds are introduced by this clarification. | No
445 | Section VII – Employer’s Requirements / INRAIL RFP – Section IV, Design Proposal, Items (e)(i), (g), (h) and (j), p.145; Section VII, Clauses 11.5 and 11.12 / The Design Proposal requires consideration of the status of available information, baseline E&S information, incorporation of E&S requirements into design and Value Engineering considering ES issues. Section VII also identifies potential requirements for additional studies and biodiversity-related design considerations. | Please confirm whether the Employer has identified any specific environmental design constraints, avoidance/no-go areas, sensitive locations or outstanding baseline information gaps that shall be explicitly considered during tender design and Value Engineering, including those associated with biodiversity, sensitive receptors, noise and vibration, water environment, contaminated land, cultural heritage or other environmentally sensitive features. | Please refer to Section VII – Employer’s Requirements / INRAIL RFP – Section IV, Design Proposal, Items (e)(i), (g), (h) and (j), p.145; Section VII, Clauses 11.5 and 11.12 / The Design Proposal requires consideration of the status of available information, baseline E&S information, incorporation of E&S requirements into design and Value Engineering considering ES issues. Section VII also identifies potential requirements for additional studies and biodiversity-related design considerations.. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
446 | Section VII – Employer’s Requirements / INRAIL DRAWINGS; Typical Cross Sections for Cross Passages / Annex A - Drawings\Annex A1 - Alignment\01_4_Plan_Profile_Drawings | The Typical Cross Sections for the CPs have not been provided in the tender documents. Kindly provide the relevant cross sections. | The Employer has provided the tender-stage reference/conceptual information available for preparation of the Proposal. The Project is Design-Build and the Contractor shall verify the information, carry out the necessary surveys/investigations and develop the Detailed Design in accordance with the mandatory Employer’s Requirements. No additional document is issued by this clarification. | No
447 | Section VII – Employer’s Requirements / INRAIL DRAWINGS; Shaft Scope and Details / Annex A - Drawings\Annex A1 - Alignment\01_4_Plan_Profile_Drawings | Only four shafts are indicated along the alignment, and the available drawings appear to show only the piling arrangement. Please clarify whether additional permanent works, such as shaft lining, staircases, internal structural elements, access arrangements, MEP provisions, etc., are also required within these shafts. Furthermore, considering the locations of the indicated shafts, they do not appear to be ideally positioned to serve as ventilation shafts. Please confirm whether separate ventilation shafts are envisaged elsewhere along the alignment. | Please refer to Section VII – Employer’s Requirements / INRAIL DRAWINGS; Shaft Scope and Details / Annex A - Drawings\Annex A1 - Alignment\01_4_Plan_Profile_Drawings. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
448 | Section VII – Employer’s Requirements / INRAIL DRAWINGS; Ventilation Shafts at Sabiha Gökçen Station / Annex A - Drawings\Annex A3 - Architectural\Sabiha_Gokcen_Airport_Station | Typical cross sections and detailed drawings for the ventilation/exhaust shafts at Sabiha Gökçen Station have not been provided. Kindly provide the relevant typical sections, dimensions, and structural requirements. | No additional typical shaft drawings are issued through this clarification. The Contractor shall develop the required ventilation/exhaust shaft geometry, dimensions and structural design as part of Detailed Design, based on the tender-stage information and the applicable Employer’s Requirements. No amendment is made to the RFP. | No
449 | Section VII – Employer’s Requirements / INRAIL DRAWINGS; Istanbul Airport Concourse and Car Park Scope / Annex A - Drawings\Annex A3 - Architectural\Istanbul_Airport_Station | Please clarify whether the civil, structural, and architectural works associated with the Concourse at Istanbul Airport, including the car park structure located above the Concourse, are included within the Contractor’s scope of works. | Please refer to Section VII – Employer’s Requirements / INRAIL DRAWINGS; Istanbul Airport Concourse and Car Park Scope / Annex A - Drawings\Annex A3 - Architectural\Istanbul_Airport_Station. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
450 | Section VII – Employer’s Requirements / INRAIL DRAWINGS; Service Roads Along the Open Alignment / Annex A - Drawings\Annex A1 - Alignment\01_4_Plan_Profile_Drawings | Service roads are indicated along the sides of the open alignment; however, these roads appear to terminate without connecting to any existing or proposed road network. Please clarify whether permanent access connections to these service roads are envisaged and, if so, kindly provide the relevant layouts and connection details. | The Employer has provided the tender-stage reference/conceptual information available for preparation of the Proposal. The Project is Design-Build and the Contractor shall verify the information, carry out the necessary surveys/investigations and develop the Detailed Design in accordance with the mandatory Employer’s Requirements. No additional document is issued by this clarification. | No
451 | Section VII – Employer’s Requirements / INRAIL DRAWINGS; Scope of Works for the YSS Line / Annex A - Drawings\Annex A1 - Alignment\01_4_Plan_Profile_Drawings | Please confirm whether the scope of works along the YSS Line is limited to track substructure/foundations, track works, and electrification works. Kindly clarify whether any additional civil, structural, earthworks, or drainage works are expected to be carried out by the Contractor along this section. | Please refer to Section VII – Employer’s Requirements / INRAIL DRAWINGS; Scope of Works for the YSS Line / Annex A - Drawings\Annex A1 - Alignment\01_4_Plan_Profile_Drawings. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
452 | Section VII – Employer’s Requirements / INRAIL DRAWINGS; Cut & Cover 4A & 4B / Annex A - Drawings\Annex A1 - Alignment\01_4_Plan_Profile_Drawings | Please clarify whether these structures are existing structures or to be constructed by the Lot-3 Contractor. If to be constructed by Lot-3 Contractor, please provide temporary traffic management plan details to be implemented at these locations | Please refer to Section VII – Employer’s Requirements / INRAIL DRAWINGS; Cut & Cover 4A & 5A / Annex A - Drawings\Annex A1 - Alignment\01_4_Plan_Profile_Drawings. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
453 | Section VII – Employer’s Requirements / INRAIL DRAWINGS; Architectural / Landscaping Requirements at Entrance and Exit Portals / Annex A - Drawings\Annex A3 - Architectural | Please clarify whether any architectural, facade, aesthetic, or landscaping requirements are envisaged for the entrance and exit portal structures. | Please refer to Section VII – Employer’s Requirements / INRAIL DRAWINGS; Architectural / Landscaping Requirements at Entrance and Exit Portals / Annex A - Drawings\Annex A3 - Architectural. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
454 | Section I – Instructions to Proposers / INRAIL RFP; PART 1 – Request for Proposal Procedures; Section I - Instructions to Proposers (ITP); Clause 19 - Proposal Security / JV Proposal Security submission details | For JV's that has not yet been officially established: Can the Proposal Securities be issued and printed separately by the relevant reputable banks, in proportion to the JV Partners' respective shares? | Please refer to Answer 42. | No
455 | Section III – Evaluation and Qualification Criteria, Evaluation of Technical Part (ITP 31) | Under the technical evaluation methodology, please clarify the objective evaluation basis that will be used to distinguish between scores of 2 (“meets the requirement”), 3 (“marginally exceeds the requirement”), and 4 (“significantly exceeds the requirement”). In particular, are there any quantitative thresholds, benchmarks, or predefined performance criteria that will be applied? | The scores shall be determined by applying the descriptors and evidence requirements set out in Section III to the content of each Technical Proposal. A score of 2 means that the requirement is met; scores of 3 or 4 require evidence that the Proposal marginally or significantly exceeds the requirement, respectively, as described in the applicable criterion. The RFP does not prescribe additional universal quantitative thresholds or a separate formula for distinguishing these scores. | No
456 | Section III – Evaluation and Qualification Criteria, Similar Work Experience | Under Similar Work Experience, please clarify whether reference projects involving longer TBM/NATM tunnels, longer railway route lengths, or higher contract values will automatically receive higher technical scores. Alternatively, will scoring be based on the technical complexity, level of difficulty, and relevance of the reference projects to the INRAIL Project? | The Technical Part will be evaluated strictly in accordance with the Rated Criteria, scoring descriptors and maximum scores stated in Section III. A score above “meets the requirement” requires the Proposal to demonstrate, with relevant and verifiable evidence, performance that exceeds the stated requirement in a manner material to the criterion being assessed. | No
457 | Section III – Evaluation and Qualification Criteria, Lot 1 TBM Experience | For Lot 1, will a reference project demonstrating 30 km or 40 km of TBM tunnelling receive a higher technical score than a project satisfying the minimum 20 km TBM tunnelling requirement? If so, please clarify the evaluation methodology, applicable thresholds, and scoring principles. | The Technical Part will be evaluated strictly in accordance with the Rated Criteria, scoring descriptors and maximum scores stated in Section III. A score above “meets the requirement” requires the Proposal to demonstrate, with relevant and verifiable evidence, performance that exceeds the stated requirement in a manner material to the criterion being assessed. | No
458 | Section III – Evaluation and Qualification Criteria / RFP Requirements for Key Personnel and Multiple Lots | It is understood that the same Key Personnel may not be proposed for more than one lot at the proposal stage. If a Bidder submits Proposals for multiple lots but is awarded only one lot, may the Bidder replace the Key Personnel proposed for the awarded lot with another person originally proposed for a non-awarded lot, provided that such person meets or exceeds the applicable qualification requirements? | No automatic substitution is permitted solely because another Lot is not awarded. Any replacement of Key Personnel after Proposal submission/award is subject to the applicable RFP and Contract provisions and requires a replacement whose qualifications are at least equivalent and the Employer/Engineer’s approval where required. | No
459 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel (OHS Manager; OHS Engineer / Site Safety Engineer) | How will the equivalency of Occupational Health and Safety (OHS) certificates obtained in foreign countries be assessed? Please clarify the acceptable certificate types and minimum qualification requirements. |  | Yes
460 | Section III – Evaluation and Qualification Criteria, Railway Systems Experience | Will High-Speed Rail projects be accepted as eligible experience under the “railway systems” experience requirements? | Yes, High-Speed Rail experience may be considered as railway-system experience, provided that the submitted reference satisfies all other requirements of the relevant criterion in Section III. | No
461 | Section III – Evaluation and Qualification Criteria / RFP Equipment Requirements for Multiple Lots | Where Proposals are submitted for multiple lots, the same equipment may not be allocated to more than one lot. At the Proposal stage, will a letter of intent to lease be accepted as sufficient evidence of equipment availability, or is a binding lease agreement required? | Please refer to Form EQU and the related qualification requirements. The Proposer shall demonstrate that the proposed equipment will be available for the Works. Owned equipment shall be supported by ownership evidence; equipment to be leased, hired or specially manufactured shall be supported by an appropriate project-specific commitment/arrangement demonstrating availability. | No
462 | Section III – Evaluation and Qualification Criteria / RFP Equipment Requirements for TBMs | For TBM equipment, will a manufacturer reservation letter, purchase option, commitment for new production, or similar arrangement be accepted as sufficient evidence of equipment availability at the Proposal stage? | Please refer to Form EQU and the related qualification requirements. The Proposer shall demonstrate that the proposed equipment will be available for the Works. Owned equipment shall be supported by ownership evidence; equipment to be leased, hired or specially manufactured shall be supported by an appropriate project-specific commitment/arrangement demonstrating availability. | No
463 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Payment of Interim Payment Certificates | Monthly Interim Payment Certificates are payable within 56 days. In case of payment delays resulting from World Bank or other financing institution disbursement delays, what contractual protections will be available to the Contractor? | Please refer to Sub-Clause 14.8 and the other applicable remedies under the Contract. Where payment is delayed beyond the contractual due date, the Contractor’s entitlement to financing charges and any further contractual remedies shall be determined in accordance with the Contract. No additional protection is introduced by this clarification. | No
464 | Sections VIII–IX – Conditions of Contract / Schedule of Priced Activities and Interim Payments | Please clarify how mobilization costs and design-related activities will be measured, substantiated, and paid through the monthly interim payment process. | Please refer to the Addendum No. 2, Amendment No. 12. | Yes
465 | Sections VIII–IX – Conditions of Contract / Conditions of Contract and Pricing Documents, Provisional Sums | What procedure will apply to the use and payment of Provisional Sum items? In addition to the stipulated 5% allowance for overhead and profit, will the Contractor be entitled to claim any other fee, additional cost, or mark-up? | Please refer to the Schedule of Priced Activities, the Provisional Sum provisions and Clause 13. The use of a Provisional Sum is subject to the Engineer’s instruction and valuation in accordance with the Contract. The stated allowance for overhead and profit shall apply where provided in the RFP; no additional mark-up is payable unless expressly permitted by the Contract. | No
466 | Sections VIII–IX – Conditions of Contract / Proposal Currency and Conditions of Contract, Currency Risk | Although the Proposal currency is Turkish Lira, certain inputs are expected to be procured in foreign currencies. Will the foreign exchange risk be borne entirely by the Contractor, or does the Contract provide any adjustment or protection mechanism in this respect? | Please refer to Clarification Response No. 815. | No
467 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Price Adjustment Formula | It is understood that the Contractor will propose the coefficients to be used in the price adjustment formula. Please clarify the criteria the Employer will apply when accepting or rejecting the proposed coefficients, including any permitted ranges. | Please refer to Sub-Clause 13.7 and the Appendix to Proposal – Table of Adjustment Data. The Proposer shall specify the applicable coefficients within the ranges prescribed in Tables A and B, and the total weightings shall equal 1.00. The Employer will assess the proposed coefficients for compliance with these requirements. | No
468 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Price Adjustment and Provisional Sums | Will the price adjustment provisions also apply to work executed under Provisional Sum items? | Price adjustment is not automatically applied to all Provisional Sum expenditures. Amounts used from Provisional Sums shall first be valued in accordance with Sub-Clause 13.4, and any price adjustment shall apply only to the extent permitted under Sub-Clause 13.7 and the applicable valuation basis. | No
469 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Variations under the Lump Sum Design and Build Contract | What is the maximum permissible limit for Variations or increases in scope under the Lump Sum Design and Build Contract? | Please refer to Clause 13. Variations, including Employer-instructed design changes, and any resulting valuation shall be administered in accordance with the Contract. Where no applicable Contract rate or price exists, the Engineer shall determine an appropriate rate or price in accordance with the valuation provisions of Clause 13. No separate maximum variation percentage is introduced by this clarification. | No
470 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Valuation of New Items | If new work items arise under the Contract, what methodology and order of precedence will be used to determine new rates? Will valuation be based on cost analysis, prevailing market rates, or comparison with similar Contract items? | Please refer to Clause 13. New work items shall be valued using applicable Contract rates or prices where appropriate. Where no applicable rate or price exists, the Engineer shall agree or determine an appropriate new rate or price in accordance with the valuation provisions of the Contract. | No
471 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Employer-Instructed Design Changes | What procedure will apply to the determination and payment of additional amounts arising from Employer-instructed design changes? | Please refer to Clause 13. Variations, including Employer-instructed design changes, and any resulting valuation shall be administered in accordance with the Contract. Where no applicable Contract rate or price exists, the Engineer shall determine an appropriate rate or price in accordance with the valuation provisions of Clause 13. No separate maximum variation percentage is introduced by this clarification. | No
472 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Extension of Time and Third-Party Delays | Will delays arising from actions, approvals, permits, or coordination processes of third-party entities such as TCDD, KGM, DHMI, IGA, TAV, DSI, or TEIAS, and not attributable to the Contractor, constitute grounds for an Extension of Time? | Entitlement to an Extension of Time shall be determined in accordance with Sub-Clause 8.5 and the other applicable provisions of the Contract. A delay by a third party does not automatically constitute an Employer-risk event; entitlement depends on the cause, allocation of responsibility under the Contract, critical-path effect, notice and substantiation. | No
473 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Performance Securities | Will the 6% Performance Security and the 1% Environmental and Social Performance Security be submitted simultaneously? Please clarify the conditions and timing for the partial or full release of the Environmental and Social Performance Security. | Yes. The Performance Security and ES Performance Security shall both be furnished within twenty-eight (28) days after receipt of the Letter of Acceptance, in the amounts stated in Contract Data Sub-Clause 4.2. Their maintenance and release shall be governed by Sub-Clause 4.2 and the applicable security forms. No separate partial-release mechanism is introduced. | No
474 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Environmental and Social Performance Security | What breaches, defaults, or non-compliance events may result in a partial or full call on the Environmental and Social Performance Security? Will any notice and cure period apply before such a call is made? | The ES Performance Security may be called where the Contractor is in breach of its Environmental and/or Social obligations and the Employer is entitled to the claimed amount under the Contract. Any notice or cure requirements applicable to the underlying breach shall be governed by the relevant Contract provisions; no separate general cure period applies solely to a call under the ES Performance Security. | No
475 | Section VII – Employer’s Requirements / Lot 1 and Lot 4 TBM Tunnels | Could the Employer provide the binding design criteria for the anticipated excavation diameters and the acceptable or envisaged TBM types (EPB, Slurry, Hard Rock, or equivalent) for the TBM tunnel sections under Lot 1 and Lot 4? | Please refer to the tunnel geometry requirements in Annex A and the applicable tunnel Technical Specifications. The mandatory excavation/internal dimensions shall govern, and any corresponding adjustment to the TBM excavation area shall be reflected in the applicable payment price. Selection of the TBM type is the Contractor’s design and construction-method responsibility based on the available geotechnical information and its additional investigations, subject to compliance with the RFP, TSI-SRT requirements and the Engineer’s consent. No specific TBM technology is mandated unless expressly stated in the RFP. | No
476 | Section VII – Employer’s Requirements / Schedule of Priced Activities and Sub-Activities, Progress Measurement | It is understood from the RFP Documents that payments will be made on a lump-sum basis through the Schedule of Priced Activities and Sub-Activities. However, no detailed provisions have been identified regarding progress measurement for interim payment purposes. In this respect, please clarify: (i) whether the Progress Measurement Methodology and Activity Weighting Schedule for each activity and sub-activity will be prepared by the Contractor after Contract award and submitted to the Employer/Engineer for approval, or whether the Employer has a predefined methodology; and (ii) if the methodology is to be prepared by the Contractor, whether any specific format or procedure governs the relationship between the approved Level 4 Programme, the priced activity schedules, and monthly interim payment applications. | Please refer to Answer 7. | No
477 | Sections VIII–IX – Conditions of Contract / Conditions of Contract, Retention Money | May the Contractor provide a Retention Money Security for an equivalent amount in lieu of the 5% retention deduction from interim payments, thereby allowing Interim Payment Certificates to be paid without retention deductions from the commencement of the Contract? | No. Retention Money Security is not acceptable. Please refer to the Contract provisions governing Retention Money. Retention shall be deducted and released in accordance with the Contract. A Retention Money Security may be used only where expressly permitted by the Contract; no additional substitution mechanism is introduced by this clarification. | No
478 | Section III – Evaluation and Qualification Criteria, Article 2 Evaluation of Technical Part (ITP 31) | Article 2, Evaluation of Technical Part (ITP 31), of Section III – Evaluation and Qualification Criteria includes the following sub-criteria: 2.2.3. Evidence of resource-cash flow alignment management on prior comparable projects - 0.50 point 2.3.3. Evidence of the bidder's track record in achieving mobilization targets on comparable contracts - 0.50 point 3.2.5. Experience managing delivery in live - 1 point 3.1.2 Diversity of geotechnical conditions managed across referenced projects - 3 points 3.2.5. Experience managing delivery in live or operationally constrained railway environments - 1 point 3.3.1. Experience in contracts involving interfaces between different types of transport infrastructure encompassing integration or coordination with terminal/stations or road networks - 3 points 3.3.2. Experience managing delivery within live or operationally constrained environments — including operational transport infrastructure — where works must be phased, sequenced, or isolated to avoid disruption to ongoing operations - 3 points 5.1.4 Evidence of QA/QC comparable projects - 1 point 5.2.3 Evidence of the Bidder's LTIFR on comparable projects – 0.5 point 5.3.5 Past implementation evidence – 0.4 point 5.4.3 Evidence of comparable biodiversity management on infrastructure projects – 1 point 6.2.3.Evidence of outcome-driven mitigation on comparable projects - 1 point 6.4.3.Evidence of successful value engineering implementation on comparable contracts - 1 point 7.1.3 Evidence of the Bidder's track record in achieving comparable circular resource targets on prior projects – 1 point 7.2.4. Implementation of an energy/carbon reporting scheme ensuring continuous tracking and quantitative assessment of reductions against the baseline - 0.5 point 7.3.3 Evidence of waste management compliance performance on comparable projects – 1 point 8.1.5 Evidence of workforce management performance on comparable labour-intensive contracts – 1 point We understand that, for the above technical evaluation sub-criteria, the Bidder is expected to describe the relevant practices and measures implemented on comparable completed and/or ongoing projects and provide supporting documentary evidence demonstrating such experience and performance. Could you please confirm whether our understanding is correct? | Confirmed. For Rated Criteria that seek evidence of prior performance or implementation, the Proposer shall describe the relevant practices/measures and provide sufficient verifiable supporting evidence from comparable completed and/or ongoing projects, as applicable to the wording of each criterion. The evaluation will be based on the evidence submitted against the stated scoring descriptors. | No
479 | Sections VIII–IX – Conditions of Contract | It is estimated that approximately 27 million m³ of excavation material will require disposal. Istanbul’s total disposal capacity is stated to be approximately 49 million m³; however, this capacity has not been confirmed. Furthermore, the combined capacity of the disposal facilities listed in the ESIA is approximately 22 million m³. In this context, it is stated that the Employer will prepare a Soil & Excavated Material Management Plan (S-EMMP)and coordinate the disposal of the excavated material. Could you please clarify when the S-EMMP is expected to be prepared and made available to the Contractor(s)? | Preparing site-specific environmental, social and occupational health and safety documents will be part of the contractual requirements of the D+B Contractor. Please refer to the Environmental and Social Section of the Employer’s Requirements. In this context, the Excavated Material & Land Management Plan, as part of the C-ESMP, will be prepared by the relevant D+B Contractor based on the final design, construction methodology, excavation quantities, reuse opportunities, disposal arrangements and haulage planning. This approach is intended to allow the D+B Contractor sufficient flexibility to develop its own excavation material management strategy in line with its final design, construction methodology and implementation programme, while complying with the applicable Project E&S requirements. Accordingly, the Contractor will be responsible for identifying and confirming suitable reuse and disposal options and their available capacities, and for planning and managing the excavation material accordingly. No separate Employer-prepared S-EMMP is currently planned to be issued to the Contractor. | No
480 | Section VII - Employer's Requirements, Clause 5.2.2 (Contractor's Knowledge of the Site) and Clause 5.8.3 (Belgrad Formation - Special Conditions for Swelling Clay). | To enable the Contractor to prepare its bid on rational, non-speculative parameters and to preserve the commercial balance between the Parties, will the Employer issue a Geotechnical Baseline Report (GBR) defining tender baseline values, including maximum swelling pressure, cohesion and other relevant parameters? If no GBR will be issued, where geotechnical parameters established through laboratory testing during excavation materially exceed the indirect values contained in the tender Geological Data Report (GDR), will such conditions be treated as Unforeseeable Physical Conditions under FIDIC Sub- Clause 4.12? | The Employer has provided the geological and geotechnical information forming part of the RFP and available for tender purposes. Such information is tender-stage information and shall be read together with Annex C and the other Site Information. The Contractor remains responsible for carrying out the additional investigations and verification necessary for its Detailed Design and construction methodology. No additional geotechnical information is issued by this clarification. | No
481 | Section VII – Employer’s Requirements / Annex C1 - Geological Data Report, Table 11 (Geotechnical Parameters Status Summary). | If mandatory boreholes and laboratory tests undertaken during detailed design establish swelling pressures in the benionitic clays of the Belgrad Formation that exceed the assumptions of the conceptual design and require an increase in segmental lining thickness, concrete grade (minimum C38), or strengthening of segment and face-support systems, will such additional - works be treated under FID{C Sub-Clause 4.12 as consequences of Unforeseeable Physical Conditions? | The Employer has provided the geological and geotechnical information forming part of the RFP and available for tender purposes. Such information is tender-stage information and shall be read together with Annex C and the other Site Information. The Contractor remains responsible for carrying out the additional investigations and verification necessary for its Detailed Design and construction methodology. No additional geotechnical information is issued by this clarification. | No
482 | Section VII - Employer's Requirements, Clause 5.4.2 (Gas Risk - Special Conditions) and Annex C1 - Geological Data Report, Clause 8.6. | Will archival mining maps relating to former coal mines in the surrounding area, together with historical gas measurements and geological records abtained by the Employer and/or the General Directorate of Highways (KGM) during construction of the motorway tunnels, be issued to tenderers by addendum as Reference Documents? | Please refer to Section VII - Employer's Requirements, Clause 5.4.2 (Gas Risk - Special Conditions) and Annex C1 - Geological Data Report, Clause 8.6.. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
483 | Section VII – Employer’s Requirements / Geotechnical Design Specification (Annex E3) and GDR Clause 5.1. | lf detailed site investigations establish that the competent rockhead beneath viaduct piers is deeper than shown in the conceptual profiles, will the additional bored-pile lengths and increased socket depths necessarily resulting from this condition be paid as additional work through an applicable unit-price mechanism? To what extent is this uncertainty deemed included in the Lump-Sum Price? | Please refer to Section VII – Employer’s Requirements / Geotechnical Design Specification (Annex E3) and GDR Clause 5.1.. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
484 | Section VII – Employer’s Requirements / Clause 5.3.2; Railway Bridge Design Technical Specification (Annex E4), Section 1.3; and Annex B1 - Conceptual Design Report, Clause 5.3.2 and Section 5.3. | Where the new railway drainage structures are designed to the current 500-year/1,000-year DSI criteria but the adjacent motorway structures remain capacity-limited to their earlier 100-year design basis, which Party will bear responsibility for backwater effects, ponding, railway embankment instability and scour arising between the two corridors? Will AYGM be responsible for coordinating with KGM regarding enlargement or modification of the adjacent motorway structures? Furthermore, will additional hydraulic protection, slope stabilization and drainage works necessitated by the existing motorway design be excluded from the Lump-Sum Price and instructed and paid as a Variation under FIDIC Clause 13? | Please refer to Fidic Clause 13. Variations, including Employer-instructed design changes, and any resulting valuation shall be administered in accordance with the Contract. | No
485 | Section VII – Employer’s Requirements / Railway Bridge Design Technical Specification (Annex E4), Section 1.3, and Superstructure Works Construction Specification (Annex G1). | If detailed BT] analyses demonstrate that Rail Expansion Joints, not shown in the conceptual design and not included in the Bill of Activities, are required on certain Lot 4 bridges for structural safety and compliance with UIC 774-3, will the supply and installation of these special track components and the associated bridge-deck modifications be excluded from our Lump-Sum Price and treated as a Variation under FIDIC Clause 13? | Please refer to Addendum No. 2, Amendment No. 17, including the AYGM Rail Expansion Gasket (REG) Technical Specification added to the RFP Documents. The final need, locations and detailed arrangement of rail expansion devices shall be established through the Contractor’s Detailed Design in accordance with the applicable track–structure interaction requirements and shall be subject to the Engineer’s consent. | Yes
486 | Section VII - Employer's Requirements, Clause 5.8.2 (Site and Station Works - Istanbul Airport Station). | Will a joint Site Handover and Defect Identification Protocol be prepared at commencement and signed by the Employer, the existing airport operator (IGA) and the Contractor, recording the design-life condition, structural integrity, waterproofing quality, cracks and water ingress of the existing shell? Please confirm that the Contractor will not be liable for damage arising after handover from latent defects in the existing structure, including water ingress caused by pre-existing waterproofing defects damaging finishes or E&M systems. | Please refer to Section VII – Employer’s Requirements, including the requirements relating to existing infrastructure, Istanbul Airport Station and interface coordination with the Airport Operator. The Contractor shall inspect, verify and assess the existing station structure and available as-built information and shall carry out the investigations and condition assessments required under the RFP. The necessary joint inspections and condition assessments shall be carried out with the Engineer/Employer, and a Site Handover Record documenting the existing conditions shall be prepared accordingly. Interface arrangements with İGA shall be established in accordance with the applicable requirements of the RFP. Responsibility for any defect, damage or condition affecting the Works shall be determined in accordance with the Contract, taking into account its cause and the Contractor’s obligations in respect of the existing structure. | No
487 | Section VII – Employer’s Requirements / Annex B1 - Conceptual Design Report, Clause 4.8.2, and Employer's Requirements, Clause 5.8.2 | If detailed design demonstrates that the existing partition wall does not satisfy the required fire-resistance limits under NFPA 130 and the Turkish Regulation on Fire Protection of Buildings (BYKHY), or cannot resist the high piston/aerodynamic pressure effects generated by heavy freight trains, will structural strengthening, thickening or fire-resistant lining of the wall be treated as a Latent Defect of the Existing Structure and paid by the Employer within Lot 4? | Please refer to Section VII, Clause 9.3 and Addendum No. 2, Amendment No. 10. The fire/life-safety design shall comply with the applicable SRT-TSI, BYKHY and the other standards expressly retained by the RFP and subject to approval of Engineer/Employer. | No
488 | Section VII - Employer's Requirements, Clause 4.8.2 (Interface with Airport Operators). | Will the Project Coordination Committee (PCC) established by AYGM act as the central facilitator on behalf of the Contractor to expedite airspace/obstacle-limitation approvals with DHMi and IGA? Where delays arise from DHMI’s approval process, will such delays constitute grounds for an Extension of Time (EOT) under FIDIC Sub-Clause 8.5? | Entitlement to an Extension of Time shall be determined in accordance with Sub-Clause 8.5 and the other applicable provisions of the Contract. A delay by a third party does not automatically constitute an Employer-risk event; entitlement depends on the cause, allocation of responsibility under the Contract, critical-path effect, notice and substantiation. | No
489 | Section VII - Employer's Requirements, Clause 4.8.2 (Interface with Airport Operators), and Stations Control and Communication System Technical Specification (Annex M2). | Where open-ended security requirements, operational outage restrictions or access constraints imposed by IGA and DHMI during connections and integration with the existing Istanbul Airport MEP and fire-detection networks result in delay or additional civil-protection/night-working costs, will the Contractor be entitled to additional time and payment? May the Contractor assume that such unforeseeable operational restrictions are excluded from the Lump-Sum Price? | Please refer to Section VII - Employer's Requirements, Clause 4.8.2 (Interface with Airport Operators), and Stations Control and Communication System Technical Specification (Annex M2).. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
490 | Section VII – Employer’s Requirements / Annex B2 - INRAIL Railway Operation Plan, Section 6.4 (Catalca-Halkali wye connection), and Section VIl, Clause 4.7. | If the final geometric layouts prepared by the Contractor under Package 1 are subsequently required to be revised by the Package 2 Signalling Contractor or TCDD for operational-safety reasons, will resulting changes to switch locations and track geometry be treated as Variations under FIDIC Clause 13? If TCDD approvals for live-line connections at the Catalca junction are delayed, will the Contractor's entitlement to EOT be preserved? | Please refer to Fidic Clause 13. Variations, including Employer-instructed design changes, and any resulting valuation shall be administered in accordance with the Contract. | No
491 | Section VII - Employer's Requirements, Clause 4.6 (Power Supply and System-Wide Simulation) and Clause 5.3.3. INRAIL Project Lot 4 ¦ Official Clarification Requests ¦ English Version UM ¢ | If there is a material parameter mismatch between the simulations prepared by the Lot 2 and Lot 4 Contractors, what duration has been allowed in the Master Programme for the Engineer's reconciliation process? If simulation results lead the Employer to change substation locations or capacities, including cancellation or relocation of Traction Substation 3 at km 18+600 from Lot 4 to another lot, what commercial mechanism will apply to the omission/adjustment of the corresponding priced activity (Activity 10.3)? | Please refer to Answer 118. | No
492 | Section VII - Employer's Requirements, Clause 4.5.3 (Signalling Interface Target Dates). | Please confirm that delays in interface sign-off by the Package 2 Signalling Contractor will not prevent Taking-Over of our completed civil works and Lot 4, and that the Contractor's entitlement to EOT and associated prolongation costs/site overheads will be preserved in respect of such delays. | Please refer to Section VII - Employer's Requirements, Clause 4.5.3 (Signalling Interface Target Dates).. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
493 | Section VII - Employer's Requirements, Clause 4.5.3, and Signalling General Technical Specification (Annex L). | If, during the Phase 2 interface process, the subsequently appointed Package 2 Contractor requires revisions to frozen civil designs, including equipment-room dimensions, HVAC capacities or cable-duct routes, to suit its own equipment requirements, will such revisions be treated as Employer Variations? Will the resulting additional cost and time be compensated through additional payment and EOT? | Please refer to Fidic Clause 13. Variations, including Employer-instructed design changes, and any resulting valuation shall be administered in accordance with the Contract. | No
494 | Section VII – Employer’s Requirements / Signalling, Telecommunication and Support Systems Specification (Annex L) and Section VII, Clause 10.1 (Systems Installation). | Are the high-capacity AC supply lines and local distribution transformers required for Point Heating included in the Contractor's scope up to the connection point of the local electricity distribution company (BEDAS/TEDA$)? Who is responsible for open- ended participation, connection and network charges imposed by the distribution company? Please confirm whether such third-party connection charges are excluded from the Lump-Sum Price. | Please refer to Section VII – Employer’s Requirements / Signalling, Telecommunication and Support Systems Specification (Annex L) and Section VII, Clause 10.1 (Systems Installation).. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
495 | Section VII – Employer’s Requirements / Section ¦X - Particular Conditions (PCC), Sub-Clause 13.4, and Section VII - Employer's Requirements, Clause 11.11. INRAIL Project Lot 4 ¦ Official Clarification Requests ¦ English Version iM v * | For physical expenditures, in-kind support or subcontract works implemented by the Contractor from this Provisional Sum, will the 5% overhead and profit mark-up defined under PCC. Sub-Clause 13.4(b)(ii) apply? What operational mechanism will the Employer establish for verification and approval by the Engineer and PIOC so that the payment-certification chain does not adversely affect the Contractor's Interim Payment Certificate (IPC) cash flow? | Please refer to the Schedule of Priced Activities, the Provisional Sum provisions and Clause 13. The use of a Provisional Sum is subject to the Engineer’s instruction and valuation in accordance with the Contract. The stated allowance for overhead and profit shall apply where provided in the RFP; no additional mark-up is payable unless expressly permitted by the Contract. | No
496 | Section IX - Particular Conditions (PCC), Sub-Clause 2.1 (Right of Access to the Site), and Section Vil - Employer's Requirements, Clauses 11.4.7 and 11.10.2. | Where the Contractor submits all E&S plans and designs on time but sectional access is delayed due to the Employer's land- acquisition process, PIOC review periods or extension of the Word Bank No-Objection process, will the Contractor be entitled to EOT and Prolongation. Costs under FIDIC Sub-Clauses 8.4/8.5? | No blanket entitlement is confirmed. Delays associated with the preparation, revision, review or approval of E&S documents, including the applicable World Bank No-Objection process, shall not give rise to EOT or additional payment where excluded by Clause 11.4.7. Any delay in Site access arising from the Employer’s land-acquisition responsibilities shall be assessed separately under Sub-Clauses 2.1 and 8.5, subject to causation, critical-path impact, notice and substantiation requirements. | No
497 | Section VII – Employer’s Requirements / General Technical Specification (Annex D), Clauses A.2.2.2 and A.2.14. | Will works required to identify and relocate unforeseen utility lines that are not shown in the utility drawings issued with the Contract, are absent from public-authority records, or pass through private-property boundaries be excluded from the Lump- Sum Price and treated as a Variation with corresponding additional time? | Please refer to Section VII – Employer’s Requirements, including Clause 6.4 – Utility Records and the requirements relating to utility identification, verification, protection and relocation. The utility information provided in the RFP is indicative, and the Contractor shall be responsible for identifying, verifying and coordinating existing utilities and for carrying out the required protection and relocation works within its contractual scope. The fact that a utility is not shown in the Tender Documents or is absent from available authority records shall not, by itself, constitute a Variation or give rise to an entitlement to additional time or payment. Any entitlement arising from particular circumstances shall be determined in accordance with the Contract. | No
498 | Section VII – Employer’s Requirements / Geological Data Report (Annex C1), Clause 10.3, and ESIA Section 6 | If contaminated soil is encountered during excavation in areas classified in the tender documents as clean/non-contaminated, will the additional environmental and logistics costs associated with excavation, testing, transport by specially licensed vehicles and disposal at authorized facilities such as STAG be treated as a Variation under FIDIC Clause 13? | Please refer to Section VII – Employer’s Requirements, including the applicable Environmental and Social requirements relating to soil contamination, excavated material and waste management. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and during execution of the Works. Please refer to Fidic Clause 13. Variations, including Employer-instructed design changes, and any resulting valuation shall be administered in accordance with the Contract. | No
499 | Section VII – Employer’s Requirements / BIM Technical Specification (Annex O) and ESIA/ESMP requirements. | Where excavation works are suspended by Conservation Boards or other competent authonities due to archaeological Chance Finds in accordance with the Cultural Heritage Management Plan and national legislation, will such suspension entitle the Contractor to an Extension of Time? Will the Employer compensate the resulting Idle Time costs of tunnel and site crews/equipment? INRAIL Project Lot 4 ¦ Official Clarification Requests ¦ English Version | Please refer to Fidic Clause 13. Variations, including Employer-instructed design changes, and any resulting valuation shall be administered in accordance with the Contract. Entitlement to an Extension of Time shall be determined in accordance with Sub-Clause 8.5 and the other applicable provisions of the Contract. A delay by a third party does not automatically constitute an Employer-risk event; entitlement depends on the cause, allocation of responsibility under the Contract, critical-path effect, notice and substantiation. | No
500 | Section VII – Employer’s Requirements / Chapter 6 – Site Information / Clause 4 – Utility Records | With reference to the “Employer's Requirement, Chapter 6 Site Information, 4 Utility Records (page 254)”, the following statement indicates that data regarding existing infrastructure and utilities is available: “...The utility information presented is indicative and based on available secondary data and official correspondence.” However, no data is available for existing infrastructure lines in the Tender Documents. Please share the relevant data regarding existing infrastructure lines. | Please refer to Answer 68. | No
501 | Section VII – Employer’s Requirements / Chapter 6 – Site Information / Clause 4 – Utility Records; Section IV – Schedule of Priced Activities / Relocation of Existing Infrastructure | No data is available for existing infrastructure utility lines in the Tender Documents. In case the Employer is unable to share the data regarding existing infrastructure and utilities, we request that the item for "Relocation of Existing Infrastructure" be paid as a provisional sum since it is not possible to provide such data from the relevant competent authorities as a Bidder in Tender Stage. Please clarify. | Please refer to Answer 68. | No
502 | Section IV – Proposal Forms – Schedule of Priced Activities / DAAB | Pricing of establishment and operation of the DAAB should not be considered as a subject of competition for Bidders as the process is not solely dependent on the Contractor's decisions. We kindly suggest either including the DAAB cost in the provisional sum or specifying a fixed price by the Employer for the related item, to have fair competition. | The Schedule of Prices for each Lot already includes items covering the establishment and operation of the DAAB. Furthermore, Part B – Special Provisions, Sub-Clause 13.4 (Provisional Sum), provides that the Employer’s share of the DAAB members’ fees and expenses shall be financed from the Provisional Sum. The DAAB Agreement sets out the applicable payment arrangements, including the portion of fees and expenses to be borne by the Contractor. Accordingly, Bidders shall price the relevant items in accordance with the existing RFP provisions | No
503 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Table C – Provisional Sums | With reference to Schedule of Priced Activities, Provisional Sum is listed as follows for each Lot: P.1 Provisional Sums: Lot 1 – TL 736,000,000.00; Lot 2 – TL 433,000,000.00; Lot 3 – TL 403,000,000.00; Lot 4 – TL 702,000,000.00 P.2 Livelihood support: Lot 1 – TL 800,000,000.00; Lot 2 – TL 450,000,000.00; Lot 3 – TL 450,000,000.00; Lot 4 – TL 750,000,000.00. However, with reference to the Section IV – Proposal Form, Table C (page 100), Provisional sums expressed in local currency are listed as only TL 736,000,000.00 for Lot 1, TL 433,000,000.00 for Lot 2, TL 403,000,000.00 for Lot 3, TL 702,000,000.00 for Lot 4. Please clarify the contradiction regarding the amount of provisional sums. | Please refer to Addendum No. 2, Amendment No. 41. | Yes
504 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities / Lot 4 | In the Schedule of Priced Activities for Lot-4, it is understood that both items of 7.3 and 7.4 are listed as NATM Tunnel 19-C by mistake. Please clarify. | Please refer to Answer 3. | No
505 | Section IV – Proposal Forms / Lot 4 – Summary Price Table for Lot 4 | With reference to the Section IV – Proposal Form, in the “Lot 4 - Summary Price Table for Lot 4” at Item No. 8 (page 137), it is understood that the phrase "Station Works Sabiha Gokcen Station" is used instead of “Station Works Istanbul Airport Station” by mistake. Please clarify. | Please refer to the Addendum No. 2, Amendment No. 35. | Yes
506 | Section VII – Employer’s Requirements / Clause 5.2.2 – Contractor’s Deemed Knowledge of Site Conditions | The tenderer kindly requests that the provision under Section 5.2.2 of Section VII – Employer’s Requirements be revised as follows: “...The Contractor shall be deemed to have fully satisfied itself, before submitting its Tender, based solely on the available information provided by the Employer as to: ... The Contractor shall treat all such hazards as foreseeable, based solely on the available information provided by the Employer, and shall price its proposal accordingly.” | Please refer to Section VII – Employer’s Requirements / Clause 5.2.2 – Contractor’s Deemed Knowledge of Site Conditions. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
507 | Section VII – Employer’s Requirements / Clause 5.2.2 – Contractor’s Deemed Knowledge of Site Conditions | The tenderer kindly requests that the provision at ultimate paragraph under Section 5.2.2 of Section VII – Employer’s Requirements be revised as follows: “The Contractor shall be entitled to Variation Orders for any changes and/or deviations from the ground conditions known in accordance with the information provided by the Employer.” | Please refer to Clause 13. Variations, including Employer-instructed design changes, and any resulting valuation shall be administered in accordance with the Contract. Where no applicable Contract rate or price exists, the Engineer shall determine an appropriate rate or price in accordance with the valuation provisions of Clause 13. No separate maximum variation percentage is introduced by this clarification. | No
508 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities / Basis of Lump Sum Prices | The tenderer kindly requests that the provision under Section IV – Proposal Forms - Schedule of Priced Activities and Sub-activities be revised as follows: “...Basis of Lump Sum Prices: All lump sum prices quoted in this Schedule are based on the Proposer's own independent assessment of all conditions, solely on the available information provided by the Employer, relevant to the execution of the Works, including but not limited to ground and geotechnical conditions, site conditions, existing infrastructure, regulatory requirements, and all other technical, logistical, and administrative factors. ... Any difference between the actual conditions encountered and those described in any Employer-furnished reference document at the time of tender shall entitle the Contractor for adjustment of the Time for Completion and/or Contract Price.” | The Employer has provided the tender-stage reference/conceptual information available for preparation of the Proposal. The Project is Design-Build and the Contractor shall verify the information, carry out the necessary surveys/investigations and develop the Detailed Design in accordance with the mandatory Employer’s Requirements. No additional document is issued by this clarification unless subsequently transmitted through an Addendum. | No
509 | Section VII – Employer’s Requirements / Clause 5.2.2 and 5.2.3; Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Conditions of Contract | Other revisions to be made to the provisions of the Contract in line with the same notion stated above. | Please refer to Section VII – Employer’s Requirements / Clause 5.2.2 and 5.2.3; Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities; Section IX – Conditions of Contract. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
510 | Section VII – Employer’s Requirements / Site Investigations and Geotechnical Information | In case the above revision requests are not entertained, and considering that the Site extends over 100 km in length, the tenderer kindly requests access to the Site to carry out the additional site investigations, surveys, boreholes, in-situ and laboratory testing and other geotechnical investigations etc. necessary to properly assess and characterize the ground and geotechnical conditions. | The Employer has provided the geological and geotechnical information forming part of the RFP and available for tender purposes. Such information is tender-stage information and shall be read together with Annex C and the other Site Information. The Contractor remains responsible for carrying out the additional investigations and verification necessary for its Detailed Design and construction methodology. No additional geotechnical information is issued by this clarification. | No
511 | Section II – Proposal Data Sheet / ITP 23.1 – Deadline for Submission of Proposals | Accordingly, the tenderer requests that a minimum period of 180 (one hundred eighty) calendar days from the date of granting access to the Site be provided for completion of the above investigations and for incorporating their results into the Tender submission; and, the tenderer kindly requests Tender Submission date to be extended 180 (one hundred eighty) days. | Please refer to the Addendum No.1. | No
512 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria, Item; 1.5 – Equipment, pp.; 57–58; Section IV – FORM; EQU – Contractor’s; Equipment | Please clarify the documentary evidence required at Proposal stage to demonstrate access to key equipment that is owned or not owned by the Proposer. For equipment identified as “Owned”, we understand that no separate documentary evidence of ownership, such as a registration/licence, invoice, fixed asset or inventory record, is required to be submitted with the Proposal and that completion of FORM EQU is sufficient. Please confirm our understanding. For equipment that is not owned by the Proposer, please clarify the documentary evidence required to demonstrate availability. In particular, please confirm whether a rental/lease/manufacturing commitment letter, letter of intent, conditional agreement or other evidence of availability will be acceptable, or whether a signed and binding project-specific rental, lease or manufacturing agreement is required to be submitted with the Proposal. | Please refer to Form EQU and the related qualification requirements. The Proposer shall demonstrate that the proposed equipment will be available for the Works. Owned equipment shall be supported by ownership evidence; equipment to be leased, hired or specially manufactured shall be supported by an appropriate project-specific commitment/arrangement demonstrating availability. | No
513 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria, Item; 1.5 – Equipment, pp.; 56–59; Section IV – FORM; EQU – Contractor’s; Equipment | Please provide or confirm the minimum technical characteristics, capacities and/or performance requirements applicable to each listed key equipment item for which no such characteristics are presently specified in Section III, including, as applicable, Tunnel Boring Machines, Drill Jumbos, Shotcrete Robots, Structural Health Monitoring Systems, Specialized OCS Installation Equipment, Bridge Erection Equipment, Rail Track Laying Machines, Tamping Machines and Cut-and-Cover Excavation Support Equipment, and clarify the criteria against which the Employer will determine compliance of such equipment. | The technical requirements for machinery and equipment deemed necessary for railway construction, including shotcrete spraying robots, drilling jumbos, excavators, railway track construction machinery, open-cut excavation equipment, and other relevant machinery, shall be consistent with the technical characteristics and performance capabilities of equipment that has a proven track record and is currently used in railway construction projects. | No
514 | Section III – Evaluation and Qualification Criteria / ITP 4.3; ITP 28.1; ITP 32.1; and 32.3; Section III –; Evaluation and; Qualification Criteria, Item; 1.5 – Equipment; Section; IV – FORM EQU –; Contractor’s Equipment | Please clarify whether the same specific item of equipment owned or controlled by a third-party equipment provider, lessor or subcontractor may be proposed by more than one Proposer/JV in separate competing Proposals. If the same equipment is identified in more than one Proposal, please confirm whether this would affect the qualification or responsiveness of any of the relevant Proposals and, if so, how the Employer will address such duplication. In particular, please clarify whether the affected Proposer(s) would be permitted to demonstrate alternative availability or replace the duplicated equipment prior to Contract award, rather than having the Proposal rejected or considered not qualified. | The same specific item of equipment owned or controlled by a third-party equipment supplier, lessor or subcontractor may be proposed by more than one Proposer under the same Lot. Each Proposer must independently demonstrate that the equipment will be available for its proposed Works and provide the commitment/availability evidence required by Form EQU. The use of the same item in multiple Proposals does not, by itself, establish compliance or non-compliance; availability shall be assessed against the evidence submitted by each Proposer. | No
515 | Section III – Evaluation and Qualification Criteria / Evaluation of; Technical Part, Factor 1,; Subfactor 1.3.1, p.60;; Employer’s Requirements; – Lot-specific scope | Subfactor 1.3.1 assesses the site-specificity of the proposed construction sequences, including TBM works, while the RFP states that the same Rated Criteria will be applied to each Lot. However, TBM works do not form part of the scope of all Lots. Please clarify how Subfactor 1.3.1 will be scored for Lots where TBM works are not applicable. In particular, please confirm that the absence of TBM works from the scope of a Lot will not result in any reduction of the available score, and that the full 1 point under Subfactor 1.3.1 may be awarded based on the quality of the proposed construction sequences for the other works applicable to the relevant Lot. If a different scoring methodology will be applied, please specify how the 1 point under Subfactor 1.3.1 will be allocated for Lots where TBM works are not applicable. | Sub-factor 1.3.1 shall be evaluated against the construction sequences relevant to the scope of the Lot being evaluated. Where TBM works are not included in a Lot, the absence of TBM works shall not by itself reduce the available score. The Proposer shall demonstrate the quality, feasibility and site-specificity of the proposed construction sequences for the works applicable to that Lot, in accordance with the scoring descriptors in Section III. | No
516 | Section III – Evaluation and Qualification Criteria / Evaluation of; Technical Part: Subfactors; 2.2.3 and 2.3.3 (p.61);; Factor 3 – Similar Work; Experience, including; Subfactors 3.1, 3.2.1–3.2.5; and 3.3 (p.62); Subfactors; 5.1.4, 5.2.3 and 5.4.3; (p.64); Subfactors 6.2.3,; 6.4.3 and 7.1.3 (p.65);; Subfactors 7.3.3 and 8.1.5; (p.66); Section III –; Qualification Criteria,; Subfactor 4.2(a) – Specific; Construction & Contract; Management Experience; (p.76 et seq.); Section IV –; Form EXP-4.2(a) – Specific; Construction and Contract; Management Experience; (pp.179–180). | Please clarify: (a) whether “comparable projects/contracts” under the Rated Criteria are required to satisfy the definition and requirements applicable to “Similar Contracts” under Qualification Subfactor 4.2(a), or whether comparability will be assessed separately according to each Rated Criterion; (b) whether the Proposer may rely on additional and/or different past projects for different Rated Criteria and, for a JV, whether relevant experience and supporting evidence/track record of any JV member, including OHS, environmental and biodiversity performance evidence, may be used for technical scoring; (c) how such past-project information and supporting evidence shall be submitted, including whether supplementary project sheets/annexes may be provided or a specific form is required; and (d) what documentary evidence will be accepted to substantiate the claimed experience and performance, including where the relevant details are not stated in an Employer-issued completion certificate or client reference. Please also clarify the acceptable evidence for demonstrating the specific characteristics relied upon for scoring, including, as applicable, tunnel lengths and construction methods (NATM/TBM), viaduct/bridge scope and complexity, geotechnical conditions, geohazards and other relevant technical characteristics of the reference project. | Comparability under the Rated Criteria shall be assessed against the wording of each applicable Rated Criterion and is not automatically limited to the qualification requirements under Sub-Factor 4.2(a). Additional and/or different relevant projects may be referenced for Rated Criteria. For a JV, relevant experience and verifiable evidence of JV members may be considered where clearly identified and applicable to the criterion concerned. Where no specific form is prescribed, supporting information may be submitted in the relevant Technical Proposal section or annexes, with clear cross-references. Employer certificates are not the only acceptable evidence; other verifiable documentary evidence may also be submitted. | No
517 | Section I – Instructions to Proposers / ITP 12.4; Section III – Rated; Criterion 2.2.2; Section IV –; Technical Proposal Forms | Considering the restriction under ITP 12.4 on including financial information in the Technical Part, Rated Criterion 2.2.2 refers to the realism of the proposed project cash-flow projection. However, no specific form or submission format for such cash-flow projection is provided in Section IV. Please confirm whether a project cash-flow projection is required to be submitted as part of the Technical Part. If so, please specify where and in what format it shall be submitted and clarify what information may be included in such cash-flow projection without contravening ITP 12.4. | Yes. Rated Criterion 2.2.2 requires the Technical Proposal to demonstrate the realism of the proposed cash-flow projection. No separate prescribed form is provided. The information should therefore be presented in a non-price form, such as percentages, normalized curves or timing profiles, without disclosing the Proposal Price or other material financial information prohibited by ITP 12.4. | No
518 | Section III – Evaluation and Qualification Criteria / Evaluation of; Technical Part, Subfactors; 4.1.4, 4.2.3 and 4.3.4;; Section IV – Forms PER-1; and PER-2; Section VII –; Employer’s Requirements,; Clause 2.4. | Please clarify whether the substitution and succession arrangements required under Subfactors 4.1.4, 4.2.3 and 4.3.4 may be demonstrated without individually nominating backup/successor personnel at Proposal stage. If backup or successor personnel are identified by name, please confirm whether Forms PER-1/PER-2 are required for such personnel and whether they will be considered as “personnel proposed at tender stage” and therefore become contractually binding upon Contract award. | The Rated Criteria do not require backup or successor personnel to be individually nominated at Proposal stage; the Proposer may demonstrate the adequacy of its substitution and succession arrangements through its proposed plan and organizational measures. If backup/successor personnel are formally proposed as Key Personnel, the applicable PER-1/PER-2 requirements shall apply and such personnel will be treated as personnel proposed at tender stage. | No
519 | Section III – Evaluation and Qualification Criteria / B.3 Combined; Evaluation (pp.68–69) and; B.4 Multiple Contracts (ITP; 40.3) (p.69) | Please clarify the tie-breaking methodology to be applied where: (i) two or more Proposers achieve the same highest Evaluated Proposal Score (B) for an individual Lot; or (ii) two or more qualified combinations of Lots result in the same highest total score under Section III – Multiple Contracts (ITP 40.3). | It is practically impossible to achieve identical outcomes, as the final ranking and selection are based on the combined evaluation of the Technical and Financial Proposals. Section III, B.3 and B.4 shall apply as stated. The RFP does not prescribe a separate tie-breaking methodology where two Proposals have the same highest Evaluated Proposal Score or where two qualified combinations of Lots result in the same highest total score. No additional tie-break criterion is introduced through this clarification. | No
520 | Section VII – Employer’s Requirements / ER 11.2, footnote 30; ER; 11.10.1–11.10.2; Contract; Data SC 2.1; GC SC 2.1; GC; SC 8.6; GC SC 20.2 | ER 11.2 footnote 30 states that the Contractor shall not be entitled to additional time or cost arising from the progressive preparation, finalization or phased implementation of the RP/LRP. However, ER 11.10.1 assigns statutory expropriation, compensation and implementation of the RP/LRP to the Employer through the relevant government authorities, while GC Sub-Clause 2.1 provides for EOT and Cost Plus Profit where the Employer fails to provide access to the Site within the required time. Please confirm whether the no-entitlement provision in ER 11.2 footnote 30 applies only to the planned/agreed phasing of the RP/LRP and land release. Where the Contractor has timely submitted all documents required from the Contractor for expropriation and/or allocation purposes, but a parcel or section is not made available by the date required under the Programme due to delay by the Employer or the relevant government authorities performing the Employer’s expropriation, allocation or RP/LRP obligations, please clarify whether the Contractor’s entitlement shall be governed by GC Sub-Clause 2.1 (EOT and Cost Plus Profit) or GC Sub-Clause 8.6 (EOT only). | The no-entitlement provision in ER 11.2 footnote 30 applies to delays arising from the progressive preparation, finalization or phased implementation of the RP/LRP as contemplated by the RFP. It does not, by itself, determine entitlement for a separate failure by the Employer to provide access to the Site. Where the facts constitute a failure by the Employer to provide access under Sub-Clause 2.1, any entitlement shall be determined under Sub-Clause 2.1, subject to Sub-Clause 20.2. Where the delay instead falls within Sub-Clause 8.6, that Sub-Clause shall apply. No automatic entitlement or classification is confirmed in advance. | No
521 | Section I – Instructions to Proposers / PDS ITP 12.2(i) | PDS ITP 12.2(i) requires the JV Agreement to identify the scope and parts of the Contract to be carried out by each JV member. At the same time, all JV members are jointly and severally liable for the execution of the entire Contract. Please confirm whether it is mandatory to separately allocate specific parts of the Works to each JV member in the JV Agreement, or whether it is sufficient to state that all JV members are jointly and severally responsible for the entire scope of the Contract. | The JV Agreement shall identify the scope/parts to be performed by each JV member as required by the PDS. This internal allocation does not limit or qualify the joint and several liability of all JV members to the Employer under ITP 4.1 and the Contract. | No
522 | Section I – Instructions to Proposers / ITP 19.3 | Please clarify the criteria for determining whether a bank or other issuing institution qualifies as a “reputable source” and whether the country in which it is established qualifies as an “eligible country” for purposes of ITP 19.3. Please also identify the applicable list or provision for determining Eligible Countries. | A security shall be issued by a bank or financial institution meeting the eligibility requirements of the RFP and subject to appropriate licensing and regulatory supervision in its country of establishment. The Employer reserves the right to verify the issuer and the authenticity/validity of the security. No separate pre-approved list is provided. | No
523 | Section VII – Employer’s Requirements / ITP 21.1–21.2; PDS ITP; 21.1; Section IV – Proposal; Forms | ITP 21.2 provides that, where the Proposer is a JV, the Proposal shall be signed by the authorized representative of the JV on behalf of the JV, so as to be legally binding on all JV members. Please clarify whether the signature of the authorized JV Representative at the designated signature place is sufficient, or whether any corporate stamp/seal is additionally required on the Proposal forms and documents. If a stamp/seal is required, please clarify whether: (i) the stamp/seal of each JV member must be affixed; (ii) only the stamp/seal of the Lead Member is required; or (iii) a stamp/seal identifying the JV itself may be used. | Please refer to Section VII – Employer’s Requirements / ITP 21.1–21.2; PDS ITP; 21.1; Section IV – Proposal; Forms. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
524 | Section VII – Employer’s Requirements / ITP 13.1; PDS ITP 15.8;; Section IV – Letter of; Proposal – Financial Part,; p.92 | Please confirm that the Total Proposal Price / Total Price to be inserted in the Letter of Proposal – Financial Part under the applicable Option shall be stated exclusive of VAT, in accordance with PDS ITP 15.8. Please also clarify whether the Proposer shall expressly add the wording “excluding VAT” next to the stated Total Price, or whether the prescribed form shall be completed without adding such wording. | Please refer to PDS ITP 15.8 and the applicable Contract/payment provisions. Proposal Prices shall be stated exclusive of VAT as required by the PDS; VAT shall be added and paid in accordance with the applicable Turkish tax legislation and the Contract. | No
525 | Section VII – Employer’s Requirements / ITP 17.4–17.5; PDS ITP; 17.4(b) and 17.5; Contract; Data SC 4.4(b); Section IV –; Subcontractors | PDS ITP 17.5 identifies the parts of the Works for which Specialized Subcontractors may be proposed, but design services are not included in this list. At the same time, Contract Data Sub-Clause 4.4(b) identifies no part of the Works for which subcontracting is prohibited. Please confirm that the Proposer may subcontract part or all of the design scope to an external designer/design consultant as an ordinary Subcontractor, subject to the overall subcontracting limit and the other applicable requirements of the RFP and Contract. If so, please clarify how such designer/design Subcontractor shall be declared at Proposal stage and specify the qualification information and supporting documents required to be submitted for it. | The design scope may be subcontracted to suitably qualified and experienced subcontractors, in accordance with the relevant provisions of the RFP. However, the experience of a design Subcontractor cannot be relied upon to satisfy the design Key Activity qualification under Section III, Item 4.2(b); the Proposer itself or at least one JV member must meet that criterion. Please also see Answer 19. | No
526 | Section VII – Employer’s Requirements / ITP 18.1–18.2; ITP; 21.1–21.2; Section IV –; Technical Proposal Forms /; Design Proposal | Please clarify the required title-block/layout and signature format for drawings and design deliverables submitted as part of the Technical Proposal. Where a drawing is prepared by an external designer/design Subcontractor, please confirm whether the title block shall show the name/logo of the Proposer/JV, the designer, or both, and whether the drawing shall be signed by the authorized JV Representative, the responsible designer/design verifier, or both. | No specific requirement is prescribed in the RFP regarding the title-block/layout, identification of the designer/design Subcontractor, or signature format for drawings and design deliverables submitted as part of the Technical Proposal. | No
527 | Section III – Evaluation and Qualification Criteria / ITP 17.4–17.5; ITP; 21.1–21.2; Section IV –; Subcontractors and; Qualification Forms | Please clarify the signature requirements for the Proposal forms and supporting documents relating to proposed Subcontractors and Specialized Subcontractors. In particular, please identify which forms or declarations, if any, must be signed by the Subcontractor’s own authorized representative and which may be completed and signed solely by the authorized JV Representative on behalf of the Proposer. | The Proposal forms shall be signed by the Proposer/JV authorized representative as required by ITP 21. Supporting commitment letters, agreements or declarations issued by a proposed Subcontractor/Specialized Subcontractor shall be signed by the relevant entity where the RFP requires such evidence. | No
528 | Section VII – Employer’s Requirements / PDS ITP 17.4–17.5; ITP; 17.4–17.5; Contract Data; SC 4.4(a)–(b) | PDS ITP 17.5 identifies a limited list of parts of the Works for which the Employer permits Proposers to propose Specialized Subcontractors. However, Contract Data Sub-Clause 4.4(b) states “N/A” for “Parts of the Works for which subcontracting is not permitted”, while Sub-Clause 4.4(a) establishes only an overall subcontracting limit of 30%. Please clarify the relationship between these provisions. In particular, please confirm whether the list under PDS ITP 17.5 is exhaustive only for the purposes of proposing Specialized Subcontractors whose specific experience may be relied upon for qualification, and that other parts of the Works not listed under PDS ITP 17.5 may nevertheless be subcontracted to ordinary Subcontractors, subject to the 30% overall subcontracting limit and the other requirements of the Contract. If this is not the intended interpretation, please identify which parts of the Works may and may not be subcontracted and clarify how Contract Data Sub-Clause 4.4(b) stating “N/A” is to be applied. | The list under PDS ITP 17.5 identifies the parts of the Works for which a Specialized Subcontractor’s specific experience may be relied upon for qualification purposes; it is not a list of all parts that may be subcontracted. Importantly, Specialized Subcontractor experience cannot be used to satisfy the design Key Activity qualification under Section III, Item 4.2(b), which must be met by the Proposer as a Single Entity or in case of JV by All members combined. A design consulting firm may join the JV under the revised Section III Items 3.2 and 4.1(a). Other subcontracting remains subject to the 30% overall limit in Contract Data Sub-Clause 4.4(a), ITP 17.4–17.5 and all other Contract requirements. Contract Data Sub-Clause 4.4(b) stating “N/A” does not create an additional prohibited-part list. | No
529 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria, p.47 | Section III, page 47 states that monetary amounts shall be converted into USD using the applicable exchange rates for construction turnover/financial data and for past contract references, and subsequently states that the official source of the exchange rate is the selling rate published by the Central Bank of the Republic of Türkiye. Please confirm that the selling rate published by the Central Bank of the Republic of Türkiye shall apply to all exchange-rate conversions required under this provision, including: (i) construction turnover and financial data, using the rate prevailing on the last day of the respective calendar year; and (ii) past contract references, using the rate applicable on the contract signing date, and that the reference to the selling rate is not limited only to past contract references. | Where a Proposer is required to state a monetary amount for qualification or evaluation purposes, the amount shall be stated in the USD equivalent using the exchange-rate source and date methodology specified in Section III for the relevant type of amount. For past contract references and financial data, the applicable dates and exchange-rate provisions in Section III shall be followed. | No
530 | Section III – Evaluation and Qualification Criteria / Item 1.4; Contractor’s; Representative and Key; Personnel; Section IV –; Forms PER-1 and PER-2;; ITP 12.2(e)–(f) | Please clarify what supporting documentary evidence, if any, shall be submitted at Proposal stage to substantiate the academic qualifications and work experience stated in Forms PER-1 and PER-2 for each proposed Key Personnel. In particular, please confirm whether completion of Forms PER-1 and PER-2 is sufficient, or whether supporting documents such as copies of diplomas/degrees, employment or project experience certificates, employer/client reference letters, payroll/social-security records or equivalent evidence are required. If supporting evidence is required, please specify the acceptable documents and whether any certification or notarization is required. | The Proposer shall complete Forms PER-1 and PER-2 and provide the information and supporting documents expressly required by Section III, Section IV and the form instructions for the relevant Key Personnel. The information must be accurate and verifiable, and the Employer may request supporting evidence for verification. The RFP does not prescribe a universal notarization or certification requirement for every diploma, employment certificate or reference letter unless expressly stated for the relevant item. | No
531 | Section I – Instructions to Proposers / ITP 12.4; Section III – Rated; Criteria 5.2.2 and 8.1.2;; Section IV – Technical; Proposal Forms | Considering the restriction under ITP 12.4 on including financial information in the Technical Part, Rated Criteria 5.2.2 and 8.1.2 refer to the adequacy of the budget allocated for the relevant activities. Please clarify what information is required to demonstrate the adequacy of such budgets, where and in what format this information shall be submitted, and whether monetary amounts are required. If monetary amounts are required, please clarify what financial information may be included in the Technical Part without contravening ITP 12.4. | For Rated Criteria 5.2.2 and 8.1.2, the Proposer shall demonstrate the adequacy of the relevant budget/resources without disclosing the Proposal Price or information from which it can be derived in the Technical Part, in accordance with ITP 12.4. The Proposer may use non-price information such as resource allocations, percentages, normalized or indexed budget profiles, cash-flow curves, staffing/equipment histograms and the proposed budget-control methodology, provided that the information demonstrates adequacy and does not reveal the Proposal Price. Any financial amounts required for pricing shall be included only in the Financial Part. | No
532 | Section III – Evaluation and Qualification Criteria / Evaluation of; Technical Part, Factor 6.3,; Subfactor 6.3.2, p.65;; Section IV – Risk; Assessment and Proposed; Management Plan | Rated Criterion 6.3.2 assesses the “availability and qualification status of alternative suppliers for critical materials.” Please clarify how the “qualification status” of an alternative supplier will be determined for the purposes of this Rated Criterion and identify the information and/or evidence expected to demonstrate such status. In particular, please clarify whether qualification is to be demonstrated through the Proposer’s internal supplier prequalification/approved vendor process, compliance with specified technical standards and certifications, previous supply experience, Employer approval, or any other particular criteria. Please also confirm whether any supporting documents, such as supplier prequalification records, certificates, references, quotations, letters of intent or availability confirmations, are required to be submitted with the Technical Proposal. | Where Section III requires evidence, track record, quantified information or a demonstration and no separate prescribed form is provided, the Proposer shall include the relevant supporting information in the corresponding Technical Proposal section, clearly cross-referenced to the applicable Rated Criterion. | No
533 | Section III – Evaluation and Qualification Criteria / Rated Criteria; 5.4 and 5.4.1, p.64;; Employer’s Requirements; Clause 11.12 – ESS6 | Rated Criterion 5.4 refers to “IFC PS6 compliance” and Subfactor 5.4.1 assesses habitat assessment and mitigation measures “beyond IFC PS6 minimum compliance”. However, Employer’s Requirements Clause 11.12 establishes the Contractor’s biodiversity obligations by reference to World Bank ESS6. Please clarify the relationship between IFC PS6 and ESS6 for the purposes of the Technical Proposal and evaluation. In particular, please confirm whether IFC PS6 is intended only as the benchmark for scoring under Rated Criterion 5.4, while compliance with ESS6 remains the applicable contractual requirement, or whether the Proposal and the Works are required to comply with both IFC PS6 and ESS6. If both standards are applicable, please clarify which requirement shall prevail in the event of any difference between them. | For the purposes of Rated Criterion 5.4, IFC PS6 shall apply as the evaluation benchmark stated in Section III. The contractual biodiversity requirements for execution of the Works remain those set out in the Employer’s Requirements, including compliance with World Bank ESS6. Reference to IFC PS6 in the Rated Criteria does not introduce a separate contractual compliance regime beyond the requirements of the Contract. | No
534 | Section III – Evaluation and Qualification Criteria / Rated; Criterion 7.2.1, p.65 | Rated Criterion 7.2.1 requires “Evidence that a construction site energy management plan has been prepared and is operational.” As the Works have not yet commenced at Proposal stage, please clarify what is meant by “operational” for the purposes of this Rated Criterion. Please confirm whether Proposers are expected to submit: (i) an INRAIL-specific construction site Energy Management Plan prepared for implementation following Contract award; (ii) evidence of an existing corporate or project-level energy management system currently in operation; or (iii) both. Please also identify the evidence required to demonstrate compliance with this criterion. | For Rated Criterion 7.2.1, “operational” should be demonstrated through evidence that the Proposer has prepared and used an energy-management plan on an existing construction site or comparable project, such as implementation records, monitoring information and evidence of the measures applied. The Proposer should also explain how the approach will be applied to the INRAIL construction sites. The criterion shall be evaluated against the wording and scoring descriptors in Section III; no separate template or additional quantitative threshold is introduced. | No
535 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria, Item; 4.2(a), p.76, Footnotes 6; and 7; Section IV – Letter; of Proposal – Technical; Part, p.91 | Footnote 6 refers to contracts under which the Proposer participated as a joint venture member or Subcontractor and states that “only the Proposer shall be considered to meet this requirement.” However, where the current Proposal is submitted by a JV, the JV itself is identified as the Proposer. Please clarify how Footnote 6 shall be applied where the current Proposer is a JV and, in particular, how experience gained by an individual JV member—whether individually, as a member of a previous JV or as a Subcontractor—shall be attributed and considered for the purposes of this qualification requirement. | For Section III, Item 4.2(a), the experience shall be evaluated in accordance with the qualification criteria and Footnotes 6 and 7. Where the current Proposer is a JV, the qualification assessment shall take account of the experience of its members only to the extent permitted by Section III and the applicable footnotes, supported by verifiable information identifying each entity’s role and the scope it performed under the referenced contract. Experience of an entity that is not part of the Proposer shall not be attributed to the Proposer unless the RFP expressly permits it. | No
536 | Section VII – Employer’s Requirements / ITP 13.1; PDS ITP 14.1; PDS; ITP 16.1; Section IV –; Letter of Proposal –; Technical Part, p.89 | PDS ITP 14.1 states that Alternative Proposals shall not be considered, whereas the Letter of Proposal – Technical Part contains the field: “Alternative No.: [insert identification No if this is a Proposal for an alternative]”. Please confirm that “N/A” shall be entered in the “Alternative No.” field for the conforming Proposal. Please also confirm that the reference to “Alternative A” under PDS ITP 16.1 relates solely to the Proposal/payment currency mechanism and shall not be entered in the “Alternative No.” field. | Confirmed. Where no Alternative Proposal is submitted, the Proposer shall enter “N/A” in the “Alternative No.” field of the Letter of Proposal – Technical Part. “Alternative A” in PDS ITP 16.1 refers to the proposal/payment currency mechanism and shall not be entered in the “Alternative No.” field. | No
537 | Section VII – Employer’s Requirements / ITP 13.1; Section IV –; Letter of Proposal –; Technical Part, p.89; PDS; ITP 1.1 | Please clarify the exact information to be inserted in the blank in the following sentence of the Letter of Proposal – Technical Part: “we, the undersigned, offer to execute the Works to ____________________, in full conformity with the said RFP Documents, and any Addenda.” In particular, please confirm whether the blank is intended to contain the Contract title and/or the identification of the relevant Lot, and please provide the exact wording to be used for each Lot. | The blank in the Letter of Proposal – Technical Part should identify the Contract/Works and the relevant Lot(s). Proposers should use the Contract title stated in the PDS, followed by the applicable Lot identification, for example: “Design and Construction of Infrastructure & Superstructure Works including Electrification – Lot [1/2/3/4]”. Where a Proposal covers multiple Lots, identify all Lots covered by that Proposal. No amendment is made to the RFP. | No
538 | Section VII – Employer’s Requirements / ITP 13.1; PDS ITP 14.1; PDS; ITP 16.1; Section IV –; Letter of Proposal –; Financial Part, p.92 | PDS ITP 14.1 states that Alternative Proposals shall not be considered, whereas the Letter of Proposal – Financial Part contains the field: “Alternative No.: [insert identification No if this is a Proposal for an alternative]”. Please confirm that “N/A” shall be entered in this field for the conforming Financial Proposal. Please also confirm that “Alternative A” under PDS ITP 16.1 relates solely to the Proposal/payment currency mechanism and is not to be entered in this field. | Confirmed. Where no Alternative Proposal is submitted, the Proposer shall enter “N/A” in the “Alternative No.” field of the Letter of Proposal – Financial Part. “Alternative A” in PDS ITP 16.1 refers to the proposal/payment currency mechanism and shall not be entered in the “Alternative No.” field. | No
539 | Section VII – Employer’s Requirements / ITP 13.1; Section IV –; Letter of Proposal –; Financial Part, p.92; PDS; ITP 1.1 | Please clarify the exact information to be inserted in the blank in the following sentence of the Letter of Proposal – Financial Part: “we, the undersigned, offer to _________, in full conformity with the said RFP Documents, and any Addenda for the total Proposal Price…” Please confirm whether the blank is intended to contain wording referring to the execution of the Works and the relevant Contract/Lot, and provide the exact wording to be used for each Lot. | The blank in the Letter of Proposal – Financial Part should contain wording identifying the Works and the relevant Lot(s), consistent with the Contract title in the PDS. Proposers should use the Contract title followed by the applicable Lot identification, for example: “to execute the Works for Design and Construction of Infrastructure & Superstructure Works including Electrification – Lot [1/2/3/4]”. Where a Proposal covers multiple Lots, identify all Lots covered. No amendment is made to the RFP. | No
540 | Section I – Instructions to Proposers / ITP 13.1; ITP 40.3; Section; III – Multiple Contracts,; p.69; Section IV – Letter of; Proposal – Financial Part,; p.92 | Section III provides that each Lot will be evaluated separately and the Contract will be awarded on a lot-by-lot basis. Accordingly, the Proposer intends to submit a separate Letter of Proposal – Financial Part for each Lot. However, the prescribed form on p.92 contains both: Option 1 – in case of one lot, and Option 2 – in case of multiple lots. Please confirm that, where a separate Financial Proposal is submitted for each Lot, Option 1 shall be used separately for each respective Lot. Please also clarify whether Option 2, the word “Or”, and the related non-applicable instructional text shall be deleted from each completed Letter of Proposal – Financial Part, notwithstanding ITP 13.1 requiring the prescribed form to be completed without alterations. | Please refer to Answer 65. | No
541 | Section VII – Employer’s Requirements / ITP 13.1; ITP 15.6–15.7;; Section IV – Letter of; Proposal – Financial Part,; p.93 | ITP 15.6 states that discounts conditional upon the award of more than one Contract will not be considered for Proposal evaluation. However, the Letter of Proposal – Financial Part contains the following fields: (i) “The discounts offered are:” (ii) “The exact method of calculations to determine the net price after application of discounts is shown below:” Please clarify how these fields shall be completed where no applicable discount is to be stated in the Proposal. In particular, please confirm whether “N/A” / “None” shall be inserted under items (i) and (ii), or whether these items and the related instructional text shall be deleted from the completed form. | Where no discount is offered, the Proposer should state “None” under “The discounts offered are” and “N/A” or “No discount offered” in the field describing the calculation method. The relevant fields should not be deleted from the Letter of Proposal – Financial Part. Any discount offered must comply with ITP 15.6–15.7; discounts conditional upon the award of more than one Contract will not be considered for evaluation. | No
542 | Section VII – Employer’s Requirements / PDS ITP 16.1; Section IV –; Letter of Proposal –; Financial Part, p.92;; Appendix to Proposal –; Table C | PDS ITP 16.1 provides under Alternative A that the Proposal prices shall be quoted entirely in Turkish Lira, while foreign currency requirements shall be identified separately in Appendix to Proposal – Table C. However, Option 1 of the Letter of Proposal – Financial Part requires the Total Price to be stated in words and figures “indicating the various amounts and the respective currencies.” Please confirm that the Total Proposal Price in the Letter of Proposal – Financial Part shall be stated entirely in Turkish Lira, and that any foreign currency requirements shall be reflected only in Appendix to Proposal – Table C and shall not be separately stated as components of the Total Proposal Price in the Letter. If not, please clarify how the Total Proposal Price field shall be completed. | Confirmed. Under Alternative A in PDS ITP 16.1, the Total Proposal Price in the Letter of Proposal – Financial Part shall be stated entirely in Turkish Lira. Any foreign-currency payment requirements shall be identified separately in Appendix to Proposal – Table C in accordance with ITP 16.1 and shall not be stated as separate foreign-currency components of the Total Proposal Price in the Letter. | No
543 | Section VII – Employer’s Requirements / PDS ITP 14.1 and 16.1;; Section IV – Letter of; Proposal –; Technical/Financial Parts,; pp.89 and 92; Table C –; Summary of Payment; Currencies, p.100 | While “N/A” is to be entered in the “Alternative No.” field of the Letters of Proposal where no Alternative Proposal is submitted, Table C – Summary of Payment Currencies on p.100 is expressly titled “Table: Alternative A.” Please confirm that the heading “Table: Alternative A” shall remain unchanged in the completed Table C, as it refers to the currency/payment mechanism selected under PDS ITP 16.1 and not to an Alternative Proposal under ITP 14. | Confirmed. The heading “Table: Alternative A” in Appendix to Proposal – Table C shall remain unchanged. It refers to the currency/payment mechanism under PDS ITP 16.1 and not to an Alternative Proposal under ITP 14.1. Where no Alternative Proposal is submitted, “N/A” shall be entered in the “Alternative No.” fields of the Letters of Proposal. | No
544 | Section IV – Proposal Forms – Lot-specific; Schedules of Priced; Activities and Sub-; activities, pp.103 onwards | Throughout the Lot-specific Schedules of Priced Activities and Sub-activities, the column heading “Deliverable” is used for all priced entries, including construction works and activities that do not constitute documentary deliverables. Please confirm that, for the purposes of these Price Breakdown tables, “Deliverable” is intended to mean the relevant priced item / Sub- activity, and does not create a separate deliverable requirement beyond the scope expressly stated in the corresponding item description and the Employer’s Requirements. Please also confirm whether the heading shall remain as “Deliverable” in the submitted forms or whether the Employer intends to revise it to “Item / Description of Sub-activity” or similar wording. | Please refer to Addendum No. 2, Amendment No. 38. | Yes
545 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities (Lots 1–4), Activity 1 – Design Completion; Section VII – Employer’s Requirements / Clauses 10.6.3, 10.6.6 and 10.6.7 | The Lot-specific Price Breakdowns include “As-Built Documentation — All Disciplines (submission and acceptance)” under Activity 1 – Design Completion, while the Final Acceptance Activity again includes “Submission and acceptance of complete As-Built documentation — all disciplines.” Please clarify whether these two priced items represent two distinct stages and payment entitlements, or whether the As-Built requirement has been duplicated in the Price Breakdown. If they are distinct, please define the scope, required level of completion, acceptance criteria and payment trigger applicable to: (i) the As-Built Documentation included under Activity 1 – Design Completion; and (ii) the complete/final As-Built Documentation included under Final Acceptance. In particular, please clarify how the As-Built item under Design Completion is intended to operate given that final As-Built documentation reflects the actual installed condition of the Works. If the duplication is unintended, please revise the affected Price Breakdown tables by Addendum. | Please refer to Addendum No. 2, Amendment No. 5. | Yes
546 | Section IV – Proposal Forms – Lot-specific; Price Breakdowns, Final; Acceptance Activity;; Contract Data SC 14.6.2;; GC 14.3, 14.6, 14.9–14.13 | The Lot-specific Price Breakdowns include a separate Final Acceptance Activity, comprising items to be completed after Taking-Over and, in certain cases, during the Defects Notification Period. Please clarify in detail the certification and payment mechanism applicable to the amounts allocated to the Final Acceptance Activity. In particular, please confirm whether the Contractor shall continue to submit Statements and receive Interim Payment Certificates after Taking-Over for the relevant Final Acceptance items. Where an amount becoming due under the Final Acceptance Activity is less than the minimum IPC amount of 0.5% of the Accepted Contract Amount stated in Contract Data SC 14.6.2, please clarify whether such amount will: (i) be accumulated until the minimum IPC threshold is reached; (ii) be certified notwithstanding the minimum IPC threshold; or (iii) be included in a subsequent Statement at Completion / Final Statement and paid through the applicable subsequent payment certificate. Please also clarify the payment trigger for each Final Acceptance Sub-activity and whether the ordinary Retention deduction mechanism continues to apply to amounts certified after Taking-Over. | Amounts allocated to the Final Acceptance Activity remain lump-sum payment items and shall be certified under Clause 14 when the relevant sub-activities are completed and verified. Statements may continue to include such amounts after Taking-Over. The minimum IPC threshold under Sub-Clause 14.6.2 and the retention/release provisions under Clause 14 remain applicable; where the amount otherwise due is below the minimum IPC threshold, it shall be dealt with through the subsequent payment procedures under Clause 14. No amendment is made to the RFP. | No
547 | Section IV – Proposal Forms – Schedule of; Payments, p.140; GC/PC; 14.4; ER 4.9.4; Lot-specific; Schedules of Priced; Activities and Sub-; activities | Section IV includes a separate “Schedule of Payments” on p.140; however, no payment schedule, table, format or completion instructions are provided. At the same time, ER 4.9.4 refers to the Activities and Sub-activities used in the Schedule of Payments, and PC Sub-Clause 14.4 addresses payments based on Milestones where such payments are specified in the Schedule of Payments. Please clarify whether: (i) the Lot-specific Schedule of Priced Activities and Sub-activities itself constitutes the Schedule of Payments for the purposes of the Contract; or (ii) the Proposer is required to prepare and submit a separate Schedule of Payments under p.140. If a separate Schedule of Payments is required from the Proposer, please specify the required format, level of detail and basis, including whether it shall be structured by Activity/Sub-activity, contractual Milestone, monthly period, or a combination thereof. If the Schedule of Payments is to be prescribed by the Employer, please provide the completed Schedule by Addendum. | Please refer to Addendum No. 2, Amendment No. 12. | Yes
548 | Section IV – Proposal Forms – Method; Statement for key; construction activities,; p.145 | Section IV, p.145 states that the Proposer shall provide Method Statements for addressing “the following risks” and carrying out “the following construction activities”; however, no list of such risks or construction activities is provided. Please identify the specific risks and construction activities for which separate Method Statements are required at Proposal stage and, if applicable, issue the completed/revised form by Addendum. | Section IV, page 145 requires Method Statements for key construction activities and relevant project risks. The RFP does not provide a separate exhaustive list of individual risks or activities for which standalone Method Statements must be submitted. The Proposer shall identify and address the key construction activities and material risks relevant to its proposed methodology, the applicable Lot and the Employer’s Requirements, and clearly cross-reference the relevant Method Statements in the Technical Proposal. No additional list or revised form is issued through this clarification. | No
549 | Section VII – Employer’s Requirements / ITP 13.1; Section IV – Code; of Conduct for Contractor’s; Personnel (ES) Form, p.147 | The Code of Conduct form on p.147 contains a “Note to the Proposer” stating that the minimum content shall not be substantially modified, that additional requirements may be added, and that the Proposer shall initial and submit the form. Unlike certain other Proposal Forms, however, it does not state whether this instructional Note is to be deleted from the final submitted document. Please confirm whether the “Note to the Proposer” shall be deleted from the Code of Conduct submitted with the Proposal, while the substantive Code of Conduct wording is retained and initialled, or whether the Note itself shall remain in the submitted form. | The Note to the Proposer provided in the box in the Code of Conduct form shall be deleted from the form submitted with the Proposal. The substantive Code of Conduct requirements shall remain and the form shall be completed and submitted in accordance with the RFP. | No
550 | Section III – Evaluation and Qualification Criteria / Sub-Factor 2.3; Pending Litigation and Sub-; Factor 2.4 Litigation; History, pp.71–72,; Footnote 3; Section IV –; Form CON-2, pp.167–168 | Sub-Factor 2.3 requires the Proposer’s financial position to remain sound assuming that “all pending litigation” is resolved against the Proposer. However, Footnote 3 under Sub-Factor 2.4 refers to litigation or arbitration resulting from contracts completed or ongoing under the Proposer’s execution, and the Pending Litigation section of Form CON-2 similarly requires Contract Identification, Employer and Total Contract Amount. Please clarify whether “all pending litigation” under Sub-Factor 2.3 is likewise limited to litigation or arbitration arising from contracts completed or ongoing under the Proposer’s execution, or whether it includes all other corporate legal proceedings irrespective of their connection with such contracts. In particular, please clarify whether ordinary-course matters such as employment/reinstatement and employee receivable claims, tax or administrative proceedings, and other non-contract-project litigation are required to be disclosed in Form CON-2. Please also confirm whether any materiality threshold applies to pending litigation required to be disclosed and, if so, specify the applicable threshold. | The Proposer shall disclose litigation/arbitration/dispute information falling within the scope and period stated in the applicable CON/FIN forms and Section III. The disclosure is not limited to claims similar to INRAIL unless the form expressly states otherwise. | No
551 | Section III – Evaluation and Qualification Criteria / Qualification,; Financial Capabilities;; Section IV – Form FIN-3.1,; p.174 and Form FIN-3.3,; p.176 | Form FIN-3.1 requires the Proposer to specify the sources of finance available to meet the cash-flow requirements of current and future contract commitments, while Form FIN-3.3 similarly requires proposed sources such as liquid assets, unencumbered real assets, lines of credit and other financial means. Please clarify the documentary evidence required at Proposal stage to substantiate each stated source of finance. In particular, please confirm whether completion of Forms FIN-3.1 and FIN-3.3, together with the required audited financial statements, is sufficient, or whether separate supporting documents such as bank reference letters, bank balance/cash availability certificates, committed credit-line letters, evidence of unencumbered assets or other financial commitments must also be submitted. If bank letters or credit-line confirmations are required, please specify the required form, level of commitment, project-specific wording, validity/date requirements and issuing institution requirements. | Forms FIN-3.1 and FIN-3.3 shall be completed in accordance with their instructions and the qualification requirements in Section III. The Proposer shall provide sufficient verifiable evidence to substantiate the stated sources of finance and financial resources. The RFP does not prescribe a universal bank-letter template, notarization requirement or fixed validity period for every type of evidence unless expressly stated. Where bank balances, credit lines or committed facilities are relied upon, the evidence should identify the available/committed amount and be issued by the relevant financial institution; assets relied upon should be supported by appropriate evidence of ownership and availability. The Employer may request further verification. | No
552 | Section IV – Proposal Forms – Others, p.184;; ITP 7; Single-Stage RFP; procedure | Section IV, p.184 contains an “Others” form requesting: “Commercial or contractual aspects of the RFP documents that the Proposer would like to discuss with the Employer during clarifications.” However, this procurement is conducted under a Single-Stage RFP procedure, and requests for clarification of the RFP are submitted and answered before Proposal submission in accordance with ITP 7. Please clarify the purpose and required content of the “Others” form in the Proposal. In particular, please confirm whether this form is not applicable to this Single-Stage RFP and may therefore be omitted or submitted stating “N/A”. If the form is required, please specify what information the Proposer is expected to include and confirm that it is not intended as a means for submitting qualifications, reservations, departures or matters for post-Proposal negotiation. | The “Others” form is intended for commercial or contractual matters raised for clarification in accordance with ITP 7 before the Proposal submission deadline. It is not a means to introduce qualifications, reservations or departures from the RFP, or to seek post-Proposal negotiation. If the Proposer has no applicable information to provide, it may state “N/A”. Any request for clarification must be submitted within the deadline and in accordance with ITP 7. | No
553 | Section VII – Employer’s Requirements / PDS, p.38 – Management; Strategies and; Implementation Plans; (MSIPs); Section IV –; Technical Proposal Forms | PDS p.38 states that, besides the MSIPs, the Proposer shall prepare and submit the following: (i) Site Organization (Project and Construction Management Chart); (ii) Method Statement; (iii) Mobilization Schedule; (iv) Construction Schedule; and (v) Draft Project Quality Plan. Please clarify whether each of these five items is required to be prepared and submitted as a separate standalone document with its own title/section, or whether the required information may be incorporated into the corresponding Technical Proposal documents/forms provided in Section IV, such as the Construction Management Strategy, Method Statements, Work Program, Contractor’s Personnel Organization Chart and QA/QC documentation. If separate standalone documents are required, please specify the required format, minimum content and location/indexing within the Technical Proposal for each document. | The five items listed in PDS shall be included in the Technical Proposal. The RFP does not require a separate standalone file for each item where the required information is clearly presented in the corresponding Technical Proposal forms/sections. The Proposer may incorporate the information into the relevant Construction Management Strategy, Method Statements, Work Program, organization chart and quality-management documentation, provided each required item is clearly identifiable, complete and cross-referenced. No additional template is prescribed by this clarification. | No
554 | Section III – Evaluation and Qualification Criteria / Evaluation of; Technical Part, Factor 4,; Subfactors 4.1.1–4.1.3,; p.63; Section IV –; Personnel / Organization; Forms | Please clarify the subject and evidence basis to be assessed under Subfactors 4.1.1 and 4.1.2. In particular, please clarify whether the required multidisciplinary coordination leadership and track record in managing civil-systems interfaces are to be demonstrated through: (i) the corporate experience of the Proposer/JV and its members; (ii) the personal experience of the proposed Key Personnel / leadership personnel; or (iii) a combination of both. Where individual experience is to be assessed, please identify which proposed positions/persons will be evaluated and clarify whether only personnel included as Key Personnel in Forms PER-1/PER-2 may be relied upon, or whether additional specialist/leadership personnel may also be presented for this Rated Criterion. Please also clarify the required supporting evidence and where such evidence should be submitted within the Technical Proposal | Sub-factors 4.1.1 and 4.1.2 shall be assessed against the evidence and descriptors stated in Section III. The Technical Proposal should provide relevant project examples demonstrating multidisciplinary coordination leadership and management of civil-systems interfaces, and identify the Proposer/JV member’s role and the scope performed. Where individual personnel experience is relied upon, the relevant person, position and experience should be identified and supported by verifiable evidence. Any additional specialist/leadership personnel relied upon should be clearly identified in the Technical Proposal; the RFP’s requirements for Key Personnel remain applicable to personnel proposed as Key Personnel. No additional scoring criterion is introduced by this clarification. | No
555 | Section VII – Employer’s Requirements / ER Sections 5.3.2 and; 5.3.5; ER Sections 4.4–4.5;; Annex L – Signaling and; Telecommunication; System Technical; Specification, Section 13. | With reference to ER Sections 5.3.2 and 5.3.5, Sections 4.4–4.5 and Annex L, please confirm which Contractor is responsible for the design, supply, installation, integration, testing and commissioning of the earthquake early warning system. Please also define the precise scope and interface boundary between Package 1 and Package 2 in respect of this system and confirm that no duplication of scope, responsibility or pricing is intended. | The earthquake early warning system is within the scope of Package 1. The Package 1 Contractor shall coordinate with Package 2 as necessary to ensure that the system interfaces with the relevant Package 2 systems and operates in a fully integrated manner. The respective interface requirements shall be coordinated and finalized during Detailed Design in accordance with the RFP | No
556 | Section VII – Employer’s Requirements / ITP 7.1, ITP 7.6 and ITP 8.1;; GC/PC Sub-Clause 1.5; [Priority of Documents]. | With reference to ITP 7.1, ITP 7.6, ITP 8.1 and Sub-Clause 1.5 [Priority of Documents], please clarify the contractual status of the Employer’s official responses to Proposers’ clarification questions. In particular, please confirm whether such responses are binding for the preparation and evaluation of Proposals and, in the event of any inconsistency between a clarification response and the RFP Document, please confirm the applicable order of precedence. Please also confirm whether any response intended to amend or modify the RFP Document will be incorporated through an Addendum pursuant to ITP 8. | Official clarification responses shall be read together with the RFP for the preparation and evaluation of Proposals. However, they do not amend or modify the RFP Document. Any modification to the RFP shall be made exclusively through an Addendum pursuant to ITP 8. In case of inconsistency, the RFP Document as amended by Addenda shall prevail. | No
557 | Section VII – Employer’s Requirements / ITP 33.1(b)–(c) and ITP; 34.1. | With reference to ITP 33.1 and ITP 34.1, please confirm whether the technical score of each substantially responsive Proposer will be communicated in writing together with the notification of the Technical Part evaluation results under ITP 33.1, prior to the public opening of the Financial Parts. If not, please confirm that the technical scores will first be disclosed at the public opening of the Financial Parts pursuant to ITP 34.1. | The RFP does not require technical scores to be communicated in the written notification under ITP 33.1. The technical scores of the Proposers whose Financial Parts are opened shall be announced at the public opening in accordance with ITP 34.1. | No
558 | Section VII – Employer’s Requirements / ITP 13.1; Section III – Item; 1.4 Contractor’s; Representative and Key; Personnel, pp.47–56;; Section IV – FORM PER-1,; p.156 | Section III, Item 1.4 specifies the mandatory Contractor’s Representative and Key Personnel positions applicable to each Lot, whereas FORM PER-1 on p.156 contains a different generic list of design and construction personnel and includes the instruction “[Modify/add others as appropriate]”. Please clarify how FORM PER-1 shall be completed. In particular, please confirm whether the Proposer shall: (i) retain all positions presently listed in FORM PER-1 and add all mandatory Lot-specific Key Personnel positions identified in Section III, Item 1.4; or (ii) modify/replace the generic list in FORM PER-1 so that the completed form reflects the mandatory Key Personnel positions applicable to the relevant Lot under Section III, Item 1.4. Please also confirm that the numbering and structure of FORM PER-1 may be adapted accordingly without constituting an unauthorized alteration of the prescribed form under ITP 13.1, and clarify whether FORM PER-2 is required for each mandatory Key Personnel position included in the completed FORM PER-1. | FORM PER-1 shall be completed to reflect the mandatory Lot-specific Key Personnel positions under Section III, Item 1.4. The generic list may be modified/adapted accordingly, and additional personnel may be included as appropriate. FORM PER-2 shall be completed for each candidate included as Key Personnel. | No
559 | Section III – Evaluation and Qualification Criteria / Financial; Capabilities; Section IV –; FORM FIN-3.4, p.177 | FORM FIN-3.4 requires the Proposer and each JV member to provide information on its current contract commitments and works in progress, but does not specify any supporting documentary evidence to be submitted for the contracts listed in the form. We understand that completion of FORM FIN-3.4 is sufficient at Proposal stage and that supporting documents such as copies of contracts, Letters of Award/Acceptance, Employer certificates, payment certificates/invoices or Employer confirmations are not required to be submitted with the Proposal, unless subsequently requested by the Employer for verification. Please confirm our understanding. If supporting evidence is required at Proposal stage, please specify the documents to be submitted for each listed contract. | Form FIN-3.4 shall include all current contract commitments and works in progress of the Proposer and each JV member. No specific supporting document is prescribed for each entry at Proposal stage; however, the Employer may request supporting evidence for verification during evaluation. | No
560 | Section III – Evaluation and Qualification Criteria / Sub-Factor; 4.1(a), General; Construction Experience,; p.75; Section IV – FORM; EXP-4.1, p.178 | Sub-Factor 4.1(a) requires more than fifteen years of experience under construction contracts but does not state that only completed contracts may be used. Please confirm that ongoing construction contracts may also be included in FORM EXP-4.1 for the purpose of demonstrating General Construction Experience, with the relevant period of actual experience stated in the form. Please also confirm that completion of FORM EXP-4.1 is sufficient at Proposal stage and that no supporting documents are required for each listed contract, unless subsequently requested by the Employer for verification. If supporting evidence is required with the Proposal, please specify the acceptable evidence, such as Contract/Letter of Award, Employer certificate, completion certificate or other equivalent documentation. | For verification of the General Construction Experience requirement under Section III, Item 4.1(a), ongoing construction contracts may be included in Form EXP-4.1, with the actual period of experience stated accurately. No specific certificate is prescribed for each entry at Proposal stage; however, the information shall be verifiable and supporting evidence may be requested by the Employer. No amendment is made to the RFP. | No
561 | Section VII – Employer’s Requirements / ITP 13.1; Section III – Sub-; Factor 4.2(b), pp.79–85;; Section IV – FORM EXP-; 4.2(b), pp.181–182 | Sub-Factor 4.2(b) permits relevant key-activity experience from contracts substantially completed or under implementation between 1 January 2011 and the Proposal submission deadline. However, FORM EXP-4.2(b) provides rows only for Year 1, Year 2, Year 3 and Year 4 for reporting the quantity, volume or rate of production performed under the reference contract. Please clarify whether the four-year structure is intended as a limitation on the information to be provided. Where the relevant key activity was performed over a period longer than four years, please confirm whether the Proposer may add further annual rows (Year 5, Year 6, etc.) to FORM EXP-4.2(b). Conversely, where the activity was performed in fewer than four years, please confirm whether the unused annual rows may be stated as “N/A”. Please also clarify the documentary evidence required at Proposal stage to substantiate the key-activity quantities, lengths, volumes and/or production rates stated in FORM EXP-4.2(b), including the evidence acceptable to demonstrate the Proposer’s or JV member’s attributable share where the reference contract was performed as part of a JV. In particular, please specify whether Employer-issued completion/interim certificates, signed quantity certificates, certified progress records, contract documents, As-Built records or equivalent supporting documents will be accepted. | The four-year layout in Form EXP-4.2(b) is not intended to limit the eligible experience period. Additional annual rows/pages may be added where necessary, and unused rows may be marked “N/A”. The quantities and attributable JV participation claimed shall be supported by sufficient verifiable evidence. No specific documentary format is prescribed unless expressly stated in the RFP. | No
562 | Section IV – Proposal Forms – Code of; Conduct for Contractor’s; Personnel (ES) Form,; pp.147–150; Particular; Conditions Sub-Clause 4.25 | The Note to the Proposer in the Code of Conduct for Contractor’s Personnel (ES) Form states that the Proposer shall initial and submit the Code of Conduct form as part of its Proposal. However, the form also contains a section headed “FOR CONTRACTOR’S PERSONNEL”, requiring: Name of Contractor’s Personnel; Signature; Date; and Countersignature of the authorized representative of the Contractor. Please clarify whether these individual personnel signature fields are required to be completed at Proposal stage. If yes, please clarify which personnel are required to individually sign the Code of Conduct, and in particular whether a separately signed Code of Conduct is required for each Key Personnel proposed in FORM PER-1/PER-2, or for any other personnel identified in the Technical Proposal. If not, please confirm that, at Proposal stage, it is sufficient for the Proposer to initial and submit the Code of Conduct form, and that the individual personnel acknowledgment/signature section will be completed after Contract award as the relevant Contractor’s Personnel are engaged. | Please refer to ITP 12.2(k), which states: "The Proposer shall submit its Code of Conduct that will apply to Contractor’s Personnel (as defined in Sub-Clause 1.1.16 of the General Conditions), to ensure compliance with the Contractor’s Environmental and Social (ES) obligations under the Contract. The Proposer shall use for this purpose the Code of Conduct form provided in Section IV. No substantial modifications shall be made to this form, except that the Proposer may introduce additional requirements, including as necessary to take into account specific Contract issues/risks." Accordingly, the Code of Conduct shall be completed for each proposed Key Personnel and duly signed in accordance with the requirements specified in the Code of Conduct Form. The completed and signed forms shall be submitted as part of the Proposal. | No
563 | Sections VIII–IX – General and Particular Conditions / GC 5.2; ER 7.3–7.4; GC; 13.3. | Please specify the period within which the Engineer shall notify the Contractor that a design submission is incomplete or non- compliant, failing which the applicable Review Period shall be deemed to have commenced on the original submission date. Please also confirm that any Engineer requirement which adds to or changes the Contract requirements, rather than correcting an actual non-compliance, shall be treated in accordance with Clause 13 [Variations and Adjustments]. | The Engineer’s review/response periods shall be those stated in the Contract and Employer’s Requirements. Where no specific period is stated for a particular coordination confirmation, the Contractor shall incorporate a reasonable review period in the approved programme and Interface Register. No deemed approval arises unless expressly provided by the Contract. | No
564 | Section VII – Employer’s Requirements / ITP 2.1–2.2; PDS ITP 16.1;; Table C; GC/PC 14.15. | Please clarify the payment and disbursement procedure applicable to each Contract payment currency, including whether payments will be made by the Employer or directly through the Bank/Financiers, and any applicable bank-account or payment-country requirements. | Payments shall be made by the Employer to the applicable bank account notified by the Contractor in accordance with the provisions of Particular Conditions Sub-Clause 14. | No
565 | Section VII – Employer’s Requirements / ITP 2.1–2.2; GC 14.7; IBRD; Loan 99430 – DFIL. | Please confirm the funding source, payment procedure and timing applicable to the VAT component of certified Contract payments, including whether VAT will be paid simultaneously with the corresponding VAT-exclusive certified amount. | Please refer to PDS ITP 15.8 and the applicable Contract/payment provisions. Proposal Prices shall be stated exclusive of VAT as required by the PDS; VAT shall be added and paid in accordance with the applicable Turkish tax legislation and the Contract. | No
566 | Section II – Proposal Data Sheet (PDS) / ITP 16.1; Section IV – Proposal Forms / Appendix to Proposal – Table C (Schedule of Payment Currencies), Provisional Sums P.1 and P.2; Section IX – Particular Conditions / Sub-Clauses 13.4 and 13.7 | Please confirm that both P.1 and P.2 Provisional Sums shall be excluded from the TRY/foreign-currency percentage calculation under Table C and that the “Provisional sums expressed in local currency” row shall include the aggregate amount of P.1 and P.2 for each Lot. Please also confirm the payment currency and price-adjustment treatment applicable to expenditure under P.2. If the aggregate amount of P.1 and P.2 is to be included, please revise Table C accordingly by Addendum or otherwise confirm how Proposers shall complete the prescribed Table C without altering its text contrary to ITP 13.1. | Please refer to Addendum No. 2, Amendment No. 41. Both P.1 and P.2 are Provisional Sums and shall be excluded from the TRY/foreign-currency percentage calculation under Table C. The row “Provisional sums expressed in local currency” shall reflect the aggregate of P.1 and P.2 for each Lot, as specified in the amended Table C. P.2 is denominated and payable in TRY and shall be administered in accordance with Sub-Clause 13.4. Any price adjustment shall apply only to the extent permitted under Sub-Clause 13.7. Proposers shall complete Table C as amended by Addendum No. 2, without further modification to the prescribed form. | Yes
567 | Sections VIII–IX – Conditions of Contract / GC/PC 13.4; Section IV –; Activity 13 and P.1/P.2; Provisional Sums; DAAB; Procedural Rules. | Please confirm that P.1 is exclusively intended to cover the Employer’s 50% share of the DAAB members’ fees and expenses, while the separately priced DAAB Activity covers the Contractor’s 50% share and its own DAAB-related costs. Please also confirm whether the 5% overhead and profit under Sub-Clause 13.4(b)(ii) applies to expenditures reimbursed under P.1 and P.2. Please also clarify how any amount by which the Employer’s 50% share of the DAAB members’ fees and expenses exceeds the P.1 Provisional Sum shall be treated, including whether such excess will be added to the Contract Price and paid by the Employer. | Please refer to Section IV – Schedule of Priced Activities and Sub-activities, Section IX – Particular Conditions, Sub-Clause 13.4 (Provisional Sums), Clause 21 and the DAAB Agreement. P.1 shall be administered in accordance with Sub-Clause 13.4, including the financing of the Employer’s share of the DAAB members’ fees and expenses. The separately priced DAAB Activity shall cover the Contractor’s share and its associated obligations in accordance with the relevant Contract provisions. The 5% overhead and profit rate specified in the Contract Data under Sub-Clause 13.4(b)(ii) shall apply only to expenditures falling within the scope of that provision and shall not automatically apply to all expenditures under P.1 or P.2. Any adjustment to the Contract Price arising from the utilization of Provisional Sums, including DAAB-related expenditures exceeding the available Provisional Sum, shall be governed by the applicable provisions of the Contract, including the relevant approval and payment procedures. | No
568 | Section III – Evaluation and Qualification Criteria / Evaluation of; Technical Part, Rated; Criteria, pp.60–66; Section; IV – Technical Proposal; Forms | Several Rated Criteria require evidence, track record, quantified information or demonstrations, whereas Section IV does not provide a separate prescribed form or submission location for each Rated Subfactor. Please clarify how supporting evidence for the Rated Criteria shall be organized and submitted. In particular, please confirm whether the required evidence may be: (i) incorporated directly into the relevant Technical Proposal document, methodology, plan or report; and/or (ii) submitted as separate supporting annexes or evidence schedules cross-referenced from the relevant Technical Proposal document. Please also clarify whether the Employer expects a separate submission or evidence schedule for each Rated Subfactor, or whether one Technical Proposal document may address and provide evidence for several related Subfactors through clear cross-references. | Where Section III requires evidence, track record, quantified information or a demonstration and no separate prescribed form is provided, the Proposer shall include the relevant supporting information in the corresponding Technical Proposal section, clearly cross-referenced to the applicable Rated Criterion. | No
569 | Section VII – Employer’s Requirements / PC 14.7(b)(iii); GC 14.6.1;; PC 16.2.2. | Please confirm that, upon suspension of the Bank’s loan or credit under PC Sub-Clause 14.7(b)(iii), the amount shown in the Contractor’s Statement shall be paid within 14 days of submission without awaiting completion of the ordinary IPC certification process under Sub-Clause 14.6, with any discrepancy rectified in the subsequent payment. Please also clarify how this 14-day period applies where the Bank’s suspension occurs after the relevant Statement has already been submitted. | Where Sub-Clause 14.7(b)(iii) applies, the amount shown in a Statement submitted while the Bank’s loan or credit is suspended shall be paid within fourteen (14) days after submission, with any discrepancy rectified in the next payment. A Statement submitted before the suspension is not retroactively brought under this 14-day period and remains subject to the otherwise applicable payment provisions. No amendment is made to the RFP. | No
570 | Sections VIII–IX – General and Particular Conditions / GC 14.4 and 14.5; Contract; Data 14.5(b)(i)/(c)(i);; Section IV – Schedule of; Priced Activities and Sub-; activities. | Please confirm that payments for Plant and Materials eligible under Sub-Clause 14.5 may be certified in accordance with Sub-Clause 14.5 independently of their subsequent incorporation into the Works, and clarify how such payments should be reflected in the Schedule of Priced Activities and Sub-activities. | The Contract Data does not identify any Plant or Materials, categories or percentages eligible for separate payment under Sub-Clause 14.5 upon shipment or delivery to Site. Accordingly, the pre-incorporation payment mechanism under Sub-Clause 14.5 is not activated for this Contract. Payments shall be assessed and certified in accordance with the Schedule of Priced Activities and Sub-activities and the applicable provisions of Clause 14; no separate payment solely upon shipment or delivery is available under this clarification. | No
571 | Sections VIII–IX – Conditions of Contract / Contract Data 4.2; PC; 4.2.1; Section X –; Performance Security and; ES Performance Security; Forms. | Please clarify the calculation basis of the Performance Security and ES Performance Security. Contract Data Sub-Clause 4.2 states 6% and 1% respectively of the Accepted Contract Amount, whereas the corresponding guarantee forms refer to the Accepted Contract Amount less Provisional Sums, if any. Please confirm the correct calculation basis for both securities. | The Performance Security and Environmental and Social (E&S) Performance Security shall be provided in accordance with the forms and requirements set out in the Request for Proposals. The amounts of these securities shall be determined based on the applicable percentages specified in the RFP and shall not include the Provisional Sums. Accordingly, Provisional Sums should be excluded when calculating the value of the Performance Security and the E&S Performance Security. | No
572 | Sections VIII–IX – General and Particular Conditions / GC/PC 4.2.1; GC 13.7. | Please confirm whether “adjustments under Clause 13” in Sub-Clause 4.2.1 include Price Adjustments under Sub-Clause 13.7. If so, once the cumulative change exceeds 20% of the Accepted Contract Amount, please clarify how and when subsequent adjustments to the Performance Security and ES Performance Security will be determined. | The provisions of General Conditions 4.2.1 shall prevail. The E&S security shall also be increased accordingly. | No
573 | Sections VIII–IX – General and Particular Conditions / GC/PC 4.2.3; PC 14.9. | Please consider allowing a 50% reduction of the Performance Security and ES Performance Security upon issuance of the Taking-Over Certificate for the whole of the Works, with the remaining 50% maintained until the contractual release conditions are satisfied. | Please refer to Contract Data Sub-Clause 4.2 and the relevant security forms. The Performance Security and ES Performance Security shall be provided and maintained in the amounts and for the periods stated in the RFP. Their reduction, release and calling are governed by the Contract and the terms of the respective security. | No
574 | Sections VIII–IX – Conditions of Contract / Contract Data 14.3(iii);; GC/PC 14.9; Section X –; Retention Money Security. | Please consider allowing the Contractor, at its option, to replace Retention Money deductions during execution with an equivalent on- demand Retention Money Guarantee up to the applicable Retention Money limit. If accepted, please confirm the applicable adjustment and release mechanism. | No, Retention Money Security is not acceptable. Please refer to the Contract provisions governing Retention Money. Retention shall be deducted and released in accordance with the Contract. A Retention Money Security may be used only where expressly permitted by the Contract; no additional substitution mechanism is introduced by this clarification. | No
575 | Sections VIII–IX – General and Particular Conditions / GC 11.4(b)(ii); GC 3.7; GC; 20.2. | Please clarify the basis and methodology for determining any reduction in the Contract Price under Sub-Clause 11.4(b)(ii), including the objective criteria and supporting evidence to be used in quantifying the “reduced value to the Employer”. | Please refer to Section VII – Employer’s Requirements / GC 11.4(b)(ii); GC 3.7; GC; 20.2.. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. N | No
576 | Sections VIII–IX – General and Particular Conditions / GC 1.1.24, 1.1.27 and 10.1;; ER 10.6.2 and 10.6.4. | Please reconcile GC Sub-Clauses 1.1.24, 1.1.27 and 10.1 with ER Sections 10.6.2 and 10.6.4 and confirm: (i) whether the Defects Notification Period commences from the relevant Date of Completion or from the date of issuance of the Taking- Over Certificate; and (ii) whether the Taking-Over Certificate is issued by the Engineer under Sub-Clause 10.1 or by the Employer as stated in ER Section 10.6.2. | Please refer to Addendum No. 2, Amendment No. 21. | Yes
577 | Sections VIII–IX – General and Particular Conditions / GC 13.2–13.3; PC/Contract; Data 3.2; World Bank; Procurement Regulations,; Annex IX, 2.10. | Please specify the benefit-sharing mechanism applicable to Value Engineering proposals under GC Sub-Clause 13.2, including the percentage or methodology by which any resulting savings or other benefits will be shared between the Employer and the Contractor. | Value Engineering proposals shall be administered under Sub-Clause 13.2. Any sharing of savings or adjustment to the Contract Price shall be determined strictly in accordance with that Sub-Clause and the Engineer’s/Employer’s acceptance of the proposal. No additional percentage is introduced by this clarification. | No
578 | Sections VIII–IX – General and Particular Conditions / GC/PC 13.6; GC 13.7; GC; 20.2. | Please clarify the methodology for determining and quantifying the portion of any Cost arising from a Change in Laws that is considered to have already been compensated through the price-adjustment mechanism under Sub-Clause 13.7. | Any entitlement arising from a Change in Laws shall be determined in accordance with the applicable Contract provisions, taking account of amounts already compensated through the contractual price-adjustment mechanism under Sub-Clause 13.7 to avoid double recovery. The Contractor shall substantiate the net additional Cost and any time effect, including the causal link and the extent to which the relevant cost has not already been compensated by price adjustment. | No
579 | Section VIII – General Conditions / Sub-Clause 15.2.1; Section IX – Particular Conditions / Sub-Clause 15.2.1 – Contractor Default / KPI-related Termination | Please confirm that the additional KPI-related termination provisions introduced under PC Sub-Clause 15.2.1 are intended to constitute a separate termination ground and do not replace the existing bankruptcy/insolvency provision under GC Sub-Clause 15.2.1(g). Please issue a corrected and consistently lettered version of PC Sub-Clause 15.2.1. | Please refer to Addendum No. 2, Amendment No. 26. | Yes
580 | Section VII – Employer’s Requirements / PC 8.1(c); Contract Data; 2.1; ER RP/LRP provisions. | Please clarify the application of PC Sub-Clause 8.1(c) together with Contract Data Sub-Clause 2.1. In particular, please confirm whether effective access to the portions of the Site reasonably necessary to commence the Works will be sufficient for issuance of the Commencement Notice, and confirm whether such initial access is required before issuance of the Commencement Notice or no later than the Commencement Date. Please confirm that access to the remaining portions of the Site will be provided progressively in accordance with a defined sectional access schedule to be agreed between the Parties and reflected in the Contractor’s Programme. Please also confirm that any exclusion of entitlement to additional time or Cost in relation to the phased RP/LRP process applies only to the planned and timely phased implementation of such process, and does not affect the Contractor’s entitlement to EOT and/or Cost where access to any section is delayed beyond the agreed sectional access date for reasons not attributable to the Contractor. | The Commencement Notice, access to the Site and phased access shall be governed by Contract Data Sub-Clause 2.1, PC Sub-Clause 8.1(c), the Employer’s Requirements and the applicable land/resettlement provisions. The RFP does not establish through this clarification a separate guaranteed sectional-access schedule or confirm that all portions of the Site will be available on the Commencement Date. The Employer will make Site access available in accordance with the Contract and applicable land-acquisition/resettlement requirements. Any entitlement to EOT and/or Cost arising from delayed access shall be assessed under the relevant Contract provisions and claims procedure, taking account of responsibility, causation, critical-path effect, notice and substantiation; no automatic entitlement is created. | No
581 | Section VII – Employer’s Requirements / ER – S&T Interface; Requirements / Interface; Management. | Please specify a reasonable review and response period for the Engineer’s written confirmation required before close-out of structures or areas containing S&T provisions, and clarify the consequence if the Engineer does not respond within such period. | The Engineer’s review/response periods shall be those stated in the Contract and Employer’s Requirements. Where no specific period is stated for a particular coordination confirmation, the Contractor shall incorporate a reasonable review period in the approved programme and Interface Register. No deemed approval arises unless expressly provided by the Contract. | No
582 | Section VII – Employer’s Requirements / ER – Interface; Management provisions;; GC 8.5 and 20.2. | Please confirm that the exclusion of EOT and additional Cost for interface coordination, harmonisation, data reconciliation and related revisions applies only to normal coordination obligations and does not apply where delay or additional work is caused by the Employer, the Engineer or another Employer-appointed contractor. | Please refer to Section VII – Employer’s Requirements / ER – Interface; Management provisions;; GC 8.5 and 20.2.. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
583 | Sections VIII–IX – General and Particular Conditions / GC/PC 14.2.1; Section X –; Advance Payment; Guarantee Form. | Please confirm that the amount of the Advance Payment Guarantee shall be progressively reduced in line with the advance payment amounts repaid through the Payment Certificates. Alternatively, if reduction following each Payment Certificate is not intended, please confirm that the Advance Payment Guarantee may be reduced quarterly based on the cumulative amount of advance payment actually repaid. | The Advance Payment Guarantee shall be maintained and reduced in accordance with the Advance Payment provisions and the form of guarantee included in the RFP. Any reduction shall correspond to the amount of advance payment recovered, subject to the wording of the guarantee and the Contract. | No
584 | Section VII – Employer’s Requirements / PC 14.6.2 and PC 14.6.3. | Please confirm that the same factual breach or event shall not give rise to duplicate or cumulative withholding under both Sub-Clause 14.6.2 and Sub-Clause 14.6.3. In particular, where an ES, local labour, cyber-security or other compliance issue is also relevant to KPI performance, any withholding should be applied only once and should not be duplicated by characterising the same facts as separate contractual breaches, unless there are genuinely distinct obligations and separately identifiable losses or consequences. | The Advance Payment Guarantee shall be maintained and reduced in accordance with the Advance Payment provisions and the form of guarantee included in the RFP. Any reduction shall correspond to the amount of advance payment recovered, subject to the wording of the guarantee and the Contract. | No
585 | Sections VIII–IX – General and Particular Conditions / GC 14.8; Contract Data; 14.8. | If it is confirmed that the 1% rate applies to the delayed-payment financing charge under Sub-Clause 14.8, please consider increasing the applicable percentage. | There will be no change to the rate specified in the RFP. The rate stipulated in Sub-Clause 14.8 shall prevail. | No
586 | Section VII – Employer’s Requirements / PC 14.6.5. | Please confirm the consequence if the Engineer does not respond within the accelerated two (2) Business Day response period for Critical KPI data disputes under Sub-Clause 14.6.5. In particular, please clarify whether the Contractor’s position will be deemed accepted, whether the disputed KPI Performance Withholding will be suspended or released pending resolution, or whether the matter will automatically proceed to the senior representatives’ meeting / DAAB procedure. | No deemed acceptance or automatic release arises if the Engineer does not respond within the two (2) Working Day period. Any disputed KPI Performance Withholding shall remain subject to Sub-Clause 14.6.5 and, if applied, shall be recorded in the notional KPI Performance Account pending resolution. Further escalation shall proceed in accordance with Sub-Clause 14.6.5 and Clause 21. No amendment is made to the RFP. | No
587 | Section VII – Employer’s Requirements / PC 14.6.3; ER 12.2; GC 8.5; and 18.4. | Please consider amending the KPI regime so that, where the Contractor claims that a KPI has been affected by an Employer-risk event, Exceptional Event or other event giving rise to an Extension of Time, the relevant KPI Performance Withholding is suspended pending the Engineer’s determination. If the Engineer determines that the event directly and materially prevented achievement of the relevant KPI, the suspension should continue for the affected period and the relevant reporting periods should not count towards sustained breach, recovery, forfeiture or Critical KPI termination thresholds. If the Engineer determines otherwise, the relevant withholding may then be applied in accordance with the Contract. | The KPI regime shall be administered in accordance with the relevant Particular Conditions, including the stated notice, objection, review and dispute procedures. The requests to introduce additional deemed-acceptance, duplicate-recovery or automatic-relief mechanisms are not accepted unless already provided by the Contract. | No
588 | Section VII – Employer’s Requirements / PC 14.6.6. | Please consider amending Sub-Clause 14.6.6 so that KPI target review is available for any Variation, Employer-risk event, Exceptional Event or other change that materially affects KPI performance, irrespective of whether the 5% value threshold is met. Please also consider that, once the Contractor submits a KPI target review request with supporting particulars, the affected KPI targets and any related KPI Performance Withholding should be suspended from the date the Engineer’s review commences until completion of the review process and any required Employer approval. If the review confirms that the relevant event materially affected KPI performance and the Employer approves the revised targets, the revised KPI targets should apply from the date the event first affected performance. | The KPI regime shall be administered in accordance with the relevant Particular Conditions, including the stated notice, objection, review and dispute procedures. The requests to introduce additional deemed-acceptance, duplicate-recovery or automatic-relief mechanisms are not accepted unless already provided by the Contract. | No
589 | Section VII – Employer’s Requirements / PC 14.6.6. | Please also consider including a deemed acceptance mechanism where the Engineer does not convene the KPI Target Review Meeting, issue its review outcome, or otherwise progress the review within the prescribed timeframes, or where the Employer does not respond to a proposed revised KPI target within a defined period. In such case, the affected KPI target and related KPI Performance Withholding should remain suspended until the review is completed or the matter is referred to the DAAB. | The request is not accepted. Sub-Clause 14.6.6 does not provide deemed acceptance or automatic suspension of KPI targets or KPI Performance Withholding. Pending completion of the review, the existing KPI targets continue to apply, and any revised target takes effect only after the Employer’s written approval and entry in the KPI Target Register. No amendment is made to the RFP. | No
590 | Section VII – Employer’s Requirements / PC 8.8; Contract Data 8.8. | Please confirm that the same period of delay shall not be subject to duplicate or cumulative Delay Damages under more than one Milestone. Please also confirm that any Delay Damages applied in respect of interim Milestones shall be reimbursed or credited to the Contractor if the Works are ultimately completed within the overall Time for Completion | Delay damages shall be applied in accordance with Sub-Clause 8.8 to the relevant Milestone, subject to any Extension of Time determined under the Contract and the applicable maximum cap. The Contract does not provide for refund or credit of delay damages validly accrued for an earlier Milestone merely because a later Milestone or the overall Works are completed on time. No amendment is made to the RFP. | No
591 | Sections VIII–IX – General and Particular Conditions / GC 8.10; GC 20.2. | Please confirm that, for the purposes of GC 8.10, “Cost” includes reasonable and demonstrable amounts incurred or payable by the Contractor to its Subcontractors as a direct consequence of an Engineer-instructed suspension for a cause not attributable to the Contractor, including standby, idle labour and equipment, demobilisation/remobilisation, prolongation and protection costs, subject to the substantiation requirements of GC 20.2. | For the purposes of GC Sub-Clause 8.10, “Cost” is determined in accordance with the Contract and may include reasonable and demonstrable costs directly incurred or payable to Subcontractors as a direct consequence of an Engineer-instructed suspension for a cause not attributable to the Contractor, subject to the requirements of Sub-Clause 8.10 and the notice, substantiation and claims procedures under Sub-Clause 20.2. The Contractor must demonstrate causation, reasonableness, mitigation and the link to the suspension. No automatic entitlement to any specific cost category or amount is created by this clarification. | No
592 | Sections VIII–IX – General and Particular Conditions / GC/PC 1.15; applicable; indemnity provisions. | Given the urban context of the Project alignment and the potential interface with nearby buildings, utilities and infrastructure, please consider clarifying and amending the Contract to provide that Contractor liability for damage to third-party property arising from tunnelling, excavation, settlement, vibration or related construction activities should sit within the Contractor’s overall limitation of liability under Sub-Clause 1.15, except to the extent such damage is caused by the Contractor’s fraud, gross negligence or wilful misconduct. This would align the risk allocation with market-standard liability principles for large urban infrastructure projects. | Please refer to Section VII – Employer’s Requirements / GC/PC 1.15; applicable; indemnity provisions.. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
593 | Section VII – Employer’s Requirements / PC 14.6.3; GC/PC 1.15. | Please confirm that any KPI Performance Withholding under Sub-Clause 14.6.3 shall count toward, and be subject to, the Contractor’s overall limitation of liability under Sub-Clause 1.15. | The KPI regime shall be administered in accordance with the relevant Particular Conditions, including the stated notice, objection, review and dispute procedures. The requests to introduce additional deemed-acceptance, duplicate-recovery or automatic-relief mechanisms are not accepted unless already provided by the Contract. | No
594 | Section III – Evaluation and Qualification Criteria / RFP / Section III –; Evaluation and; Qualification Criteria | With reference to the RFP / Section III – Evaluation and Qualification Criteria / For contracts denominated in United States Dollars (USD): The contract price at contract signing date shall be updated to present value using the U.S. Bureau of Labor Statistics (BLS) Producer Price Index (PPI): Final Demand (Series ID: WPUFD4), based on the index value applicable 14 days prior to the bid submission deadline. However, we note that the historical data available for Series WPUFD4 goes back only to November 2009, while some of our similar contracts were signed before this date. Could you please clarify how the contract prices of projects signed before November 2009 should be updated to present value? | The U.S. Bureau of Labor Statistics (BLS) website (https://www.bls.gov/) provides historical data through its Data Tools section. Proposers are advised to consult the relevant datasets and retrieve the historical data corresponding to the periods required for preparation of their Proposals. As the required data is publicly available through the BLS website, Proposers should identify and use the applicable indices and reference periods relevant to their Proposal. | No
595 | Section III – Evaluation and Qualification Criteria / 5.2.3 (OHS —; LTIFR) | For "Evidence of the bidder's LTIFR on comparable projects," please clarify: (i) the definition of a Lost Time Injury — i.e. the threshold that counts (e.g. ≥1 lost workday, >3 lost days) and whether restricted-work cases and fatalities are included (ii) the calculation/normalisation basis (per 200,000 or 1,000,000 hours); ; (iii) the reference period; and (iv) JV treatment (each member vs aggregate) and whether subcontractor hours are included. | For the purpose of the Rated Criterion, the Proposer shall state the LTIFR definition and calculation basis used for the submitted comparable projects and provide verifiable supporting records. The Employer will evaluate the evidence on a consistent basis against the criterion; the RFP does not introduce a different project-specific LTIFR definition through this clarification. | No
596 | Section III – Evaluation and Qualification Criteria / 5.3.5 / 5.4.3 /; 6.2.3 (E&S evidence) | For the E&S evidence sub-factors (environmental past-implementation 5.3.5; comparable biodiversity management on infrastructure projects 5.4.3; outcome-driven mitigation 6.2.3), please define "comparable/infrastructure projects" (is it the qualification "Similar contracts" definition?), the acceptable evidence format (client references, audit/monitoring records, certificates), the number of reference projects for full marks, and the acceptable period. | Please refer to Section II – Proposal Data Sheet (PDS)I 5.3.5 / 5.4.3 /; 6.2.3 (E&S evidence). The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
597 | Section X – Contract; Agreement, Clause 2;; GC/PC Sub-Clause 1.5; [Priority of Documents];; Section VII – Employer’s; Requirements | Please clarify the relationship between the contract-wide order of precedence under the Contract Agreement and GC/PC Sub-Clause 1.5 and the separate hierarchy stated within the Employer’s Requirements. We understand that the Contract Agreement and GC/PC Sub-Clause 1.5 govern priority between the principal Contract documents, while the hierarchy stated within the Employer’s Requirements applies only to resolving inconsistencies among the Employer’s Requirements and their Annexes/Technical Specifications. Please confirm our understanding. If this is not the intended interpretation, please provide the complete harmonized order of precedence to be applied. | The Contract-wide order of precedence under the Contract Agreement and Sub-Clause 1.5 governs the Contract Documents. Any internal hierarchy stated within the Employer’s Requirements applies within that document set and does not override the Contract-wide order of precedence. | No
598 | Section VII – Employer’s Requirements / PDS ITP 16.1(b); PDS ITP; 38.1; Appendix to Proposal; – Table C | Please specify the required source and reference date for the exchange rates to be entered by the Proposer in Appendix to Proposal – Table C under PDS ITP 16.1(b), considering that such rates will apply to Contract payments, while PDS ITP 38.1 uses the TCMB selling exchange rates applicable on the Proposal submission deadline for Proposal evaluation. | As specified in PDS - ITP 16.1: “The rates of exchange to be used by the Proposer in arriving at the local currency equivalent and the percentage(s) mentioned in (a) above shall be specified by the Proposer in the Appendix to Proposal - Table C, and shall apply for all payments under the Contract so that no exchange risk will be borne by the successful Proposer.” Accordingly, each Proposer shall determine and specify the currencies and exchange rates to be used in its Proposal in accordance with the requirements of ITP 16.1 and Table C of the Appendix to Proposal. The exchange rate source and currency specified under ITP 38.1 are intended solely for the purpose of proposal evaluation and conversion of proposal prices to a common currency. They shall not be used for determining the currencies or exchange rates applicable to payments under the Contract. | No
599 | Sections VIII–IX – General and Particular Conditions / GC 1.13(a)–(b); ER 7.6. | Please provide a Lot-specific Permit and Approval Responsibility Matrix identifying each material permit, approval, consent, licence, no- objection or authorisation required for the Works, the responsible Party, the relevant authority/asset owner, the applicant/signatory and any Employer/AYGM assistance or coordination required. | The allocation of permits, approvals and third-party consents shall be determined from the Contract and the Employer’s Requirements, including the interface and statutory-approval provisions. The Contractor shall prepare and maintain the detailed Permit/Approval Register as part of contract implementation. No separate tender-stage matrix is issued by this clarification. | No
600 | Section VII – Employer’s Requirements / World Bank Procurement; Regulations for IPF; Borrowers, Seventh; Edition, September 2025,; Annex II, para. 9.1(b)–(c);; GC 13.1–13.3. | Please confirm whether the Contracts awarded under this RFP will be subject to the World Bank’s prior review. If so, please confirm that, in accordance with Annex II, paragraph 9.1(c) of the World Bank Procurement Regulations for IPF Borrowers, the Bank’s prior no-objection will be required before agreeing to any Variation Order or Contract amendment which, singly or cumulatively with previous Variations/amendments, increases the original Contract amount by more than 15%. Please also confirm the applicability of paragraph 9.1(b) to any material modification of the scope or other significant change, irrespective of the 15% threshold. | The World Bank’s review arrangements are matters between the Borrower/Employer and the Bank under the financing/procurement framework. They do not modify the Proposer’s obligations or create a separate contractual approval condition unless expressly stated in the RFP. | No
601 | Section VII – Employer’s Requirements / PC 14.6.3 and 14.6.5. | Please clarify the relationship between the pre-withholding objection procedure under PC Sub-Clause 14.6.3 and the KPI Data Dispute Resolution Procedure under PC Sub-Clause 14.6.5. Please confirm that a single written notice submitted within the earliest applicable time limit, and containing the information required under both Sub-Clauses, may satisfy both procedures without requiring duplicate notices and shall preserve the Contractor’s right to refer the KPI data dispute to the DAAB. | The pre-withholding objection procedure under Sub-Clause 14.6.3 and the KPI Data Dispute Resolution Procedure under Sub-Clause 14.6.5 are separate requirements. A single written submission may address both only if it is clearly identified for both purposes, is submitted within the earliest applicable time limit, and contains all information required under both Sub-Clauses. Compliance with Sub-Clause 14.6.5 remains a condition precedent to referral of a KPI data dispute to the DAAB. No amendment is made to the RFP. | No
602 | Sections VIII–IX – General and Particular Conditions / GC 1.1.73, 14.3, 14.4; PC; 14.3–14.4; ER 4.9.1, 4.9.2,; 4.9.4 | Please confirm that monthly interim payments for lump-sum Activities and Sub-activities shall be valued proportionally based on the actual percentage of compliant work completed during the relevant payment period, and that payment shall not be deferred until full completion of an Activity or Sub-activity unless the relevant payment is expressly identified as a completion-based Milestone in the Schedule of Payments. Please also provide or clarify the intended Schedule of Payments, as the Schedule of Payments included in Section IV currently does not specify any instalments, percentages or payment Milestones. | Please refer to Answer 7. | No
603 | Section VII – Employer’s Requirements / PC 14.6.2 | Please clarify the procedure and calculation basis for any withholding under Sub-Clause 14.6.2. Please confirm that any amount withheld shall be limited to the value, rectification/replacement cost or amount directly affected by the relevant non-compliance, unperformed obligation or error, as applicable, and that the Engineer shall provide the Contractor with the calculation and reasons supporting the withholding. Please also clarify whether the Contractor will be given an opportunity to respond to the proposed withholding before it is applied in the relevant IPC, and when the withheld amount will be released following remedy of the relevant non-compliance or performance of the obligation. | Withholding under Sub-Clause 14.6.2 shall be limited to the amount determined by the Engineer under the applicable provision, including, where relevant, the value of the unperformed obligation/work or the cost of rectification or replacement. The amount may remain withheld until the relevant obligation has been performed or the rectification/replacement completed. Sub-Clause 14.6.2 does not establish a separate pre-withholding objection procedure; any dispute shall be dealt with under the applicable Contract provisions. No amendment is made to the RFP. | No
604 | Section VII – Employer’s Requirements / PC 15.2.1; PC 14.6.3–14.6.5 | Please confirm that, where the Contractor implements the permanent corrective measures required by a Notice to Correct within the 28-day period under PC Sub-Clause 15.2.1, the Contractor shall be allowed the following two consecutive reporting periods to demonstrate maintained compliance with the relevant Critical KPI, and that the Employer shall not exercise the corresponding termination right during that verification period. | The KPI regime shall be administered in accordance with the relevant Particular Conditions, including the stated notice, objection, review and dispute procedures. The requests to introduce additional deemed-acceptance, duplicate-recovery or automatic-relief mechanisms are not accepted unless already provided by the Contract. | No
605 | Section I – Instructions to Proposers / ITP 12.5; Contract Data /; PC 21.1 and 21.6 | Please clarify the application of the nationality requirement under PC Sub-Clause 21.1 where the Proposer is a Joint Venture comprising both Turkish and foreign members. In particular, if such Joint Venture is treated as a “foreign Contractor”, please confirm: (i) whether DAAB candidates proposed by either the Employer or the Proposer must not have Turkish nationality, being the nationality of the Employer; (ii) how the nationality of the “Contractor” is to be determined for a mixed-nationality JV for the purpose of assessing DAAB member eligibility; and (iii) whether the Turkish DAAB candidates currently proposed by the Employer under Contract Data Sub-Clause 21.1 would remain eligible in such case. | Part B – Special Provisions, Sub-Clause 21.1 states that, where the Contract is with a foreign Contractor, DAAB members shall not have the same nationality as the Employer or the Contractor. Please refer to Addendum No. 2, Amendment No. 20, for the determination of a JV’s status and the treatment of JV-member nationalities. If the successful Contractor is determined to be a foreign Contractor, all DAAB members, including candidates proposed by the Employer, shall be appointed in compliance with the applicable nationality requirements during Contract finalization and signing. A candidate who does not meet those requirements will not be eligible for appointment. | Yes
606 | Section I – Instructions to Proposers / ITP 12.5; Letter of Proposal; – Technical Part | Where a Proposer submits a Proposal for more than one Lot, please confirm whether the same three potential DAAB members may be proposed for all Lots. If separate DAAB candidate lists are required for each Lot, please confirm that three different potential DAAB members, together with their respective CVs, shall be submitted for each Lot. | Please refer to Section IX, Clause 21 and Addendum. The DAAB nomination, nationality, remuneration and cost-sharing requirements shall be applied as stated therein. The same candidates may be proposed for more than one Lot provided that the RFP requirements are satisfied and their availability/independence is demonstrated. | No
607 | Section III – Evaluation and Qualification Criteria / Item 1.5; Contractor’s Equipment;; Section IV – FORM EQU;; ER Section 2.4 | Please clarify whether the specific key equipment identified in FORM EQU at Proposal stage will become contractually binding upon Contract award. If so, please confirm whether the Contractor may subsequently replace or substitute any proposed equipment with alternative equipment meeting or exceeding the specified minimum characteristics, capacity and performance requirements, subject to the Engineer’s prior written approval, and clarify the applicable approval procedure. If the individual equipment items are not contractually binding, please confirm that the Contractor may change the proposed make, model, source or specific unit after Contract award, provided that the required minimum quantity, characteristics, capacity, performance and availability are maintained. | The equipment proposed in Form EQU forms part of the qualification basis of the Proposal. Following award, the Contractor shall provide equipment meeting or exceeding the stated capability and availability requirements. Any proposed replacement shall be subject to the Contract/Engineer’s approval and shall not reduce the Contractor’s demonstrated capacity. | No
608 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria –; Page 69, Section 4.; Multiple Contracts (ITP; 40.3) | According to the provisions set forth under Section 4, it is understood that the reference projects submitted under Section 4.2(a) Specific Construction & Contract Management Experience are required to be demonstrated separately for each Lot. In this regard, we kindly request clarification as to whether the reference projects submitted under Section 4.2(a) are also required to be used for demonstrating compliance with Section 4.2(b) Specific Similar Construction & Contract Management Experience, or whether bidders may submit different reference projects under Section 4.2(b), provided that the relevant qualification requirements are satisfied. Furthermore, for bidders submitting proposals for multiple Lots, we would appreciate clarification on the application of the qualification requirements under Section 4.2(b) in conjunction with the provisions of Multiple Contracts (ITP 40.3). Specifically, where a qualification criterion such as: “Experience in the design of railway systems (including tunnels) with a route length of at least 20 km under a single contract” is specified under Section 4.2(b) for each Lot, can the same 20 km reference project be used to demonstrate compliance for all four Lots, or is the bidder required to demonstrate the criterion cumulatively across the Lots (i.e., 20 km × 4 = 80 km in total)? More generally, when a bidder is evaluated for the award of multiple Lots, should the qualification thresholds defined under Section 4.2(b) be assessed on a cumulative basis, or may the same qualifying reference project(s) be relied upon across multiple Lots? | As stated in the Qualification - 4.(b) For the above and any other contracts substantially completed and under implementation (referenced by the proposer for 4.2(a) or any orher contracts) may be used to satistfy the requirements of 4.2(b). As specified in Section III, "The criteria for qualification are the aggregate (cumulative sum of) minimum requirement for respective lots as specified under items 3.1 (financial capability), 3.2 (average annual construction turnover), 4.2(a) (Specific Construction & Contract Management Experience) and 4.2(b) (Key Activities) of Section III." Accordingly, for evaluation of 4.2(b) the cumulative of the Lots will be considered, this includes aggregate sum of the minimum thresholds specified for each Lot. | No
609 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria –; Page 62 – Factor 3: Similar; Work Experience | We kindly request clarification regarding the evaluation methodology applicable to Factor 3: Similar Work Experience. Our understanding is that the technical scoring under this factor will be determined exclusively based on the references submitted pursuant to Section 4.2(b) Specific Similar Construction & Contract Management Experience, whereas the experience demonstrated under Section 4.2(a) Specific Construction & Contract Management Experience will be considered solely for qualification purposes and will not contribute to the technical evaluation score. Please confirm whether this interpretation is correct. | The requirements set out under Section 4.2(a) and (b), Specific Similar Construction and Contract Management Experience, are qualification requirements that will be assessed on a pass/fail basis to determine the Proposer's eligibility and qualification. In contrast, Factor 3 forms part of the rated evaluation criteria and will be assessed and scored against the applicable sub-factors. While there may appear to be some overlap between the qualification requirements and the rated criteria, the evaluation under Factor 3 and its respective sub-factors may require different supporting documentation. Proposers are therefore advised to carefully review each sub-factor and submit adequate documentary evidence demonstrating the relevant experience and qualifications required for scoring under the rated criteria. | No
610 | Section VII – Employer’s Requirements / Annex G - Track Works; (Superstructure) Technical; Specifications | Page 27: 6.2. Determination of the Suitability of a New Sub-Ballast Source All reports and documents relating to the operation of the specified quarry (quarry licence, drilling studies, EIA reports, reserve calculations, etc.) must be submitted to the Employer by the Tenderers. Page 38: NOTE: Form to be completed by individuals or companies participating in the tender Please clarify whether the above documents are required to be submitted with the Proposal, or whether they are to be provided after Contract award as part of the material/source approval process. | Please refer to Answer 203. | No
611 | Section VII – Employer’s Requirements / Annex G - Track Works; (Superstructure) Technical; Specifications | Page 4: 2.2.1. Sampling from the Quarry and Determination of Conformity Following the collection of samples from the quarry, the Bidders shall deliver the relevant ballast samples to the laboratory prior to the tender date and shall submit the delivery records for the samples they have delivered, together with receipts confirming payment of the testing fees, along with their tenders. Do these reports, forms and documents have to be delivered to the Employer together with the tender submission documents, since this is not a single procurement tender of related material? | Please refer to Addendum No. 2, Amendment No. 16. The pre-tender ballast sample delivery and testing-fee receipt requirement in Annex G3 Clause 2.2.1 has been deleted. No further amendment is made to the RFP. | Yes
612 | Section I – Instructions to Proposers / ITP 12.2(h), p.12; ITP 30.2,; p.24 | ITP 12.2(h) requires the Technical Part to include “Details of any departures in their Technical Part from the RFP documents”, whereas ITP 30.2 provides that a Proposal containing a material deviation, reservation or omission would not be considered substantially responsive. Please clarify the intended scope of the requirement under ITP 12.2(h). Where the Proposer has no departures from the RFP Documents, please confirm whether a separate “NIL / No Departures” statement is required and, if so, specify the required format and location within the Technical Proposal. | In case there is no departures from the RFP document, Proposers are not required to submit additional documents. | No
613 | Section I – Instructions to Proposers / PDS ITP 12.3(e), p.39; PDS; ITP 22.1(b), p.42 | PDS ITP 22.1(b) requires separate digital copies of the Technical Part and Financial Part on USB, while ITP 12.3(e) additionally requires the priced Price Schedules to be provided digitally on CD/USB Memory within the Financial Proposal. Please confirm whether the priced Price Schedules may be included in the same USB containing the Financial Part, or whether a separate CD/USB Memory shall be provided. | The priced Price Schedules may be submitted in electronic format on a CD or USB memory device as part of the Financial Proposal. The priced Price Schedules and the Financial Proposal in electronic format should be enclosed within the envelope containing the Financial Proposal, in accordance with PDS ITP 22.1(b) and ITP 12.3(e). | No
614 | Section VII – Employer’s Requirements / ER 5.1, pp.218–219; ITP; 12.4 | ER Section 5.1 requires the Tenderer to provide an itemized summary of the principal Contractor’s preliminaries and indirect cost categories, identify the principal assumptions underlying the Tender Price, describe the methodology adopted for major cost and schedule risks, and provide a summary explanation of the risk allowance and contingency approach. Please clarify in what form/document within the Financial Proposal this information shall be submitted, and whether a separate statement/schedule is required. | The information required by Employer’s Requirements Section 5.1 shall be included as a clearly identified statement within the Financial Proposal, unless a particular item is expressly required elsewhere in the RFP. The statement should itemize the principal preliminaries and indirect cost categories, state the principal assumptions underlying the Tender Price, describe the methodology for major cost/schedule risks and summarize the risk allowance/contingency approach. No separate prescribed form is identified in the RFP; the information must be provided in a manner consistent with ITP 12.4 and must not disclose financial information in the Technical Part. | No
615 | Section VII – Employer’s Requirements / Clauses 7.7 and 8.2; Annex O – BIM Technical Specification / Clause 6.1 (BIM Execution Plan) | Annex O – BIM Technical Specification, Clause 6.1 refers to the “Draft BIM Execution Plan submitted during the tender proposal stage”, and Annex 1 provides a Draft BIM Execution Plan Template. However, a Draft BIM Execution Plan is not expressly listed among the tender-stage submission requirements in the RFP/PDS/Proposal Forms. Please confirm whether a Draft BIM Execution Plan is required to be submitted as part of the Proposal. If so, please clarify under which part/section of the Proposal it shall be submitted. | No. Submission of a Draft BIM Execution Plan (BEP) as part of the Proposal is not required. Please refer to Section VII – Employer’s Requirements, Clauses 7.7 and 8.2, and Addendum No. 2, Amendment No. 27 (Annex O, Clause 6.1). The BIM Execution Plan is a mandatory post-award deliverable and shall be submitted to the Engineer for review and consent within twenty-eight (28) days of Contract award. The BEP shall be approved before the commencement of any Detailed Design activities. Accordingly, the reference in Annex O, Clause 6.1, to a Draft BIM Execution Plan submitted during the tender proposal stage shall not be interpreted as a requirement for Proposal submission. | Yes
616 | Section VII – Employer’s Requirements / Clause 7.7; Annex O – BIM Technical Specification / Clause 6.1 (BIM Execution Plan) | Annex O – BIM Technical Specification, Clause 6.1 states that the BIM Execution Plan shall be submitted within 30 working days following the relevant Site handover, whereas ER Clause 7.7 requires the BIM Execution Plan to be submitted within 28 days after Contract award. Please clarify which requirement shall prevail and confirm the applicable triggering event and submission deadline for the BIM Execution Plan. | Please refer to Addendum No. 2, Amendment No. 27 (Annex O, Clause 6.1), and Section VII – Employer’s Requirements, Clause 7.7. The BIM Execution Plan shall be submitted to the Engineer for review and consent within twenty-eight (28) calendar days after Contract award. The triggering event shall be the Contract award date, not the Site handover date. Annex O, Clause 6.1, is amended accordingly to ensure consistency with ER Clause 7.7. | Yes
617 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria | With reference to Section III – Evaluation and Qualification Criteria, Criterion 3.2 – Average Annual Construction Turnover: “Minimum average annual construction turnover of: For Lot 1: USD 732,000,000 (Seven Hundred Thirty-Two million USD) For Lot 2: USD 410,000,000 (Four Hundred Ten million USD) For Lot 3: USD 390,000,000 (Three Hundred Ninety million USD) For Lot 4: USD 704,000,000 (Seven Hundred Four million USD), calculated as total certified payments received for contracts in progress and/or completed within the last 5 years (2021, 2022, 2023, 2024 and 2025), divided by 5 years.” We understand that the “Construction Income” figures stated in our Audited Financial Statements / Independent Auditor’s Reports for the respective years may be used in Form FIN-3.2 for the calculation of the Average Annual Construction Turnover required under Criterion 3.2. Please confirm whether our understanding is correct. | Please refer to Answer 9. | No
618 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria | With reference to Section III – Evaluation and Qualification Criteria, Clause 3.1 Financial Capabilities and Form FIN-3.1, we understand that the financial information in Form FIN-3.1 shall be completed based on financial statements audited by an independent audit firm. Due to company mergers and inflation accounting, our 2025 audited financial statements include the financial information for the years 2025, 2024, 2023 and 2022, while the financial information for 2021 is presented in a separate audited financial statement. Accordingly, we understand that Form FIN-3.1 may be completed based on the 2025 audited financial statements covering the years 2025, 2024, 2023 and 2022, together with the separate 2021 audited financial statements, and that both sets of audited financial statements may be submitted as supporting documents. Kindly confirm whether our understanding is correct. | Form FIN-3.1 shall be completed in accordance with its instructions using the Proposer’s financial information and identified sources of finance. The information is used for qualification and does not replace the project cash-flow/rated-criteria submissions required elsewhere in the Technical Proposal. | No
619 | Section VII – Employer’s Requirements / Annex E1 §5.12.1; Annex E4 | Reference is made to Annex E1 §5.12.1 "Bridges – Viaducts and Engineering Structures" and to Annex E4 in its entirety. Both documents establish a complete design basis for railway bridges, and the two bases differ in load models, dynamic factors, horizontal actions, derailment actions and the limit state framework. Reference is further made to the cover sheet of Annex E, which places the Design Services Annex above the Discipline-Specific Technical Specifications in the order of precedence while stating in the accompanying text that the Design Services Annex does not supersede the technical requirements of any discipline-specific Technical Specification. We note that Annex E3 contains an express disclaimer subordinating itself to the Employer’s Requirements, whereas Annex E4 contains no equivalent provision. We therefore kindly ask the Employer to confirm that Annex E4 governs the design of railway bridges in its entirety, and that the loading and design provisions of Annex E1 §5.12.1 and §4.3.4 are superseded and are to be disregarded. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. Please also refer to Amendment No. 40. Railway bridge and viaduct loading and action requirements shall be governed by Annex E4, including its applicable load models, dynamic effects, centrifugal and nosing forces, braking and derailment actions, and load combinations. The original Annex E1 Clause 5.12.1 is superseded. | Yes
620 | Section VII – Employer’s Requirements / Annex E4 §1.1; Annex E1; §5.12.1 and §5.12.2 | Reference is made to Annex E4 §1.1, which states that the specification covers the design and assessment of railway bridges, and to Annex E1 §5.12.1 and §5.12.2, which address bridges, viaducts, engineering structures, tunnels and cut-and-cover structures under a single heading. The scope boundary between the two documents is therefore undefined for viaducts, culverts, cut-and-cover box structures, retaining walls, overbridges and buried structures carrying or crossed by the railway. We kindly ask the Employer to clarify which document governs each of these structure types. | Annex E4 governs the railway-specific design requirements for the rail-carrying parts of bridges and viaducts. Other structure types remain subject to their relevant discipline-specific specifications. Please refer to Addendum No. 2, Amendments Nos. 31 and 40, and the revised Annex E1 attached thereto; the original Annex E1 Clause 5.12.1 is superseded. | Yes
621 | Section VII – Employer’s Requirements / Annex E4 §1.4; Annex E4; §3.8 | Reference is made to Annex E4 §1.4, which sets the service life of standard bridges at 100 years and states that Special Bridges are subject to their own Special Technical Specifications, and to Annex E4 §3.8, which classifies suspension bridges, cable-stayed bridges and arch bridges as Special Bridges in accordance with TKDY-2020. The Works include modification of the Yavuz Sultan Selim Bridge, which is a suspension bridge and therefore a Special Bridge. No Special Technical Specification for that structure has been included in the Tender documentation. We kindly ask the Employer to issue the applicable Special Technical Specification, or alternatively to confirm the design basis, performance objectives and seismic performance levels to be adopted for that structure. | Please refer to Section VII – Employer’s Requirements / Annex E4 §1.4; Annex E4; §3.8. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
622 | Section VII – Employer’s Requirements / Annex E1 §4.3.1; Annex E4; §1.4 | Reference is made to Annex E1 §4.3.1, Table 4.1 "Design service life", which carries a caption but contains no content, and to Annex E4 §1.4, which sets 100 years for standard bridges. We kindly ask the Employer to issue the content of Table 4.1 and to confirm whether the 100-year service life applies to all permanent structures of the Works, including tunnels, cut-and-cover structures, retaining structures and stations. | The required design service life shall be as stated in the applicable discipline-specific Technical Specification. Where Annex E4 specifies the service life for railway bridges, that requirement governs railway bridges; component service lives shall comply with the relevant product/device specifications and maintenance/replacement strategy. | No
623 | Section VII – Employer’s Requirements / Annex E4 §3.5.3.2 | Reference is made to Annex E4 §3.5.3.2, which requires the characteristic values of Load Model LM 71 to be multiplied by the classification factor α selected from the series 0.75, 0.83, 0.91, 1.00, 1.10, 1.21, 1.33 and 1.46, and which states that α ≥ 1 is recommended for international lines and that the factor may be specified project- specifically by the Authority. No value of α is stated in Annex E4, Annex E1 or any other Tender document, notwithstanding that Annex E1 §2.1 specifies a 25 t axle load and TSI freight category E4. Since α governs the vertical loads and, where greater than unity, also the nosing, traction, braking and derailment actions, tenderers will otherwise price structures of materially different capacity for the same scope. We kindly ask the Employer to state the value of α to be applied. | Please refer to Answer 122. | No
624 | Section VII – Employer’s Requirements / Annex E4 §3.5.3.3; Annex E4 §3.5.5.1 | Reference is made to Annex E4 §3.5.3.3, which states that the lines or line sections for which Load Model SW/2 is to be taken into account shall be specified by the Authority, and to Annex E4 §3.5.5.1, which permits a different maximum speed of 80 km/h to be accepted for SW/2. Annex E1 §2.1 lists SW/2 among the applicable load models but identifies no sections. We kindly ask the Employer to state the sections of the line for which SW/2 applies, and the maximum speed to be associated with that load model. | Please refer to Addendum No. 2, Amendment No. 29, Section VII, Annex E4, including Clauses 3.5.3.3 and 3.5.5.1. The amendment will identify the sections for which Load Model SW/2 applies and the associated maximum speed, or specify the common assumption to be used by all Proposers where no default standard value exists. The applicable values/applicability decisions shall be clarified before Proposal submission so that Proposers do not adopt inconsistent design assumptions. | Yes
625 | Section VII – Employer’s Requirements / Annex E4 §3.5.4.5 | Reference is made to Annex E4 §3.5.4.5, which requires the dynamic factor to be taken as Φ2 for lines where maintenance is carried out with care and diligence and as Φ3 for lines with standard maintenance, and which further states that Φ3 shall be used where no dynamic load factor has been specified. The two factors differ materially, Φ2 being bounded at 1.67 and Φ3 at 2.00. No election is made in the Tender documentation. We kindly ask the Employer to state whether Φ2 or Φ3 applies, having regard to the maintenance regime envisaged for the line. | Please refer to Addendum No. 2, Amendment No. 28, Section VII, Annex E4 Clause 3.5.4.5. The dynamic factor Φ3, applicable to lines with standard maintenance, shall be used for Load Models LM71, SW/0 and SW/2 and calculated using the applicable determinant length LΦ. Where Annex E4 requires dynamic analysis, the corresponding track-irregularity effects based on standard maintenance shall also apply. The factor Φ2 specified in Annex E4 Clause 3.3 for the LM71-based fatigue check shall be replaced by Φ3; the specific provisions for separate fatigue-train models remain applicable. | Yes
626 | Section VII – Employer’s Requirements / Annex E4 §3.5.5.4 and §4.8; Annex E4 §2.4.3.3 | Reference is made to Annex E4 §3.5.5.4 and §4.8, which require the combined response of bridge and track to be verified and which state that, for ballastless track, the method of analysis shall be specific to the project and approved by the Authority; and to Annex E4 §2.4.3.3, which leaves the limits on deck end rotations for ballastless track to be determined by the Authority. Reference is further made to Annex E1 §5.2, §5.2.1 and §5.2.2, which describe both ballasted and ballastless track but nowhere define their respective extents. We kindly ask the Employer to state where ballastless track is required — in particular in tunnels, on viaducts, on the Yavuz Sultan Selim Bridge and in stations — and to state the analysis method and the deck end rotation limits to be applied to those structures. | The bridge–track interaction analysis and the applicable deck-end rotation criteria for ballastless track shall be established during Detailed Design in accordance with Annex E4, taking into account the characteristics and performance requirements of the proposed ballastless track system. | No
627 | Section VII – Employer’s Requirements / Annex E4 | Reference is made to the further parameters which Annex E4 expressly reserves to the Authority and which are not stated anywhere in the Tender documentation, namely: the increased height of application ht of the centrifugal force above 1.80 m for specific vehicle types such as double-stack container traffic (§3.5.5.1); the additional requirements applicable to heavy traffic at speeds exceeding 120 km/h (§3.5.5.1, note to Table 3.5.5.1.2); the additional requirements for braking effects where the loaded track length exceeds 300 m (§3.5.5.3), which is relevant given the viaduct lengths envisaged; the load to be applied to cantilevers longer than 0.5 m carrying rail traffic (Table 3.5.4.5.3-1, note a); the permissible difference in transverse deflection between adjacent decks and the additional limits on deck end rotations adjacent to switches and expansion joints (§2.4.3.3 and §2.4.3.4); and the passenger comfort requirements for temporary bridges (§2.4.4.2). We kindly ask the Employer to state each of these values. | Please refer to Addendum No. 2, Amendment No. 29. Section VII, Annex E4 (Authority-specified parameters). The amendment will list the parameters reserved for the Employer/Authority for which no default standard value exists, specify applicable values or applicability decisions before Proposal submission where these materially affect safety, scope or price, and identify any parameters that Proposers must propose on a common basis. The final amendment must make the required tender-stage assumptions clear to all Proposers. | Yes
628 | Section VII – Employer’s Requirements / Annex E4 | Reference is made to Annex E4, Table 2.4.3.4.1, which sets limits on the maximum horizontal rotation angle and on the change in radius of curvature of the track by reference to the symbols α1 to α3 and r1 to r6, the numerical values of which are given only as "recommended values" in Note 3 to that table. We kindly ask the Employer to confirm that the recommended values are to be adopted as the design values, or otherwise to state the values that apply. | Please refer to Addendum No. 2, Section VII, Annex E4, Table 2.4.3.4.1. Values for α1–α3 and r1–r6 shall be applied in accordance with the relevant EN standard where that standard expressly defines them. Any parameter reserved for Authority determination for which no default standard value exists will be identified and addressed in Amendment No. 29, with a common tender-stage basis established for all Proposers before Proposal submission. | Yes
629 | Section VII – Employer’s Requirements / Annex E1 §2.1, §4.3.4 and §5.12.1; Annex E4 §3.5.3; Annex E1 | Reference is made to Annex E1 §2.1, §4.3.4 and §5.12.1, and to Annex E4 §3.5.3. Annex E1 defines the vertical railway loading three times and incompatibly: as LM 71 with SW/0 and SW/2 in §2.1; as loads to be provided by the vehicle manufacturer on the basis of actual wagon geometry in §4.3.4; and as a real-train live load with fixed impact factors in §5.12.1. Annex E4 requires LM 71, SW/0, SW/2, the "unloaded train" model and, where applicable, HSLM. The manufacturer-based model of Annex E1 §4.3.4 is systematically less onerous than LM 71 and would not satisfy Annex E4. We kindly ask the Employer to confirm that Annex E4 §3.5.3 governs and that Annex E1 §4.3.4 and §5.12.1 are of no effect in respect of vertical railway loading. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. Please also refer to Amendment No. 40. Vertical railway loading for bridges and viaducts shall be in accordance with Annex E4 Clause 3.5.3 and the applicable classifications and load combinations. The original Annex E1 Clauses 4.3.4 and 5.12.1 shall not be relied upon where superseded by the revised Annex E1 and Annex E4-specific requirements. | Yes
630 | Section VII – Employer’s Requirements / Annex E1 §5.12.1; Annex E4 §3.5.4.5 | Reference is made to Annex E1 §5.12.1 and to Annex E4 §3.5.4.5. The former prescribes fixed dynamic factors of 1.30 for simply supported spans up to 40 m and 1.45 over the supports of continuous beams, whereas the latter requires the dynamic factor to be determined from the determinant length LΦ in accordance with Table 3.5.4.5.3- 1, yielding values up to 1.67 for Φ2 and 2.00 for Φ3. For short determinant lengths — deck slabs, cross-girders, ballast retaining elements and short culverts — the fixed value of 1.30 is materially lower than the value required by Annex E4. We kindly ask the Employer to confirm that Annex E4 §3.5.4.5 governs. | Please refer to Answer No. 629, Addendum No. 2, Amendments Nos. 28, 31 and 40, and the revised Annex E1 attached thereto. The applicable dynamic factor and related fatigue checks for railway bridges shall be governed by Annex E4 as amended by Amendment No. 28. | Yes
631 | Section VII – Employer’s Requirements / Annex E1 §5.12.1; Annex E4 §3.5.5.2 | Reference is made to Annex E1 §5.12.1 and to Annex E4 §3.5.5.2. The former requires a lateral force of 10 per cent of the axle load applied 1.10 m above rail level, whereas the latter requires a nosing force of characteristic value Qsk = 100 kN applied horizontally at the top plane of the rails, perpendicular to the track centreline, multiplied by α where α exceeds unity and not multiplied by the dynamic factor. The two provisions differ in magnitude, in point of application and in their combination with other actions. We kindly ask the Employer to confirm that Annex E4 §3.5.5.2 governs. | Please refer to Answer No. 629, Addendum No. 2, Amendments Nos. 31 and 40, and the revised Annex E1 attached thereto. The railway-bridge nosing/lateral-force requirements shall be those specified in Annex E4 Clause 3.5.5.2. | Yes
632 | Section VII – Employer’s Requirements / Annex E1 §5.12.1 ; Annex E4 §3.5.5.3 | Reference is made to Annex E1 §5.12.1 and to Annex E4 §3.5.5.3. The former defines a braking force of 20 per cent of the axle load, whereas the latter requires a traction force of 33 kN/m limited to 1000 kN and a braking force of 20 kN/m limited to 6000 kN for LM 71, SW/0 and HSLM, and 35 kN/m for SW/2, applied at the top plane of the rails, multiplied by α for LM 71 and SW/0 and not multiplied by the dynamic factor. We kindly ask the Employer to confirm that Annex E4 §3.5.5.3 governs. | Please refer to Answer No. 629, Addendum No. 2, Amendments Nos. 31 and 40, and the revised Annex E1 attached thereto. The railway-bridge traction and braking actions shall be those specified in Annex E4 Clause 3.5.5.3. | Yes
633 | Section VII – Employer’s Requirements / Annex E1 §5.12.1; Annex E4 §3.12 | Reference is made to Annex E1 §5.12.1, which specifies a combined "Braking and Derailment Force" equal to 20 per cent of the axle load, and to Annex E4 §3.12, which treats derailment as an Exceptional Limit Case and requires two separate verifications: Design Case I, in which the derailed train remains within the track area and the structure is checked against α × 1.4 × LM 71 placed within 1.5 s of the track centreline; and Design Case II, in which the derailed train rests at the deck edge and overall stability is verified against α × 1.4 × LM 71 over a maximum length of 20 m. The provision in Annex E1 corresponds to neither. We kindly ask the Employer to confirm that Annex E4 §3.12 governs and that derailment is to be verified as an exceptional limit case. | Please refer to Answer No. 629, Addendum No. 2, Amendments Nos. 31 and 40, and the revised Annex E1 attached thereto. Derailment actions for railway bridges and viaducts shall be assessed in accordance with Annex E4 Clause 3.12. | Yes
634 | Section VII – Employer’s Requirements / Annex E1 §5.12.1; Annex E4 §3.3 | Reference is made to Annex E1 §5.12.1, which directs that detailed design be carried out in accordance with the General Directorate of Highways Technical Specification for Road Bridges or the AASHTO LRFD Bridge Design Specifications, and to Annex E4 §3.3, which prescribes its own set of limit states and load factors in Table 3.3.1, comprising Strength, Equilibrium, Service, Fatigue, Exceptional and Earthquake combinations with train load groups. The two are not compatible, and neither corresponds to the partial factors of TS EN 1990 Annex A2. We kindly ask the Employer to confirm that the limit states and load factors of Annex E4 §3.3 govern, and that the partial factors of TS EN 1990 Annex A2 are not to be applied. | Please refer to Answer No. 629, Addendum No. 2, Amendments Nos. 31 and 40, and the revised Annex E1 attached thereto. The relevant railway-bridge load combinations and factors shall be governed by Annex E4 Clause 3.3 and Table 3.3.1. | Yes
635 | Section VII – Employer’s Requirements / Annex E1 §2.1 and §3.1.1; Annex E1 §5.13 and §7; Annex E1 §5.14, Annex B1; §8.1.1 | Reference is made to Annex E1 §2.1 and §3.1.1, which state a design speed of 160 km/h with testing at 176 km/h; to Annex E1 §5.13 and §7, which require the overhead contact system and traction power supply to be designed for 160 km/h plus 10 per cent; to Annex E1 §5.14, which requires the signalling and telecommunications systems to be suitable for train speeds of 200 km/h; and to Annex B1 §8.1.1, which states a maximum train operating speed of 200 km/h. As specified, the overhead contact system and power supply limit operation to 176 km/h while the signalling system is procured for 200 km/h. We kindly ask the Employer to state the design speed and the maximum permitted line speed applicable to each section of the line. | Please refer to Answer 105. | No
636 | Section VII – Employer’s Requirements / Annex E4 §3.5.4.4; Annex E4 §3.5.3; Annex E4; §3.5.5.1 | Reference is made to Annex E4 §3.5.4.4, Note 4, which provides that dynamic analysis is not required where the first natural frequency of the bridge lies within the limits of Figure 3.5.4.4.2 and the maximum line speed at the bridge location does not exceed 200 km/h, and to Annex E4 §3.5.3, which requires Load Model HSLM where dynamic analysis is performed. Reference is further made to Annex E4 §3.5.5.1, which recommends that an increased maximum line speed be adopted in order to allow for potential future changes to the infrastructure and to the trains. We kindly ask the Employer to state the maximum line speed to be adopted at each structure for the purposes of Annex E4 §3.5.4.4, and to confirm whether an increased speed is to be adopted for future- proofing and, if so, its value. | For the purposes of the dynamic analysis requirements under Annex E4, the maximum line speed to be adopted shall be 160 km/h. No increased speed for future-proofing is required. | No
637 | Section VII – Employer’s Requirements / Annex E1 §5.12.2 | Reference is made to Annex E1 §5.12.2, which requires the tunnel free cross-sectional area to be determined in accordance with UIC 779-11 using the maximum permitted speed within the tunnel as an input, and to the ambiguity identified in D.1 above. The free cross-sectional area, and hence the excavation quantities, are materially sensitive to this value. We kindly ask the Employer to state the speed to be adopted for this purpose. | Please refer to Annex B2 – Railway Operation Plan. For the purpose of determining the tunnel free cross-sectional area in accordance with UIC 779-11, the maximum permitted speed to be adopted shall be 160 km/h. | No
638 | Section VII – Employer’s Requirements / Annex E4 §2.1.1; Annex E4; §4.1; Annex E4 §5.1 | Reference is made to Annex E4 §2.1.1, which lists the AASHTO LRFD Bridge Design Specifications, 9th Edition 2020 among the source standards; to Annex E4 §4.1, which lists the AASHTO LRFD Bridge Design Specifications 2017; and to Annex E4 §5.1, which lists the AASHTO LRFD Bridge Design Specifications 2007. Three different editions of the same specification are therefore invoked in three chapters of the same document. We kindly ask the Employer to state the edition that governs. | Please refer to Addendum No. 2, Amendment No. 30, Section VII, Annex E4 Clauses 5.1 and 6.1. The governing edition of the AASHTO LRFD Bridge Design Specifications for resistance verification of concrete and steel railway bridges shall be the 9th Edition (2020), consistent with Annex E4 Sections 2 and 3. The reference to “latest edition in force” will not apply; the load factors in Annex E4 Table 3.3.1 remain applicable, and other standards are supplementary only as expressly stated in the amended Annex E4. | Yes
639 | Section VII – Employer’s Requirements / Annex E4 §5.1; Annex E4; §6.1 | Reference is made to Annex E4 §5.1, which lists TS EN 1992-1:2004, TS EN 1992-2:2004, ACI 318M-05 and TS 500- 2000 concurrently as the reference standards for reinforced and prestressed concrete bridges, and to Annex E4 §6.1, which lists TS EN 1993-1-1:2005, TS EN 1993-1-8:2005, TS EN 1993-1-9:2005 and the withdrawn prestandard prEN 1993-2:2003 together with the AASHTO LRFD Bridge Design Specifications 2017 for the limit states of §6.3. These documents employ different resistance formats, and none of them is dimensionally consistent with the load factors of Annex E4 Table 3.3.1, which are not the partial factors of TS EN 1990. We kindly ask the Employer to state the single resistance code to be applied to concrete and to steel respectively, and to confirm that it is to be used together with the load factors of Annex E4 Table 3.3.1. | Please refer to Addendum No. 2, Amendment No. 30. | Yes
640 | Section VII – Employer’s Requirements / Annex E4 §2.1.1 | Reference is made to the source standards table of Annex E4 §2.1.1, which attributes §3.3 "Load Factors and Load Combinations" to TS EN 1991-2:2004. TS EN 1991-2 contains no combination rules or partial factors, these being given in TS EN 1990 Annex A2, and the content of Table 3.3.1 corresponds to neither. We kindly ask the Employer to confirm the origin and the intended application of the load factors given in that table. | The load factors and load combinations specified in Annex E4, Table 3.3.1 are based on the AASHTO LRFD Bridge Design Specifications and shall apply to the design of the Works. Please refer to Addendum No. 2, Amendment No. 30. | Yes
641 | Section VII – Employer’s Requirements / Annex E3 §4 and §5; Annex E4 §3.3 | Reference is made to Annex E3 §4 and §5, which determine bearing capacity by means of global safety factors, being 3 for shallow foundations and 2 or 3 for piles, with a footnote to the effect that the resistance factors of the AASHTO LRFD Design Specifications shall be used where design is carried out in accordance with Load and Resistance Factor Design principles; and to Annex E4 §3.3, which produces factored load effects. The format in which foundation verifications are to be carried out, and the load set to be transmitted to those verifications, are therefore undefined. We kindly ask the Employer to state the geotechnical design format to be applied and the corresponding load combinations. | Load combinations are taken from Annex E4, geotechnical design of shallow and deep foundations shall be done in accordance with TKDY-2020. | No
642 | Section VII – Employer’s Requirements / Annex E4 §1.3.3 and §1.3.5; Annex E1 §1.6; Annex B1 §5.3.1 | Reference is made to Annex E4 §1.3.3 and §1.3.5, which require a 100-year flood for floodplain management and a design flood not exceeding a 500-year return period for the verification of foundation stability, treated as an exceptional limit case; to Annex E1 §1.6, which requires the water level corresponding to the 500-year flood with a minimum freeboard of 1.5 m and the 1000-year flood with the same freeboard where population is exposed or economic loss may arise; and to Annex B1 §5.3.1, which states that the State Hydraulic Works has increased the design return period for hydraulic bridges from 500 to 1000 years. We kindly ask the Employer to state the governing return periods and freeboard requirements. | Please refer to Section VII – Employer’s Requirements / Annex E4 §1.3.3 and; §1.3.5; Annex E1 §1.6;; Annex B1 §5.3.1. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
643 | Section VII – Employer’s Requirements / Annex E4 §3.6; Annex E1; §5.12.1 | Reference is made to Annex E4 §3.6, which determines the design wind speed by the expression given for VDZ on the basis of terrain roughness class II and adopts a basic wind speed of 25 m/s for the verification of wind acting on trains, and to Annex E1 §5.12.1, which requires wind loads to be determined in accordance with TS 498 and TS EN 1991-1-4 and wind on live load in accordance with the AASHTO LRFD Bridge Design Specifications. Three different bases are therefore invoked for the same action. We kindly ask the Employer to state the governing basis for wind actions on bridges and on trains. | The applicable wind actions on bridges and trains shall be determined during Detailed Design based on the site-specific conditions along the Project alignment and in accordance with the applicable standards and requirements of the RFP. Please refer to Addendum No. 2, Amendment No. 40. | Yes
644 | Section VII – Employer’s Requirements / Annex E4 §10.1; Annex E1; §4.3.4 and §5.12.1 | Reference is made to Annex E4 §10.1, which requires both the H30-S24 loading and the HL-93 loading of the AASHTO LRFD specification to be considered as road vehicle loads, and to Annex E1 §4.3.4 and §5.12.1, which require the H30-S24 Standard Truck Load of the Technical Specification for Road Bridges, with detailed design permitted in accordance with the AASHTO LRFD specification. We kindly ask the Employer to confirm whether both load models are required, and whether they are to be treated as alternatives with the more onerous governing or as a combined envelope. | Both H30-S24 and HL-93 load models shall be considered during Detailed Design in accordance with the applicable requirements of the RFP. Please refer to Addendum No. 2, Amendment No. 40. | Yes
645 | Section VII – Employer’s Requirements / Annex E1 §3.2.3; Annex B1; §4.1.4.1 | Reference is made to Annex E1 §3.2.3 and to Annex B1 §4.1.4.1. The table in Annex E1 §3.2.3 gives a minimum main line curve radius of 2500 m, with 2000 m in exceptional cases, for a design speed of 160 km/h; the text of the same clause states that a minimum radius of 450 m is recommended and that 300 m may be used in exceptional circumstances; and Annex B1 states that a minimum radius of 1500 m is adopted. At the maximum cant and cant deficiency stated in Annex E1, radii of 450 m and 300 m correspond to permissible speeds of approximately 103 km/h and 84 km/h respectively and are therefore incompatible with the stated design speed. We kindly ask the Employer to state the governing minimum radius. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. For horizontal curve radii and section-specific design speeds, refer to the requirements of the revised Annex E1 and the express amendment to Annex B1 Clause 4.1.4.1 under Amendment No. 31. The superseded text of the original Annex E1, including its former Clause 3.2.3 and Table 3.6, does not apply. The relevant conceptual alignment shall be verified during Detailed Design. | Yes
646 | Section VII – Employer’s Requirements / Annex E1 §3.2.1; Annex E1; §3.2.4 | Reference is made to Annex E1 §3.2.1, which states a maximum cant of 130 mm and a maximum cant deficiency of 150 mm, and to Annex E1 §3.2.4, which states that the maximum permissible cant is 150 mm and that the unbalanced cant must not exceed 100 mm, or 130 mm in exceptional cases. We kindly ask the Employer to state the governing values of maximum cant and maximum cant deficiency. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. Please also refer to Amendment No. 32. The applicable cant, cant-deficiency and related criteria shall be those stated in the revised Annex E1, which supersedes the original Clauses 3.2.1 and 3.2.4. Annex B1 remains subject to any separate express amendments. | Yes
647 | Section VII – Employer’s Requirements / Annex E1 §3.2.5; Annex B1; §4.1.4.5 | Reference is made to Annex E1 §3.2.5, Table 3.7, which limits the cant ramp gradient to 2.00 mm/m with an absolute maximum of 2.50 mm/m, and to Annex B1 §4.1.4.5, which states that the corresponding quantity shall not exceed 35 mm/m by reference to EN 13803-1:2017. The two values differ by more than an order of magnitude, and the parameter designation and units given in Annex B1 appear to be inconsistent with one another. We kindly ask the Employer to state the governing limit and to confirm the intended parameter and units. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. Please also refer to Amendment No. 33 for the express amendments to Annex B1 Clause 4.1.4.5 and Table 5. Under the revised Annex B1 Table 5, the general cant-ramp-gradient values are 0.20% (suggested) and 0.25% (maximum); the former 35 mm/m statement is deleted. The superseded Annex E1 Table 3.7 shall not be used. | Yes
648 | Section VII – Employer’s Requirements / Annex E1 §3.3.2; Annex B1; §4.2.1 | Reference is made to Annex E1 §3.3.2, which sets the minimum length of a constant gradient at 0.56 times the design speed, being approximately 90 m at 160 km/h, and to Annex B1 §4.2.1, which states a minimum length of 50 m. We kindly ask the Employer to state the governing value. | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. Please also refer to Amendment No. 34. The minimum constant-gradient length and applicable exceptional criteria shall be determined under the revised Annex E1, Clause 3.3.2. The former 50 m minimum in Annex B1 Clause 4.2.1 is replaced by the express wording in Amendment No. 34. | Yes
649 | Section VII – Employer’s Requirements / Annex E1 §5.8.1 | Reference is made to Annex E1 §5.8.1, which permits a sleeper spacing of up to 75 cm, and to Annex B1 §4.4.1, which specifies a spacing of 620 mm. The value governs rail bending stresses and is an input to the ballast and sub-ballast thickness calculation to UIC 719 required by Annex E1 §5.1.1. We kindly ask the Employer to state the governing spacing. | Please refer to Section VII – Employer’s Requirements / Annex E1 §5.8.1. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
650 | Section VII – Employer’s Requirements / Annex E1 §5.5.1; Annex E1; §3.4 and §5.5.1 | Reference is made to Annex E1 §5.5.1, which states that rails shall be manufactured from R260 grade steel and, in the same clause, that R350HT shall be considered the preferred option with the Contractor required to justify any reversion to R260; and to Annex E1 §3.4 and §5.5.1, which require grooved rail profiles complying with TS EN 14811 on the main line, that standard being applicable to tramway track. We kindly ask the Employer to state the required rail grade and the locations to which each applies, and to confirm that the requirement for grooved rail is deleted. | Please refer to Section VII – Employer’s Requirements / Annex E1 §5.5.1; Annex E1; §3.4 and §5.5.1. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
651 | Section VII – Employer’s Requirements / Annex E1 §2.1; Annex E1; §3.4 and §1.8.4; Annex E1; §3.4; Annex B1 §4.5.2 | Reference is made to Annex E1 §2.1, which requires the platform edge to be located not less than 1750 mm from the track centreline, and to Annex E1 §3.4 and §1.8.4, which require the gap between a stationary vehicle and the platform edge to be between 50 mm and 80 mm. With rolling stock of the width envisaged for the Project, these two requirements cannot be satisfied simultaneously. Reference is further made to Annex E1 §3.4, which constructs the clearance envelope from static, dynamic and vehicle gauges without reference to any UIC reference profile, and to Annex B1 §4.5.2, Table 7. We kindly ask the Employer to state the governing platform dimensions and the reference kinematic gauge to be used for structure gauge determination, having regard to freight traffic of TSI category E4. | Please refer to Section VII – Employer’s Requirements / Annex E1 §2.1; Annex E1; §3.4 and §1.8.4; Annex E1; §3.4; Annex B1 §4.5.2. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
652 | Section VII – Employer’s Requirements / Annex E1 §3.4; Annex E1; §3.2.2; Annex E1 §5.13 | Reference is made to Annex E1 §3.4 and Table 3.10, which refer to metro lines and to vehicles supplied at 750 V DC through a third rail or at 750 or 1500 V DC through a catenary, and which give vehicle parameters of a metro character; to Annex E1 §3.2.2, which derives the minimum tangent length from the distance covered by a metro vehicle in two seconds; and to Annex E1 §5.13, which specifies 154/25 kV AC traction substations and a 25 kV overhead contact system. We kindly ask the Employer to confirm that §3.4, Table 3.10 and the associated provisions are superseded for the purposes of loading, clearance and alignment, and to state the reference vehicles to be adopted. | Please refer to Section VII – Employer’s Requirements / Annex E1 §3.4; Annex E1; §3.2.2; Annex E1 §5.13. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
653 | Section VII – Employer’s Requirements / Annex E1 §5.12.2 and; §5.12.9 | Reference is made to Annex E1 §5.12.2 and §5.12.9, which describe emergency exit structures and dimension their staircases for the evacuation of a stranded train, but which nowhere state a maximum spacing between emergency exits or cross-passages. Given the extent of twin-tube and single-tube tunnelling in the Works, this requirement is a principal determinant of cost. We kindly ask the Employer to state the maximum spacing to be adopted and the governing standard. | For clarity, please refer to Addendum No. 2, Amendment No. 10, Section VII, ER Clause 9.3.4, together with the corresponding amendment to ER Clause 9.3.1. NFPA 130 shall apply to underground station structures and station-specific emergency ventilation, passenger evacuation and station-safety requirements. SRT-TSI shall apply to alignment structures, including mainline railway tunnels and twin-bore tunnel cross-passages; the maximum cross-passage spacing is 500 m under the amended Clause 9.3.4. Mandatory Turkish requirements, including BYKHY where applicable, also remain applicable. SRT-TSI does not replace NFPA 130 across the entire project; the standards apply within their respective scopes. | Yes
654 | Section VII – Employer’s Requirements / Annex E1 §1.8.4, Annex E1; §1.10 and Annex B1 §4.7 | Reference is made to Annex E1 §1.8.4, which requires escape distances of 15 m where no sprinkler system is provided and 25 m where one is provided, these being the values of the Turkish Regulation on Fire Protection of Buildings, and to Annex E1 §1.10 and Annex B1 §4.7, which invoke the platform clearance and evacuation criteria of NFPA 130. The escape distances stated cannot be applied to a platform serving 400 m trains. We kindly ask the Employer to state the scope of application of each criterion. | Please refer to Addendum No. 2, Amendment No. 10, and the corresponding amendment to ER Clause 9.3.1. NFPA 130 shall apply to underground station structures and station-specific passenger evacuation and emergency-egress requirements, together with mandatory Turkish requirements including BYKHY where applicable. SRT-TSI shall apply to alignment structures, including mainline railway tunnels and cross-passages. The conflicting or overlapping provisions will be clarified by the amendment; station evacuation criteria shall not be determined by applying SRT-TSI as a blanket replacement for NFPA 130. | Yes
655 | Sections VIII–IX – Conditions of Contract Section VII – Employer’s Requirements | Please confirm that the Turkish Seismic Code for Isolated and Damped Bridges and Viaducts applies to the railway bridges and viaducts of the Project, and that a design solution incorporating seismic isolators and/or energy dissipation devices is acceptable to the Employer where the Contractor demonstrates full compliance with the applicable codes and performance requirements. | The Turkish Seismic Code for Isolated and Damped Bridges and Viaducts applies where an isolated/damped bridge solution is adopted or otherwise falls within its scope. The Contractor may propose such a solution as part of the Detailed Design, subject to compliance with the RFP, statutory requirements and the Engineer’s consent. | No
656 | Section VII – Employer’s Requirements | Please state whether any Employer, AYGM or TCDD internal directive, standard practice or prior-approval requirement (not reflected in the Tender Documents) applies to the use of anti-seismic devices on railway structures. | Please refer to Section VII – Employer’s Requirements. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
657 | Section VII – Employer’s Requirements | Please confirm the Bridge Importance Class to be assigned to (i) the main line bridges and viaducts, (ii) the Wye connection viaducts, and (iii) elevated station structures. | The Bridge Importance Class shall be determined in accordance with TKDY-2020 and Annex E4 for the relevant structure and operational function. The Contractor shall demonstrate the adopted classification in the Design Basis and Detailed Design submissions. No additional blanket classification is introduced by this clarification unless expressly stated in Annex E4. | No
658 | Section VII – Employer’s Requirements | Please confirm the target performance levels and associated earthquake ground motion levels (DD-1 / DD-2 / DD- 3, and Uninterrupted Use / Limited Damage / Controlled Damage) to be achieved for each class. | Please refer to Section VII – Employer’s Requirements. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
659 | Sections VIII–IX – Conditions of Contract Section VII – Employer’s Requirements | Please confirm whether operational continuity of the line immediately following the DD-2 event is a contractual requirement, and if so, state the post-earthquake track geometry and alignment tolerances that must be satisfied, together with the corresponding RAMS/availability targets. | Please refer to Sections VIII–IX – Conditions of Contract. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
660 | Section VII – Employer’s Requirements | Please confirm that EN 15129 and the EN 1337 series shall be added to §4.2 of ANNEX E1 as applicable standards for anti-seismic devices and structural bearings respectively. If not, please specify the product standard, conformity assessment and marking regime that shall apply. | The RFP does not add EN 15129 or the EN 1337 series as new mandatory standards through this clarification. The Contractor shall comply with the standards expressly identified in Annex E1/Annex A1 and all mandatory applicable Turkish legal and regulatory requirements. Where the Contractor proposes to use EN 15129 for anti-seismic devices or EN 1337 for structural bearings, it shall identify the applicable standard and conformity-assessment/marking documentation in the Detailed Design for the Engineer’s review, in accordance with the RFP. | No
661 | Section III – Evaluation and Qualification Criteria Section VII – Employer’s Requirements | Please confirm the required qualification and acceptance testing regime: type testing, prototype/full-scale testing, factory production control, accreditation requirements for the testing laboratory, witnessing arrangements, and the treatment of property modification (λ) factors, ageing, temperature and velocity effects in design. | Please refer to Section VII – Employer’s Requirements, including Annex P – Qualification, Testing, Inspection and Commissioning Technical Specification, and the applicable product/system Technical Specifications and referenced standards. The applicable qualification, type, factory, site and acceptance testing, test procedures, witnessing and acceptance requirements shall be established and demonstrated in accordance with these requirements. The Contractor shall demonstrate compliance with the applicable design and product-standard requirements, including the relevant material/property modification and environmental or operational effects, where applicable. | No
662 | Section VII – Employer’s Requirements | Please confirm the design service life required for bearings and anti-seismic devices relative to the structure design service life at R5, and the required provisions for inspection access, instrumentation/monitoring, jacking points and replaceability of devices without interruption of railway operation. | The required design service life shall be as stated in the applicable discipline-specific Technical Specification. Where Annex E4 specifies the service life for railway bridges, that requirement governs railway bridges; component service lives shall comply with the relevant product/device specifications and maintenance/replacement strategy. | No
663 | Sections VIII–IX – Conditions of Contract Section VII – Employer’s Requirements | Please confirm that UIC 774-3 (and, as applicable, EN 1991-2 §6.5.4) shall be the governing basis for track–structure interaction analysis, and that these references shall be incorporated into ANNEX E1 as contractual requirements. | Confirmed. Track–structure interaction analysis shall be performed in accordance with Annex E4 and the applicable UIC 774-3 / EN 1991-2 provisions. | No
664 | Section VII – Employer’s Requirements | Please state the binding limits to be verified — additional rail stresses in compression and tension, relative displacement between deck and track under braking/traction, and end rotation limits — together with the design assumptions to be adopted (temperature ranges, longitudinal track resistance for ballasted and ballastless track, stress-free temperature). | The Ballasted/Ballastless Track Itinerary has been added to the RFP Documents regarding the application of ballasted and ballastless track. Please refer to Addendum No. 2, Amendment No. 15. The applicable limits and design assumptions for track–structure interaction analysis shall be determined during Detailed Design in accordance with Annex E4 and the applicable provisions of UIC 774-3 and EN 1991-2. Where slab track is adopted, the applicable limits and requirements specified by the proposed slab track system manufacturer shall also be taken into consideration. | Yes
665 | Section VII – Employer’s Requirements | Please confirm whether rail expansion devices are permitted on the main running lines, under what conditions, and whether any Employer restriction applies to their number or location. | Please refer to Answer 370. | No
666 | Section VII – Employer’s Requirements / .pdf - Section; III, page 67 | To support the preparation of a fully responsive Technical Proposal, please clarify the relationship between the Technical Proposal scoring criteria and the required Technical Proposal deliverables. Specifically, we kindly request that the Client provide a matrix identifying, for each technical evaluation factor and sub-factor: -the applicable score weighting; -the corresponding required Technical Proposal section, form, or deliverable; -the specific information, methodology, evidence, and supporting documentation expected; -the applicable evaluation standard for scores 0 to 4; and -whether the criterion is evaluated solely from the Technical Proposal or also from other submitted documents. This clarification would enable Proposers to demonstrate compliance clearly and ensure that all required evidence is presented in the appropriate submission sections. | Please refer to Section VII – Employer’s Requirements / .pdf - Section; III, page 67. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
667 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria,; Clause 1.4, Items 1, 2 | Reference: Section III – Evaluation and Qualification Criteria, Clause 1.4 – Contractor’s Representative and Key Personnel Project Manager and Civil Works Deputy Project Manager – Items 1 and 2 For the Project Manager and Civil Works Deputy Project Manager positions, the RFP requires relevant project management experience on two railway systems construction contracts using the FIDIC Yellow or Gold Book Conditions of Contract. We note that, for the Design Manager under Item 24, the RFP refers more generally to experience in railway infrastructure projects under Design & Build contracts, without restricting such experience to a specific FIDIC form. Furthermore, Item 1 expressly defines railway systems as including metro, light rail, tram, funicular and similar projects, while Item 2 refers generally to railway systems without providing the same examples. Accordingly, please confirm that, for Items 1 and 2: - relevant experience gained under equivalent Design & Build contractual arrangements may also be considered acceptable for the purpose of satisfying this requirement. In particular, please confirm that contracts which, irrespective of the specific standard form or contractual denomination adopted, are substantially equivalent to the FIDIC Yellow Book in terms of their key characteristics, including the Contractor's responsibility for both the design and execution of the Works in accordance with the Employer's requirements, may be submitted as qualifying references. Such an interpretation would allow the assessment to focus on the substance, scope and allocation of design and construction responsibilities under the relevant contract, rather than exclusively on the use of a specific standard form of contract. Accordingly, please confirm that Design & Build contracts or other equivalent contractual forms, demonstrating the above characteristics, will be accepted as equivalent experience for the purposes of the relevant qualification requirement.; and - Railway systems experience includes metro, light rail, tram, funicular and other comparable urban or interurban rail projects. All other role-specific, academic and overall professional experience requirements would remain unchanged. | Please refer to Section III – Evaluation and Qualification Criteria, Clause 1.4, Items, 1 and 2. The proposed equivalence for Items 1 and 2 is not acceptable. The minimum number of qualifying contracts stated for each position also remains applicable. | No
668 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria,; Clause 1.4, Item 33 | Reference: Section III – Evaluation and Qualification Criteria, Clause 1.4 – Contractor’s Representative and Key Personnel NATM Tunnel Engineer – Item 33 For the NATM Tunnel Engineer position, the RFP requires a Bachelor’s Degree in Civil Engineering. Considering the direct relevance of Mining Engineering/Geological Engineering to underground excavation, rock mechanics and NATM tunnelling works, please confirm whether a Bachelor’s Degree (BSc) inMining Engineering/Geological Engineering may be accepted as equivalent to a Bachelor’s Degree in Civil Engineering, provided that the proposed candidate meets all the relevant and overall professional experience requirements specified in the RFP. | No, it is not acceptable. Please refer to Section III – Evaluation and Qualification Criteria, Clause 1.4, Item 33. The requirement shall be applied as stated in the RFP. | No
669 | Section III – Evaluation and Qualification Criteria / Evaluation and; Qualification Criteria,; Clause 1.4 – Key Personnel | In the event that a Proposer submits Proposals for multiple Lots and is awarded only one or some of those Lots, please clarify whether a Key Personnel proposed for a Lot that is not awarded to the Proposer may subsequently replace a Key Personnel originally proposed for an awarded Lot. | Please refer to Answer 458. | No
670 | Section VII – Employer’s Requirements / TUN - GEO-1 | Will an access tunnel be required to connect the shafts—which are shown on the route plans and have a Type-12 cross-section—to the tunnels? | See Section VII – Employer’s Requirements Section 5.3.1 "For underground works, the Contractor shall identify the proposed tunnelling methodology, indicative shaft and access strategy, excavation sequencing philosophy, TBM launch and retrieval assumptions, NATM staging principles where applicable, and the proposed integration of underground works with surface access and logistics constraints. | No
671 | Section VII – Employer’s Requirements / TUN - GEO-2 | Could you please provide information on the construction methodology for the Type 2A, 2B, and 5 tunnels located between the TBM tunnels along the route, which will be excavated using the NATM method? After the TBM tunnels are completed, will these NATM tunnels be constructed by breaking up the segments, or will they be excavated using additional shafts and connecting tunnels, through which the TBM will be passed? | The detailed construction methodology, including the sequence and means of excavation and the interface with the adjacent TBM tunnels, shall be developed by the Contractor as part of the Detailed Design and Construction Methodology, subject to compliance with the Employer’s Requirements, applicable standards, safety requirements and the Engineer’s approval/consent. | No
672 | Section VII – Employer’s Requirements / MEP-1 | Safety in Tunnels Subsystem (ref. TSI SRT - Regulation EU 1303/2014) Given the presence of tunnels in the project and that MEP installations for safety are within the scope of this contract, we request the following specifications: 1) Tunnel Classification and Design Basis 1. Design Fire Scenario: What is the design fire scenario (heat release rate) assumed for the tunnel ventilation and emergency systems design? 2. Rolling Stock Fire Category: What is the required fire category (Category A or B) for rolling stock that will transit through the tunnels? 2) Evacuation and Rescue Facilities 3. Evacuation and Rescue Points: How are evacuation and rescue points planned along the tunnels? Please provide locations and specifications. | Please refer to Section VII – Employer’s Requirements / MEP-1. The requirement shall be applied as stated in the RFP. The Contractor/Proposer shall demonstrate compliance with the applicable Contract and Employer’s Requirements in its Proposal and, where relevant, during Detailed Design. | No
673 | Sections VIII–IX – Conditions of Contract | With reference to the tender provisions regarding payment currencies and fixed exchange rates, we kindly request clarification on to how any difference between the TRY Contract Value and the TRY equivalent of payments made in foreign currency at the fixed contractual exchange rates should be treated, in particular: 1. Whether such exchange-rate differences should increase/decrease the Contract Value and be reflected through adjustment/correction invoices; 2. How the related VAT adjustment should be handled, particularly where the actual cash received is lower than the invoiced TRY amount; | (1) Please refer to Clarification Response No.815. (2) Proposal Prices shall be stated exclusive of VAT as required by the PDS; VAT shall be added and paid in accordance with the applicable Turkish tax legislation and the Contract. | No
674 | Section III – Evaluation and Qualification Criteria | If a proposer participates in the tender using the parent company’s qualifications and track record, is it permissible to subsequently establish a subsidiary to join the JV and execute relevant works, with the parent company issuing a guarantee letter to assure the subsidiary’s ability to fulfill its obligations? If this approach is feasible, please advise on the specific requirements. If this approach does not sufficiently meet the client’s requirements, please advise whether there are alternative mechanisms that would allow this structure to be established, as well as any additional conditions the clientmayimpose. | A Proposer may rely only on the qualifications and experience of the legal entity/entities constituting the Proposer. Contract award will be to the Proposer. Post-award restructuring may not be used to alter the Proposer without the Employer’s prior approval and compliance with the Contract and Procurement Regulations. | No
675 | Section I – Instructions to Proposers / ITP 12.2(b) | The RFP requirements for the proposer bank guarantee states "The written letter confirming the validity of the Proposal Security from the issued Bank shall be provided". please kindly clarify the format for such confirmation letter, whether this letter shall be issued from the bank along with the guaranteeortheproposer shall writewith its letterhead to confirmthe validity? | Please refer to Answer 123. | No
676 | Section VII – Employer’s Requirements / Form CON-2 | The Proposer is required to disclose the pending litigation and litigation history information. Please kindly clarify on the type of the litigation cases that, which case of litigation shall we put into? or is thereany conditionlimit regardingthetype andamount ofthelitigation cases? | The Proposer shall disclose litigation/arbitration/dispute information falling within the scope and period stated in the applicable CON/FIN forms and Section III. The disclosure is not limited to claims similar to INRAIL unless the form expressly states otherwise. | No
677 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report; Annex E1 – Design Technical Specification | In the concept design provided in the tender attachments, most horizontal curve radii are set at 1,500 m. However, Attachment E1, “Design Technical Specifications,” stipulates that the minimum curve radius for a main line with a design speed of 160 km/h should be 2,000 m. Please clarify whether the Employer intends to strictly adhere to the conceptual design documents regarding the selection of parameters such as curve radii. Could you provide train operation calculation data and clarify whether adjustments to the line’s curve radii should be considered during the tender preparation phase? | Please refer to Addendum No. 2, Amendment No. 31, and the revised Annex E1 – Design Technical Specification attached thereto. For horizontal curve radii and section-specific design speeds, refer to the requirements of the revised Annex E1 and the express amendment to Annex B1 Clause 4.1.4.1 under Amendment No. 31. The superseded text of the original Annex E1, including its former Clause 3.2.3 and Table 3.6, does not apply. The relevant conceptual alignment shall be verified during Detailed Design. | Yes
678 | Section VII – Employer’s Requirements / AppendixK—TechnicalSpecifications; for TunnelElectromechanical; Engineering | According to Appendix K, “Technical Specifications for Tunnel Electromechanical Engineering,” thereare a totalof fourshafts in BidSection 1.However,Appendix 8,“Excavation Work Volume Estimate Report,” of the Environmental Impact Assessment document cited in Appendix D indicates there are 10 shafts. There is an inconsistency between the two documents. Please clarify which version should be considered authoritative. Furthermore, is there a possibility of optimizing the number and locations of the shafts, and could the design of auxiliary tunnels be considered? | The Reference/Conceptual Design is tender-stage information. The Contractor may develop and optimise the Detailed Design, subject to compliance with all mandatory Employer’s Requirements, interfaces, approvals and performance criteria and subject to the Engineer’s consent. Such optimisation does not of itself entitle the Contractor to an adjustment of the lump-sum Contract Price unless it constitutes a Variation under the Contract. | No
679 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Part 2 -Alignment Part 2 | Bridge-38 in Lot 4 crosses four overhead power lines. Please clarify whether the Employer confirms that the lines will be relocated or rerouted without any adjustments to the horizontal and vertical alignmentdesigns, and providerelevant documentation. | Please refer to Section VII – Employer’s Requirements and Annex A1 – Alignment Drawings / Part 2 – Alignment Part 2. The Contractor shall be responsible for the necessary protection, relocation and/or rerouting of the existing overhead power lines affected by Bridge-38, including all required coordination with the relevant utility authorities. The final arrangements shall be determined during Detailed Design based on the verified existing conditions and applicable requirements. | No
680 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Part 2 - Alignment Part 2 | Can long-span structures be used for sections that cross roads? Are reference drawings and structural designs available for long-span structures? | The Reference/Conceptual Design is tender-stage information. The Contractor may develop and optimise the Detailed Design, subject to compliance with all mandatory Employer’s Requirements, interfaces, approvals and performance criteria and subject to the Engineer’s consent. Such optimisation does not of itself entitle the Contractor to an adjustment of the lump-sum Contract Price unless it constitutes a Variation under the Contract. | No
681 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Part 2 -Alignment Part 2 | During this stage and the following design process, is there a possibility of optimizing the longitudinal profile for Lot 1 to reduce the excavation work required for the vertical shaft and potentialauxiliary tunnels? | The Reference/Conceptual Design is tender-stage information. The Contractor may develop and optimise the Detailed Design, subject to compliance with all mandatory Employer’s Requirements, interfaces, approvals and performance criteria and subject to the Engineer’s consent. Such optimisation does not of itself entitle the Contractor to an adjustment of the lump-sum Contract Price unless it constitutes a Variation under the Contract. | No
682 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Part 2 -Alignment Part 2 | Regarding the longitudinal profile along the entire route, could localized optimizations be made in subsequent stages—for example, between Bridge-5 and Bridge-6—to reduce the scope of bridge- relatedconstruction work? | The Reference/Conceptual Design is tender-stage information. The Contractor may develop and optimise the Detailed Design, subject to compliance with all mandatory Employer’s Requirements, interfaces, approvals and performance criteria and subject to the Engineer’s consent. Such optimisation does not of itself entitle the Contractor to an adjustment of the lump-sum Contract Price unless it constitutes a Variation under the Contract. | No
683 | Section VII – Employer’s Requirements | Works interface: Unclear interface demarcation in the scope of works (e.g., responsibility for system integration and joint commissioning, the scope of utility relocation/diversion works, and the ownershipoftemporary facilities)? | Interface responsibilities shall be determined from the multi-contract and interface provisions of Section VII and the applicable Lot scope. Utility relocation/diversion shall be governed by the utility provisions of the RFP, while temporary facilities and working arrangements shall remain the Contractor’s responsibility unless otherwise expressly stated. System integration and joint commissioning interfaces shall be managed in accordance with the applicable interface and Testing and Commissioning requirements. No separate interface allocation is introduced through this clarification. No amendment is made to the RFP. | No
684 | Section VII – Employer’s Requirements | Technical standards: Priority determination when multiple standards coexist; confirmation of minimumacceptance criteriafor performanceindicatorsnot specified inthe tender documents? | Please refer to the order-of-precedence provisions of the Contract and the hierarchy stated in the Employer’s Requirements. The discipline-specific Technical Specifications shall govern their respective subject matter, subject always to the Contract-wide order of precedence. Where more than one standard is referenced or applicable to the same subject, the standard expressly identified as governing in the relevant Technical Specification shall apply. Where no such priority is expressly stated and an irreconcilable conflict exists between the applicable standards, the matter shall be referred to the Engineer for determination and shall not be resolved unilaterally by the Contractor. Where a specific minimum acceptance criterion or performance requirement is not expressly stated in the RFP, the applicable requirements and acceptance criteria of the governing standard shall apply | No
685 | Section I – Instructions to Proposers (ITP) / ITP 12.2(e) | Could you please clarify which specific documents are required to be submitted as documentary evidence under this provision, with reference to Section I – Instructions to Proposers (ITP), Clause 12.2(e), which requires “documentary evidence that the Proposer continues to be eligible and qualified to perform the contract if its Proposal is accepted”? | The forms and supporting documents required under Sections III and IV of the RFP constitute the documentary evidence demonstrating the Proposer's continued eligibility and qualification to perform the contract if its Proposal is accepted. | No
686 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel; Section IV – Proposal Forms / Key Personnel Requirements | Please clarify whether, where a candidate does not hold a Bachelor’s degree in the specifically required discipline but holds a Master’s degree in the required discipline, such candidate will be considered to satisfy the educational qualification requirement for the relevant Key Personnel position. In particular, please confirm whether a Master’s degree in the specified discipline may compensate for a Bachelor’s degree in a different discipline, provided that the candidate otherwise meets all other stated qualification and experience requirements. | The educational qualification shall be assessed against the specific minimum degree requirement stated for the position. A Master’s degree does not automatically cure the absence of a required Bachelor’s degree in a specified discipline unless the academic qualification can be demonstrated to be equivalent and acceptable under the applicable professional/educational recognition framework. | No
687 | Section IX – Particular Conditions / PCC Sub-Clause 19.2.3(a) – Professional Indemnity Insurance | Please confirm whether the requirement under PCC Sub-Clause 19.2.3(a) is strictly intended to be 20% of the Accepted Contract Amount, without any fixed cap, irrespective of the availability of such insurance capacity in the international market. | Please refer to Answer 300. | No
688 | Section IX – Particular Conditions / PCC Sub-Clause 19.2.3(a) – Professional Indemnity Insurance | If the required limit cannot be provided by a single insurer, please confirm whether the requirement may be satisfied through a layered insurance programme involving multiple insurers, co-insurers and/or reinsurers, and whether the required limit is to apply on an Each and Every Claim and/or annual aggregate basis. | The required Professional Indemnity cover may be arranged through an insurance programme involving multiple insurers/reinsurers, provided that the aggregate cover, terms, continuity and evidence of insurance fully satisfy Sub-Clause 19.2.3 and are acceptable to the Employer. | No
689 | Section IX – Particular Conditions / PCC Sub-Clause 19.2.3(a) – Professional Indemnity Insurance | Alternatively, would the Employer consider a commercially placeable fixed maximum PI limit or an alternative insurance structure, taking into account the available international market capacity for major railway and tunnelling projects? | Please refer to Answer 300. | No
690 | Section VII – Employer’s Requirements / Environmental and Social Requirements – Vegetation Clearance, Biodiversity and Restoration | Please confirm whether a tree/vegetation inventory or assessment is available for each Lot, including the approximate number, location, species and relevant classification of trees that may require removal. | Please refer to the ESIA/ESMP and the Environmental and Social requirements of the RFP. The Contractor shall verify affected vegetation, obtain the permits and approvals allocated to it, implement avoidance/minimisation, removal, replanting/compensation and restoration measures, and include the associated costs in the Contract Price except where the RFP expressly provides a separate payment item. No additional inventory or separate payment mechanism is introduced by this clarification. | No
691 | Section VII – Employer’s Requirements / Environmental and Social Requirements – Vegetation Clearance, Biodiversity and Restoration | Please clarify the applicable requirements for trees that need to be removed, including: - whether compensatory replanting or other ecological compensation is required; - the applicable replacement/compensation ratio, if any; - the required species, size and planting standards; and - the required maintenance period and acceptance criteria. | Please refer to the ESIA/ESMP and the Environmental and Social requirements of the RFP. The Contractor shall verify affected vegetation, obtain the permits and approvals allocated to it, implement avoidance/minimisation, removal, replanting/compensation and restoration measures, and include the associated costs in the Contract Price except where the RFP expressly provides a separate payment item. No additional inventory or separate payment mechanism is introduced by this clarification. | No
692 | Section VII – Employer’s Requirements / Environmental and Social Requirements – Vegetation Clearance, Biodiversity and Restoration | Please clarify the permits and approvals required for tree removal and vegetation clearance, the relevant authorities, and the applicable statutory fees, compensation payments or other charges. In particular, please confirm whether such costs are deemed to be included in the Contractor’s lump-sum obligations or are subject to separate payment under the Contract. | Please refer to the ESIA/ESMP and the Environmental and Social requirements of the RFP. The Contractor shall verify affected vegetation, obtain the permits and approvals allocated to it, implement avoidance/minimisation, removal, replanting/compensation and restoration measures, and include the associated costs in the Contract Price except where the RFP expressly provides a separate payment item. No additional inventory or separate payment mechanism is introduced by this clarification. | No
693 | Section VII – Employer’s Requirements / Environmental and Social Requirements – Vegetation Clearance, Biodiversity and Restoration | Please clarify the requirements concerning the ownership, removal, transportation, disposal or permitted utilization of timber and other vegetation waste generated from tree removal activities. | Please refer to the ESIA/ESMP and the Environmental and Social requirements of the RFP. The Contractor shall verify affected vegetation, obtain the permits and approvals allocated to it, implement avoidance/minimisation, removal, replanting/compensation and restoration measures, and include the associated costs in the Contract Price except where the RFP expressly provides a separate payment item. No additional inventory or separate payment mechanism is introduced by this clarification. All Environmental and Social (E&S) documents have been disclosed on the AYGM website. In addition, the Environmental and Social Impact Assessment (ESIA) and Environmental and Social Management Plan (ESMP) were updated and re-disclosed on 8 October 2026 to incorporate the supplementary assessments and management plans. Bidders are advised to regularly monitor the AYGM website for the latest versions of all Environmental and Social (E&S) documents, including any updates, revisions, or supplementary documents disclosed during the tender process. Bidders shall ensure that their proposals take into account the most up-to-date E&S documentation available on the AYGM website. | No
694 | Section VII – Employer’s Requirements / Environmental and Social Requirements – Vegetation Clearance, Biodiversity and Restoration | Please confirm whether tree removal, replanting, ecological compensation and related restoration works are deemed to be included in the relevant Lump Sum Activities, or whether any separate measurement/payment mechanism will apply. | Please refer to the ESIA/ESMP and the Environmental and Social requirements of the RFP. The Contractor shall verify affected vegetation, obtain the permits and approvals allocated to it, implement avoidance/minimisation, removal, replanting/compensation and restoration measures, and include the associated costs in the Contract Price except where the RFP expressly provides a separate payment item. No additional inventory or separate payment mechanism is introduced by this clarification. | No
695 | Section VII – Employer’s Requirements / Utilities; Section IV – Schedule of Priced Activities / Activity 2 – Relocation of Existing Infrastructure | We note that the Tender Documents do not provide sufficient information regarding the existing utility networks and the associated works, including, but not limited to, their locations, alignments, dimensions, technical specifications, quantities, protection, relocation, diversion and/or reconstruction requirements. In the absence of relevant utility drawings, detailed technical information and quantities, it is difficult for prospective Bidders to accurately assess the scope of works, construction requirements and associated costs of the utility-related works. This may result in significant uncertainties in tender pricing and in the preparation of the Technical Proposal, and may also affect the comparability of the Bidders' offers. Therefore, we kindly request the Employer to consider removing the utility-related works from the current Tender scope, in particular from Activity No. 2 – Relocation of Existing Infrastructure, and to address such works under a separate arrangement once sufficient design information and quantities become available. Alternatively, if the Employer intends to retain these works within the current Tender scope, we kindly request the Employer to provide the relevant utility drawings, technical requirements, detailed quantities and other necessary information to enable Bidders to properly assess the scope and prepare a reliable and reasonably accurate tender price and Technical Proposal. | Please refer to Answer 68. | No
696 | Section II – Proposal Data Sheet / ITP 23.1 – Deadline for Submission of Proposals | Considering the significant scale, complexity and technical interfaces of the Project, including railway infrastructure, tunnels, bridges, stations, utilities, railway systems and other associated works, substantial time is required for prospective Bidders to properly review and understand the Tender Documents, assess the technical and commercial risks, coordinate with potential partners and subcontractors, develop appropriate construction methodologies, undertake local investigations, obtain competitive quotations and prepare a comprehensive Technical and Financial Proposal. In addition, the clarification of the above matters, together with the necessary detailed quantity reviews, design coordination, construction planning, local supplier/subcontractor assessment and mobilisation planning for four separate Lots, requires sufficient preparation time in order to enable Bidders to submit complete, technically sound and commercially competitive offers. Accordingly, we respectfully request the Employer to extend the current Proposal Submission Deadline from 14 October 2026 to 14 December 2026. | Please refer to Addendum No. 1 regarding the revised Proposal submission deadline under PDS ITP 23.1. | No
697 | Section VII – Employer’s Requirements / Clause 2.1; Section IV – Schedule of Priced Activities / Testing and Commissioning; NoBo and AsBo | Please confirm the expected scope of services and deliverables to be provided by the NoBo and AsBo, including the anticipated assessment stages, reviews, inspections, certification/assessment reports and required authority interfaces, and whether any specific minimum scope or number of assessment activities is envisaged by the Employer. | The NoBo and AsBo shall perform the assessment and certification activities required by the applicable EU/TSI, CSM-RA and national regulatory framework and the Employer’s Requirements. The required assessment activities, reports and certificates shall be coordinated with the Contractor’s design, testing and commissioning programme. The RFP does not prescribe a fixed minimum number of assessment cycles; the required scope shall be sufficient to obtain the certificates and approvals required for Taking-Over. | No
698 | Section VII – Employer’s Requirements / Clause 2.1; Section IV – Schedule of Priced Activities / Testing and Commissioning; NoBo and AsBo | Please provide, where available, the list of NoBo and AsBo organizations currently considered acceptable for this Project, or clarify the accreditation, authorization and acceptance criteria that the proposed bodies must satisfy. In particular, please confirm whether internationally accredited bodies with the relevant railway experience may be proposed by the Contractor, subject to the Employer’s and relevant national authority’s acceptance. | No exclusive Employer-approved list is provided. The proposed NoBo shall meet the designation/notification requirements applicable under the EU interoperability framework, and the proposed AsBo shall be acceptable to the Employer and the relevant national safety authority for the required scope. International accreditation or railway experience alone does not replace these requirements. | No
699 | Section VII – Employer’s Requirements / Clause 2.1; Section IV – Schedule of Priced Activities / Testing and Commissioning; NoBo and AsBo | Considering that the final scope and duration of the independent assessment and certification activities may depend on the approved design, certification plan and regulatory process, please confirm whether the Employer would consider providing these services under a Provisional Sum or another measurable payment mechanism based on actual services performed, rather than as a fixed Lump Sum. Alternatively, please clarify whether any defined cap, maximum number of assessment cycles, or other contractual mechanism will apply to the Contractor’s financial responsibility for NoBo and AsBo services. | The request is not accepted. Engagement of the NoBo and AsBo and the associated assessment/certification services are Contractor obligations and shall be included in the lump-sum Contract Price under the applicable Testing and Commissioning activities. No Provisional Sum, separate cap or fixed maximum number of assessment cycles is specified. | No
700 | Section II – Proposal Data Sheet / ITP 23.1 – Deadline for Submission of Proposals | The RFP document for this tender, announced and published in July 2026, states in SECTION II - PROPOSAL DATA SHEET (PDS): ITP 23.1 that the tender submission date is October 14, 2026. However, some critical machines and materials need to be supplied from international suppliers. We would like to note that price offers cannot be obtained from foreign suppliers where these materials and machines will be supplied during the holiday season in July and August. Therefore, and in order to ensure fair competition, we request an extension of two months to the tender submission date, i.e. January 14, 2027. | Please refer to Addendum No. 1 regarding the revised Proposal submission deadline under PDS ITP 23.1. | No
701 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Section 5.2; Annex C1 – Geological Data Report | Regarding geotechnical data, ANNEX B1 - Conceptual Design Report; Section 5.2 (pages 45-46) last paragraph states: "More detailed information is provided in the Geotechnical Data Report included within the tender documents." However, while the documents include a geological report and drawings, this report does not contain numerical information on soil and rock classification. The report in question does not go beyond listing formation and rock names. Due to the lack of geotechnical design parameters, drawings and reports for the dimensional and static tunnel design of both conventional tunnels and tunnels to be excavated by TBM (Tunnel Boring Machine) are not included in the tender documents. Furthermore, considering the tender schedule, there is no reasonable time frame for design. The literature mentions numerous cases where tunnels with insufficient geological and geotechnical data encountered various problems during both TBM selection and excavation. In this situation, contrary to the tender philosophy of underground works, almost all geological and geotechnical risks remain the responsibility of the contractor, creating a situation that is extremely contradictory to a lump-sum pricing method. Therefore, we request that the reference documents stated to be used in the geological profile drawing be provided and that a reasonable time frame (3 months, i.e. January 14, 2027) be given for preliminary design as of the provision of those documents to bidders. | Please refer to Answer 344. The Employer has provided the tender-stage geological/geotechnical information available for the Proposal. The Contractor remains responsible for the additional investigations and verification required for TBM selection, tunnel/segment design and construction methodology. | No
702 | Section VII – Employer’s Requirements / Annex F – Civil Works (Infrastructure) Technical Specification / Clause 2.2A.2 – Geotechnical Information | Geological and geotechnical reports of the route are vital for the selection of the TBM (Tunnel Boring Machine) and the design of its segment (thickness). These reports, mentioned in the appendices, are not included in the tender documents and obtaining them is essential. Therefore, we kindly request the mentioned reports and drawings. | Please refer to Answer 344. | No
703 | Section VII – Employer’s Requirements / Annex C1 – Geological Data Report / Appendix A | The ANNEX C1_Geological Data Report document, Appendix A, Table 13, refers to geological and geotechnical investigation reports with project and report numbers. We believe this is necessary to ensure equitable competition and to understand the existing rock/soil conditions. We also request the drilling logs, laboratory results, and core box photographs of the AS-coded boreholes (boreholes AS-2 to AS-125 (inclusive)) shown in sheets 11-20 of the "Inrail Geological Profile" drawing derived from the aforementioned reports. | Please refer to Answer 344. | No
704 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Clause 4.6 – Alignment Studies / Istanbul Airport Station | The paragraph regarding the status of Istanbul Airport Station (page 35) states, "At the entrance and exit of the Istanbul Airport Station, TBM tunnels have been constructed." This means that TBMs cannot be slid through the station. However, during the site visit, the Representatives of the Client stated that there was no obstacle to sliding the TBMs through the station floor. We kindly request clarification on this matter. | The tender-stage statement regarding the existing Istanbul Airport Station/TBM interfaces shall be verified by the Lot 4 Contractor through coordination with İGA and the available as-built/site information. The Contractor shall develop a constructible TBM launch/retrieval/sliding methodology as part of the Detailed Design and construction methodology, subject to the airport operator’s requirements and the Engineer’s consent. No assurance is given that TBM sliding through the station floor is unconstrained. | No
705 | Section VII – Employer’s Requirements / Annex C1 – Geological Data Report / Appendix B – Longitudinal Geological Profile – Reduced Extracts | “Reduced extracts from the longitudinal geological profile (.dwg) are included in this appendix, at a scale appropriate for printed reproduction. The extracts show: geological formation distribution; borehole projections; interpreted geological unit boundaries; tectonic lineaments; and indicative NATM excavation support class envelopes (NATM sections only). The full longitudinal geological profile in .dwg format is issued separately as part of the tender data package and constitutes the primary reference. In the event of any discrepancy between the reduced extracts and the full dwg, the full .dwg takes precedence.” However, the specified reduced .dwg files are not included in the folder named Annexes of Annex C1. We request that these drawings be provided. | The Employer has provided the tender-stage geological profile information available in the RFP package. If a referenced DWG is included in the issued tender data package, that full DWG shall govern over reduced extracts. No additional drawing is issued by this clarification; Proposers shall use the files provided with the RFP and notify the Employer promptly of any inaccessible file. | No
706 | Section I – Instructions to Proposers (ITP) / Clause 19 – Securing the Proposal; Section II – Proposal Data Sheet (PDS) / ITP 19; Section IV – Proposal Forms / Proposal Security (Bank Guarantee) | With reference to the tender for the “Design and Construction of Infrastructure & Superstructure Works Including Electrification – Lots 1, 2, 3 and 4,” we respectfully request clarification regarding the expiry wording of the Proposal Security / Bank Guarantee. The relevant form provides that the guarantee shall expire upon the occurrence of the specified events, including receipt of the Beneficiary’s notification regarding the result of the RFP process or 28 days after the expiry of the Proposal validity. Our issuing bank has advised that, in accordance with its standard guarantee wording, it normally includes an additional provision stating: “but in any event no later than XXXXXXX (the expiry date)” Accordingly, please confirm whether the Employer would accept a Proposal Security containing such an additional expiry-date provision, provided that the stated expiry date is not earlier than the latest date required under the Tender Documents and the guarantee otherwise fully complies with the prescribed form and validity requirements. Alternatively, please confirm the specific expiry date that the Employer requires Tenderers to state in the Proposal Security so that the issuing bank can prepare the guarantee accordingly. | The Employer will accept an additional ultimate expiry-date provision in the Proposal Security, provided that the stated date is not earlier than twenty-eight (28) days after the expiry of the Proposal validity period stated in the RFP and provided that such wording does not otherwise amend, qualify or limit the obligations under the prescribed Proposal Security form. | No
707 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Deadline for Submission of Proposals | In order to prepare our bid properly, it is necessary to conduct a comprehensive market research, obtain quotations from suppliers and manufacturers, evaluate the technical and commercial requirements in detail, and prepare all information and documentation requested under the tender documents. In this regard, in order to allow sufficient time for the preparation of a comprehensive, competitive, and realistic offer, would it be possible to extend the current bid submission period by 45 days? | Please refer to Addendum No. 1 regarding the revised Proposal submission deadline under PDS ITP 23.1. | No
708 | Section VII – Employer’s Requirements / Annex C1 – Geological Data Report / Table 12 – Excavation Waste Storage Areas; Project E&S Instruments / Soil & Excavated Material Management Plan (S-EMMP) | The capacity of the existing disposal sites specified for the Anatolian Side is considered potentially insufficient for the storage of the waste materials expected to arise from the works associated with the three sections. In this regard, if the capacity of the existing disposal sites proves to be insufficient and additional disposal sites are required, will the Employer be responsible for providing the necessary additional disposal sites and addressing the associated requirements? | Please refer to Answer 301. | No
709 | Section VII – Employer’s Requirements / Clause 9.3.4 – Fire and Life Safety; Annex A1 – Alignment and Tunnel Drawings; Annex B1 – Conceptual Design Report; Annex K – Tunnel Electromechanical Works Technical Specification / Escape and Emergency Egress Requirements | The existing escape tunnel connection for the T-5 Tunnel under Lot-2 is considered potentially insufficient in terms of the required escape distance. It is observed that the distance between the escape tunnel connection and the entrance and exit portals exceeds 1,000 meters. In this regard, in accordance with the applicable design and safety criteria, will an additional escape tunnel be required? | Please refer to Answer 209. | No
710 | Section VII – Employer’s Requirements / Clause 11.10.1 – Land Acquisition and Expropriation; Annex D – General Technical Specification / Clause A.2.2.42; Section VIII – General Conditions / Sub-Clause 2.1 – Right of Access to the Site | During the construction phase, if additional expropriation or land allocation is required to provide access roads and service roads to tunnel portals, viaduct piers, and other structures where access may be challenging, will the Employer be responsible for carrying out the relevant expropriation and/or land allocation procedures? | Please refer to Answer 187. | No
711 | Section VII – Employer’s Requirements / Clause 11.10.1 – Land Acquisition and Expropriation; Clause 7.2.3 – Existing Utilities; Annex D – General Technical Specification / Clause A.2.2.42 | In the event that additional expropriation or land allocation is required for utility relocation works, will the Employer be responsible for carrying out the necessary expropriation and/or land allocation procedures? | Please refer to Answer 187. | No
712 | Section I – Instructions to Proposers (ITP) / ITP 19.1 and ITP 19.3; Section II – Proposal Data Sheet (PDS) / ITP 19 and ITP 19.3 | The Employer is kindly requested to confirm whether an unconditional and irrevocable proposal guarantee in original physical copy directly issued by a reputable bank duly authorised and licensed under the laws of a country outside Türkiye would be acceptable for submission of the proposal. | Please refer to Answer 123 and ITP 19.1, ITP 19.3 and the corresponding PDS provisions. Yes. An unconditional and irrevocable Proposal Security issued directly by a reputable bank duly authorised in an eligible country outside Türkiye is acceptable, provided that the guarantee is submitted in original form and fully complies with the form, amount, validity and other requirements of the RFP, including the required written confirmation of validity from the issuing bank. The additional correspondent-financial-institution requirement under ITP 19.3 applies to a non-bank financial institution located outside the Employer’s Country. | No
713 | Section IX – Particular Conditions (PC) / Part A – Contract Data / Sub-Clause 19.2.3(a) – Professional Indemnity Insurance | The Employer is kindly requested to confirm whether the 20% limit is reasonable.According to our quotation,the limit is too high to be accepted by the insurance markets。 | Please refer to Answer 300 and Contract Data Sub-Clause 19.2.3(a). The request is not accepted. The minimum Professional Indemnity Insurance cover remains not less than 20% of the Accepted Contract Amount. The required cover shall be maintained in accordance with the Contract Data and the applicable deductible requirements. Market availability does not reduce the stated minimum requirement, and the Contractor shall obtain compliant insurance and include the associated cost in its Proposal. | No
714 | Section VII – Employer’s Requirements / Annex A1 – Alignment Drawings / Part 1; Annex E4 – Railway Bridge Design Technical Specification | Given that construction activities related to bridge erection are affecting certain sections, would the client agree to use alternative structural forms (such as box girders or steel bridges) at this stage? If so, could the client please provide the relevant structural design drawings? | Please refer to Answers 153 and 346. | No
715 | Section VII – Employer’s Requirements / Clause 5.1.1 – Design and Build Disclaimer; Clause 4.8.1 – Interface with KGM and the YSS Bridge Corridor; Annex A1 – Alignment Drawings / Part 1 | Cut&Cover-4A and Cut&Cover-5A must pass under one side of the Kuzey Marmara Otoyolu to transition to the reserved alignment of the Yavuz Sultan Selim Bridge. According to the construction method provided by the Employer for this phase, partial closure of the O-7 Motorway is required as part of the construction organization measures. Given the heavy traffic volume on this motorway, Is it possible to use alternative construction methods (such as pipe jacking) to minimize the impact on local traffic? | Please note that the mentioned cut&cover tunnels (4A&5A) are already existing structures. | No
716 | Section VII – Employer’s Requirements / Clause 6 – Site Information / Utility Records; Clause 7.2.3 – Utility Records | Reference: Tender Document Part VII, Clause 6 (Site Information), Sub-clause 4 (Utility Records) The clause requires that “ The Contractor shall obtain all required utility data and related information from the relevant public authorities prior to and during the execution of the Works, in accordance with the authorizations and access letters to be provided by the Employer.” However, the Employer has not provided such authorizations and access letters to bidders at the tender stage, and bidders cannot obtain sufficient utility data and related information at this stage. Could the Employer disclose the utility data and related information within the project impact scope to all bidders for reference, allowing bidders to assess relevant protection measures, construction duration and costs? | Please refer to Answer 68. | No
717 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities / Notes | In the BOQ Notes, it is stated that: “For each of the activities, the Proposer has the option to add up to three (3) additional sub‑activities to the existing sub‑activities indicated below”. We wish to seek clarification whether the limit of three (3) additional sub‑activities applies: (i)as a total cap for the subject activity (i.e. maximum three additional sub‑activities in total, to be added at the same‑level after the existing sub‑activities); OR (ii)to each individual existing sub-activity (i.e. up to three additional sub‑activities may be inserted under every existing sub‑activity respectively). | The limit of up to three (3) additional sub-activities applies to each Activity as a whole, not to each individual existing sub-activity. Accordingly, for each Activity, the Proposer may add a maximum of three (3) additional sub-activities at the same sub-activity level. The additional sub-activities submitted at Proposal stage will form part of the contractual pricing/payment breakdown. No amendment is made to the RFP. | No
718 | Section II – Proposal Data Sheet (PDS) / ITP 16.1; Section IV – Proposal Forms / Appendix to Proposal – Table C – Summary of Payment Currencies | ITP 16.1 states that the currency(ies) of the Proposal and the payment currency(ies) shall be in accordance with Alternative A as described below: Alternative A (Proposers to quote entirely in local): (a) The prices shall be quoted by the Proposer in the Schedules of Priced Activities and Sub-activities entirely in Turkish Lira and further referred to as “the local currency”. A Proposer expecting to incur expenditures in other currencies for inputs to the Works supplied from outside the Employer’s country (referred to as “the foreign currency requirements”) shall indicate in the Appendix to Proposal - Table C, the percentage(s) of the Proposal Price (excluding Provisional Sums), needed by the Proposer for the payment of such foreign currency requirements, limited to no more than three foreign currencies. Since nearly all suppliers, including those based in Turkey, prefer to settle and receive payment in USD or EUR when issuing quotations to us, could the Proposer declare a 100% foreign currency requirement percentage for USD or EUR in Table C? | No, the Proposers cannot provide 100% of their Proposals as a foreign-currency. ITP 16.1 shall be applied as stated. The percentage(s) entered in Table C shall reflect the Proposer’s foreign-currency requirements for inputs to the Works supplied from outside the Employer’s country. The percentages stated by the Proposer shall accurately reflect its eligible foreign-currency requirements and shall be limited to no more than three foreign currencies. | No
719 | Section I – Instructions to Proposers (ITP) / ITP 19.8 and ITP 4.1 – JV Proposal Security | If the Tender is being submitted by a Joint Venture, kindly confirm whether the Proposal Security may be provided separately by each JV partner in proportion to its respective participation share in the Joint Venture. | Please refer to Answer 42 and ITP 19.8. No. Where the JV has not been legally constituted at the time of Proposal submission, the Proposal Security shall be in the names of all future JV members as named in the letter of intent. Separate Proposal Securities issued individually by the JV members in proportion to their respective JV participation shares do not satisfy ITP 19.8. | No
720 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification; Annex J2 – Catenary Systems Technical Specification / Design Speed | While the design speed is specified as 160 km/h in ANNEX E1 - Design Technical Specification, it is specified as 200 km/h in ANNEX J2 - Catenary Systems Technical Specification. This discrepancy affects traction power simulations, catenary mechanical design, mast spacing calculations, and the type of contact wire to be adopted. Furthermore, while 107 mm² or 120 mm² CuETP contact wire may be used for a 160 km/h line, a 120 mm² CuAg0.1 contact wire is generally required for a 200 km/h line. Since this difference has a direct impact on project costs, please confirm the final design speed to be adopted for the project. | The geometry of the alignment shall be done according to the design speed of 160 km/hr; on the other hand, the electrification works shall be done considering the design speed as 200 km/hr. | No
721 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J2 – Catenary Systems Technical Specification; AYGM-INR-EL-FP-001/002/003/004 – Feeding Plans | ANNEX J2 - Catenary Systems Technical Specification states that a tunnel earthing system shall be installed for tunnels longer than 400 m and that disconnectors and voltage transformers shall be located at tunnel portals. However, according to TSI-SRT requirements and current TCDD practices, catenary earthing arrangements are generally required for tunnels longer than 1,000 m. In addition, different tunnel earthing groupings are shown in AYGM-INR-EL-FP-001, AYGM-INR-EL-FP-002, AYGM-INR-EL-FP-003, and AYGM-INR-EL-FP-004 feeding plans. Please clarify whether the tenderers shall follow the requirements stated in ANNEX J2 or the arrangements shown on the feeding plans for design and quantity take-off purposes. | The requirements of Annex J2 shall be followed for the tunnel earthing and associated catenary equipment requirements. The tender-stage feeding plans are reference/conceptual plans and shall be further developed and coordinated through the system-wide power-supply simulations and Detailed Design in accordance with Section VII, Clause 5.3.3. Any difference in the conceptual grouping shown on the feeding plans shall be resolved in the final approved feeding plan without waiving the mandatory requirements of Annex J2. | No
722 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J1 – Traction Substations Technical Specification | ANNEX J1 - Traction Substations Technical Specification states that the final locations and ratings of traction transformers will be determined based on the results of traction power simulations. For tender-stage pricing and equipment selection, please clarify which transformer rating shall be considered. | Please refer to Answer 51. | No
723 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Annex J1 – Traction Substations Technical Specification / 154 kV Equipment Short-Circuit Rating | ANNEX J1 - Traction Substations Technical Specification specifies the rated short-circuit current of the 154 kV primary equipment as 31.5 kA. However, TEİAŞ may require a 50 kA short-circuit rating, which would significantly affect equipment selection and project costs. Please confirm the short-circuit level that shall be adopted for design and pricing purposes. | For Proposal purposes, the minimum short-circuit rating stated in Annex J1 shall be taken as the tender requirement. The Contractor remains responsible for the Detailed Design, protection and short-circuit studies and for obtaining the required TEİAŞ and other competent-authority approvals in accordance with Section VII, Clause 5.3.3. Where the approved Detailed Design or the competent authority requires a higher equipment rating, the Contractor shall provide equipment compliant with the approved requirements as part of its Design-Build obligations. | No
724 | Section VII – Employer’s Requirements / Clauses 5.3.4 and 5.3.5 – TCDD Network, Maltepe CTC and Package 2 Interfaces; Annex M1 – Mainline SCADA & Control Systems Technical Specification | ANNEX M1 - Mainline SCADA & Control Systems Technical Specification states that the SCADA Control Centre will be located in Maltepe. Please clarify whether a new standalone SCADA system is required to be installed at the Maltepe Control Centre or whether the new system shall be integrated into the existing SCADA infrastructure. If integration is required, please define the scope of the integration works. | Please refer to Section VII – Employer’s Requirements, Clauses 5.1 and 5.3.5, and Annex M1. The Contractor shall provide the SCADA system within its respective scope and shall ensure the necessary interfaces and integration with the relevant systems at the Maltepe Control Centre. The final integration arrangement and interface requirements shall be developed and coordinated during Detailed Design in accordance with the RFP. Package 2 is a separate contract for Signaling, Telecommunication and Supporting Systems and is not part of this tender. The Package 1 Contractors shall coordinate with the Package 2 Contractor in accordance with the applicable interface requirements. | No
725 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; AYGM-INR-EL-FP-001 – Feeding Plan / Neutral Sections | According to AYGM-INR-EL-FP-001 Feeding Plan, no traction substation is shown within the relevant section. It is understood that this section will be fed from the traction substation located around km 27+000 in LOT-2 and from the existing traction substation, which is assumed to be Osmangazi TSS. Under normal operating conditions, a neutral section would be expected between these two feeding zones; however, no neutral section is shown on the feeding plan. Please clarify whether a neutral section will be provided in this section and, if so, indicate its approximate location. | Section VII, Clause 5.3.3 requires the Lot 2 and Lot 4 Contractors to prepare the system-wide traction power simulations and a feeding plan including the proposed locations of neutral sections for review and approval. Accordingly, the absence of a neutral section from the tender-stage conceptual feeding plan shall not be interpreted as confirmation that no neutral section is required. The need for and final location of any neutral section shall be determined through the required simulations and Detailed Design and shall be subject to the Engineer’s and Employer’s approval. | No
726 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel / Railway Safety Manager; Section VII – Employer’s Requirements / Clause 2.4 – Contractor’s Representative and Key Personnel | Kindly elaborate on the requirements for the Railway Safety Manager position, including the required qualifications and experience, scope of responsibilities, required work items, and level of involvement. | Please refer to Section III, Item 1.4 and Section VII, Clause 2.4. One Railway Safety Manager is required for each Lot. The minimum qualification and experience requirements are a Bachelor’s Degree in Engineering, eight (8) years of relevant railway safety management experience and twelve (12) years of overall professional experience. The Railway Safety Manager shall form part of the Contractor’s Key Personnel and shall be available to the extent necessary to fulfil the Contractor’s railway-safety management, coordination and compliance obligations under the Employer’s Requirements throughout the applicable design, construction, testing and commissioning activities. The RFP does not prescribe a separate payment item or a separate fixed minimum level of effort for this position beyond the Key Personnel availability and resource-schedule requirements. | No
727 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Deadline for Submission of Proposals | After a thorough review of the tender documents, technical specifications, and scope of works, we respectfully request a six (6) week extension of the bid submission deadline, moving the date from 14 October 2026 to 25 November 2026. This additional time will enable us to conduct the most comprehensive technical and commercial study possible, including detailed site assessments, accurate quantity take-offs, careful coordination with our suppliers and subcontractors, and the development of value-engineered solutions. Our objective is to submit a proposal of the highest quality that fully meets the Commission's expectations and best serves the success of the project. We believe this extension will be of mutual benefit, allowing all bidders to prepare well-considered and competitive submissions, and ultimately supporting the most favorable outcome for the Commission. We remain fully committed to this tender and would be grateful for your kind consideration of this request. Please do not hesitate to contact us should you require any further information or clarification. Thank you for your time and consideration. We look forward to your favorable response. | Please refer to Addendum No. 1. | No
728 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel / Project Manager and Civil Works Deputy Project Manager | According to RFP Section III Evaluation and Qualification Criteria / Contractor’s Representative and Key Personnel Item 1 and 2 In many countries, tenders issued by public institutions-which are funded by internal resources rather than international funding agencies-are executed under the specific contract regulations of the relevant national laws, rather than directly under the FIDIC Conditions of Contract. Therefore, if a contract: - Assigns design responsibility to the Contractor, - Is a lump-sum contract, - Provides for international arbitration in the event of disputes, - Places full responsibility on the Contractor, can the completion of one or more such projects serve as a valid reference for a Project Manager and an Deputy Project Manager (Construction Works)? Please confirm. If the conditions specified above are met, is experience gained under the FIDIC Silver Book and BOT (Build-Operate-Transfer) contracts also considered valid experience? | The proposed equivalence is not confirmed. For the Project Manager and Civil Works Deputy Project Manager, Section III expressly requires the specified railway-system contract experience using FIDIC Yellow Book or FIDIC Gold Book Conditions of Contract. A national public-works contract, FIDIC Silver Book, BOT, EPC or other contractual form may demonstrate relevant general professional experience, but it does not substitute for the express Yellow/Gold Book experience requirement in Items 1 and 2. The minimum number of qualifying contracts stated for each position also remains applicable. No amendment is made to the RFP. | No
729 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Proposal Submission Deadline; ITP 26.1 – Opening of Technical Parts; Section I – ITP 8 – Amendment of RFP Document | We respectfully request a six-week extension to the tender submission deadline to allow sufficient time to complete our technical and commercial assessments and prepare a comprehensive, fully coordinated tender submission. Please confirm whether this extension can be granted and advise the revised submission and opening dates. | Please refer to Addendum No. 1. | No
730 | Section VII – Employer’s Requirements / Clauses 5.1.1 and 5.5.2 – Design and Build / Lot 1 Station Works – Sabiha Gökçen Airport Station; Annex A – Drawings AYGM-INR-ARC-SGA-005 and SGA-006 | The connecting tunnels providing access to the elevators at elevation +0.55 (Level −50 m), shown on layout drawing AYGM-INR-ARC-SGA-005, are not indicated in Section A–A on drawing AYGM-INR-ARC-SGA-006. Please confirm whether these connecting tunnels are required at Level −50 m and form part of the Contractor’s scope. Please also confirm whether the associated elevators serve only Levels −50 m and −30 m, with no stops at other levels. | The architectural drawings are tender-stage conceptual information and shall be reconciled and completed through the Contractor’s Detailed Design. The Lot 1 Contractor shall provide all connecting tunnels, shafts, lifts and other access/egress elements required for a complete and compliant Sabiha Gökçen Airport Station. The omission of a connection in a sectional drawing does not constitute an exclusion from the Works. The final lift stopping levels and connecting arrangements shall be established in the approved Detailed Design in accordance with accessibility, fire-life-safety and operational requirements. | No
731 | Section VII – Employer’s Requirements / Clauses 5.1.1 and 5.5.2 – Design and Build / Lot 1 Station Works – Sabiha Gökçen Airport Station; Annex A – Drawings AYGM-INR-ARC-SGA-004 and SGA-006 | The two northwestern staircases between axes T8 and T9, shown at elevation +20.55 (Level −30 m) on layout drawing AYGM-INR-ARC-SGA-004, are shaded gray, which we understand denotes future construction. However, the corresponding staircases on the Level −10 m plan, referenced as drawing AYGM-INR-ARC-SGA-006, are shown in color, suggesting that they form part of the Lot 1 Contractor’s scope. Please clarify this discrepancy and confirm whether both staircases, including their connecting structures between Levels −30 m and −10 m, are to be constructed under the Lot 1 Contract or reserved for future construction. | The future works at the relevant station include the SHT line connection. The connection tunnel at Level -30.00 m, together with the other elements highlighted as part of the current Works in the conceptual plans and sections, shall be constructed under this Contract. The stairways providing connection to the future SHT platform and the associated platform tunnels shall be considered as future works and are not included in the current construction scope. The architectural drawings are conceptual and shall be read together with the Employer’s Requirements. Grey shading in a tender-stage drawing shall not, by itself, be interpreted as excluding an element from the Contract. The Lot 1 Contractor shall construct all other stairways and connecting structures required by the approved Detailed Design for a complete, safe and operational station. | No
732 | Section VII – Employer’s Requirements / Clause 5.5.2 – Lot 1 / Infrastructure Relocations; Clause 6.4 – Utility Records | In order to properly assess the Infrastructure Relocation scope, quantities and associated costs of these works, we kindly request the Employer to provide all available information, drawings, surveys, utility maps and technical requirements related to the existing and proposed utility infrastructure within the Project limits. This information should include, but not be limited to, utilities and facilities under the responsibility of İSKİ, İGDAŞ, TEİAŞ, TEDAŞ, BOTAŞ, DSİ, telecommunication operators, municipalities and other relevant authorities, including: -Water supply, wastewater and stormwater networks; -Natural gas and other pipeline systems; -High-voltage, medium-voltage and low-voltage electrical lines, including underground and overhead systems; -Telecommunication, fiber-optic and other communication cables; - Irrigation, drainage and other DSİ infrastructure; -Municipal and other public utility networks and facilities. For each affected utility, where available, please provide details such as the existing alignment and location, depth/elevation, size/capacity, utility owner, required relocation or protection arrangement, approximate relocation lengths/quantities, applicable authority requirements and any available approved or preliminary relocation designs. | Please refer to Section VII, Clause 6.4 – Utility Records. The utility information made available in the Tender Documents is indicative. The Contractor is responsible for collecting, verifying, updating, modelling and coordinating all existing underground and above-ground utility information and for liaising with the relevant authorities and utility owners. The Employer will provide the authorizations/access letters required for such coordination where applicable. Tenderers shall base their Proposals on the information made available, the site visit and their own assessment, while allowing for the verification and coordination obligations stated in the RFP. | No
733 | Section VII – Employer’s Requirements / Clauses 4.6 and 4.8.3 – Power Supply Coordination / TEİAŞ; Clause 5.3.3 – Power Supply Design – Cross-Lot Obligations; Annex J – Power Supply and Traction Power Systems | External Power Supply for Traction Substations – Lots 1–4 Please confirm the required external power supply arrangement for the traction substations to be constructed under Lots 1, 2, 3 and 4, including: - the required voltage level and connection arrangement; - the proposed/available TEİAŞ or other utility connection points; - the approximate location of the connection points and available capacity; - the responsibility for the external transmission/connection line from the existing network to the traction substation; - whether the Contractor is responsible for the design, permits, construction, testing and commissioning of such external connection works; and - any applicable TEİAŞ/utility connection fees, land/wayleave requirements and other statutory charges. For the substations identified at Lot 2 – approximately KM 27+000 and Lot 3 – approximately KM 7+600, please provide, where available, the relevant existing network information and proposed connection arrangement. | The external traction-power supply scope shall be developed in accordance with Section 5.3.3 and Annex J. The power system is based on 154 kV supply connections to the TEİAŞ network. The Lot 2 and Lot 4 Contractors shall carry out the system-wide traction-power simulations, identify and propose suitable connection points and obtain the necessary TEİAŞ/energy-authority approvals. The final supply points, transformer locations and transmission/distribution arrangement based on the approved simulations determined by the contractor shall be approved by Employer/Engineer. Each Lot Contractor shall design, construct, test and commission the power-supply works falling within its Lot, including the applicable external connection/transmission works and interfaces. Permits, approvals and associated Contractor-scope costs shall be included in the Proposal Price. The locations stated in the RFP, including approximately km 27+000 and km 7+600, are indicative planning locations only. No additional guaranteed network-capacity data is issued through this clarification. | No
734 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Clause 4.8.3 – TEİAŞ Interface; Clauses 11.6.3 and 11.10.1 – Permits, Land Access and Allocation of Responsibilities; Annex J | Traction Substation Land and Access Requirements Please clarify whether the land required for the traction substations, including the substation footprint, external terminal structures and permanent/temporary access roads, will be provided by the Employer or acquired/provided by the Contractor. If the Contractor is responsible for land acquisition or temporary/permanent access, please clarify the applicable expropriation, land-use, wayleave and statutory cost allocation. | Please refer to Answers 45 and 187. Permanent land required for the traction substations and permanent access forming part of the Project Works shall be dealt with under the land-acquisition/expropriation provisions of the Employer’s Requirements. The Contractor shall provide the design and technical information necessary to define such land requirements. Temporary access, additional working areas, wayleaves or other arrangements arising from the Contractor’s construction methods outside the Site shall remain the Contractor’s responsibility and cost unless otherwise expressly provided by the Contract. | No
735 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design; Clause 4.8.3 – TEİAŞ Interface; Clause 10.7 – Electrical Systems; Annex J | Testing, Energization and Commissioning Please confirm the scope of TEİAŞ/utility-required testing, inspection, approval, energization and commissioning of the traction substations and their external power connections. Please also clarify which associated costs and statutory fees are to be borne by the Contractor. | All testing, inspection, approval, energization and commissioning required by TEİAŞ and/or the relevant electricity authority for the traction substations and their external power connections shall be included in the Contractor’s scope to the extent applicable to its Lot. The Contractor shall coordinate with the relevant authorities, prepare and submit the required studies and documentation, obtain the approvals and complete the tests and energization necessary for operation. All Contractor-side costs, permit/approval costs and statutory charges required for its scope shall be included in the Proposal Price unless the RFP expressly allocates a particular charge to the Employer. | No
736 | Section VII – Employer’s Requirements / Clause 5.3.2 – Tunnel Electromechanical Works; Clauses 10.7 and 10.9 – Electrical / Tunnel E&M Systems; Annexes J and K | Tunnel and Other Auxiliary Power Connections The Tender Documents require auxiliary electrical power supply arrangements for tunnels and other facilities throughout the four Lots. Please clarify: - whether the Contractor is responsible for obtaining the external utility connection for each tunnel/auxiliary facility; - whether the Employer has identified or obtained preliminary connection points from the relevant electricity distribution utility; - the applicable connection voltage levels and available capacities; - whether connection costs, cables, transformers, land/wayleave, permits and utility charges are included in the Contractor's scope; and - whether any existing utility network information, preliminary connection studies or correspondence with TEİAŞ/distribution companies can be provided to Tenderers. | The Contractor is responsible for providing the complete auxiliary-power arrangements required for tunnels and other facilities within its Lot, including the necessary utility interfaces, connection works, transformers/cables, permits, approvals and commissioning. Any information provided by the Employer regarding existing networks is indicative and shall be independently verified by the Contractor with the relevant utility. Final connection points, voltage levels and capacities shall be developed through the Detailed Design and authority-coordination process. No additional guaranteed preliminary connection study or network-capacity commitment is issued through this clarification. The applicable Contractor-scope connection and authority costs shall be included in the Proposal Price. | No
737 | Section I – ITP 15.1 – Proposal Prices / Single Responsibility; Section VII – Employer’s Requirements / Clauses 5.3.2–5.3.3; Annex J | Information Required for Tender Pricing Considering that the above external power supply works may have a significant impact on the capital cost, construction programme and temporary/permanent works, we kindly request the Employer to provide the available network information, connection arrangements and applicable cost/responsibility allocation, or otherwise confirm the basis upon which Tenderers should price these works. We would appreciate the Employer's clarification so that all Tenderers can assess and price the external power supply requirements on a consistent basis. | Please refer to Answers 50, 51 and 52. The Proposer shall price the external power-supply and electrification works on the basis of the RFP Documents, the available tender information and its own verification, on a single-responsibility Design-Build basis. Final connection points, capacities, routes and arrangements shall be developed through the required power-supply simulations, Detailed Design, utility coordination and approvals. All obligations within the Contractor’s scope shall be included in the Proposal Price unless expressly allocated otherwise in the Contract. No additional network information is issued through this clarification and | No
738 | Section IV – Proposal Forms / Lot 2 – Activity 9 – Systems Installation Substantial Completion / Item 9.1 – Electrification Foundation and Infrastructure Works; Section VII – Clause 5.3.3; Annex J | Question: The Bidder understands that the scope of works under Item 9.1 includes: (1) OCS concrete foundations, masts, portal, drop tube in tunnel, etc. and (2) Substation building and civil works, site grading(preparation), access road and perimeter wall. Please confirm this understanding is correct? If not, please provide detailed clarification. | Item 9.1 is a lump-sum functional package for the civil/foundation and infrastructure works required for the electrification system within the Lot. It includes, as applicable to the approved Detailed Design, foundations and support infrastructure for OCS masts/portals and tunnel supports, together with the civil and infrastructure works necessary for traction substations, sectioning facilities and associated installations. The Schedule is not intended to be an exhaustive bill of quantities. The Proposer shall allocate the complete scope among the listed sub-activities without omission or double counting, in accordance with the Employer’s Requirements and its design. | No
739 | Section IV – Proposal Forms / Lot 2 – Activity 9 / Item 9.3 – Sectioning, Insulation, Substation and Sectioning Post Works; Section VII – Clause 5.3.3; Annex J | Question: The Bidder understands that the works under Item 9.3(Sectioning, insulation, substation and sectioning post) refers to the 27.5 kV switching post/sectioning stations on the main line (see the following figure). Please confirm this understanding is correct? If not, please provide detailed clarification for accurate pricing. | The proposed interpretation is too narrow. Item 9.3 covers the complete sectioning and insulation works and the substation and sectioning-post works required within the Lot under the approved Detailed Design. It is not limited only to 27.5 kV main-line switching/sectioning posts. The Contractor shall include all equipment, interfaces and associated works falling within this functional package and coordinate the allocation with Items 9.1, 9.4 and 9.5 so that the full electrification scope is priced once. | No
740 | Section IV – Proposal Forms / Lot 2 – Activity 9 / Item 9.4 – Switchyard and Electrical Distribution Works; Section VII – Clause 5.3.3; Annex J | Question: The Bidder understands that the scope of works under Item 9.4 applies to the Switchyard and electrical distribution works on the 154 kV side of the Traction Substation and the Switchyard and electrical distribution works on the 27.5 kV side. Please confirm this understanding is correct? If not, please provide detailed clarification for accurate pricing. | Confirmed in principle. Item 9.4 covers the complete switchyard and electrical-distribution works required for the traction-power system within the Lot, including the applicable 154 kV side and the downstream traction/auxiliary distribution arrangements required by the approved Detailed Design. The exact configuration and voltage levels shall be determined in accordance with Annex J, the approved power-supply design and authority requirements. | No
741 | Section IV – Proposal Forms / Lot 2 – Activity 9 / Item 9.5 – Protection, Metering, Earthing and Safety Systems; Section VII – Clause 5.3.3; Annex J | Question: The Bidder understands that the scope of works under Item 9.5 covers the works just related to the Traction Substation and the 154 kV transmission line. Please confirm this understanding is correct? If not, please provide detailed clarification for accurate pricing. | The proposed interpretation is too narrow. Item 9.5 covers the complete protection, metering, earthing, bonding and electrical-safety systems required for the power-supply and electrification works within the Lot. This includes, as applicable, traction substations, switchyards, sectioning facilities, OCS/return-circuit and associated electrical installations, and is not limited only to the traction substation and 154 kV transmission line. The final scope shall follow Annex J and the approved Detailed Design. | No
742 | Section IV – Proposal Forms / Lot 2 – Activity 9 / Item 9.6 – SCADA and Telecommunication Works; Section VII – Clauses 4.5 and 5.3.5 – Package 2 Interfaces; Annexes L and M | Question: The Bidder understands that the scope of works under Item 9.6 covers systems in the whole line (lot 1, lot 2, lot 3 and lot 4). Please confirm this understanding is correct? If not, please provide detailed clarification for accurate pricing. | Please refer to Answer 29. Package 2 is a separate contract for Signaling, Telecommunication and Supporting Systems and is not part of this tender. Item 9.6 under the relevant Lot does not transfer the corridor-wide Package 2 scope to the Lot Contractor. It covers the SCADA and telecommunication works expressly included within the respective Lot scope, including the applicable electrification, MEP/control systems and interfaces with Package 2. The Proposer shall price the scope applicable to the Lot for which it submits a Proposal. | No
743 | Section IV – Proposal Forms / Lot 2 – Activity 9 / Item 9.7 – Environmental and Dismantling Works; Section VII – Employer’s Requirements / Environmental and Social Requirements | Question: Please clarify the inclusions within the work package under Item 9.7 for accurate pricing. | Please refer to Answer 115. The environmental and dismantling works under the relevant Systems Installation activity comprise the environmental protection, reinstatement and related measures, and dismantling/removal works, directly associated with the systems works covered by that Activity. Works allocated to other Activities, including general civil works and relocation of existing infrastructure, shall not be duplicated under this item. No separate technical specification is issued through this clarification. | No
744 | Section IV – Proposal Forms / Table of Forms – Daywork Schedule; Addendum | Kindly confirm whether a Daywork Schedule is required to be submitted as part of the tender. We could not identify the relevant format or template within the tender documents even it has been shown in the Table of forms. Could you, please kindly provide the applicable format. | Please refer to Answer 258 and Addendum No. 2, Amendment No. 6. Daywork is not applicable under the RFP as amended. The Daywork Schedule entries are deleted from the Table of Forms and no Daywork Schedule or Daywork rate tables are required to be submitted. | Yes
745 | Section IX – Particular Conditions / Sub-Clause 14.3 – Application for Interim Payment; Section IV – Schedule of Priced Activities and Sub-activities; Addendum | Kindly clarify how payments will be made and what payment proportions or milestones will be applied to the lump-sum items. We understand that lump-sum prices are to be provided for each structure identified in the BOQ. Kindly confirm how these lump-sum items are expected to be further subdivided for payment purposes and whether the Employer will provide a prescribed payment breakdown or template. | Please refer to Answer 7. Please refer to Addendum No. 2, Amendment No. 12. | Yes
746 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities / Superstructure (Track) Works – Track Maintenance Works during Construction (Lots 1–4) | Could you provide the content and definition of the item named "Track Maintenance Works" under Superstructure (Trackworks) acitivity? | “Track maintenance works (during construction period)” means all inspections, monitoring, adjustment, correction and maintenance necessary to keep the track infrastructure affected by or installed under the Contract safe, serviceable and within the required tolerances throughout the construction period until Taking-Over. It includes, as applicable, track-geometry correction, tamping/lining, rail and fastening maintenance, turnout maintenance, ballast/slab-track related remedial works, cleaning and correction of defects or damage arising during construction. The extent shall be determined by the actual condition of the Works and the Employer’s Requirements. | No
747 | Section IX – Contract Data / Sub-Clause 1.1.27 – Defects Notification Period; Section VII – Clauses 10.6.4 and 10.10.13 – Defects Notification / O&M Supervision; Section IX – Sub-Clause 1.1.95 – Milestones; Addendum | 1. Are the Defects Notification Period and the Defects Liability Period the same concept? 2. Both the Defects Liability Period and the O&M Supervision Period commence upon issuance of the Taking-Over Certificate. Can we therefore interpret the Defects Liability Period and the O&M Supervision Period as one and the same concept? If not, please sort the following key milestones mentioned under Clause 10. Testing, Commissioning and Trial Operations in chronological order: Trial Running, Trial Operations, Provisional Acceptance, Final Acceptance, Taking-Over Certificate, Defects Liability Period and O&M Supervision Period. Please also specify the durations of the Defects Liability Period and the O&M Supervision Period. 3. Should all the above milestones mentioned under Clause 10. Testing, Commissioning and Trial Operations, namely Trial Running, Trial Operations, Provisional Acceptance, Final Acceptance, Taking-Over Certificate, Defects Liability Period and O&M Supervision Period, be completed within the 2-year period specified under Milestone 4? | Please refer to Addendum No. 2, Amendment No. 21. | Yes
748 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 1.1.86 and 1.1.95 – Time for Completion and Milestones; Addendum | In RFP documents, Particular Conditions, page 389, the table regarding the Milestones below are mentioned. According to that table, we see that the duration from the commencement date to the end of the Test & Commissioning Completion period is 84 months, however the project duration for each lot is 60 months (1826 days) according to the RFP documents. Could you please clarify if the Test & Commissioning period is included in 60 months’ project duration or not. | Please refer to Answer 5. Please refer to Addendum No. 2, Amendment No. 3. | Yes
749 | Section IX – Particular Conditions / Sub-Clause 4.26 – Milestones; Part A – Contract Data / Sub-Clause 8.8 – Delay Damages | Kindly confirm that any delay damages applied and deducted from the Contractor during the execution of the Project in respect of delays in achieving the other Milestones shall be refunded to the Contractor upon the timely completion of Milestone 4, meaning the timely completion of the Project in accordance with the Contract. | No. Delay damages validly accrued for failure to achieve a contractual Milestone within its applicable Time for Completion are not refunded merely because a later Milestone, including Milestone 4, is achieved on time. The application of delay damages shall be governed by Sub-Clauses 4.26 and 8.8, including any Extension of Time determined under the Contract and the applicable maximum cap. | No
750 | Section III – Evaluation and Qualification Criteria / Item 1.5 – Equipment; Section IV – Proposal Forms / Contractor’s Equipment | With reference to “Section III – Evaluation and Qualification Criteria, 1.5 Equipment”; the Proposer must demonstrate that it has access to the key equipment listed. The item named “Cut-and-Cover Excavation Support Equipment” is not clearly defined by the Client and may be led to misunderstanding. Please clarify the equipment. | For the purposes of Section III, Clause 1.5, “Cut-and-Cover Excavation Support Equipment” means the plant and equipment necessary to execute the Contractor’s proposed cut-and-cover excavation-support and retaining system safely and effectively. Depending on the proposed methodology, this may include equipment for diaphragm walls/secant piles, drilling/piling, anchors/struts, excavation, lifting and associated support operations. The Proposer shall identify in Form EQU the equipment it proposes to use and demonstrate access to the minimum number required for the relevant Lot. | No
751 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 4.4(a) – Maximum Subcontracting | Under Particular Conditions Part A – Contract Data, Sub-clause 4.4(a), “Maximum allowable accumulated value of work subcontracted (as a percentage of the Accepted Contract Amount)” is stated as 30% (thirty percent). We kindly request to allow at least %50 of the Contract Price. | The request is not accepted. The maximum allowable accumulated value of work subcontracted remains 30% of the Accepted Contract Amount in accordance with Contract Data Sub-Clause 4.4(a) and ITP 17.4. | No
752 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 4.7.2 – Errors in Items of Reference | Under Particular Conditions Part A – Contract Data, Sub-clause 4.7.2, “Period for notification of errors in the items of reference” is stated as 28 days. We kindly request to increase 28 days to 42 days. | The request is not accepted. The period for notification of errors in the items of reference remains 28 days in accordance with Contract Data Sub-Clause 4.7.2. | No
753 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 8.8 – Delay Damages | Under Particular Conditions Part A – Contract Data, Sub-clause 8.8, “Delay damages payable for each day of delay”: We kindly request to apply the application of delay damage percentage only on the specific scope defined under each milestone. (For example, 0.05% of full amount covering the Works of Milestone 2 in case of delays in completion of the Milestone 2.) | The request is not accepted. Delay damages under Contract Data Sub-Clause 8.8 remain 0.05% of the Accepted Contract Amount, less the Provisional Sum for DAAB, for each day of delay in achieving the relevant Milestone, subject to the maximum amount stated in the Contract Data. The calculation is not limited to the value of the scope assigned to the delayed Milestone. | No
754 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 14.2.3 – Repayment of Advance Payment | Under Particular Conditions Part A – Contract Data, Sub-clause 14.2.3, “Repayment of Advance payment”: We kindly request to decrease the percentage of repayment of the Advance Payment to %15 to ease the case flow for the Project execution. | The request is not accepted. The advance-payment repayment provisions remain as stated in Contract Data Sub-Clause 14.2.3. Repayment shall commence upon reaching the applicable 5% certified-payment threshold, the percentage deduction shall remain 25%, and the advance payment shall be fully repaid before 90% of the Accepted Contract Amount less Provisional Sums has been certified for payment. | No
755 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 14.6.2 – Minimum Amount of Interim Payment Certificate | Under Particular Conditions Part A – Contract Data, Sub-clause 14.6.2, “Minimum Amount of Interim Payment Certificates”: We kindly request to reduce 0.5% to 0.1% as 0.5% will be extremely hard, especially at the initial stages of the Project, and the Contractor will struggle to submit a Statement achieving 0.5% of the Accepted Contract Amount. | The request is not accepted. The minimum amount of an Interim Payment Certificate remains 0.5% of the Accepted Contract Amount in accordance with Contract Data Sub-Clause 14.6.2. | No
756 | Section IX – Particular Conditions / Sub-Clause 14.1 – The Contract Price | In the Particular Conditions (PC), Sub-Clause 14.1, “The Contract Price”: We kindly request to revise the following sections: “If the Contractor fails to attend or send a representative at the time and place stated in the Engineer’s Notice (or otherwise agreed with the Contractor), the measurement made by (or on behalf of) the Engineer …” and, “If the Contractor fails to attend or send a representative at the time and place stated in the Engineer’s Notice (or otherwise agreed with the Contractor), the Contractor shall be deemed to have accepted the records as accurate.” as follows: “If the Contractor fails to attend or send a representative at the time and place stated in the Engineer’s Notice (or otherwise agreed with the Contractor), on purpose, …” So that the Contractor shall not face consequences for not attending due to reasons not attributable to the Contractor. | The request is not accepted. Sub-Clause 14.1 shall apply as stated. The Engineer is required to give the contractual notice for measurement or examination of records, and where the Contractor fails to attend or send a representative at the notified or otherwise agreed time and place, the consequences expressly stated in Sub-Clause 14.1 shall apply. No additional requirement that such failure be intentional or “on purpose” is introduced. Any entitlement arising from a specific event or circumstance shall be determined under the applicable provisions of the Contract. | No
757 | Section IX – Particular Conditions / Sub-Clause 14.6.3 – KPI Performance Withholding / Corrective Action Plan | In the Particular Conditions (PC), Sub-Clause 14.6.3, the time limit for a Corrective Action Plan is stated as 10 working days. We kindly request it to be increased to 20 working days. | The request is not accepted. The Corrective Action Plan period remains ten (10) working days from the Engineer’s written notification, subject to any shorter period permitted by Sub-Clause 14.6.3 due to the seriousness of the breach. | No
758 | Section IX – Particular Conditions / Sub-Clause 14.6.3 – KPI Performance Account | Under Sub-Clause 14.6.3, it is stated that: “…Any amount remaining in the KPI Performance Account on the date of issue of the Taking-Over Certificate for the relevant Lot shall be permanently forfeited by the Contractor and retained by the Employer…” The Contractor opines that the above provision does not allow the Contractor to rectify the issues faced just before the issuance of the Taking-Over Certificate, and result in loss without right to remedy. Kindly replace the “Taking-Over Certificate” with the “Performance Certificate” so that the notion of the provision is still protected while the Contractor is given opportunity to rectify the non-compliance. | The request is not accepted. The forfeiture point for amounts remaining in the KPI Performance Account remains the Taking-Over Certificate for the relevant Lot. Before that point, withheld amounts may be recovered where the Contractor restores compliance with the relevant KPI target and maintains compliance for the required consecutive reporting periods, subject to the notice, objection and dispute procedures in the Particular Conditions. | No
759 | Section IX – Particular Conditions / Sub-Clause 14.6.3 – KPI Performance Withholding; Section VII – Employer’s Requirements / Clause 12.2 – Contractual Performance Framework | Under Particular Conditions (PC), page 431 of the Inrail RFP documents, under the title of KPI Performance Withholding during an Extension of Time, it is stated as follows: “Where the Engineer determines under Sub-Clause 8.5 that the Contractor is entitled to an extension of time as a result of: …” and “KPI Performance Withholding shall be suspended only: (i) in respect of each KPI specifically identified by the Engineer as having been materially affected; …” The tenderer opines that the KPIs having been affected, even not materially, should be evaluated for suspension of KPI Performance Withholding considering the case described for such effects are due to an extension of time where the Contractor is entitled for additional time. Kindly delete the word “materially” and read it as follows: “(i) in respect of each KPI specifically identified by the Engineer as having been affected”. | The request is not accepted. An Extension of Time does not automatically suspend KPI Performance Withholding. Suspension applies only to the specific KPI(s) whose achievement is determined by the Engineer to have been materially prevented by an Employer-risk event or an Exceptional Event, and only for the period of direct material effect, in accordance with Sub-Clause 14.6.3. | No
760 | Section IX – Particular Conditions / Sub-Clause 15.2.1(g) – Termination for KPI Non-Performance; Sub-Clauses 14.6.3–14.6.5; Section VII – Clause 12.2 | Under Sub-Clause 15.2.1(g), we kindly request to add: “, provided that such cases are not caused by events not attributable to the Contractor (for example, a rightful entitlement to additional time, etc.),” to read as follows: “…15.2.1(g) as an additional ground for default, provided that such cases are not caused by events not attributable to the Contractor (for example, a rightful entitlement to additional time, etc.), as follows: …” | The requested addition is not accepted. Sub-Clause 15.2.1(g) shall be read together with the Contract provisions governing Extension of Time, Employer-risk events, Exceptional Events, KPI withholding/suspension and KPI target review. An Extension of Time does not, by itself, suspend the KPI regime. Where the Engineer determines that achievement of a specific KPI was materially prevented by an Employer-risk event or an Exceptional Event, the applicable suspension period shall be treated in accordance with Sub-Clause 14.6.3 and shall be disregarded for the purposes of calculating the Critical KPI breach thresholds under Sub-Clause 15.2.1. In addition, the notice and remedy provisions expressly applicable under Sub-Clauses 15.1 and 15.2.1(g), including the applicable Notice to Correct and corrective-measure period, remain applicable. | No
761 | Section VII – Employer’s Requirements / Clauses 4.5 and 5.3.5 – Package 2 Signaling, Telecommunication and Supporting Systems Interface; Annex L; Section IV – Systems Installation / SCADA and Telecommunication | With reference to ANNEX-L “Technical Specifications for Signalling, Telecommunications and Support Systems”, it is stated as Signaling and Telecommunication works will be procured separately and are not included within the scope of this Tender. So that, please clarify the context of “telecommunication works” that will be paid from “Item No. 9.6: SCADA and Telecommunication Works” under “Activity 9 – Systems Installation Substantial Completion”. | Package 2 covers the corridor-wide Signalling and Telecommunications System and is procured separately. The expression “SCADA and telecommunication works” in Item 9.6 of the relevant civil/electrification Lot does not transfer the Package 2 scope to that Lot Contractor. It covers the Lot-specific SCADA, communication/data interfaces and associated local equipment expressly required for the Contractor’s own electrification, tunnel, station and other systems, together with the interface works necessary for integration with Package 2 and the central control systems. The Contractor shall not duplicate the core signalling and telecommunications systems allocated to Package 2. | No
762 | Section VII – Employer’s Requirements / Clauses 4.5, 5.3.2 and 5.3.5 – Lot 4 Control / Communication Interfaces; Annexes L and M | Are the control and communication system for station on Lot-4 included in the scope of the Tender? If yes, please specify the relevant subactivity. | Please refer to Answer 29. Station control and communication systems are included in Lot 4 only to the extent expressly required within the Lot 4 scope, including station MEP/local control, SCADA and communication interfaces as applicable. The core railway Signaling and Telecommunication scope is procured separately under Package 2. The relevant Lot systems/MEP/SCADA Activities and sub-activities shall be used for pricing the scope included in this Contract; no additional sub-activity is introduced through this clarification. | No
763 | Section VII – Employer’s Requirements / Clauses 4.5 and 5.3.5 – Package 2 Interface; Annexes L and M – SCADA / Control Systems | We understand that each Lot section will install its own SCADA equipment, without any monitoring points, servers, software, etc., and will carry out the integration at the SCADA center which will be installed under the scope of Signalization Package. Please confirm. | The understanding is not fully correct. Each Lot Contractor shall provide the complete local SCADA/automation functionality required for the systems within its own scope, including the necessary monitoring/control points, local controllers, communications, software/configuration and local workstations/servers where required by the applicable technical specifications. The central and corridor-wide interfaces shall be coordinated with the Package 2 Signalling and Telecommunications contractor and the central control facilities. The Lot Contractor may not omit components expressly required by Annex M or other Employer’s Requirements on the assumption that they will be supplied under Package 2. | No
764 | Section VII – Employer’s Requirements / Annex J2 – Catenary Systems Technical Specification / Clause 12.11.2.1 | With reference to ANNEX-J2 Catenary Systems Technical Specification 12.11.2.1, please confirm that 120 mm² Cu-ETP catenary wire meeting the technical requirements can be used. | The contact/catenary wire material and section shall comply with Annex J2, the approved Detailed Design and all applicable electrical and mechanical performance requirements. A 120 mm² Cu-ETP wire may be proposed where it satisfies all requirements of Clause 12.11.2.1 and the other governing provisions and is accepted through the design/material approval process. This clarification does not constitute advance approval of a particular manufacturer or product. | No
765 | Section VII – Employer’s Requirements / Clauses 5.2.1–5.2.3 – Geotechnical Risk Allocation; Annex C1 – Geological Data Report | Given that the risks of methane, karst/voids, liquefaction, swelling clay, incomplete rock-mass classification, and hydrogeological characterization are identified as foreseeable risks under Employer’s Requirement 5.2.2, does this mean that FIDIC Yellow Book Clause 4.12 is entirely excluded in respect of these risks, or can the Contractor still invoke Clause 4.12 where the actual physical conditions encountered exceed the reasonably foreseeable extent of those risks and therefore constitute unforeseeable physical conditions, giving rise to an entitlement to additional time and/or Cost? | Please refer to Section VII, Employer’s Requirements, Clauses 5.2.1 to 5.2.3. The hazards expressly identified in Clause 5.2.2, including methane, karstification/voids, liquefaction, swelling clay, incomplete rock-mass classification and incomplete hydrogeological characterization, are allocated as foreseeable risks and shall be independently investigated and priced by the Contractor. Accordingly, the mere occurrence or greater severity of conditions of the nature described does not, of itself, create an entitlement to additional time or Cost. Any condition genuinely outside the risk allocation and qualifying as an unforeseeable physical condition shall be dealt with strictly in accordance with the applicable Conditions of Contract and the facts of the event; no blanket or advance entitlement is confirmed. | No
766 | Section VII – Employer’s Requirements / Clauses 5.1.1 and 5.2.1–5.2.3 – Design and Build / Geotechnical Risk Allocation; Annex C1 – Geological Data Report | In the event that material errors, discrepancies, or deviations are subsequently identified in the Geotechnical Data Report, Conceptual Design, or other reference data provided by the Employer, under what circumstances would the Contractor be entitled to claim an Extension of Time, additional payment, and/or a Variation? Which of the data and information provided by the Employer are contractually binding, and which are intended to be indicative only? | Please refer to Section VII, Employer’s Requirements, Clauses 5.1.1 and 5.2.1 to 5.2.3, and the Drawings Disclaimer. The Reference Design, Conceptual Design, Geological Data Report and other tender-stage reference information are provided for tender/reference purposes and, unless expressly stated otherwise in the Contract, do not constitute a warranty by the Employer as to completeness, accuracy or sufficiency for Detailed Design or construction. The Contractor shall independently review and verify the data and develop the Detailed Design. A discrepancy or error in reference information does not automatically give rise to a Variation, Extension of Time or additional payment. Any entitlement, if any, shall arise only where the relevant facts satisfy an express provision of the Contract and shall be determined under the applicable claim/Variation procedures. | No
767 | Section IX – Particular Conditions / Sub-Clause 21.6 – Arbitration; Addendum | If the Contractor is a Turkish entity, which arbitral institution will have jurisdiction over and administer the arbitration proceedings pursuant to Particular Conditions Sub-Clause 21.6? | Please refer to Particular Conditions Sub-Clause 21.6(b). If the Contract is with a domestic Contractor, arbitration proceedings shall be conducted in accordance with the laws of the Employer’s country, i.e. Türkiye. The RFP does not designate a specific arbitral institution to administer arbitration proceedings for domestic Contractors. The arbitration shall therefore be conducted in accordance with Sub-Clause 21.6(b) and the applicable laws of Türkiye. Please refer to Addendum No. 2, Amendment No. 20. | No
768 | Section IX – Particular Conditions / Sub-Clauses 14.3 and 14.4 – Interim Payments / Schedule of Payments; Section VII – Clause 4.9.4 – Contractual Milestones; Addendum | While Particular Conditions Sub-Clause 14.3 provides for monthly interim payments, Particular Conditions Sub-Clause 14.4 also contemplates payments being made upon the achievement of specified Milestones. If the Milestone-based payment mechanism is applied, would the monthly interim payments continue to be made as scheduled, or would payment of the relevant monthly interim amounts be deferred pending achievement of the applicable Milestones? In such circumstances, how would Delay Damages and KPI Performance Withholding be applied, and could these amounts also be deducted from payments due upon achievement of the relevant Milestones? | Statements may continue to be submitted monthly under Sub-Clause 14.3, but payment for each lump-sum priced deliverable/sub-activity is due upon its completion and acceptance, as clarified in Addendum No. 2, Amendment No. 12 (as revised). An incomplete deliverable is not paid proportionally based solely on progress. Contractual Milestones are schedule obligations and are distinct from the priced payment deliverables. Delay damages under Sub-Clause 8.8 and KPI Performance Withholding under the applicable Contract provisions shall be applied against the amended milestone dates and in accordance with the Contract. | Yes
769 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Proposal Submission Deadline; Section I – ITP 8 – Amendment of RFP Document | Given the scope and scale of the project, it has been determined that a detailed cost analysis is required to ensure a sound assessment. However, the fact that many suppliers are currently operating under restricted schedules due to force majeure events makes it difficult to obtain price quotations and causes delays in the process. In order to conduct a reliable and realistic cost analysis for the work items and to prepare a competitive proposal, we hereby submit our request for extension to tender date by a period of no less than sixty (60) days, and we respectfully request your consideration and appropriate action regarding this matter. | Please refer to Addendum No. 1 regarding the revised Proposal submission deadline under PDS ITP 23.1. | No
770 | Section VII – Employer’s Requirements / Annex J2 – Catenary Systems Technical Specification / Contact Wire Height Requirements | Appendix J2 of the Overhead Contact System (OCS) Technical Specification stipulates that the nominal height of the contact wire above rail level is 5300 mm, and the minimum height under difficult conditions shall not be less than 5000 mm. Please confirm whether this height standard complies with the gauge height requirements for train operation and freight loading. | Confirmed. The nominal and minimum contact-wire heights stated in Annex J2 are contractual design parameters and shall be applied together with the applicable rolling-stock gauge, electrical-clearance, pantograph and freight-loading requirements. The Contractor shall verify compatibility with the adopted rolling-stock envelopes and all applicable standards through the Detailed Design and obtain the Engineer’s approval. | No
771 | Section VII – Employer’s Requirements / Clause 5.3.2 – Special System Works / Earthquake Early Warning System; Clauses 4.5 and 5.3.5 – Package 2 Interfaces | Is the earthquake early warning system specified under Special System Works in Clause 5.3.2 of Part 7 – Employer’s Requirements (Infrastructure and Superstructure Track Works – General Scope for All Lots) the same system as the earthquake early warning system referred to in Clause 5.3.5 (Lot 2: Signalling, Telecommunications and Auxiliary Systems)? If they refer to the same system, please confirm whether Lot 2 shall be responsible for its implementation. | The earthquake early warning requirement is a Project-wide special-system requirement and shall be implemented as an integrated function. Each Lot Contractor is responsible for the equipment, civil/electrical provisions and interfaces falling within its own Lot and systems scope, while the Package 2 Signalling and Telecommunications contractor is responsible for the signalling/telecommunications and central interfaces allocated to Package 2. The requirement shall therefore not be interpreted as being wholly transferred to Package 2 merely because integration with signalling and central systems is required. The Contractors shall coordinate the final architecture through the interface-management and Detailed Design process. | No
772 | Section VII – Employer’s Requirements / Annex K – Tunnel Electromechanical Works Technical Specification / Clause 2.2; Clause 1.2 – Document Precedence and Interpretation | Clause 2.2 of ANNEX K *Tunnel Electromechanical Works Technical Specifications* stipulates that tunnel fire-fighting and ventilation systems shall be installed for tunnels with a length of 1,000 metres or more. NFPA 130 requires such systems for tunnels with a length of 1,000 feet (304 m) or more. Please clarify which standard shall prevail. | Please refer to Addendum No. 2, Amendment No. 10, and the corresponding amendment to ER Clause 9.3.1. SRT-TSI shall govern the applicable fire/life-safety requirements for alignment structures, including mainline railway tunnels, together with the project-specific provisions of Annex K. NFPA 130 shall apply to underground station structures and station-specific emergency ventilation, passenger evacuation and safety requirements. Mandatory Turkish requirements remain applicable where relevant. | Yes
773 | Section VII – Employer’s Requirements / Annex K – Tunnel Electromechanical Works Technical Specification / Clauses 2.2 and 5.9; Clause 1.2 – Document Precedence and Interpretation | Clause 2.2 Scope of Work of ANNEX K requires that tunnel fire extinguishing systems shall only be installed in tunnels with a length of 1,000 metres or more. Whereas Clause 5.9 requires one fire hydrant to be installed at each tunnel portal. Please confirm that Clause 5.9 shall be interpreted subject to Clause 2.2, meaning that fire hydrant systems are only required at the portals of tunnels of 1,000 metres or longer. This interpretation is also in line with the relevant requirements of SRT TSI within the specification framework of this project. | The proposed interpretation is not confirmed. The portal-hydrant requirement in Clause 5.9 is a specific contractual requirement and shall be applied wherever that clause requires it; it is not automatically limited only to tunnels of 1,000 m or greater unless the Contract expressly states such limitation. The complete fire-water and fire-fighting arrangement shall be developed in accordance with Annex K, the applicable standards and the approved fire-life-safety design. | No
774 | Section VII – Employer’s Requirements / Annex K – Tunnel Electromechanical Works Technical Specification / Clause 2.2 – Emergency Signs | Clause 2.2 Scope of Work of ANNEX K requires emergency signs to be installed in all tunnels with a length greater than 100 m and less than 400 m, as well as cut-and-cover sections. Please clarify whether power supply shall be provided for the emergency signs inside such tunnels. | Yes. Where illuminated/powered emergency signs are required by Annex K, the Contractor shall provide the complete electrical supply, cabling, emergency/backup supply and control arrangements necessary for their continuous and safe operation, in accordance with the applicable fire-life-safety and electrical requirements. These works are included in the tunnel electromechanical scope. | No
775 | Section VII – Employer’s Requirements / Clause 5.3.2 – Special System Works / Water Mist Fire Suppression and Climate Sensor Systems; Annex K | Is the water mist system specified under Special System Works in Clause 5.3.2 of Part 7 – Employer’s Requirements (Infrastructure and Superstructure Track Works – General Scope for All Lots) identical to the water-based fire suppression and fire protection systems described in ANNEX K Tunnel Electromechanical Works Technical Specifications? Please confirm whether water mist systems shall be installed inside tunnels within the scope of Lot 2 and Lot 3. If installation is required, please specify the exact locations. Additionally, regarding the climatic sensor system (another special system), please clarify whether such sensors are to be installed only in tunnel areas, or whether relevant sensors shall also be installed on subgrade and bridge sections. | The water-mist requirement stated in the Employer’s Requirements is a contractual special-system requirement and shall be read together with Annex K. Water-mist fire suppression shall be provided in the tunnels and station areas where required by the Employer’s Requirements and the approved fire-life-safety design, including Lots 2 and 3 where applicable. The exact zones, arrangement, coverage and performance criteria shall be developed by the Contractor through the Detailed Design, fire-risk analysis, applicable standards and authority approvals. The climatic-sensor system is not limited to tunnels; sensors shall be provided along the railway line, at stations and other relevant facilities/locations as required by the approved design and the Employer’s Requirements. | No
776 | Section VII – Employer’s Requirements / Annex M3 – Building Automation Systems Technical Specification / Clauses 1.1 and 6.1; Clauses 4.5, 5.3.2 and 5.3.5 | Clause 1.1 of ANNEX M3 requires that the scope of this Contract includes the design, supply, installation and commissioning of the Building Automation and Control System (BACS). Such system shall enable local monitoring and control of electromechanical systems installed at project stations, ventilation shafts and tunnels via Local Control Rooms (LCR) at each station, together with centralised monitoring and control via the Central Control Room (CTC Centre). Clause 6.1 of ANNEX M3 specifies that the purpose of BACS (Building Automation and Control System) is to control and monitor all tunnel ventilation, heating, ventilation and air-conditioning (HVAC) and electromechanical (E&M) systems within project stations, shafts and tunnels under both normal and emergency conditions. Control and monitoring shall be centrally managed by the installed control and monitoring system (Central BACS/BMS System), with local control via independent/autonomous server workstations installed by the Contractor within the Local Control Room (LCR) at each station. Please clarify whether the Building Automation and Control System (BACS) applies only to station electromechanical works and adjacent sections within Lot 1 and Lot 4. Lot 2 and Lot 3 contain no stations. Please confirm whether BACS is still required for Lot 2 and Lot 3. If BACS is required, please confirm whether the communication channel for centralised monitoring and control of the BACS installed in tunnels of Lot 2 and Lot 3 via the Central Control Room (CTC Centre) shall be provided under Lot 2 (Signalling and Telecommunications Systems package). | BACS is not limited to Lots 1 and 4. Where a Lot contains tunnels, shafts or other electromechanical installations requiring local monitoring and control, the Lot Contractor shall provide the BACS/local automation functions required by Annex M3 even if there is no station within that Lot. Lots 2 and 3 shall therefore provide the applicable tunnel/shaft BACS equipment and local control functions. Corridor-wide communications and central-control interfaces shall be coordinated with the Package 2 Signalling and Telecommunications contractor in accordance with the interface requirements. | No
777 | Section VII – Employer’s Requirements / Clause 5.3.2 – Special System Works / Water Mist Fire Suppression; Clause 9.3 – Fire Life Safety; Annex K | The Request for Proposals Works — Section VII – Employer’s Requirements specifies that water mist fire suppression systems shall be installed in tunnels along the railway alignment. However, relevant standards including TSI SRT, BYKHY and NFPA do not mandate water mist fire suppression systems inside tunnels. Please clarify whether water mist fire suppression systems are required to be installed in the tunnels. | Yes. The RFP expressly requires water-mist fire suppression as a Special System. The fact that a referenced standard may not independently mandate water mist does not remove this project-specific Employer’s Requirement. The system shall be designed, supplied, installed, integrated, tested and commissioned in the locations determined by the Employer’s Requirements and the approved fire-life-safety design. | No
778 | Section VII – Employer’s Requirements / Clauses 4.5 and 5.3.5 – Package 2 Interface; Annex M2 – Stations Control and Communication System Technical Specification; Annex L | The tender documents clearly state that the Signalling and Telecommunications Systems will be tendered as Lot 2. A review of the table of contents of all technical annexes shows that, in addition to Annex L which sets out technical requirements for signalling and telecommunications systems, telecommunications systems are also covered in ANNEX M2 – Stations Control and Communication System Technical Specification. The systems include the Transmission System (TNS), Telephone System (CTL), Radio System (CRA), Announcement System (CPA), Closed Circuit Television System (CCTV), Central Clock System (CCL), Access Control (Security) System (CSE), System Control and Data Acquisition System (SCADA), Passenger Information System (PIS), and Passenger Access Control and Fare Collection System (FCS). Based on the functional requirements and composition of the telecommunications system, all the above systems form part of the telecommunications system. Together with the telecommunications-related subsystems described in Annex L, they constitute the complete railway telecommunications system, delivering functions such as data transmission, voice communication, train-to-ground radio communication, information dissemination, video surveillance, equipment status monitoring and alarming, and passenger ticketing. No subsystems shall be split out from this scope. Please clarify and confirm whether the telecommunications systems described in technical ANNEX M2 fall within the tender scope of Lot 2 (Signalling and Telecommunications Systems) and are excluded from the scope of this Lot. | The telecommunications systems allocated to Package 2 shall be provided under the separate Signalling and Telecommunications contract. However, Annex M2 also defines station/control-system requirements and interfaces that may require Lot-specific civil, electrical, local equipment or integration provisions from the relevant Lot Contractor. Accordingly, the Lot Contractor shall not duplicate the core Package 2 telecommunications systems, but shall provide all local works, provisions and interfaces expressly assigned to its Lot under the Employer’s Requirements and coordinate them with Package 2. The scope shall be determined by the allocation and interface provisions of Chapter 4, Annex L, Annex M and the relevant Lot requirements, read together. | No
779 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 1.1.86 and 1.1.95 – Time for Completion and Milestones; Addendum | Please clarify whether the 2-year period stated under the fourth milestone is a maximum duration. In practice, if all prescribed works are completed within one year, does this mean that the fourth milestone can be deemed completed accordingly. In addition, please confirm whether the scope of works covered by the fourth milestone includes subsystem testing, integrated commissioning & testing, dynamic testing, trial operation, provisional acceptance and defect rectification works. | Please refer to Answer 5. Please refer to Addendum No. 2, Amendment No. 3. | Yes
780 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 1.1.86 and 1.1.95 – Time for Completion and Milestones; Section VII – Clause 4.9.4; Addendum | The RFP specifies an overall Time for Completion of 1,826 days, while the durations specified for Milestones 1 to 4 are 12, 36, 12 and 24 months respectively. As these durations appear to result in a total period of 84 months when applied sequentially, could the Employer please clarify the intended relationship between the overall Time for Completion and the milestone durations? | Please refer to Answer 5. Please refer to Addendum No. 2, Amendment No. 3. | Yes
781 | Section VII – Employer’s Requirements / Clauses 5.2.1–5.2.3 – Geotechnical Risk Allocation; Annex C1 – Geological Data Report | The RFP states that the Geological Data Report (GDR) is provided for information only and lacks formal rock mass classifications, complete hydrogeology, or detailed gas profiling. Given the mandatory requirement to submit Gas Monitoring Plans (Lot 1/Lot 4), Karst Management Plans (Lot 2), and Swelling Clay Designs (Lot 4), will the Employer provide additional baseline measurement data during tendering to establish a unified commercial baseline? | No additional tender-stage geotechnical commercial baseline is currently planned. The Geological Data Report and other Employer-provided geological/geotechnical information are reference information and do not constitute a comprehensive or warranted characterization of the Site. The disclosed hazards, including gas, karstification/voids, swelling clay and incomplete hydrogeological characterization, are to be treated as foreseeable risks and independently investigated and characterized by the Contractor. The Contractor shall prepare the required management plans and designs based on its own investigations and approved Detailed Design. | No
782 | Section VII – Employer’s Requirements / Clauses 5.2.1–5.2.3 – Geotechnical Risk Allocation; Annex E1 – Design Technical Specification; Section IV – Soil Improvement Works | Since ground improvement methods and depths must be determined entirely by the Contractor under a lump-sum model,can the Employer confirm whether unexpected sub-surface anomalies (e.g., major uncharted mine galleries or deep karstic voids) encountered beyond the 200m borehole spacing will be eligible for compensation under Provisional Sums? | The Contractor shall bear full responsibility for all subsurface conditions encountered during the execution of the Works, including unforeseen geological and geotechnical anomalies such as uncharted mine galleries, karstic voids, and other ground conditions. The Contractor/Proposer shall be solely responsible for conducting all necessary investigations, determining and implementing appropriate ground improvement and mitigation measures, and bearing all associated costs. Such costs shall be deemed included in the Contract Price, and no additional compensation shall be provided under Provisional Sums for these conditions. | No
783 | Section VII – Employer’s Requirements / Clauses 4.8.1 and 5.7.2–5.7.3 – YSS Bridge Interface / Lot 3; Annex E4 – Railway Bridge Design Technical Specification | Lot 3 requires full structural compatibility, dynamic response, wind stability, and rail expansion joint designs for the lower deck of the YSS Bridge. Will the Employer provide full as-built structural drawings, structural health monitoring (SHM) baseline logs, and existing bridge deck expansion calculations from KGM/Bridge Operator prior to bid submission? | The Contractor shall obtain the structural and technical documentation required for the YSS Bridge directly from KGM and the Bridge Operator and shall coordinate all bridge-interface design with those entities. The Employer is not committing through this clarification to issue an additional complete set of as-built drawings, SHM baseline logs or historical expansion calculations before Proposal submission. Tenderers shall use the information made available and allow for the verification, data collection and authority coordination required for the Detailed Design. | No
784 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clause 2.1 – Right of Access to the Site; Section VII – Clauses 5.1, 7 and 11.10 – Design / Land and Access Responsibilities | The Employer’s Requirements specify that Major Milestone 1 (Alignment Freeze) must be achieved within 12 months from the Commencement Date to enable AYGM to finalize the Resettlement Action Plan (RAP) and initiate land expropriation. If land access is delayed by AYGM post-Milestone 1, will the Contractor be granted an automatic Extension of Time (EOT) and compensation for standby costs without impacting the overall 60-month construction schedule? | Please refer to Answer 75. No automatic Extension of Time or automatic compensation for standby costs is confirmed. Any entitlement arising from delayed access to land/Site after Milestone 1 shall be determined in accordance with the Contract and the facts of the specific event, including actual causation and impact on the approved programme. The contractual Time for Completion is adjusted only to the extent an Extension of Time is established under the Contract. | No
785 | Section VII – Employer’s Requirements / Clause 6.1 – Topographic Survey; Annex A – Drawings; Clause 5.1.1 – Design and Build Disclaimer | A detailed map is available in the alignment plan and profile folder, but it does not include elevation Z values. Would it be possible to provide those? | No additional guaranteed topographic/elevation dataset is issued through this clarification. The drawings and survey information provided are tender-stage reference information. The Contractor shall carry out the topographic surveys and verification necessary for the Detailed Design and construction and shall establish the required coordinates and elevations from approved survey control. | No
786 | Section VII – Employer’s Requirements / Clauses 5.1.1, 5.8.2 and 6.6 – Lot 4 / Istanbul Airport Station / Existing Infrastructure Records; Addendum | It is specified that the Lot 4 scope includes fitting out, finishing, and completing the Istanbul Airport Station within an underground box structure that has already been constructed and reserved. Would the Employer kindly clarify and provide the following detailed as-built information for the pre-existing reserved station structure? | Please refer to Addendum, Amendment No. 9. The sentence in Clause 5.8.2 stating that as-built information relating to the completed Istanbul Airport Station structure would be made available as part of the tender dossier has been deleted. Accordingly, no additional complete or warranted as-built package is committed through this clarification. Under Clauses 5.1.1 and 6.6, the Lot 4 Contractor remains responsible for collecting available information, inspecting and measuring the existing structure, verifying its geometry, condition and interfaces, and carrying out any additional investigations necessary for the Detailed Design and construction. No further amendment is made to the RFP. Please refer to Addendum No. 2, Amendment No. 9. | Yes
787 | Section VII – Employer’s Requirements / Clauses 4.6, 4.7, 4.8.3 and 5.3.3 – Traction Power Interfaces / Existing TCDD Network / TEİAŞ; Annex J | i. Please confirm the final electrical interface arrangement between the new INRAIL traction-power system and the existing TCDD/Marmaray electrified network at the Çayırova/Gebze end and the existing TCDD electrified network at the Çatalca end. ii. Please confirm whether electrical separation by means of a neutral section is required at each interface before connection to the existing electrified lines. iii. Please confirm whether any section of the INRAIL line is intended to be supplied from the existing network under normal or contingency operation. If so, please identify the relevant line section(s), applicable operating scenario(s) and intended source of supply. iv. Where supply support from the existing network is intended, please confirm that the existing supply arrangement has adequate capacity to meet the INRAIL traction-power demand under the applicable normal and contingency operating scenarios. | The final electrical interface arrangement at the Çayırova/Gebze and Çatalca ends shall be established through the system-wide power-supply simulations, interface coordination, TCDD/TEİAŞ requirements and the approved Detailed Design. Neutral sections and other electrical separation arrangements shall be provided where required by the approved feeding and protection scheme. No fixed assumption that a defined part of INRAIL will be normally supplied from the existing network is introduced through this clarification. Any normal or contingency support from existing networks shall be demonstrated and agreed through the coordinated simulations and approvals. The Contractor shall obtain and verify the network data required for the design with the relevant authorities. | No
788 | Section VII – Employer’s Requirements / Clauses 4.6.2–4.6.4 and 5.3.3 – Traction Power Simulation / N−1 Coordination; Annex J | i. If support from the existing electrified networks is envisaged during the loss of an end traction substation or other contingency conditions, please provide the data required to model the relevant sections of the existing lines as electrical boundary conditions. ii. Please confirm whether any enhancement, modification or additional equipment within the existing electrified networks or at their interfaces with INRAIL is required. Where such works are identified as necessary, please clarify the responsible party for design, approvals, procurement, construction, commissioning and associated costs. | Where existing networks are to be represented as electrical boundary conditions, the relevant Contractor shall obtain and verify the necessary network data through coordination with TCDD, TEİAŞ and the affected asset owners and shall harmonize the assumptions with the other Lot Contractors. Any interface modifications or additional equipment necessary to satisfy the contractual performance and integration requirements and falling within the Contractor’s allocated scope shall be included in the Proposal Price. Only a change instructed by the Engineer that constitutes a Variation under Clause 13 may give rise to the corresponding contractual entitlement. | No
789 | Section VII – Employer’s Requirements / Clauses 4.6, 4.7 and 5.3.3 – Existing-Network / Traction Power Interfaces; Annex J | Please confirm whether any additional traction substation and/or other complementary equipment or subsystem identified as necessary by the simulation study within the INRAIL project boundaries shall be treated as part of the Contractor’s scope and paid under the Contract. | Please refer to Answers 50, 51 and 52. The Contractor has single responsibility for developing the traction-power design and providing the substations, equipment and complementary systems required to satisfy the performance and operational requirements of the Contract. Any additional traction substation or equipment identified as necessary through the Contractor’s required simulation/design development within the existing contractual requirements shall be included in the lump-sum Contract scope and shall not be separately payable. A separate entitlement may arise only where the Engineer instructs a Variation that changes the contractual requirements, in which case Clause 13 shall apply. | No
790 | Section VII – Employer’s Requirements / Clauses 4.6.2–4.6.4 and 5.3.3 – Train Operation / Traction Power Simulation Inputs; Annex B2 and Annex J | i. Please provide the data for the representative worst-case passenger rolling stock for the traction-power system simulation study, including tractive and regenerative-braking effort curves; train formation and total length; masses; train running-resistance data; auxiliary load; power factor; pantograph-to-wheel efficiency; and voltage-dependent current limits. For example, a 2×8-car (16-car) HT80000 high-speed trainset with a 16 MW power rating can be accommodated at the 400 m platforms of both airport stations. Please confirm whether such a trainset will be used on the line. ii. Please confirm that the passenger rolling stock operating on the INRAIL line will have a voltage-dependent current-limitation function in accordance with EN 50388. iii. Please confirm that the passenger rolling stock operating on the INRAIL line will comply with the voltage levels specified in EN 50163, including a minimum operating voltage of 17.5 kV. | The traction-power simulations shall be based on the Operations Plan, Annex E, the final alignment and the vehicle-performance characteristics agreed through the system-wide simulation-coordination process. The RFP does not designate the example 2×8-car HT80000 trainset as a binding tender assumption through this clarification. The Lot 2 and Lot 4 Contractors shall coordinate and agree the representative passenger-train data and conservative operating scenarios with the other Contractors and the Engineer before performing the simulations. The rolling stock used for the approved study shall satisfy the applicable EN 50163/EN 50388 requirements, including voltage/current-limit functions where applicable. No additional fixed rolling-stock dataset is issued through this clarification. | No
791 | Section VII – Employer’s Requirements / Clauses 4.6.2–4.6.4 and 5.3.3 – Freight Train / Traction Power Simulation Inputs; Annex B2 and Annex J | i. Please provide the data for the representative worst-case freight train for the traction-power simulation study, including locomotive type(s); the maximum number of locomotives operating simultaneously in one freight train; tractive and regenerative braking effort curves of the locomotive(s); freight train formation and total length; masses of both locomotive(s) and the freight carriages; train running resistance data; auxiliary load; power factor; pantograph-to-wheel efficiency; voltage-dependent current limits; use of banking/assisting locomotives. If applicable, please identify locations, gradients, and operating conditions for any banking/assisting operation, as well as any locations at which freight-train tonnage changes along the INRAIL corridor. For reference, the E68000 Locomotive is a 5 MW electric locomotive. Please confirm whether the E68000, or an equivalent or more onerous locomotive configuration, shall be adopted for the traction-power system simulation study. ii. Please confirm that the locomotives for freight trains running on the INRAIL line will have the current limitation function against train voltage, per EN 50388. iii. Please confirm that the locomotives for freight trains running on the INRAIL line will comply with the described voltage levels in EN 50163, i.e., the minimum operating voltage will be 17.5 kV. | The freight-train assumptions for the traction-power simulations shall be established from the Operations Plan and through the system-wide simulation-coordination process. The RFP does not designate the E68000 locomotive or any particular locomotive configuration as a binding tender assumption through this clarification. The Lot 2 and Lot 4 Contractors shall develop, coordinate and agree a representative conservative freight scenario, including train mass, formation, locomotive performance, assisting/banking operation where applicable and electrical characteristics, and shall document the agreed assumptions in the Simulation Coordination Record. The rolling stock represented in the approved study shall comply with the applicable EN 50163/EN 50388 requirements. No additional fixed dataset is issued through this clarification. | No
792 | Section VII – Employer’s Requirements / Clauses 4.6.2–4.6.4 and 5.3.3 – Operating Timetable / Headway / Traction Power Simulation; Annex B2 and Annex J | Please provide the operating timetable and the required minimum operational headway for the traction-power system sizing simulation study. | The design timetable, service pattern and operating assumptions shall be based on the Operations Plan and shall be harmonized through the system-wide simulation-coordination process required by Sections 4.6 and 5.3.3. The Employer does not issue an additional binding headway/timetable through this clarification. The Contractors shall agree and document the common operating scenarios with the Engineer and relevant Contractors before commencing the traction-power studies. | No
793 | Section VII – Employer’s Requirements / Clauses 4.6.2 and 4.6.4 – Harmonization of Simulation Inputs / Integrated System-Wide Simulation; Clause 5.3.3; Annex J | Please confirm that the traction-power simulation software used by each Lot Contractor for the design and verification studies shall have been independently assessed and shall hold a valid Attestation of Conformity Certificate in accordance with EN 50641:2020, “Requirements for the validation of simulation tools used for the design of electric traction power supply systems”, for the AC 25 kV 50 Hz test case. Please further confirm that each Lot Contractor shall submit to the Employer/Engineer, before commencing the simulation studies, a valid Attestation of Conformity Certificate and the associated independent assessment report for the software. The submitted assessment report shall include the software output values and the corresponding reference values for all parameters specified in the applicable EN 50641 test case. | The simulation software shall be fit for purpose, technically validated and capable of demonstrating compliance with the Contract and applicable standards. The RFP does not introduce, through this clarification, an additional mandatory qualification requirement that every simulation package must hold a specific EN 50641 Attestation of Conformity certificate unless such certificate is expressly required by the governing technical specification. The Contractor shall provide sufficient validation/verification evidence for the proposed tool and methodology for the Engineer’s review and shall comply with EN 50641 where applicable to the contractual design. | No
794 | Section VII – Employer’s Requirements / Clauses 5.1.1 and 5.8.2 – Lot 4 / Istanbul Airport Station; Annex A – Drawing AYGM-INR-ARC-IST-006 | GENERAL NOTES: 3-MIDDLE AND SIDE PLATFORMS SHALL BE CONSTRUCTED. We understand that side platforms already exists they will be demolished and then reconstructed according to new freight lines . Please confirm. | The Istanbul Airport Station drawings are tender-stage/conceptual information. The existing station structure and platform arrangements shall be surveyed and verified by the Lot 4 Contractor, and the final passenger/freight platform configuration shall be established in the approved Detailed Design. The Contractor shall carry out any demolition, alteration and reconstruction of existing platform elements that is necessary to achieve the required passenger/freight separation, track alignment, clearances and station functionality. The Tenderer shall not assume that the existing side platforms can remain unchanged solely on the basis of the conceptual drawings. | No
795 | Section VII – Employer’s Requirements / Clauses 5.1.1 and 5.8.2 – Lot 4 / Istanbul Airport Station; Annex A – Drawing AYGM-INR-ARC-IST-002 | GENERAL NOTES: 6-SEPERATION WALL SHALL BE CONSTRUCTED BETWEEN FREIGHT AND PASSENGER LINES AS SHOWN ON DRAWINGS. New seperation walls passes over TVF floor openings at the grids B1 and D10. Shape of the opening to be revised at the existing floor please confirm. | The separation of freight and passenger areas is a contractual requirement. Where the approved separation-wall alignment conflicts with an existing TVF opening or other element of the station shell, the Contractor shall verify the existing condition and develop the necessary structural modification/reconfiguration through the Detailed Design, subject to the Engineer’s and relevant airport/operator approvals. The required modifications are included in the Lot 4 station completion scope. | No
796 | Section VII – Employer’s Requirements / Clauses 5.1.1 and 5.8.2 – Lot 4 / Istanbul Airport Station; Annex A – Drawing AYGM-INR-ARC-IST-004 | At the both ends of the statin strucrure there are reserve spaces at concourse level. And also in the same area of the car park level tehere are some shaft structuresat the existing stiation. Please provide information about the function of these reserve rooms if any defined. | The reserve spaces shown in the conceptual/as-built station information do not constitute a separate Employer-defined operational use unless expressly stated elsewhere in the Contract. Their final use, treatment and interface requirements shall be verified during the Detailed Design in coordination with İGA, the metro/airport interfaces and the Engineer. The Contractor shall preserve or adapt such spaces as required by the approved station design and shall not assign an alternative use without approval. | No
797 | Section VII – Employer’s Requirements / Annex I4 – Stations Platform Screen Door System Technical Specification / Clause 9.6; Clause 5.8.2 – Istanbul Airport Station; Annex A – Drawing AYGM-INR-ARC-IST-007 | ANNEX I4 - Stations Platform Screen Door System (PSDS) Technical Specification 9.6 "ARCHITECTURAL AND ASSEMBLY DETAILS" All fabrication, installation, and finishing works required to cover the area above the PSD up to the ceiling level shall be measured and paid separately under the applicable unit rate items. The materials used shall be Class A non-combustible and shall be capable of withstanding the wind loads specified above. In addition, the selected materials shall not adversely affect the architectural aesthetics. At the Annex A section drwings area above the PSD is open. Please confirm that the area above the psd wiil be covered. | Confirmed. The requirement of Annex I4 governs. The fabrication, installation and architectural finishing required to close/cover the area above the PSD up to ceiling level shall be provided where required by the approved PSD and station design, using the specified non-combustible materials and satisfying the structural/aesthetic requirements. The conceptual drawing depiction does not waive this specification requirement. Under this lump-sum Contract, the work shall be included in the relevant priced station/PSD scope; it will not create a separate entitlement merely because the conceptual drawing shows the area open. | No
798 | Section VII – Employer’s Requirements / Clauses 5.1.1 and 5.5.2 – Lot 1 / Sabiha Gökçen Airport Station; Annex A – Drawings AYGM-INR-ARC-SGA-010 and SGA-001 | There is room called PARKING FOR 101 CARS at the ground level schedule. Is it enclosed car park or is it an open car park area? In the ground floor plan or siteplan there is not any arrangement for the same. Please clarify. | The parking indication on the Sabiha Gökçen conceptual station drawings is part of the tender-stage architectural concept and shall be verified and developed through the Detailed Design and airport-interface coordination. The Tenderer shall not infer a guaranteed enclosed/open configuration from the room schedule alone where the plan/site plan does not define it. The final arrangement shall comply with the approved station design, airport requirements, access/fire-life-safety requirements and the Employer’s Requirements. | No
799 | Section VII – Employer’s Requirements / Clauses 5.1.1, 5.5.2 and 9.3 – Lot 1 / Sabiha Gökçen Airport Station / Fire Life Safety; Annex A – Drawing AYGM-INR-ARC-SGA-005 | Between platform start and T5 connection the travel distance is more then 25m, as per NFPA 130 it should be minimum 25m or one car length whichever is greater. Please confirm that connction tunnel position can be revised as per the requierment. | Yes. The tender-stage station layout may be refined during Detailed Design, subject to the Engineer’s review/consent and compliance with the Contract. For underground station structures, station-specific passenger evacuation and emergency-egress requirements shall be checked against NFPA 130 and applicable mandatory Turkish requirements, including BYKHY where relevant. Please refer to Addendum No. 2, Amendment No. 10 and the corresponding amendment to ER Clause 9.3.1 for the clarified scope of NFPA 130 and SRT-TSI. | No
800 | Section VII – Employer’s Requirements / Annex I4 – Stations Platform Screen Door System Technical Specification / Clause 9.1; Clause 5.5.2 – Sabiha Gökçen Airport Station | Annex I14, 9.1 GENERAL A full-length Platform Screen Door (PSD) System will be installed based on architectural projects along the edge of all station platforms located on the HSR line. Platform screen doors are not shown in the architectural drawings. Please confirm that there should be PSD at SAW platforms. | Confirmed. Annex I4 requires a full-length Platform Screen Door system along the HSR station platforms. Accordingly, PSDs shall be included for the Sabiha Gökçen Airport Station platforms in accordance with the approved architectural and systems design, notwithstanding their omission from a particular conceptual drawing. | No
801 | Section VII – Employer’s Requirements / Applicable Laws, Standards and Fire Life Safety Requirements; Clause 9.3; Turkish Civil Defence Shelter Regulation | SIĞINAK YÖNETMELİĞİ - CİVİL SHELTER REGULATION ARTICLE 10 It is a fundamental requirement that metro systems to be constructed be designed and built to serve as general shelters when necessary. Furthermore, it is a fundamental requirement that the Ministry of Transport and Infrastructure and municipalities arrange existing metro and other underground rail system stations and tunnels to meet the standards of general shelters by rectifying deficiencies, in accordance with needs analyses and planning determined based on the opinion of the Disaster and Emergency Management Presidency. Is there any civil shelter requirement for this project please clarifiy | The Contractor shall comply with all applicable Turkish laws and regulations, including the Civil Defence Shelter Regulation to the extent applicable to the Project. The RFP does not create a separate exemption from statutory shelter requirements. During Detailed Design, the Contractor shall determine the applicable shelter provisions for the underground railway/station facilities, coordinate with the competent authorities and incorporate any required measures into the Works. No additional project-specific shelter requirement is introduced through this clarification. | No
802 | Section VII – Employer’s Requirements / Annex I1 – Stations Environmental Control Technical Specification; Clauses 5.3.2 and 5.5.2 / 5.8.2 – Station E&M Works | Spaces for EXF and INF system, shafts and fan rooms could not be identified in the architectural drawings, please confirm that these systems should be constructed for both stations. | Confirmed. The station environmental-control systems required by Annex I1, including the applicable EXF/INF systems, shafts, fan rooms and associated equipment, shall be provided for both station works as required by the approved fire-life-safety, ventilation and environmental-control design. Their omission or incomplete depiction in conceptual architectural drawings does not remove the technical-specification requirement. The exact arrangement and dimensions shall be developed through the Detailed Design. | No
803 | Section VII – Employer’s Requirements / Annex O – BIM Technical Specification / Clause 5.5 – Station Model Requirements; Clause 1.2 – Document Precedence and Interpretation | 5.5 Station Model Requirements ● PSD alignment tolerance shall be controlled within ±10 mm. ● Platform widths shall be minimum 2.5 m for single-direction circulation and minimum 4.0 m for double-direction circulation. ● Tactile paving shall be continuous with a width of 60 cm. ● Ramps shall be controlled to a maximum slope of 8%. ● Accessible elevators shall comply with EN 81-70 standards (minimum dimensions: 110 x 140 cm). ● Emergency exit widths shall be minimum 180 cm. ● Firefighting equipment shall be accessible within a maximum distance of 25 m. Please confirm that these requiermnts to be reviewed as per standards codes and other ERQ documents. | Confirmed, subject to the Contract’s document-precedence rules. The requirements stated in Annex O are contractual BIM/design-coordination requirements and shall be checked and coordinated with the Employer’s Requirements, other applicable Technical Specifications, standards and authority requirements during Detailed Design. In the event of an ambiguity or conflict, Section VII, Clause 1.2 shall apply: the stated order of precedence governs, and a conflict between documents of equal rank, including Technical Specification Annexes, shall be referred to the Engineer for written determination. The Contractor shall not resolve such a conflict unilaterally. | No
804 | Section VII – Employer’s Requirements / Annex I2 – Stations Auxiliary Systems Technical Specification / LHD and Fiber-Optic Temperature Detection; Clause 5.3.2 | The Specification requires both an LHD system and a fiber optic temperature detection system for the first 100 m of the tunnel from the platform end, resulting in duplicated detection coverage. Please clarify whether both systems are intended to be installed within this section, or whether only the fiber optic temperature detection system is intended to be used in the tunnels. | Both detection systems shall be provided where the applicable clauses of Annex I2 expressly require them. The overlap in coverage for the first 100 m from the platform end is therefore not, by itself, a basis for omitting either system. Any proposed optimization or consolidation shall require a technically justified Detailed Design and the Engineer’s approval and must maintain all required fire-detection functionality, redundancy and interfaces. Tenderers shall price the requirements as stated. | No
805 | Section VII – Employer’s Requirements / Annex I2 – Stations Auxiliary Systems Technical Specification / Tunnel Socket-Line Cable Requirements; Clause 5.3.2 | While the power, lighting, signalling and communication cables along the tunnel route are specified as armoured and/or mechanically protected in the relevant sections of the Specification, no armour requirement is specified for the tunnel socket outlet circuits, and the supply cable is specified as N2XH. Please clarify whether all cables installed within the tunnels are required to be armoured/mechanically protected, or whether the use of unarmoured N2XH cables is permitted for the tunnel socket outlet circuits. | Where Annex I2 expressly specifies N2XH cable for the tunnel socket-outlet circuits, that cable type may be used provided that the complete installation satisfies all fire-performance, mechanical-protection, routing and installation requirements of the Contract. A general requirement for armoured/mechanically protected cables shall not be interpreted as automatically replacing a more specific cable-type requirement; instead the Contractor shall provide the necessary mechanical protection by the approved installation method where required as part of the detailed design subject to approval of the Engineer/Employer. | No
806 | Section VII – Employer’s Requirements / Annex I1 – Stations Environmental Control Technical Specification / Generator Room Ventilation | Will the generator radiator be remotely mounted, or will it be installed as an integral part of the generator package? If a remote radiator arrangement is envisaged, dedicated supply and exhaust fans will be required to ensure adequate ventilation and heat dissipation within the generator room. Kindly confirm. | The RFP does not prescribe a single mandatory radiator arrangement for the generator package. The Contractor shall select and design an integral or remote radiator arrangement as part of the approved generator-room/HVAC design, taking account of heat rejection, combustion air, ventilation, acoustic and fire requirements. Where a remote radiator or the heat-load calculation requires dedicated supply/exhaust fans, the Contractor shall provide them as part of the complete system. The final arrangement shall be subject to the approval of the Engineer and the Employer. | No
807 | Section VII – Employer’s Requirements / Annex K – Tunnel Electromechanical Works Technical Specification / Water-Based Fire Extinguishing System; Clause 1.2 – Document Precedence and Interpretation | For metro line tunnels, the design is based on providing one hydrant at every 45 m. However, the relevant document specifies that one fire hose cabinet shall be provided at every 120 m. It also states that hydrants will be provided only at the tunnel entrances. Could you please clarify which fire protection system arrangement shall be implemented? | The fire-water system shall comply with the complete contractual requirements of Annex K and the applicable fire-life-safety requirements. The provisions for portal hydrants, hose cabinets and any interval-based hydrant/hose-reel arrangement shall therefore be coordinated in the Contractor’s fire strategy and Detailed Design rather than treated as mutually exclusive. If the cited Annex K provisions create an actual internal inconsistency that cannot be reconciled by design, the matter shall be referred to the Engineer for written determination in accordance with Section VII, Clause 1.2; the Contractor shall not unilaterally select one conflicting requirement. | No
808 | Section VII – Employer’s Requirements / Clause 6.5 – Groundwater, Surface Water and Hydrology; Clause 4.8.4 – DSİ Interface; Annex A – Drawings | The provided map boundaries are insufficient for verifying whether the culvert catchment areas have been accurately delineated and, consequently, for checking the accuracy of the culvert size calculations. Maps at a 1:25,000 scale, prepared by the General Command of Mapping, are required for this purpose. If this work is to be carried out, these data must be obtained. | No additional 1:25,000 catchment-area mapping is issued through this clarification. The Contractor is responsible for carrying out the hydrological/hydraulic studies required for the Detailed Design and DSİ approvals, including catchment delineation, design-discharge calculations and verification/sizing of culverts and drainage structures. The Contractor shall obtain and use the mapping, survey and authority data necessary for those studies. | No
809 | Section VII – Employer’s Requirements / Clause 6.4 – Utility Records | We did not see any data regarding existing utility lines (electricity, natural gas, wastewater, potable water, and stormwater) among the information provided. This data is required to conduct a survey for utility relocation work. | Please refer to Section VII, Clause 6.4 – Utility Records. The available utility information is indicative and is not warranted as complete. The Contractor shall obtain the required information from the relevant authorities and utility owners, carry out the necessary surveys/investigations and verify the exact location, depth, condition and ownership of utilities before design and construction. The Employer will provide appropriate authorization/access letters where applicable. | No
810 | Section VII – Employer’s Requirements / Annex E – Design Technical Specifications / Rainfall Intensity and Drainage Design; Clause 6.5 – Hydrology | Should the rainfall return period to be used for route drainage quantity (BOQ) calculations be taken as a minimum of 100 years, as specified in Section 1.6 of the technical specifications document? | Confirmed. The minimum return period stated in the applicable technical specification shall be used for the drainage design unless a more onerous requirement is imposed by the competent authority, the applicable standard or the site-specific risk assessment. Accordingly, where Section 1.6 specifies a minimum 100-year return period, the Contractor shall use not less than 100 years for the relevant design calculations. | No
811 | Section I – Instructions to Proposers / ITP 12.4 – Financial Information in the Technical Part; Section III – Evaluation of Technical Part / Factor 2.2 – Resource Mobilization & Cash-Flow Planning | Cash-Flow Information in the Technical Proposal; PDS ITP 12.3(e) provides that a Proposal shall be declared non-responsive if material financial information related to the Proposal Price is included in the Technical Part. At the same time, Rated Criterion 2.2 evaluates cash-flow projections and resource-cash flow alignment. Please clarify the required format for presenting cash-flow information in the Technical Proposal. In particular, please confirm whether such information should be presented only as percentages, normalized curves or non-monetary indices, without disclosure of Proposal Price or monetary values. | The Technical Part shall not contain the Proposal Price or any material financial information related to the Proposal Price, in accordance with ITP 12.4. For the purpose of Rated Criterion 2.2, cash-flow planning should therefore be presented in a non-price form, such as percentages, normalized curves or indices, timing profiles and resource-to-cash-flow relationships, sufficient to demonstrate the realism and alignment required by the Rated Criterion. No monetary amount or other information from which the Proposal Price, or a material part of the Financial Proposal, could be derived shall be included in the Technical Part. Proposal Price information and related monetary details shall remain in the Financial Part. | No
812 | Section IX – Contract Data / Sub-Clause 1.1.27 – Defects Notification Period; Section VII – Clause 10.6.4 – Defects Notification; Annex D – Warranty; Addendum | Defects Notification Period and Warranty Period Employer's Requirements further provide that the Defects Liability Period commences upon issuance of the Taking-Over Certificate and continues for the period defined in the Contract. However, Annex D – General Technical Specification states that the Warranty Period shall be 60 months commencing from the date of Final Acceptance and that all installed systems shall remain under the Contractor's warranty during such period. Please clarify the contractual relationship between the 730-day Defects Notification Period and the 60-month Warranty Period. In particular, please confirm whether the 60-month Warranty Period constitutes an additional warranty obligation commencing after Final Acceptance, or whether it is intended to run concurrently with or form part of the Defects Notification Period. | Please refer to Answer 292 and Addendum No. 2, Amendment No. 21. The Defects Notification Period (DNP) is 730 days commencing from the Taking-Over Certificate. The 60-month Warranty Period in Annex D is a separate surviving contractual obligation and commences from Final Acceptance; it is not part of, nor does it replace, the 730-day DNP. Accordingly, the two periods have different commencement points and contractual functions and are to be administered separately in accordance with the RFP as amended. | Yes
813 | Section VII – Employer’s Requirements / Annex J2 – Catenary Systems Technical Specification / Clauses 2.2, 5.3, 5.6 and 10.1.1; Addendum | Clauses 2.2, 5.3 and 5.6 of Annex J2 specify the catenary system design/operational requirement based on 200 km/h +10%, whereas Clause 10.1.1 requires the catenary design criteria, drawings and documentation to be prepared based on 250 km/h +10%. Please confirm the governing design speed, including the applicable margin, to be adopted for the catenary system design, dynamic interaction assessment, testing and acceptance. | Please refer to Addendum No. 2, Amendment No. 7. The governing catenary-system design/operational speed is 200 km/h and the applicable +10% margin shall be applied where required by Annex J2 for design/dynamic interaction purposes. The conflicting 250 km/h reference is superseded by the Addendum. The amended requirement shall govern design, documentation, testing and acceptance. | Yes
814 | Section VII – Employer’s Requirements / Clause 12.4 – KPI Schedule / KPI E1 – Excavated Material Reuse and Disposal Compliance | Subject: Clarification and Request for Amendment – KPI E1: Alignment with Material Recovery & Circular Economy Targets Clause Reference: Environmental & Social Management Plan / Key Performance Indicators – KPI E1 Clarification & Recommendation: Under the present wording of KPI E1 ("≥ 85% reuse or licensed disposal for total excavated material"), off-site disposal at a licensed facility is treated as functionally equal to material recovery/reuse. Consequently, a Contractor achieving %85 licensed disposal with zero material recovery technically meets the metric target, which may inadvertently disincentivize cut-and-fill optimization, crushing, or off-site repurposing. To align project performance with international waste hierarchy standards (e.g., IFC Performance Standards / World Bank Group EHS Guidelines), we kindly ask the Employer to clarify: • Is it the Employer’s intention to allow 100% or 85% target to be fulfilled via licensed off-site disposal? (If 100% is aimed for licensed disposal, then it practically means that there is no incentive for reuse) • Would the Employer consider replacing or splitting KPI E1 into two explicit targets to ensure both circular economy and traceability goals are met? • KPI E1a (ReuseTarget): X% of non-hazardous excavated material diverted from landfills via on-site backfill, sub-base processing, or off-site repurposing. • KPI E1b (Traceability & Legal Compliance): 100% of all off-site material movements (whether for reuse or final disposal) supported by official waste manifest documentation and pre-approved licensed receiving facilities. | KPI E1 shall be applied as stated in the Employer’s Requirements. For non-hazardous excavated material, the KPI measures the percentage of total excavated material that is reused within the permanent Works, repurposed at approved off-site locations, or disposed of at pre-approved licensed disposal facilities, with the required material tracking and disposal documentation. Hazardous material requires 100% disposal through certified hazardous-waste facilities. The request to replace or split KPI E1 into separate new KPI targets is not accepted. | No
815 | Section II – Proposal Data Sheet (PDS) / ITP 15.3 – Price Adjustment; ITP 16.1 – Proposal / Payment Currencies; Section IV – Schedule of Cost Indexation / Tables A–C; GC Sub-Clause 13.7 | The RFP requires the Proposal and payments to be entirely in Turkish Lira, while ITP 15.3 provides for price adjustment during execution and ITP 16.1 requires Proposers to identify their foreign currency requirements for inputs supplied from outside Türkiye. In this respect, please clarify whether, for imported or foreign-currency-dependent inputs such as rails, turnouts, OCS materials, electrical and electromechanical equipment, the indices/reference prices under the Schedule of Cost Indexation may be based on appropriate foreign or international indices/reference prices (e.g. Eurostat, LME or other internationally recognised indices), notwithstanding that the Contract and payments are denominated in Turkish Lira. Please also confirm whether the resulting adjustment will be calculated in accordance with GC Sub- Clause 13.7 and converted/paid in Turkish Lira, and specify the applicable exchange-rate basis, if any, to be used for such foreign-currency-related cost components. | Please refer to ITP 15.3, ITP 16.1 and the Table of Adjustment Data. Under Alternative A, the prices in the Schedules of Priced Activities and Sub-activities shall be quoted entirely in Turkish Lira; however, Contract payments are not necessarily limited to Turkish Lira. A Proposer may identify in Table C up to three foreign currencies for its foreign-currency payment requirements in accordance with ITP 16.1. For price adjustment, the prescribed indices in Table A shall apply to the local-currency portion of the Proposal/ Contract Price. While Table B shall be completed for the applicable foreign-currency portions of the Proposal/Contract Price. Appropriate published and verifiable foreign or international indices/reference prices may be proposed for the relevant foreign-currency cost elements, subject to the requirements of the Table of Adjustment Data and the Schedule of Cost Indexation. Price adjustment shall be calculated in accordance with Sub-Clause 13.7 in the relevant contractual payment currency. Where the currency of origin of an index differs from the relevant Contract/payment currency, the Z0/Z1 correction factor specified in the Schedule of Cost Indexation shall apply. The payment currencies, proportions and applicable exchange rates shall be those established under ITP 16.1 and Table C. Accordingly, foreign-currency adjustments are not automatically converted and paid entirely in Turkish Lira. | No
816 | General Conditions / Sub-Clause 14.5 – Plant and Materials Intended for the Works; Section IX – Particular Conditions / Contract Data; Section IV – Schedule of Priced Activities | The Conditions of Contract are based on the FIDIC Conditions of Contract for Plant and Design- Build, Second Edition 2017, Reprinted 2022 with amendments (Yellow Book). In this respect, we kindly request clarification regarding the application of Sub-Clause 14.5 [Plant and Materials intended for the Works] of the General Conditions, read in conjunction with Sub- Clause 14.4 [Schedule of Payments] and the applicable Particular Conditions. Considering the substantial value and long-lead procurement requirements of major Plant and Materials under the Contract, including but not limited to rails, turnouts, track materials, OCS materials and equipment, traction power equipment, and tunnel and station electromechanical equipment, please clarify whether eligible Plant and Materials may be included in Interim Payment Certificates: (a) upon shipment; and/or (b) upon delivery to and proper storage at the Site, prior to their permanent incorporation into the Works. If Sub-Clause 14.5 is applicable to this Contract, please confirm: 1. the categories of Plant and Materials eligible for payment upon shipment and/or delivery to Site; 2. the percentage of the eligible value to be included in the relevant Interim Payment Certificate; 3. the applicable documentary, ownership, insurance, storage, security and/or guarantee requirements; and 4. whether such payment under Sub-Clause 14.5 shall be certified separately from the milestone- based payments under the Schedule of Payments, or shall be considered as part of the relevant Activity/Sub-activity milestone payment. If payment for Plant and Materials prior to their permanent incorporation into the Works is not intended under the Contract, please confirm that Sub-Clause 14.5 of the General Conditions shall not apply. We also kindly request the Employer to clarify the relevant entries, if any, in the Contract Data identifying the Plant and Materials eligible for payment upon shipment and/or upon delivery to Site. | Please refer to Answer 288. No Contract Data entry is provided for Sub-Clause 14.5, and no list of Plant or Materials or applicable percentage for payment upon shipment or delivery to Site is prescribed for this Contract. Accordingly, the payment mechanism under Sub-Clause 14.5 is not activated for this Contract. Therefore, Plant and Materials, including rails, turnouts, track materials, OCS materials and equipment, traction power equipment, and tunnel or station electromechanical equipment, are not eligible for separate interim payment solely upon manufacture, shipment, off-Site storage or delivery to Site prior to their incorporation into the Works. Interim payments shall instead be assessed and certified in accordance with the Schedule of Priced Activities and Sub-activities and the applicable provisions of Clause 14. No separate categories, percentages or pre-incorporation payment arrangements under Sub-Clause 14.5 apply. | No
817 | Section VII – Employer’s Requirements / Annex P – Testing and Commissioning Technical Specification / Clause 34.1.8 | Annex P, Section 34.1.8 states that costs arising from repeated tests due to defects or failures shall be borne by the Contractors and further states that “the costs associated with testing and commissioning shall be shared equally among the contractors.” In the event that an integrated test or commissioning activity fails or must be repeated due to a defect, non-conformance, incomplete work or non-readiness attributable to a specific Lot Contractor or the Package 2 Contractor, please confirm that the resulting re-testing and associated costs shall be borne by the Contractor responsible for such failure and shall not be shared with Contractors whose works and interfaces have successfully complied with the relevant requirements. Please also clarify whether the equal cost-sharing provision applies only to common Project-wide testing and commissioning activities where no failure is attributable to a particular Contractor, and confirm whether the Package 2 Contractor is included in such cost sharing. | Where a test or commissioning activity must be repeated because of a defect, non-conformance, incomplete work or non-readiness attributable to a specific Contractor, the resulting re-testing and associated costs shall be borne by the responsible Contractor and shall not be shifted to Contractors whose works/interfaces complied with the applicable requirements. Any equal cost-sharing provision applies only to common Project-wide testing/commissioning costs for which the Contract expressly provides shared allocation and which are not attributable to a particular Contractor. The separate Package 2 Signalling and Telecommunications testing/commissioning cost allocation shall be applied as stated in the Employer’s Requirements. | No
818 | Section VII – Employer’s Requirements / Clauses 10.1.3–10.1.4 and 10.3.6 – Testing and Commissioning / System Demonstration Tests; Annex P – Clause 35 | Reference: Annex P – Section 35, System Demonstration Tests Annex P requires the Contractor to provide/identify the resources necessary for System Demonstration Tests, including rolling stock. Please clarify whether the passenger and freight rolling stock required for System Demonstration Tests, Trial Running and Trial Operations will be provided by the Employer/TCDD or by the Contractor. If the Contractor is responsible, please confirm the required rolling stock types and quantities and clarify responsibility for drivers/operating personnel, traction energy, TCDD access/paths and associated operating costs. | Unless the Contract expressly states otherwise, the Contractor shall provide or arrange all resources necessary for Testing, Commissioning, System Demonstration Tests, Trial Running and Trial Operations, including test loads and rolling stock, and shall include the associated costs in the Contract Price. The required passenger/freight rolling-stock types, quantities, operating personnel, access/paths and operating arrangements shall be developed and coordinated with the Engineer, TCDD/Railway Operator and other relevant Contractors as part of the approved Testing and Commissioning Master Plan. No Employer-provided rolling-stock commitment is made through this clarification. | No
819 | Section VII – Employer’s Requirements / Clause 5.3.2 – Special System Works / Water Mist Fire Suppression; Clause 10.9.4; Annex K | Subject: Implementation of Water Mist Fire Suppression Systems in Tunnels and Stations Clause Reference: RFP Document, Section 5.3.2 & Section 10.9.4 Request for Clarification: 1- Section 5.3.2 – Special System Works: "The Contractor shall be responsible for the design, procurement, installation, testing, and commissioning of the water mist fire suppression system for the tunnels and station areas along the railway line. The system shall be designed in compliance with applicable national and international standards, Employer's Requirements, and relevant authority approvals, and shall be integrated with fire detection and alarm systems where required. The Contractor's scope of work shall cover all equipment, piping systems, nozzles, pumps, control panels, cabling, software/automation interfaces, and auxiliary systems necessary to ensure safe, reliable, and maintainable operation." 2- Section 10 – Testing, Commissioning and Trial Operation, Subsection 10.9 MEP Systems, Item 10.9.4 Fire Detection and Fire Suppression Systems: "The Contractor shall provide fully integrated fire detection, fire alarm, fire suppression, and smoke management systems. Tests shall include detector functional tests, alarm verification, cause-and-effect verification, sprinkler and water mist systems, hydrants, hose reels, gaseous fire suppression systems where applicable, fire pumps, valve monitoring, fire water storage, emergency shutdown sequences, and interface testing with HVAC, SCADA, signaling, passenger information systems, and emergency communication systems." The provisions above require the installation of a water mist fire suppression system for stations and tunnels. However, the Annexes do not contain any information regarding the technical criteria or specification requirements for the water mist system. Since water mist systems entail specialized technical requirements, if the execution of this system is requested within the scope of the INRAIL project, we kindly request the Employer to provide detailed technical data regarding the specific installation areas in both tunnels and stations, as well as the complete technical specification requirements. | The water-mist fire-suppression system is expressly required by the Employer’s Requirements and shall therefore be included in the Contractor’s scope. The Contractor shall develop the detailed technical design, performance criteria, zoning/coverage, hydraulic calculations, equipment selection, interfaces and testing requirements in accordance with the applicable national/international standards, the fire-risk/fire-life-safety strategy and authority approvals. The exact installation areas in tunnels and stations shall be determined through the approved Detailed Design. The absence of a separate prescriptive water-mist annex does not remove the requirement. | No
820 | Section VII – Employer’s Requirements / Clauses 4.8.3 and 5.3.3 – TEİAŞ / Main Power Supply; Annex J | Subject: Main Power Supply (154 kV) Sources of the System Clause Reference: RFP Document, Annex D, Annex J, Annex K Request for Clarification: The relevant sections of RFP Document Annex D, Annex J, and Annex K outline the power supply requirements and criteria for each lot of the system. In particular, Section 1.2 of Annex J1 states: "In accordance with the scope defined above, the contractor of each section shall be responsible for the construction and commissioning of the substation, the installation of 154 kV power transmission lines (including required busbars and neutral sections), and the line-side power distribution (including resolving interfaces with preceding/subsequent existing or ongoing railway sections); all materials, transportation, and labor shall be included in the scope." Pursuant to this provision, it is understood that bringing the 154 kV power transmission lines to the substations is required within the scope of work. However, route analyses indicate that in certain sections, TEİAŞ's existing 154 kV power transmission line infrastructure is located at a considerable distance from the alignment. In areas where no investment plan by TEİAŞ in close proximity to the alignment is anticipated, please confirm whether—regardless of the distance—the 154 kV power supply shall be transmitted from the nearest TEİAŞ facility to the 154/25 kV substations to be constructed under this tender via excavation, high lattice towers, or other applicable methods, and that all such works (including expropriation costs and all other associated expenses arising under these circumstances) are deemed to be included in the tender prices. | The Contractor shall include the 154 kV external power-supply works required for its contractual power-supply arrangement in accordance with Annex J and Section 5.3.3. The Lot 2 and Lot 4 Contractors shall identify and propose suitable TEİAŞ connection points through the required system-wide studies and simulations and shall obtain the necessary approvals at their own cost. The final supply arrangement shall be established based on the approved studies, TEİAŞ/relevant authority requirements and the Engineer’s/Employer’s approval. The final connection arrangement may require 154 kV transmission-line works from the approved TEİAŞ connection point to the relevant traction substation. The Contractor shall include in its Proposal Price all design, coordination, permitting, construction, testing and commissioning works and associated costs falling within its contractual scope, irrespective of the transmission-line solution and distance, unless otherwise expressly provided in the Contract. Where permanent Project land is required for such works, statutory land acquisition, expropriation and compensation shall be dealt with in accordance with the land-acquisition provisions of the Employer’s Requirements. | No
821 | Section III – Evaluation and Qualification Criteria / Item 1.5 – Equipment / Articulated Dump Truck (Minimum 30 Ton Payload) | Subject: Articulated Dump Truck (Min. 30 Ton Payload) Within the scope of equipment qualification criteria in the RFB, an "Articulated Dump Truck (min. 30 Ton Payload)" is required. In Türkiye, articulated dump trucks of this capacity and specification are mostly characterized as construction equipment / off-road rock-earthmoving trucks, and it may not be possible to operate them on public roads in the same manner as standard road trucks. In this context, we kindly request clarification on the following points: • Are the requested vehicles required to be road-registered trucks, or will articulated dump trucks registered as construction equipment (off-road heavy machinery) and suitable for site/off-road use be accepted? • Is it envisaged that these vehicles will be operated on public roads within the scope of the project, or is their use restricted solely to the construction site area? • At the qualification stage, will a vehicle road registration certificate be required, or will a construction equipment registration certificate, invoice, proof of ownership, and manufacturer technical documentation be accepted? • Is the minimum 30-ton payload capacity a mandatory qualification requirement? Would it be acceptable to propose dump trucks with lower payload capacities that are permitted in road traffic in Türkiye and capable of meeting the haulage requirements of the project? | The minimum 30-ton payload is a mandatory equipment characteristic for qualification. Articulated dump trucks registered/used as construction equipment for off-road/site operations are acceptable provided that they satisfy the specified minimum capacity and are suitable and legally permitted for their intended use under the Contractor’s methodology. The RFP does not require them to be ordinary road-registered haulage trucks merely for qualification. The Proposer shall provide the ownership/lease/manufacturer and other Form EQU evidence necessary to demonstrate access to compliant equipment. Vehicles with a payload below 30 tons do not satisfy the stated minimum equipment requirement. | No
822 | Section II – Proposal Data Sheet (PDS) / ITP 12.2(i) – Joint Venture Arrangements; Section I – ITP 4.1 | The Employer is kindly requested to clarify whether the Joint Venture Agreement required to be submitted in accordance with the ITP must be identical in all respects to the Joint Venture Agreement to be used during the project performance phase, or whether, at the tender stage, it is sufficient to submit a Joint Venture Agreement setting out the general principles and satisfying the requirements stipulated in ITP Clause 12.2(i). In the latter case, the detailed Joint Venture Agreement may be further developed and finalized after the award of the Contract, in accordance with the principles established in the Joint Venture Agreement submitted at the tender stage. Furthermore, we kindly request the Employer to clarify whether the requirement for the allocation of works under ITP Clause 12.2(i) obliges the Proposer to explicitly specify, in the Joint Venture Agreement, the specific scope of works to be undertaken by each Joint Venture Member. To what level of detail must the allocation of works be specified, and how should any adjustments to such allocation be handled during the project performance phase? | Please refer to Answer 63 and ITP 12.2(i). At Proposal stage, the Proposer may submit either a JV Agreement or a letter of intent to enter into a JV together with a draft agreement, as permitted by the RFP. The tender-stage JV documentation need not be identical in every administrative detail to the agreement used during Contract execution; however, it shall already contain and comply with all mandatory JV provisions required by the RFP, including the identification of the lead member, the lead/principal share, joint and several liability, and the scope and parts of the Contract to be carried out by each JV member. The scope allocation shall identify at least the principal parts of the Works to be carried out by each JV member and shall correspond to the respective member’s experience and capacity. The RFP does not require a detailed allocation of every individual activity, quantity or contract value unless such detail is otherwise necessary to demonstrate compliance. Following award, administrative or implementation details of the JV arrangements may be further developed, provided that the JV composition, constitution, legal status and the scope and parts of the Contract allocated to each member are not altered without the prior consent of the Employer. | No
823 | Section III – Evaluation of Technical Part / Factor 3 – Similar Work Experience | Please confirm whether, for the purpose of evaluation under Factor 3 – Similar Work Experience, the Proposer may reference additional projects other than those submitted for qualification under Section III, Sub-Factors 4.2(a), 4.2(b) and 4.2(c), provided that such projects are properly substantiated and relevant to the respective rated criteria. | Confirmed. For the purpose of the Rated Criteria under Factor 3 – Similar Work Experience, the Proposer may reference additional relevant projects beyond those used to demonstrate the minimum qualification requirements under Section III, Sub-Factors 4.2(a), 4.2(b) and 4.2(c), provided that the additional references satisfy the applicable Rated Criterion requirements and are clearly identified and supported by verifiable evidence in the Technical Proposal. Qualification and rated-criteria evaluation remain separate assessments and will be carried out strictly in accordance with Section III and ITP 31. | No
824 | Section III – Evaluation of Technical Part / Factor 4 – Organization & Key Personnel | With reference to Factor 4 – Organization & Key Personnel, please confirm whether the technical evaluation may take into account additional Key Personnel and specialist experts proposed by the Proposer beyond the minimum mandatory Contractor’s Representative and Key Personnel, provided that such personnel are clearly identified in Form PER-1, supported by Form PER-2, and included in the Contract Personnel Organization Chart. Please also confirm that such additional personnel may be considered for the evaluation under Factor 4.2 “Specialized Expert Competence & Value-Added Human Capital” and the relevant sub-factors. | Confirmed. Additional suitably qualified specialist experts/personnel proposed beyond the minimum mandatory Contractor’s Representative and Key Personnel may be taken into account under Factor 4, including Factor 4.2 “Specialized Expert Competence & Value-Added Human Capital”, where they are clearly identified in the Technical Proposal, included in the Contract Personnel Organization Chart and, where proposed as additional Key Personnel, included in Form PER-1 and supported by the relevant Form PER-2 information. Such additional personnel may contribute to the assessment of the breadth and complementarity of specialist expertise under the applicable Factor 4.2 sub-factors. This does not replace, reduce or otherwise modify the mandatory minimum Key Personnel requirements. | No
825 | Section III – Evaluation and Qualification Criteria / Item 1.5 – Equipment; Section IV – Proposal Forms / Contractor’s Equipment | For key equipment to be specially manufactured for the Project, particularly TBMs, please confirm that at Proposal stage the Proposer may provide the proposed manufacturer, required technical capacity/specifications, procurement/manufacturing strategy and delivery programme, while information such as year of manufacture, current location and current status may be indicated as “Not Applicable / To be specially manufactured”. | Please refer to Answer 1 and Form EQU. For key equipment to be specially manufactured for the Project, including TBMs, the Proposer shall provide the proposed manufacturer, the required technical characteristics/capacity, details of the manufacture arrangement specific to the Project, and the strategy/programme demonstrating that the equipment will be available for execution of the Works. Where the equipment has not yet been manufactured, information such as year of manufacture, current location and current status may, as factually applicable, be stated as “Not Applicable / To be specially manufactured”. The Proposal shall otherwise demonstrate compliance with the applicable equipment requirements and availability for the Works. | No
826 | Section III – Evaluation and Qualification Criteria / Item 1.5 – Equipment / Drill Jumbo for NATM Works; Section IV – Contractor’s Equipment | With reference to Section III, Clause 1.5 – Equipment, Drill Jumbos for NATM Works are specified as minimum key equipment for all Lots. The Proposer intends, subject to the actual geological and geotechnical conditions, to adopt mechanical excavation methods for certain NATM sections, such as roadheaders and/or excavators equipped with hydraulic breakers, instead of drill-and-blast excavation. Please confirm whether, where the Proposer demonstrates that the proposed mechanical excavation method is technically appropriate and provides suitable alternative excavation equipment in the Technical Proposal and Form EQU, the specified Drill Jumbo requirement may be replaced by such alternative equipment. In such case, please also confirm that the omission of Drill Jumbos from Form EQU would not result in non-compliance with the minimum equipment requirements under Section III, Clause 1.5. | The minimum key equipment requirements in Section III, Clause 1.5 remain applicable for qualification. A Proposer may propose mechanical excavation methods for particular NATM sections where technically appropriate; however, this does not waive the stated minimum requirement to demonstrate access to the specified Drill Jumbos. Accordingly, omission of the required Drill Jumbos from Form EQU would not satisfy Clause 1.5 unless the RFP is formally amended. | No
827 | Section VII – Employer’s Requirements / Clauses 9.3.4 and 5.9.2 – Emergency Egress and Cross-Passages; Addendum | Section VII Clause 9.3.4 requires cross-passages in all twin-bore TBM tunnels at a maximum spacing of 250 m in accordance with NFPA 130. However, in the conceptual design drawings the cross-passage spacing in several sections exceeds 300 m. Please confirm: 1. whether the Proposal (technical solution and pricing) shall be based on a maximum spacing of 250 m throughout; 2. whether the same maximum spacing applies to twin-bore NATM sections and cut-and-cover sections; 3. whether any additional cross-passages resulting from the 250 m requirement shall be deemed included in the lump-sum price of the respective tunnel. | For clarity, please refer to Addendum No. 2, Amendment No. 10, Section VII, ER Clause 9.3.4, together with the corresponding amendment to ER Clause 9.3.1. NFPA 130 shall apply to underground station structures and station-specific emergency ventilation, passenger evacuation and station-safety requirements. SRT-TSI shall apply to alignment structures, including mainline railway tunnels and twin-bore tunnel cross-passages; the maximum cross-passage spacing is 500 m under the amended Clause 9.3.4. Mandatory Turkish requirements, including BYKHY where applicable, also remain applicable. SRT-TSI does not replace NFPA 130 across the entire project; the standards apply within their respective scopes. | Yes
828 | Section VII – Employer’s Requirements / Clauses 5.2.1–5.2.3 – Geotechnical Risk Allocation; Lot 3 / Clause 5.7.2; Annex C1 – Geological Data Report; Section IV – NATM Tunnel Lump-Sum Activities | Each NATM tunnel is priced as a lump sum “complete, all support classes”. Please confirm: 1. whether the Employer will provide a Geotechnical Baseline Report (GBR) or the distribution of rock mass / support classes for each tunnel as a common basis for all Proposers; 2. where the actual distribution of rock/support classes differs materially from such baseline, whether any measurement or adjustment mechanism applies, or whether this risk is borne entirely by the Contractor. | The Employer will not provide a Geotechnical Baseline Report or a contractual distribution of rock/support classes for pricing. The geological/geotechnical information in the Tender Documents is reference information and the Contractor is responsible for the investigations, geotechnical characterization, support-class selection and Detailed Design necessary for the NATM works. The lump-sum prices shall include the support measures required by the actual conditions and approved design. A difference in the actual distribution of support classes from tender-stage information does not, by itself, create a measurement or price-adjustment entitlement. Any entitlement, if any, shall be determined only under the Conditions of Contract for circumstances outside the Contractor’s allocated risk. | No
829 | Section IV – Proposal Forms / Schedule of Priced Activities – Ballastless Track; Section VII – Employer’s Requirements / Clause 5.3.2 and Lot-Specific Track Scope; Annex G; Addendum– Ballasted/Ballastless Track Itinerary | The Schedule of Priced Activities includes a lump-sum item “Ballastless (slab) track construction — complete (all locations)” for each Lot (Lot 1 item 9.3, Lots 2/3 item 8.3, Lot 4 item 9.3), while the Section VII scope clauses for each Lot only require “construction of ballasted and ballastless track in accordance with the approved design”, without defining the extent or system of ballastless track. Please confirm: 1. whether the extent of ballastless track is to be determined by the Contractor in its design, subject to the Engineer’s approval (e.g. based on tunnel length, bridges and transition zones), or whether the Employer has any minimum requirement; 2. whether the Employer requires any specific ballastless track system; 3. the track form to be adopted on the lower rail deck of the YSS Bridge, and any limitations on track structure load and construction depth. | Please refer to Addendum, Amendment No. 15, by which a Ballasted/Ballastless Track Itinerary for track superstructure on bridges and viaducts has been added to the RFP. That itinerary, together with the Employer’s Requirements, Annex G and the approved Detailed Design, forms the tender basis for the applicable track form and locations and shall not be disregarded by treating the entire ballastless-track extent as a free Contractor choice. No proprietary ballastless-track system or additional minimum quantity is introduced through this clarification beyond the contractual documents. For the YSS Bridge lower deck, the Contractor shall comply with the added itinerary and the existing bridge/interface requirements and shall develop the loads, construction depth, fixings, expansion/transition arrangements and dynamic compatibility in the Detailed Design, subject to the required KGM/Bridge Operator and Engineer approvals. No further amendment is made to the RFP. Please refer to Addendum No. 2, Amendment No. 15. | Yes
830 | Section VII – Employer’s Requirements / Clauses 4.8.1, 5.7.2–5.7.3 and 6.6 – YSS Bridge / Existing Structures / Lot 3 | Based on site and document review, two Type E cut-and-cover structures near the YSS Bridge in Lot 3 appear to have already been constructed. Please confirm: 1. which structures along the alignment have already been constructed or are under construction by others and are to be treated as existing structures outside the construction scope of this Contract; 2. the scope of this Contract in relation to such existing structures (condition survey and assessment, strengthening, interface connection, or use only); 3. please provide the as-built drawings and inspection records of these structures. | Please refer to Answers 386 and 431. The Employer has provided the tender-stage reference/conceptual information available regarding existing and previously constructed structures. The Contractor shall verify the actual condition, geometry and interfaces through its own surveys/investigations and develop the Detailed Design accordingly. The scope in relation to any existing structure includes the surveys, assessments, interface works and any measures required by the Contract to complete the Works. No additional definitive existing-structure list, as-built package or inspection record is issued through this clarification unless subsequently transmitted by Addendum. | No
831 | Section IV – Proposal Forms / Station Electromechanical Works – Lifts and Escalators; Section VII – Clauses 5.5.2 and 5.8.2; Annex I | Station electromechanical works in the Schedule of Priced Activities include lifts and escalators, but no passenger demand forecast or equipment provision requirements are given in the RFP. Please provide the design passenger demand (long-term peak hour) for each station and the minimum provision requirements for lifts and escalators, so that the quantity and specification of such equipment can be determined. | The station lift/escalator provision shall be developed by the Contractor through the approved station Detailed Design, based on the applicable Operations Plan/passenger-demand information, accessibility requirements, evacuation analysis, applicable standards and airport/rail interfaces. The RFP does not issue additional binding long-term peak-hour passenger-demand figures or minimum lift/escalator quantities through this clarification. The Contractor shall provide sufficient equipment to satisfy the functional, accessibility, capacity and fire-life-safety requirements of the Contract and obtain the Engineer’s approval. | No
832 | Section VII – Employer’s Requirements / Clauses 4.6, 4.8.3 and 5.3.3 – Traction Power Supply / Substation Locations / TEİAŞ; Annex J | Section VII Clause 5.3.3 provides that the final power supply points and the number and location of transformers will be decided by the Employer based on the feeding plans of the Lot 2 and Lot 4 Contractors and the approved simulation results, and lists indicative transformer substation locations from the conceptual design (e.g. km 27+000, km 7+600, km 18+600) for planning reference only. Please confirm: 1. whether the number, locations and capacity of traction substations and sectioning posts in the Proposal shall be priced on the basis of these indicative locations; 2. please provide grid data for the candidate TEİAŞ 154 kV connection substations, including maximum and minimum short-circuit power and voltage unbalance limits; 3. whether any difference between the finally approved number, location or capacity of substations and the Proposal basis will be treated as a Variation. | The transformer-substation locations identified in the conceptual design are indicative planning references only. The Proposer shall price the complete traction-power system required to satisfy the Employer’s Requirements, taking the tender-stage information into account while allowing for the system-wide simulations and Detailed Design that will determine the final number, locations and capacities. The Lot 2 and Lot 4 Contractors shall obtain the necessary TEİAŞ network data and approvals for candidate connection points; no additional guaranteed short-circuit-power or voltage-unbalance dataset is issued through this clarification. A difference between the indicative and finally approved arrangement arising from the Contractor’s design/performance obligations does not automatically constitute a Variation. A Variation arises only where the Engineer instructs a change that qualifies under Clause 13. | No
833 | Section IV – Proposal Forms / Table of Forms – Daywork Schedule; Addendum | Reference is made to ITP 38.1 of Section II - Proposal Data Sheet (PDS), which states: In the second step, the Employer will convert the amounts in various currencies in which the Proposal Price is payable (excluding Provisional Sums but including Daywork where priced competitively) to the single currency identified above at the selling rates established for similar transactions by the authority specified and on the date stipulated above. The table of contents of SECTION IV - PROPOSAL FORMS under Section III – Evaluation and Qualification Criteria (Page 87 of the Tender Documents) also explicitly refers to four tables to be included under the Daywork Schedule: “Schedule of Daywork Rates: 1. Labor”, “Schedule of Daywork Rates: 2. Materials”, “Schedule of Daywork Rates: 3. Contractor’s Equipment” and “Daywork Summary”. However, we note that no Daywork Schedule has been provided in the Tender Documents for bidders to enter prices. We request clarification from the Employer on this matter. | Please refer to Addendum No. 2, Amendment No. 6. | Yes
834 | Section IV – Proposal Forms / Schedule of Payments; Section IX – Particular Conditions / Clause 14 – Contract Price and Payment; Addendum | Section IV - Proposal Forms of the Tender Documents requires us to submit the Schedule of Payments. However, no template for the Schedule of Payments is provided within the Tender Documents. We request clarification from the Employer whether we may prepare the format and contents of the Schedule of Payments at our own discretion based on our understanding. | Please refer to Addendum No. 2, Amendment No. 12. | Yes
835 | Section VII – Employer’s Requirements / Clauses 5.9.1 and 5.9.3 – Excavated Material Management / Construction Logistics; Environmental and Social Requirements; Clause 12.4 / KPI E1; Section I – ITP 15.1 – Single-Responsibility Lump-Sum Proposal Price | Can the designated spoil disposal area specified in the bidding documents satisfy the spoil disposal requirements of the project? In case of insufficiency, shall the contractor be obligated to resolve such matter at its own discretion and cost? | The RFP does not warrant that any single referenced or indicative spoil-disposal area has sufficient capacity for the Project. Under Section VII, Clauses 5.9.1 and 5.9.3, the excavation volumes are indicative and the Contractor is responsible for verifying its quantities and for identifying sufficient compliant reuse, transportation, storage and final-disposal arrangements. All disposal sites to be used under the Contract shall be identified and pre-approved through the C-ESMP before excavation commences, and haulage shall be addressed in the Construction Logistics Plan. Accordingly, if an identified facility does not have sufficient capacity, the Contractor shall arrange other compliant reuse/disposal options within its contractual scope and lump-sum price. Any separate entitlement could arise only where an Engineer-instructed change constitutes a Variation under the Contract; no such entitlement is created merely by insufficient capacity at an indicative facility. | No
836 | Section III – Evaluation of Technical Part (ITP 31) / Rated Criteria – Supporting Evidence | Article 2, Evaluation of Technical Part, of Section III – Evaluation and Qualification Criteria lists the following sub-factors, for which supporting evidence is required. In order to ensure a clear and consistent understanding of the documentary requirements, could you please clarify what type of supporting evidence is expected to be submitted for each of the sub-factors listed below? In particular, please clarify whether confirmation/reference letters issued by the respective Employers are required, or whether other supporting documentation demonstrating the relevant experience and performance would also be considered acceptable. • 2.2.3 Evidence of resource-cash flow alignment management on prior comparable projects • 2.3.3. Evidence of the bidder's track record in achieving mobilization targets on comparable contracts • 3.2.1. Evidence of multi-system integration delivery (trackwork, electrification, and signaling) on contracts of comparable scale and interface complexity. • 3.2.2. Commissioning outcomes and interface management performance on referenced projects, as evidenced through RAMS KPIs, FAT/SAT/SIT completion records, or client references. • 3.2.3. Experience with EU interoperability requirements, including engagement with Assessment Bodies (AsBo) • 3.2.4. Notified Bodies (NOBO) for subsystem certification. • 3.2.5. Experience managing delivery in live or operationally constrained railway environments. • 3.3.1. Experience in contracts involving interfaces between different types of transport infrastructure encompassing integration or coordination with terminal/stations or road networks. • 3.3.2. Experience managing delivery within live or operationally constrained environments — including operational transport infrastructure — where works must be phased, sequenced, or isolated to avoid disruption to ongoing operations. • 4.1.1. Evidence of multidisciplinary coordination leadership in the corridor-scale rail or infrastructure projects. • 4.1.2 Track record in managing civil-systems interfaces under time and geotechnical pressure. • 4.3.2 Robustness of the RACI matrix in unambiguously assigning decision-making authority across key processes design, construction, QA, and ESHS — without creating reporting bottlenecks. • 5.1.4 Evidence of QA/QC performance track record on comparable projects • 5.2.3 Evidence of the bidder’s LTIFR on comparable projects, • 5.3.5 Past implementation evidence • 5.4.3 Evidence of comparable biodiversity management on infrastructure projects • 6.2.3.Evidence of outcome-driven mitigation on comparable projects. • 6.4.3.Evidence of successful value engineering implementation on comparable contracts. • 7.1.3. Evidence of the bidder's track record in achieving comparable circular resource targets on prior projects • 7.3.3 Evidence of waste management compliance performance on comparable projects. • 8.1.5 Evidence of workforce management performance on comparable labor- intensive contracts | Employer/client confirmation or reference letters are not mandatory for all of the listed Rated Criteria unless expressly required by the wording of a particular criterion. The Proposer shall submit sufficient, relevant and verifiable information and supporting documentation appropriate to the nature of each respective sub-factor. For sub-factors relating to prior experience, track record, performance or past implementation, acceptable supporting evidence may include, as applicable, Employer/client certificates or references, completion or taking-over records, approved progress or performance reports, KPI records, RAMS documentation, FAT/SAT/SIT records, audit or certification records, OHS statistics, environmental/social monitoring records, waste or biodiversity management records, value-engineering approvals/records, and other objective project documentation capable of substantiating the claimed experience or performance. For sub-factors that assess the content or robustness of the current Technical Proposal itself, such as Sub-Factor 4.3.2 concerning the RACI matrix, the relevant proposal document, matrix, methodology, organizational arrangements and supporting explanations shall constitute the principal evidence; prior Employer reference letters are not required unless otherwise expressly stated. The specific evidence submitted should correspond directly to the wording of the relevant sub-factor. For example, Sub-Factor 3.2.2 expressly identifies RAMS KPIs, FAT/SAT/SIT completion records or client references as possible evidence. The Employer may request clarification of the submitted Proposal in accordance with ITP 28. | No
837 | Section IV – Proposal Forms / Form FIN-3.4 – Current Contract Commitments / Works in Progress; Section III – Financial Capability | At the beginning of “Section III – Evaluation and Qualification Criteria”, it is stated that the contract amounts should be updated using the U.S. Bureau of Labor Statistics (BLS) Producer Price Index (PPI): Final Demand (Series ID: WPUFD4), based on the index value applicable 14 days prior to the bid submission deadline. We understand that this update does not apply to Form FIN-3.4 – Current Contract Commitments/Works in Progress. Otherwise, the total value of our current contracts would be significantly overstated. Could you please confirm whether our understanding is correct? | Confirmed. The BLS PPI present-value updating methodology at the beginning of Section III applies to the monetary value of past contract references used for qualification/evaluation, as stated there. It does not require the values of current contract commitments/works in progress reported in Form FIN-3.4 to be escalated by the BLS index. Form FIN-3.4 shall reflect the Proposer’s actual current commitments/works in progress in accordance with the form and the applicable financial-capability criteria. | No
838 | Section III – Evaluation and Qualification Criteria / Item 4.2(b) – Key Activities and Footnote 9; Addendum | In Section III – Evaluation and Qualification Criteria, Clause 4.2(b) requires that each key activity be completed “under a single contract”. However, Footnote 9 states that “Volume, number, or rate of production of any key activity can be demonstrated in one or more contracts combined if executed during the same time period.” These two provisions appear to be inconsistent. Could you please clarify whether the experience for each key activity must be demonstrated under a single contract only, or whether it may be demonstrated through multiple contracts executed during the same time period, as indicated in Footnote 9? | Please refer to Addendum No. 2, Amendment No. 8. | Yes
839 | Section II – Proposal Data Sheet (PDS) / ITP 16.1 and ITP 38.1 – Proposal / Payment Currencies; Section IV – Table C – Summary of Payment Currencies | We note that ITP 16.1 states that “The prices shall be quoted by the Proposer in the Schedules of Priced Activities and Sub-activities entirely in Turkish Lira.” However, ITP 38.1 states that Proposal prices expressed in various currencies will be converted into Turkish Lira for the purpose of evaluation. Since ITP 16.1 requires all Proposal prices to be quoted entirely in Turkish Lira, there appears to be no circumstance under which currency conversion would be necessary during the evaluation process. Kindly clarify whether ITP 38.1 is a standard provision included inadvertently, or whether Proposers are permitted to quote certain components of their Proposals in currencies other than Turkish Lira. | ITP 38.1 is intentional and is not an inadvertent standard provision. Under Alternative A, the Proposal Price in the Schedule of Priced Activities and Sub-activities shall be quoted entirely in Turkish Lira. A Proposer that expects foreign-currency expenditure shall state, in Table C, the portions of the Proposal Price required to be paid in up to three foreign currencies and the exchange rates used to establish those portions. For evaluation, the Employer converts the resulting payment-currency amounts to Turkish Lira using the CBRT selling rate on the Proposal submission deadline, as stated in ITP 38.1. Proposers are therefore not permitted to quote the Schedule prices themselves in foreign currency. | No
840 | Section IV – Schedule of Cost Indexation / Table B – Foreign Currency (FC); Section II – PDS / ITP 16.1 | In the Table of Adjustment Data – Table B (Foreign Currency / FC), kindly clarify the source of the foreign currency indices/exchange rates to be used for EUR and USD. And please confirm that the base date for the currency indices/exchange rates shall be 28 days before the deadline of the submission of bids. | For Table B – Foreign Currency (FC), the Proposer shall specify the source and base value of the applicable cost index or reference price for each foreign-currency cost element. The RFP does not prescribe a single common index source specifically for EUR or USD; the applicable indices/reference prices shall be identified by the Proposer in Table B. If the source of an index or reference price is in doubt, it shall be determined by the Engineer in accordance with the Schedule of Cost Indexation. For Table B, the “Base value and date” is the applicable index value twenty-eight (28) days before the Proposal submission date. Exchange rates used for the payment-currency allocation under Table C and those used for Proposal evaluation under ITP 38.1 are governed separately by ITP 16.1 and ITP 38.1, respectively, and should not be confused with the base-date indices under Table B | No
841 | Section II – Proposal Data Sheet (PDS) / ITP 1.1 – Lots; ITP 22.1(b) – Proposal Copies / Packaging; Section I – ITP 15.6 – Multiple Lots | Please clarify whether, in the event that a Bidder submits bids for more than one Lot, separate bid packages shall be submitted for each Lot, or whether a single bid package covering all Lots for which the Bidder is bidding is acceptable. | A single Proposal may cover one or more Lots, as permitted by ITP 1.1. The RFP does not require a completely separate outer Proposal package for each Lot. The Proposal shall comply with the single-stage two-envelope submission requirements of ITP 22, while all Lot-specific technical, qualification and financial schedules/forms must be clearly identified and separately completed for each Lot for which the Proposer submits a Proposal. | No
842 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Proposal Submission Deadline; Section I – ITP 8 – Amendment of RFP Document | Considering the scale, complexity, and multidisciplinary nature of the Project and the substantial effort required to prepare the technical proposal, qualification documentation, environmental and social submissions, financial proposal, proposal security arrangements, price adjustment schedules, payment currency schedules, and supporting evidence, we respectfully request an extension of the Proposal Submission Deadline by a minimum of two (2) months. | Please refer to Addendum No. 1 regarding the revised Proposal submission deadline under PDS ITP 23.1. | No
843 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel / Items 1–43 | With reference to Section III – Evaluation and Qualification Criteria / Contractor’s Representative and Key Personnel / Minimum Years of Relevant Experience in Similar Works and Overall Professional Experience, we kindly request clarification regarding the meaning of “relevant experience” We understand that the relevant experience may include the types of works specified under Section III – Evaluation and Qualification Criteria / 4.2(a) Specific Construction & Contract Management Experience, namely: (a) Infrastructure works — including, inter alia, earthworks, tunneling, bridges, and viaducts — carried out under contracts for light rail, metro, mainline railway, or highway projects; AND (b) Railway superstructure works — including, inter alia, tracklaying, ballasting (or slab construction), rail welding, fastening installation, turnout assembly and electrification — carried out under contracts for light rail, metro, and/or mainline railway projects. Accordingly, we understand that experience gained in highway, bridge, and viaduct projects may also be considered as relevant experience for the Contractor’s Representative and Key Personnel requirements. Please confirm our understanding. | The meaning of ‘relevant experience’ shall be assessed separately for each Key Personnel position against the specific role and experience wording stated in Section III. The corporate similar-work categories in Clause 4.2(a) do not automatically redefine the personnel criteria. Experience on highway, bridge, viaduct or other infrastructure works may be considered where it is relevant to the particular position and the criterion is not expressly railway/tunnelling/system-specific; however, it cannot substitute for railway-specific or other expressly stated experience requirements. | No
844 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel / Relevant Academic Qualifications | With respect to the “Relevant Academic Qualifications” requirements specified for the relevant positions, could you please confirm whether candidates who hold a degree in a field different from the specific academic discipline stated in the requirements may also be proposed, provided that they have demonstrable professional experience throughout their career in performing the duties and responsibilities relevant to the respective position and fully meet the specified relevant experience requirements for that position? | The academic qualifications stated in the Key Personnel table are minimum requirements, and professional experience does not by itself replace a required academic discipline. Where a criterion expressly permits a 'related discipline', the relevance of the proposed degree may be assessed against that wording. Where the criterion specifies a particular degree without such flexibility, the Proposer shall demonstrate that the candidate satisfies the stated qualification; if the diploma title differs, the Proposer may submit official evidence of formal equivalence for the Employer’s assessment. This clarification does not grant blanket pre-approval to degrees outside the wording of Item 1.4. | No
845 | Section III – Evaluation and Qualification Criteria / Item 1.4 – Contractor’s Representative and Key Personnel / Items 10, 11, 12 and 14 – Large Works Experience | In the Key Personnel criteria table, the expression “large works” is used for various positions under the column “Minimum years of relevant experience in similar works and overall professional experience.” In this regard, we understand that the term “large works” is not limited to any specific project type or sector and that, provided the required professional experience relevant to the respective position is satisfied, experience gained in large-scale construction projects such as transportation infrastructure, airports, energy projects, industrial facilities, buildings/superstructure works, dams, ports, and similar major construction projects may also be considered acceptable under this criterion. Kindly confirm whether our understanding is correct. | Confirmed in principle. Where the criterion uses the expression ‘large works’ without limiting it to a particular sector, relevant experience may be demonstrated on large-scale construction/infrastructure works in different sectors, provided that the nature, scale and responsibilities are relevant to the position. However, any additional role-specific requirement stated in the same criterion—such as tunnelling, railway, environmental/social or other specialized experience—must also be satisfied and is not waived by the broader ‘large works’ wording. | No
846 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Items 1–2 – Project Manager and Civil Works Deputy Project Manager | It is understood that a significant portion of railway and other large-scale infrastructure projects in Türkiye have been implemented under contractual frameworks such as projects procured pursuant to Public Procurement Law No. 4734 and contracted in accordance with Public Procurement Contracts Law No. 4735, FIDIC Red Book, Design & Build, EPC, or other contractual models under which the Contractor assumes design responsibility. Accordingly, requiring Key Personnel to have experience exclusively under the FIDIC Yellow Book / Gold Book may significantly restrict the pool of qualified candidates who have worked on infrastructure and railway projects of comparable scale and complexity. In this respect, considering that the Employer has also applied FIDIC Red Book conditions in internationally financed projects in the past, it is considered that the specific FIDIC book applied should not, by itself, be the sole determining factor in assessing the technical competence of personnel. Furthermore, Sections 4.2(a) and 4.2(b) of the RFP indicate that similar corporate experience is not limited to FIDIC Yellow Book / Gold Book projects and that comparable projects executed under Design & Build arrangements may also be accepted. In this context, provided that the candidate possesses the required technical, construction, coordination, and contract management experience for the relevant position, it is considered appropriate, in terms of preserving competition and broadening the pool of qualified candidates, to also recognize experience gained on large-scale infrastructure and/or railway projects executed under FIDIC Red Book, Design & Build, EPC, contracts governed by Laws No. 4734/4735, or other similar/equivalent contractual models as satisfying the FIDIC Yellow Book / Gold Book experience requirement. Accordingly, we kindly request confirmation that such experience may be accepted as meeting the FIDIC Yellow Book / Gold Book experience requirement. | The requested broad equivalence is not accepted. For Items 1 and 2, the RFP expressly requires the specified experience on railway-system contracts using FIDIC Yellow Book or FIDIC Gold Book Conditions of Contract. Experience under FIDIC Red Book, Silver Book, EPC, BOT, Laws No. 4734/4735 or other contractual models may demonstrate general professional competence but does not substitute for the stated Yellow/Gold Book requirement unless the RFP is formally amended. | No
847 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Item 5 – Topographical Engineer | For the Topographical Engineer position, the RFP requires a “Bachelor’s Degree in Survey or Topographical Engineering.” In Türkiye, this discipline has historically been offered under different program titles, including Cadastral and Surveying Engineering, Geodesy and Photogrammetry Engineering, Geomatics Engineering, and Surveying Engineering. In this regard, the Higher Education Executive Board, by its decision dated 22.04.2009, recognized Geodesy and Photogrammetry Engineering, Surveying Engineering, and Geomatics Engineering as equivalent programs. This equivalency was also taken into consideration in the decision of the 8th Chamber of the Council of State, E:2015/5466, K:2015/6682. Accordingly, we kindly request confirmation that bachelor’s degrees obtained from such equivalent engineering programs shall be accepted as meeting the requirement, without requiring the exact diploma title “Survey Engineering” or “Topographical Engineering.” | Item 5 requires a Bachelor’s Degree in Survey or Topographical Engineering. The RFP does not provide a separate list of alternative Turkish diploma titles that are automatically deemed acceptable. Where the diploma title differs from the wording of the criterion, the Proposer may submit official evidence that the degree is formally equivalent to Survey/Topographical Engineering, and the Employer will assess the submitted evidence against the qualification criterion. The candidate must also meet the specified relevant and overall experience requirements. | No
848 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Item 8 – Architect; Section VII – Lot-Specific Station Scope | For Lots 1 and 4, passenger station works are expressly included within the respective Lot scopes, whereas no passenger station is identified within the specific scope of Lots 2 and 3. Accordingly, in order to align the personnel requirements with the actual scope of works, we kindly request that the Architect position be removed for Lots 2 and 3. Kindly confirm whether the Architect position may be removed for Lots 2 and 3. | The request is not accepted. Section III expressly requires one Architect for each of Lots 1, 2, 3 and 4. The Architect requirement is not limited only to Lots containing passenger stations, because architectural/interface requirements may also arise from other buildings, operational structures and facilities within the Works. The minimum Key Personnel requirement shall therefore remain as stated. | No
849 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Item 9 – Geotechnical Engineer | For the Geotechnical Engineer position, the academic qualification requirement is stated as a “Bachelor’s Degree in Civil Engineering and a Master’s Degree in Geotechnical Engineering.” Considering the scope of the works, including ground, geological and geophysical investigations and assessments, it is considered that graduates holding a Bachelor’s Degree in Geological Engineering or Geophysical Engineering may also possess the relevant technical background for the position, provided that they meet the required professional experience criteria. This is also supported by the academic classifications of the Council of Higher Education of Türkiye (YÖK) in fields such as Geotechnics, Engineering Geology, Rock Mechanics, Applied Geology and Applied Geophysics; by the content related to geomechanics, statics, strength of materials, soils and engineering structures included in the Geological and Geophysical Engineering education criteria of MÜDEK; and by the roles assigned to Civil, Geological and Geophysical Engineers under Türkiye’s regulations governing soil and foundation investigations. Accordingly, we kindly request confirmation as to whether candidates holding a Bachelor’s Degree in Geological Engineering or Geophysical Engineering and meeting the relevant professional experience requirements may also be considered eligible for the Geotechnical Engineer position. | The request is not accepted. For the Geotechnical Engineer position, the RFP expressly requires a Bachelor’s Degree in Civil Engineering together with an MSc in Geotechnical Engineering. Accordingly, a Bachelor’s Degree in Geological Engineering or Geophysical Engineering does not satisfy the stated minimum academic qualification for this position, even where the candidate has relevant geotechnical experience. The Proposer may propose geologists, geophysicists or other specialists for other relevant functions where permitted by the RFP, but the minimum qualification requirement for the Geotechnical Engineer shall remain as stated. | No
850 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Items 10–11 – Environmental and Social Manager / Environmental Specialists | For the Environmental and Social Manager position, the academic qualification requirement is stated as a “Bachelor’s Degree in Environmental Engineering, Social Sciences or a related discipline,” while for the Environmental Specialists position, it is stated as a “Bachelor’s Degree in Environmental Engineering.” Considering the multidisciplinary nature of environmental management and assessment activities, it is considered that other relevant environmental and natural science disciplines may also provide an appropriate academic background. In this respect, the classifications of the Council of Higher Education of Türkiye (YÖK) include Environmental Sciences and Management, as well as fields such as ecology, Environmental Impact Assessment (EIA), climate change and environmental management, within the broader environmental sciences framework. MÜDEK criteria for Environmental Engineering education also cover interdisciplinary subjects such as biology, ecology, earth sciences, sustainability and environmental impact assessment. Furthermore, under the EIA practices of the Ministry of Environment, Urbanization and Climate Change of Türkiye, graduates of Biology, Geological Engineering and other relevant engineering and natural science disciplines, in addition to Environmental Engineers, may take part in EIA studies. Accordingly, we kindly request confirmation that candidates holding a Bachelor’s Degree in Environmental Science, Environmental Management, Biology, Geological Engineering, Ecology, or another directly related/equivalent environmental discipline, and meeting the required Environmental / Environmental and Social experience criteria, will also be considered eligible for the Environmental and Social Manager and Environmental Specialists positions. | The two positions shall be assessed separately in accordance with their respective qualification requirements. For the Environmental and Social Manager, the RFP requires a Bachelor’s Degree in Environmental Engineering, Social Sciences or a related discipline. Accordingly, another academic discipline may be considered where the Proposer demonstrates that it is directly relevant to the environmental and social responsibilities of the position, provided that the candidate also meets the required ten (10) years of relevant Environmental and Social experience in the construction of large works and fifteen (15) years of overall professional experience. For the Environmental Specialists, however, the RFP specifically requires a Bachelor’s Degree in Environmental Engineering and does not provide for “related” or “equivalent” disciplines. Accordingly, degrees in Environmental Science, Environmental Management, Biology, Geological Engineering, Ecology or other disciplines cannot be confirmed as satisfying this academic requirement under the current RFP. The qualification requirements remain as stated. | No
851 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Item 12 – Social Specialist | For the Social Specialist position, the requirement is stated as “8 years of relevant Social experience in the construction of large works.” It is understood that “relevant Social experience” is not limited solely to experience gained under the title of “Social Specialist”, but may also include responsibilities undertaken on large-scale projects in areas such as stakeholder engagement, community relations, social impact assessment, land acquisition and resettlement, grievance management, public consultation, and other similar social- related activities. In this regard, the Council of Higher Education of Türkiye (YÖK) classifications place fields such as social work, social policy, social psychology, anthropology, and sociology within the same broader academic framework, while the EIA practices of the Ministry of Environment, Urbanization and Climate Change of Türkiye cover social impacts, stakeholder engagement, public participation, and grievance mechanisms. Furthermore, in major infrastructure projects implemented by İLBANK and AYGM, the responsibilities of roles such as Social Specialist, Stakeholder Engagement Specialist, and Community Relations personnel overlap in areas including stakeholder engagement, grievance management, land acquisition/resettlement, and social risk management. Accordingly, we kindly request confirmation that candidates who have actually performed such social- related responsibilities on large-scale construction projects may have their experience accepted as “relevant Social experience” regardless of their job title. | Confirmed. The assessment of “relevant Social experience” will be based on the substance of the candidate’s actual duties and responsibilities and is not limited to experience gained under the specific job title of “Social Specialist”. Experience gained in the construction of large works in areas such as stakeholder engagement, community relations, social impact assessment, land acquisition and resettlement, grievance management, public consultation and other comparable social-risk management functions may be considered as relevant Social experience, provided that such experience is adequately demonstrated. The candidate shall also meet the academic qualification requirement and the minimum requirement of eight (8) years of relevant Social experience in the construction of large works and twelve (12) years of overall professional experience. | No
852 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Items 13, 18, 19 and 20 – Specialist Personnel | Considering that the positions of Resettlement and Livelihood Restoration Specialists, Biodiversity & Ecology Specialist, Archaeologist / Cultural Heritage Expert, and Gender and SEA/SH Specialist require specialized expertise and project-specific professional services, we understand that such services may be provided through specialized consultancy firms and/or subcontractors operating in the relevant fields. In this context, we kindly request confirmation that the relevant experts are not required to be directly employed on the Bidder’s payroll and that it would be sufficient and acceptable, at the tender stage, to demonstrate through a Declaration, Commitment Letter, Letter of Intent, or similar binding undertaking document that suitably qualified personnel meeting the academic and professional requirements specified in the RFP for each position will be made available throughout the project period. | The RFP does not require the listed Key Personnel to be direct payroll employees of the Proposer. Such personnel may be engaged through appropriate employment, consultancy or other contractual arrangements, provided that the arrangements comply with the RFP and the Contract. However, at Proposal stage, a general undertaking by a consultancy firm, subcontractor or other entity to provide suitably qualified personnel at a later stage is not sufficient. The Proposer shall identify the proposed individuals for each Key Personnel position, include them in Form PER-1 and the required resource schedule, and submit Form PER-2 for each proposed individual, including the individual’s signed declaration confirming availability and time commitment for the position. The proposed individuals shall meet the applicable academic and professional qualification requirements. In addition, the Resettlement and Livelihood Restoration Specialist, Biodiversity & Ecology Specialist, Archaeologist / Cultural Heritage Expert, and Gender and SEA/SH Specialist are required to be engaged on a full-time basis in accordance with the Employer’s Requirements. The Contractor remains responsible for their mobilization, continuous availability and performance under the Contract. | No
853 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Item 20 – Gender and SEA/SH Specialist | Law is among the accepted academic disciplines for the Gender and SEA/SH Specialist position. In this context, we understand that experience gained by Legal and Human Resources professionals working at head office and/or project level in areas such as gender-related matters, SEA/SH, discrimination, workplace conduct, employee grievances and complaints, disciplinary matters, workplace investigations, employee relations, ethics and compliance, Code of Conduct, equal opportunity, and similar matters may be considered as “relevant Gender and SEA/SH experience”, without necessarily having been acquired under a specific project or infrastructure work. These matters are considered to form part of the activities that may typically be handled by Legal and Human Resources functions, including labour law, employee relations, grievance/complaint management, disciplinary processes, workplace investigations, ethics, compliance, and equal opportunity. Accordingly, we kindly request confirmation that candidates holding a Bachelor’s Degree in Law, Human Resources Management, Psychology, Sociology, Labour Economics and Industrial Relations, Business Administration, or another related/equivalent discipline, and having demonstrable experience in the above areas together with the other experience requirements specified for the position, may be considered eligible for the Gender and SEA/SH Specialist position. | Relevant Gender and SEA/SH experience will be assessed on the actual duties performed rather than the candidate’s job title. Experience gained in legal, HR, ethics/compliance or comparable functions may be considered where the candidate can demonstrate substantive responsibilities directly relevant to gender, SEA/SH prevention/response, discrimination, grievances, workplace conduct, investigations, Code of Conduct and equal opportunity. The candidate must also hold an academic qualification falling within the disciplines permitted by the RFP (or an acceptable related/equivalent discipline) and meet the required relevant and overall experience. General HR or legal experience that is not demonstrably related to Gender/SEA/SH will not be sufficient. | No
854 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Item 14 – OHS Manager | For the OHS Manager position, the requirement is stated as “10 years relevant OHS experience in construction of large works contracts, SIF prevention protocols for tunnelling.” We understand that the entire 10 years of relevant OHS experience is not required to have been gained exclusively on tunnelling projects or specifically in connection with SIF prevention protocols for tunnelling. Rather, it would be sufficient for the candidate to have the required 10 years of OHS experience in construction of large works contracts, together with demonstrable experience in SIF prevention protocols related to tunnelling activities. Kindly confirm whether our understanding is correct. | Confirmed. The requirement is for ten (10) years of relevant OHS experience in the construction of large works contracts, together with demonstrable experience in SIF prevention protocols for tunnelling, as well as fifteen (15) years of overall professional experience. The RFP does not require the entire ten-year period of relevant OHS experience to have been gained exclusively on tunnelling projects. However, the Proposer shall separately demonstrate that the proposed OHS Manager has relevant experience in SIF prevention protocols applicable to tunnelling activities. | No
855 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Item 43 – Airport Interface Coordinator | For the Airport Interface Coordinator position, the requirements are stated as “Bachelor’s Degree in Engineering, Aviation Management or related discipline” and “3 years relevant coordination experience in airport operational environments.” In this context, we kindly request confirmation that a Bachelor’s Degree in Business Administration may be considered within the scope of a “related discipline”, and that candidates holding such a degree who have gained extensive and demonstrable professional experience throughout their careers in airport operations and operational processes, operational planning, coordination, airport control center activities, and coordination of related airport operations, and who meet the specified relevant experience and overall professional experience requirements, may be considered eligible for the Airport Interface Coordinator position. | A Bachelor’s Degree in Business Administration may be considered under the term “related discipline” where the Proposer demonstrates that the academic background is relevant to the Airport Interface Coordinator role. However, such acceptance is not automatic and will be assessed together with the supporting academic documentation submitted with the Proposal. The candidate must also independently satisfy the minimum requirement of three years of relevant coordination experience in airport operational environments and ten years of overall professional experience. Relevant professional experience does not, by itself, replace the academic qualification requirement. | No
856 | Section VII – Employer’s Requirements / Clauses 5.8.2–5.8.3 – Lot 4 / Istanbul Airport / Tunnels 19-C and 20-A; Section IV – Lot 4 / Activity 7 – Structural Works: Tunnels | A. We kindly request confirmation as to whether the T19c and T20a NATM main tunnels, located on both sides of the existing Istanbul Airport Station, have already been completed and whether the construction works related to these tunnels are included within the scope of this Contract. In the event that the said tunnels have not yet been completed and their construction is envisaged within the scope of this Contract, we kindly request clarification on the following matters: B. Considering the shallow overburden, close proximity of the T19c and T20a NATM main tunnels to each other, and their location beneath the operational areas of the airport, please clarify: i. whether any interruption, restriction, or specific working window is envisaged for airport operations; ii. if airport operations are required to continue uninterrupted, whether any specific construction methodology, sequencing, or protection measures are expected to be implemented by the Contractor; and iii. whether there are any specific technical, safety, monitoring, operational coordination, or other related requirements to be taken into account during construction. | The RFP does not identify Tunnel-19-C or Tunnel-20-A as completed or excluded existing works. On the contrary, Section VII, Clause 5.8.3 lists Tunnel-19-C (NATM, approximately Ch. 31+352–31+552) and Tunnel-20-A (NATM, approximately Ch. 0+631–0+804) in the indicative Lot 4 tunnel structure list; they shall therefore be treated as included in the Lot 4 scope. The Contractor shall verify the existing conditions and interfaces and develop the necessary Detailed Design, construction methodology, sequencing, temporary works, settlement/deformation monitoring, protection, access and safety measures. Works within the airport environment shall be coordinated with the airport operator and relevant authorities in accordance with the airport-interface requirements. The RFP does not establish through this clarification a guaranteed airport shutdown, restriction or working-window entitlement. | No
857 | Section II – Proposal Data Sheet (PDS) / ITP 16.1(b) and ITP 38.1; Section IV – Table C – Summary of Payment Currencies | Under Alternative A, the Proposal Price is quoted entirely in TRY. However, PDS ITP 16.1(b) allows each Proposer to specify its own exchange rates in Table C, while PDS ITP 38.1 requires the resulting foreign currency portions to be reconverted into TRY using the CBRT selling exchange rates applicable on the Proposal submission deadline for evaluation and comparison purposes. As a result, the evaluated Proposal Price may differ from the TRY Proposal Price submitted by the Proposer and may depend on exchange rates applicable on a future date which are not known at the time the Proposal is being prepared. In order to ensure a consistent, transparent and predictable basis for evaluation among all Proposers, please specify a common exchange rate source and a reference date known to all Proposers sufficiently in advance of the Proposal submission deadline, to be used for the exchange rates entered in Table C and for the evaluation of Proposals. For example, the applicable rates may be based on the Base Date or another fixed date notified by the Employer in advance, such as fourteen (14) days prior to the Proposal submission deadline, so that all Proposers can determine the exchange rates to be used and calculate the resulting evaluated Proposal Price when preparing their Proposals. | The requested change to a fixed advance reference date is not accepted. Under ITP 16.1(b), the Proposer shall specify in Table C the exchange rates used to determine the local-currency equivalent and the corresponding payment-currency percentages. Those exchange rates shall apply for Contract payments in accordance with ITP 16.1. For Proposal evaluation and comparison, ITP 38.1 separately provides that the corrected Proposal Price shall first be broken down into the respective payment currencies using the exchange rates specified by the Proposer under ITP 16.1, and that those amounts shall then be converted into Turkish Lira using the CBRT selling exchange rates applicable on the Proposal submission deadline. Accordingly, the exchange-rate methodology and reference date for evaluation shall remain as specified in ITP 38.1. No alternative advance reference date will be introduced. | No
858 | General / Particular Conditions / Sub-Clause 14.15 – Currencies of Payment; Section IV – Table C – Summary of Payment Currencies; Section II – PDS / ITP 16.1 | With reference to Particular Conditions Sub-Clause 14.15, please confirm that the term “Schedule of Payment Currencies” refers to “Table C – Summary of Payment Currencies” included in the Appendix to Proposal. If not, please identify the document or schedule referred to as the “Schedule of Payment Currencies” and clarify where it is provided in the RFP. | Confirmed. For the purposes of Sub-Clause 14.15, the term “Schedule of Payment Currencies” refers to the completed Appendix to Proposal – Table C, “Summary of Payment Currencies”, which forms part of the completed Schedules under the Contract. No separate additional Schedule of Payment Currencies is provided or intended under the RFP. | No
859 | Section II – PDS / ITP 15.8 and ITP 16.1; Section IV – Schedule of Cost Indexation / Table C; GC Sub-Clauses 13.7, 14.3, 14.7 and 14.15; PDS ITP 49.1(b) – VAT | With reference to PDS ITP 16.1, Table C – Summary of Payment Currencies, GC Sub-Clauses 13.7, 14.3, 14.7 and 14.15 and PC Sub-Clause 14.15, please confirm our understanding of the payment calculation and payment procedure under the Contract as follows: (i) for each monthly payment period, the value of the Works executed shall first be determined based on the progress achieved against the relevant priced Activities and Sub-activities; (ii) the resulting value of the Works executed shall then be allocated among the payment currencies in accordance with the percentages stated in Table C; (iii) the portion allocated to each foreign payment currency shall be converted from its TRY equivalent into the relevant foreign currency using the fixed exchange rate specified by the Proposer for that currency in Table C; (iv) the applicable price adjustment under Sub-Clause 13.7 and the Schedule of Cost Indexation shall be calculated and paid separately for each payment currency; and (v) subject to the other applicable additions and deductions under Sub-Clause 14.3, the resulting amounts shall be certified and paid in the respective payment currencies. Please confirm whether the above calculation sequence is correct. If not, please specify the applicable calculation methodology and sequence. Please also confirm that, where Table C includes TRY and three foreign currencies, the Contractor shall issue four separate invoices, one for each payment currency, and that each invoiced amount will be paid separately in the relevant currency to the Contractor’s bank account designated for that currency. Please further clarify whether the VAT applicable to each payment currency component shall be invoiced and paid in the same respective currency, or whether VAT shall be invoiced and paid entirely in TRY. If a different invoicing or payment procedure is intended, please specify the applicable procedure. | The payment and currency arrangements shall be applied in accordance with PDS ITP 16.1, Table C – Summary of Payment Currencies, Sub-Clause 13.7 and the Schedule of Cost Indexation, and Clause 14 of the Conditions of Contract. The Schedule of Priced Activities and Sub-activities is expressed in Turkish Lira, while Table C establishes the contractual payment currencies, the applicable proportions and the exchange rates specified by the Proposer. In accordance with ITP 16.1, those exchange rates shall apply for Contract payments. Price adjustment shall be calculated in accordance with Sub-Clause 13.7 and the applicable Table(s) of Adjustment Data for the relevant currency of payment. Payments shall be certified and made in accordance with Clause 14 and the Schedule of Payment Currencies, subject to the applicable additions, deductions, retentions and other contractual adjustments. The RFP does not prescribe a separate detailed calculation sequence beyond the above contractual provisions, nor does it require the Contractor to issue exactly one separate invoice for each payment currency or specify separate bank accounts for each currency. Similarly, while the RFP provides for VAT to be included in the Contract Price in accordance with the applicable VAT rate, it does not prescribe a specific currency or invoicing mechanism for VAT in the circumstances described. The applicable requirements shall therefore be governed by the Contract and applicable Turkish legislation. No additional invoicing or VAT-currency requirement is introduced through this clarification. | No
860 | General Conditions / Clause 13 and Sub-Clause 13.7 – Variations / Cost Adjustment; Sub-Clauses 19.1 and 19.2.1 – Insurance for the Works; Contract Data / Sub-Clause 19.2.1(b) | Please clarify whether, throughout the period of insurance under Sub-Clause 19.2.1, the sum insured under Sub-Clause 19.2.1 shall be adjusted so as to reflect increases in the full replacement value of the Works resulting from: (i) Variations under Clause 13 [Variations and Adjustments]; (ii) cost escalation under Sub-Clause 13.7 [Adjustments for Changes in Cost]; and (iii) other increases in the actual cost of reinstating or replacing the Works during the Contract period. Considering the scale and risk profile of the Works, particularly the extensive tunnel and underground structures, including TBM excavation and associated works, such increases in replacement value may have a material impact on the required insurance coverage and related premium. If such adjustment is required, please specify the applicable adjustment/revaluation mechanism and the frequency at which the insured value is required to be updated. | The insurance under Sub-Clause 19.2.1 shall at all times comply with the replacement-value requirement under the Contract, including the additional amount specified in the Contract Data, namely 20% of the replacement value of the Works. Accordingly, where the replacement value of the Works changes during the required insurance period, including as a result of Variations or other changes affecting the value of reinstatement or replacement, the insured amount shall be adjusted as necessary to maintain the level of cover required under Sub-Clause 19.2.1. The RFP does not prescribe a separate fixed revaluation formula or periodic revaluation frequency for this purpose. Compliance shall therefore be maintained throughout the applicable insurance period in accordance with Sub-Clause 19.2.1 and the Contract Data | No
861 | Section III – Evaluation and Qualification Criteria / Item 4.2(b) – Key Activities | Under Section III – Evaluation and Qualification Criteria, Clause 4.2(b), the Key Activities are defined separately and an experience requirement ‘under a single contract’ is specified for each activity. Accordingly, we understand that each Key Activity may be demonstrated by a different reference contract that independently satisfies the requirements applicable to that activity, and that all Key Activities required for a Lot are not required to have been performed under the same reference contract. We kind ly request clarification as to whether our understanding is correct. | Confirmed. The Key Activities under Clause 4.2(b) constitute separate qualification requirements and may be demonstrated by different reference contract(s). The RFP does not require all Key Activities applicable to a Lot to have been performed under one and the same reference contract. For each individual Key Activity, the specific requirements stated in Clause 4.2(b), including any requirement for experience “under a single contract” and the applicable footnotes concerning the demonstration of volume, number or rate of production, shall apply. Accordingly, different Key Activities may be supported by different qualifying reference contracts, subject to the requirements applicable to each respective Key Activity. | No
862 | Section II – Proposal Data Sheet (PDS) / ITP 1.1 – Lot-Wise Bidding; Section III – Multiple Contracts / ITP 40.3 | Under Section II – Proposal Data Sheet, ITP 1.1, Proposals are submitted and evaluated on a lot -wise basis. When read together with Section III – Evaluation and Qualification Criteria, ‘Multiple Contracts (ITP 40.3)’, we understand that a Proposer’s failure to satisfy the cumulative qualification requirements for all Lots for which it has submitted Proposals would not result in the rejection of its Proposals for the individual Lots for which it is separately qualified. In this context, we kindly request confirmation of the following: • Qualification will be assessed separately for each Lot and a Proposal meeting the requirements of the relevant Lot will remain valid. • The cumulative qualification requirement will be applied at the stage of determining the combination of Lots that the Proposer may be awarded. • If the Proposer does not meet the cumulative requirement for all Lots for which it has submitted Proposals, all of its Proposals will not be rejected; contract allocation will be made, in accordance with the evaluation method set out in the RFP Documents , among the Lot or combination of Lots for which the Proposer is qualified. | Confirmed. Qualification will be assessed in relation to each individual Lot. Where a Proposer is considered for award of more than one Lot, the cumulative qualification requirements specified under the Multiple Contracts provisions of Section III shall be applied to determine the combination of Lots for which the Proposer is qualified. Failure to satisfy the cumulative qualification requirements for all Lots for which Proposals have been submitted shall not, by itself, result in rejection of an otherwise substantially responsive Proposal for an individual Lot for which the Proposer satisfies the applicable qualification requirements. Where the Proposer is not qualified for the combination of all Lots for which it would otherwise be considered for award, the contract award shall be determined, in accordance with ITP 40.3 and Section III, on the basis of the highest total score for the combination of Lots for which the Proposer is qualified. | No
863 | Section III – Evaluation and Qualification Criteria / Item 4.2(a) – Specific Construction & Contract Management Experience | Under Section III – Evaluation and Qualification Criteria, Clause 4.2(a), similar work experience may be demonstrated, for infrastructure works, through light rail, metro, mainline railway or highway projects, and, for railway superstructure works, through light rail, metro and/or mainline railway projects. However, the portion of the total contract value required for the relevant Lot that must be derived directly from railway projects is not separately defined. Considering that the Works predominantly comprise railway infrastructure, railway superstructure and electrification works, and in order to ensure that similar work experience is assessed in closer alignment with the scope of the Project, we request that t he references submitted under Clause 4.2(a) be accepted in accordance with the following principles: • Where the similar work experience is demonstrated by one contract, the submitted reference shall be a railway project. • Where the similar work experience is demonstrated by two contracts, at least one contract shall be a railway project and the reference with the higher contract value shall be a railway project, while the other reference may be one of the other linear transport infrastructure projects accepted under Clause 4.2(a). • Where the similar work experience is demonstrated by three contracts, the two references with the highest contract values shall be railway projects, while the third reference may be one of the other linear transport infrastructure projects accepted under Clause 4.2(a). In this context, we kindly request that the above principles be applied under Clause 4.2(a). | The requested additional restrictions are not accepted. Under Clause 4.2(a), the Proposer is already required to demonstrate both (a) the specified infrastructure works and (b) the specified railway superstructure works. These requirements may be demonstrated by the same contract or by separate qualifying contracts, subject to the applicable contract-value and number-of-contract requirements stated in the RFP. Where separate contracts are relied upon, the reference contract(s) used to demonstrate the railway superstructure requirement shall necessarily relate to light rail, metro and/or mainline railway works, as expressly required under Clause 4.2(a). However, the RFP does not require that the highest-value reference contract, or any specified proportion of the aggregate value of the submitted references, be attributable to railway projects. Accordingly, no additional ranking, proportional-value or allocation requirement will be introduced beyond the requirements already stated in Clause 4.2(a). | No
864 | Section III – Evaluation and Qualification Criteria / Item 4.2(a) – JV Similar Work Experience | Under Section III – Evaluation and Qualification Criteria, Clause 4.2(a), the Specific Construction & Contract Management Experience requirement for a JV may be satisfied collectively by the JV members; however, no separate minimum railway similar work experience requirement is defined for each JV member. Considering the scale, technical complexity and railway -oriented nature of the Works, we kindly request the Employer’s view on whether requiring the other JV members to demonstrate railway project experience at a specified minimum level may be considered i n order to ensure a more balanced distribution of technical capability among the JV members. | The request is not accepted. Under Section III, Sub-Factor 4.2(a), the Specific Construction & Contract Management Experience requirement for a Joint Venture shall be satisfied collectively by the JV members in accordance with the stated JV compliance requirements. No separate minimum similar railway-project experience requirement is prescribed for each individual JV member. Accordingly, no additional experience requirement will be introduced for individual JV members beyond those expressly stated in Section III. The requirements of Sub-Factor 4.2(a), including the applicable requirements concerning the qualifying reference contracts, shall remain as specified in the RFP. | No
865 | Section III – Evaluation and Qualification Criteria / Item 4.2(b) – Railway Route-Length Experience | Under Section III – Evaluation and Qualification Criteria, Clause 4.2(b), we understand that the requirement for “experience in the construction of a railway line with a route length of at least 20 km” refers to the railway route length, irrespective of th e number of tracks, rather than the total track length. We kindly request your confirmation. | Confirmed. Where the criterion refers to a railway line with a ‘route length’ of at least 20 km, the stated length is the route length of the railway alignment and is not multiplied by the number of parallel tracks. The reference must otherwise satisfy all requirements of the applicable Key Activity criterion. | No
866 | Section III – Evaluation and Qualification Criteria / Item 1.4 / Item 1 – Project Manager | Under Section III – Evaluation and Qualification Criteria, the Project Manager is required to have served as Project Manager under two separate contracts for the construction of railway systems, and such contracts are required to have been implemented under the FIDIC Yellow Book or FIDIC Gold Book conditions. Considering that under EPC/Turnkey contracts implemented under the FIDIC Silver Book, responsibility for design, construction, system integration and completion is undertaken by the Contractor in an integrated manner, we understand that Project Manager exp erience gained on railway system projects implemented under the FIDIC Silver Book will also be considered equivalent to experience gained under the FIDIC Yellow Book and Gold Book, as the Silver Book entails a broader and more comprehensive level of contra ctor management, coordination and responsibility than the Yellow Book. Furthermore, instead of the requirement for experience under two separate contracts, we kindly request your confirmation that, provided all other experience and qualification requirements are satisfied, experience gained as Project Manager under at least o ne railway system contract implemented under the FIDIC Yellow Book, Gold Book or Silver Book will be accepted as sufficient. | The request is not accepted. The RFP expressly requires the proposed Project Manager to have served as Project Manager on two contracts for the construction of railway systems implemented under the FIDIC Yellow Book or FIDIC Gold Book Conditions of Contract. Experience gained under the FIDIC Silver Book or other EPC/Turnkey contractual arrangements will not be considered as satisfying this specific requirement. Likewise, experience under only one qualifying contract does not meet the requirement for two contracts. The requirement remains unchanged. | No
867 | Section I – ITP 32.3 – Financial Opening of Responsive / Qualified Proposals; Section II – PDS / ITP 31.2; Section III – Combined Evaluation | PDS ITP 31.2 states that the Technical Proposals will be scored and that the technical evaluation will carry a weighting of 70% in the overall evaluation. However, no minimum technical score threshold to be applied for the opening of the Financial Proposals is clearly specified. In this context, in order to ensure equal treatment and transparency in the competition, we kindly request clarification as to whether the Financial Proposals of all Proposers receiving a technical score will be opened, or whether a minimum technical score must be achieved for the Financial Proposal to be opened. If a minimum technical score is to be applied, we kindly request that the applicable threshold and the evaluation principles governing the opening of the Financial Proposals be specified. | No separate minimum numerical technical score is specified in the RFP as a condition for opening the Financial Part. In accordance with ITP 33.3, only the Financial Parts of Proposals that are determined to be substantially responsive to the RFP and submitted by qualified Proposers shall be opened. Accordingly, the opening of the Financial Part is not subject to achievement of a separate minimum Rated Criteria score. The Technical Scores obtained under the Rated Criteria will be taken into account subsequently in the combined technical and financial evaluation in accordance with Section III. | No
868 | Section I – ITP 21.1–21.2 – Signing of Proposal / JV; Section II – PDS / ITP 12.2(i) and ITP 21.1 – JV Representative / Authority | We kindly request clarification of the scope of authority of the JV Representative to be appointed on behalf of the Joint Venture. In this context, please confirm whether the Technical and Financial Proposals are required to be signed by the duly authorize d representatives of the JV members rather than solely by the JV Representative. In addition, please clarify whether a notarized power of attorney or authorization document will be required for the JV Representative where notarization is not expressly stipulated in the RFP Documents, and whether the JV Representative must necessarily be selected from the lead member. | Under ITP 21.2, a JV Proposal shall be signed by an authorized representative of the JV on behalf of the JV and in a manner legally binding on all JV members, as evidenced by a power of attorney signed by the legally authorized representatives of the JV members. Accordingly, separate signatures of each JV member on every Technical and Financial Proposal document are not required, provided that the person signing the Proposal has been duly authorized in accordance with ITP 21.1 and ITP 21.2. With respect to the JV Representative, the RFP shall be read together with PDS ITP 12.2(i), which requires the JV Agreement to nominate a lead member having the authority to lead and bind the JV and to conduct all business for and on behalf of all JV members during the procurement process and, if awarded, during Contract execution. The JV Representative shall therefore be duly authorized consistently with this arrangement. The RFP requires the relevant authorization/power of attorney to be in writing. No separate notarization requirement is stipulated in the RFP; therefore, no additional notarization requirement is introduced through this clarification, without prejudice to any requirements of applicable law. | No
869 | Section II – Proposal Data Sheet (PDS) / ITP 1.1 – Multiple Lots; ITP 22.1(b) – Proposal Copies / Packaging | Under Section II – Proposal Data Sheet, ITP 1.1, Proposers may submit Proposals for one or more Lots and the Proposals will be evaluated on a lot-wise basis. PDS ITP 22.1(b) defines the submission arrangements for the printed and digital copies of the Technical and Financial Proposals. In order to ensure that the Lots are evaluated independently and separately, we understand that, where Proposals are submitted for more than one Lot, a completely separate and self -contained Proposal package shall be prepared for each Lot; the Technical Proposal and Financial Proposal for each Lot shall be placed in separate envelopes together with the relevant printed and USB copies, and each Lot shall be submitted in a separate lot -specific outer envelope. We kindly request clarification that each Lot sha ll be submitted as a separate Proposal file independent from the other Lots. | The understanding that each Lot must be submitted in a completely separate outer Proposal package is not confirmed. A Proposer may submit one Proposal covering one or more Lots, provided that the submission complies with ITP 22 and that all Lot-specific Technical and Financial forms, schedules and evidence are clearly identified and separately completed for each Lot. The Technical Part and Financial Part shall remain in the separate envelopes required by the RFP, together with the required copies/USBs. | No
870 | Section II – Proposal Data Sheet (PDS) / ITP 14.1 – Alternative Proposals; ITP 16.1 and ITP 38.1 – Currency Methodology; Section IV – Table C | We understand that, under ITP 14.1, alternative Proposals are not permitted, whereas ‘Alternative A’ under ITP 16.1 constitutes the methodology applicable to Proposal and payment currencies. Accordingly, the Proposal Price will be submitted entirely in Tur kish Lira, while Table C will indicate the distribution of the Proposal Price between Turkish Lira and foreign currencies for payment purposes. When read together with ITP 38.1, we understand that, for financial evaluation purposes, the Proposal Price will first be apportioned among the payment currencies stated in Table C using the exchange rates specified by the Proposer, and that the resulting foreign currency amounts will subsequently be converted back into Turkish Lira using the Central Bank of the Republic of Türkiye selling rate applicable on the Proposal submission deadline. Accordingly, we understand that the Evaluated Bid Cost used for financial evaluation may differ from the total Turkish Lira Proposal Price submitted, and that the Evaluated Bid Cost calculated in this manner will be used for comparison of the Financial Proposals. We kindly request clarification of this matter. | Confirmed. ‘Alternative A’ in ITP 16.1 is the prescribed Proposal/payment-currency mechanism and is unrelated to alternative technical Proposals under ITP 14.1. The Schedule of Priced Activities is quoted entirely in Turkish Lira. Table C identifies the contractual payment-currency portions and the exchange rates used by the Proposer for that allocation. For evaluation, ITP 38.1 requires the Employer to break down the corrected Proposal Price into the payment currencies and then convert those amounts to Turkish Lira using the CBRT selling rates on the Proposal submission deadline. Accordingly, the evaluated cost used for comparison may differ from the nominal Turkish Lira Proposal Price as a consequence of the prescribed conversion methodology. | No
871 | Section III – Evaluation of Technical Part / Factor 3 – Similar Work Experience | Under Section III – Evaluation and Qualification Criteria, it is understood that the evaluation under Factor 3 – Similar Project Experience is not limited solely to the reference contracts submitted for qualification purposes under Clauses 4.1 and 4.2. In this context, in addition to the references submitted to satisfy the qualification criteria, may the Proposer submit additional similar projects and reference contracts meeting the relevant scoring criteria for evaluation under Factor 3? | Confirmed. For the purpose of evaluation and scoring under Factor 3 – Similar Work Experience, the Proposer shall submit and clearly identify in its Technical Proposal all project references on which it intends to rely for the Rated Criteria. These references are not limited to the contracts submitted for qualification purposes under Section III, Sub-Factors 4.1 and 4.2. Accordingly, the Proposer shall also submit any additional similar project references that it wishes to have considered for scoring under Factor 3, together with the relevant verifiable supporting evidence. References submitted for qualification purposes may also be considered under Factor 3 where they satisfy the applicable Rated Criteria requirements and are clearly identified for that purpose. The qualification assessment and the Rated Criteria evaluation are separate assessments and shall be carried out in accordance with their respective requirements under Section III. | No
872 | Section III – Evaluation of Technical Part / Factors 3.1–3.3 – Similar Work Experience / Completion Threshold | Under Section III – Evaluation and Qualification Criteria, Factor 3 – Similar Work Experience, it is expressly stated that a reference project submitted under Factor 3.1 shall be at least 80% complete. However, the same completion percentage is not separately stated for Factors 3.2 and 3.3. In this context, will the minimum 80% completion requirement also apply to reference projects submitted under Factors 3.2 and 3.3? | The 80% completion threshold applies where it is expressly stated, namely Factor 3.1. Factors 3.2 and 3.3 shall be evaluated in accordance with their own stated wording and evidence requirements; an unstated 80% completion threshold will not be added to those sub-factors through clarification. Where evidence from an ongoing project is relied upon, it must nevertheless be sufficiently developed, relevant and verifiable to demonstrate the experience/performance claimed. | No
873 | General Conditions / Sub-Clause 14.5 – Plant and Materials Intended for the Works; Section IX – Contract Data / Payment Provisions | Considering that FIDIC Yellow Book Sub -Clause 14.5 allows payment for Plant and Materials, we kindly request confirmation that the following critical materials and equipment will be eligible for payment at the manufacturing/procurement, shipment and/or delivery-to-Site stages, subject to satisfaction of the required ownership, insurance, storage, documentation and security/guarantee conditions: • Reinforcing steel • Precast concrete segments and sleepers • Prestressed/post-tensioned beams and stressing systems • Rails • Rail fastening systems • Railway switches, turnouts and crossing components • Main equipment and materials for electrification, traction power, catenary and other electromechanical systems In addition, we kindly request confirmation that materials and equipment securely stored off Site may also be eligible for such payment against appropriate documentation and guarantees, and that the applicable payment percentage, valuation method and deduc tion/set-off principles following incorporation into the Permanent Works will be clarified by the Employer. | Please refer to Answers 288 and 816. Sub-Clause 14.5 does not make the listed materials or equipment automatically eligible for payment at manufacture/procurement, shipment, off-Site storage or delivery-to-Site stages. The RFP/Contract Data do not introduce a separate blanket list of eligible items, a special payment percentage or a new valuation/set-off mechanism for such pre-incorporation payment. Any certification under Sub-Clause 14.5 may occur only if and to the extent that the Sub-Clause and the applicable Contract Data make it applicable and all contractual conditions are satisfied. Otherwise, interim certification shall follow the priced Activities/Sub-activities and Clause 14. | No
874 | Section IV – Schedule of Cost Indexation / Table B – Foreign Currency (FC); Section II – PDS / ITP 16.1 | Under the Table of Adjustment Data – Table B (Foreign Currency (FC)), we kindly request clarification as to which official source shall be used for the foreign currency indices and/or exchange rates applicable to USD. | For Table B, the Proposer shall identify an appropriate published and verifiable source for the USD cost index/reference price applicable to each relevant cost element. The RFP does not prescribe one single official USD index for all cost elements. The base value shall be the applicable index value twenty-eight (28) days before the Proposal submission date. If the proposed index source is in doubt, it shall be determined by the Engineer in accordance with the Schedule of Cost Indexation. Exchange rates for Proposal evaluation are separately governed by ITP 38.1. | No
875 | Section VII – Employer’s Requirements / Clause 5.5.2 – Lot 1 / Viaduct-B; Section IV – Lot 1 / Activity 6 / Item 6.2 – Viaduct-B; ITP 15.1–15.2 – Lump-Sum Pricing | At the beginning of Viaduct-B located at Lot 1 KM 0+285, due to the railway crossing coinciding with the viaduct area, an approximately 60 m span viaduct deck is expected to be constructed. Under which item will the required additional support system and construction system be paid? | The required temporary/support and construction systems necessary to construct Viaduct-B in accordance with the approved Detailed Design are included in the lump-sum price of the relevant viaduct/bridge and associated civil/temporary-works activities. The Schedule of Priced Activities is not a remeasurement BOQ; any item necessary for completion that is not separately identified is deemed included in the relevant lump-sum prices. No separate additional payment arises solely because a particular support/construction method is required. | No
876 | Section VII – Employer’s Requirements / Clauses 5.5.2 and 5.9.3 – Lot 1 / TBM-1 Portal / Construction Logistics; Section IV – Lot 1 / Activities 3 and 7; ITP 15.1–15.2 | As the TBM-1 entrance portal located at Lot 1 KM 0+588 falls within the boundary of a military area, various road diversion works are expected to be required around the portal. If such works are carried out, we kindly request clarification as to whether th eir costs will be paid under the tunnel items or under the road diversion items in the Schedule of Rates/Prices. | Any temporary or permanent road-diversion/access works required for construction of the TBM-1 entrance portal and falling within the Contractor’s design/construction responsibility shall be included in the applicable lump-sum activities, whether allocated by the Proposer to the tunnel, relocation/road-diversion or ancillary/temporary-works sub-activity. The Proposer shall avoid double counting and may use the permitted additional sub-activities to show its pricing breakdown. The absence of a separate line item does not create a separate-payment entitlement. | No
877 | Section VII – Employer’s Requirements / Clauses 4.8.4, 5.6.2 and 6.5 – DSİ Interface / Lot 2 / Bridge-3; Section IV – Lot 2 / Activity 6 / Item 6.3 | Within Lot 2, Bridge -3 at KM 28+829 crosses the existing DSİ canal and its approximately 42 m -high intermediate piers are located within the canal. It is considered that, in order to construct the bridge foundations, the existing DSİ canal may need to be p artially demolished and subsequently reconstructed. In this context, we kindly request clarification as to whether obtaining the necessary permits and approvals from DSİ, as well as all works associated with demolition and reconstruction of the existing canal, will be within the Contractor’s scope and responsibility. | Yes. The Contractor is responsible for coordinating with DSİ and obtaining the approvals required for works affecting DSİ facilities. If partial demolition, diversion, protection and reconstruction of the canal is necessary to execute Bridge-3 in accordance with the approved Detailed Design, those works shall be included within the Contractor’s scope and the applicable bridge/hydraulic/utility-interface lump-sum activities. The Contractor shall maintain the required hydraulic function and comply with DSİ requirements. | No
878 | Section VII – Employer’s Requirements / Clauses 5.2 and 5.6.2 – Geotechnical Risk / Lot 2 / Tunnel-8; Section IV – Lot 2 / Activities 3, 4 and 7 | At the exit portal of Tunnel -8 located at Lot 2 KM 46+539, additional slope support and/or shoring works are expected to be required in order to ensure the stability of the cut slopes. If such works are carried out, we kindly request clarification as to whether the related payment will be made under the tunnel items or under the ground improvement items. | Slope-support, shoring and ground-stabilization measures required at the Tunnel-8 portal shall be designed and constructed by the Contractor as part of the complete portal/tunnel and earthworks/ground-improvement scope. The Schedule of Priced Activities is lump-sum; the Proposer shall allocate the price to the most appropriate tunnel/ground-improvement sub-activity in its Proposal and may use the permitted additional sub-activities. No separate entitlement arises merely because the final approved design requires additional support compared with the conceptual arrangement. | No
879 | Section VII – Employer’s Requirements / Clauses 5.7.2 and 6.6 – Lot 3 / Existing Structures and Site Conditions; Section IV – Lot 3 / Relocation / Ancillary Works | We kindly request clarification as to whether the existing truck park located at Lot 3 KM 09+600 will be removed within the scope of the Project. If it is to be removed, please specify which party will be responsible for demolition, relocation/diversion, reconstruction and similar works, and how such works will be paid if they are to be carried out by the Contractor. | The Tenderer shall verify the existing Site condition and the status of the truck park through its investigations and interface coordination. If demolition, relocation/diversion, protection or reinstatement of the truck-park facilities is required to execute the Works within the Contract scope and Site, the Contractor shall carry out the necessary works in coordination with the relevant owner/authority and include the cost in the applicable lump-sum civil/relocation/ancillary activities. Any permanent land acquisition outside the Contractor’s responsibility shall be dealt with under the Contract’s land-access/expropriation provisions. | No
880 | Section VII – Employer’s Requirements / Clauses 5.2 and 5.7.2 – Geotechnical Risk / Lot 3; Section IV – Lot 3 / Activity 4 – Soil Improvement Works | As the area around Lot 3 KM 18+400 was previously used as a fill area, it is considered that the bearing capacity of the existing ground may be insufficient. An appropriate ground improvement method is expected to be required in this section. If such works are carried out, we kindly request clarification as to whether their costs will be paid under the ground improvement items. | Ground-improvement measures required because of the actual Site conditions at approximately KM 18+400 shall be developed by the Contractor through its site investigations and approved Detailed Design. The associated work is included in the lump-sum earthworks/ground-improvement scope. The tender-stage conceptual information does not constitute a guaranteed ground baseline and does not create an additional-payment entitlement merely because improvement proves necessary. | No
881 | Section VII – Employer’s Requirements / Clauses 5.1.1, 5.8.2 and 6.1 – Lot 4 / Bridge-38 / Topographic Survey; Annex A – Drawings; Section IV – Lot 4 / Activity 6 / Item 6.7 | For Bridge-38 located between Lot 4 KM 19+180 and KM 22+100, the ground level of approximately +17.00 m shown in the plan -profile drawings around KM 20+773 does not correspond to the existing Site level of approximately +43.40 m, and a new road has been co nstructed in the area. It is therefore anticipated that the bridge vertical alignment may need to be raised, pier heights increased, and the bridge extended by moving the start chainage backward and the end chainage forward. We kindly request clarification as to how any additional payments arising from such works will be made. | The plan/profile drawings are tender-stage/conceptual information. The Contractor shall verify the existing topography, roads and Site conditions through survey and shall develop the final Bridge-38 alignment, span arrangement, pier geometry and limits in the approved Detailed Design. Adjustments required to satisfy the Employer’s Requirements and actual verified Site conditions are included within the Contractor’s lump-sum Design-Build responsibility and do not automatically create additional payment. Only an Engineer-instructed change that constitutes a Variation under Clause 13 may give rise to the corresponding contractual entitlement. | No
882 | Section IV – Schedule of Priced Activities / Minor Structures; Section VII – Lot-Specific Scope / Minor Structures and Environmental Requirements; ITP 15.1–15.2 – Lump-Sum Pricing | If additional culverts, underpasses, overpasses and ecological bridges are required, under which items will such works be paid? | Additional culverts, underpasses, overpasses and ecological bridges that are required by the Employer’s Requirements and/or the Contractor’s approved Detailed Design for completion of the Works shall be included in the relevant lump-sum civil/minor-structures and environmental/mitigation activities. The Proposer shall price the complete Works and may use the permitted additional sub-activities for its breakdown. Such design development does not constitute a separate remeasurement item. If the Engineer subsequently instructs genuinely additional work outside the contractual scope, it shall be dealt with under Clause 13 [Variations and Adjustments]. | No
883 | Section IV – Proposal Forms / Lot 1 – Activity 3 / Items 3.1, 3.3 and 3.5 – Alignment Infrastructure and Slope Stabilization | Under Schedule of Priced Activities – Lot 1, Activity 3, the start points of Items 3.1, 3.3 and 3.5 all appear to have been inadvertently stated as ‘Project Start’. Considering that the relevant open -line sections should be defined as consecutive sections along the alignment, these descriptions prevent accurate pricing of the BOQ scope without duplication. We therefore kindly request that the ‘Project Start’ descriptions in Items 3.3 and 3.5 be corrected to reflect the proper start points and that the revised BOQ be issued. | Confirmed. The repeated ‘Project Start’ wording in Lot 1 Activity 3 for Items 3.3 and 3.5 is a drafting error. The open-line sections shall be described as consecutive sections consistent with the alignment and the relevant start/end chainages. The Schedule of Priced Activities are corrected by Addendum No. 2, Amendment No. 42 to remove the duplication/ambiguity. | Yes
884 | Section IV – Proposal Forms / Lot 4 – Summary Price Table / Activity 8 – Station Works; Section VII – Clause 5.8.2 – Istanbul Airport Station | Under Schedule of Priced Activities – Lot 4 Summary Price Table, Activity 8, the station name is inadvertently stated as ‘Sabiha Gökçen Station’. The other sections of the RFP Documents clearly indicate that the station within Lot 4 is İGA Istanbul Airport / Istanbul Airport Station. We therefore kindly request that the expression ‘Sabiha Gökçen Station’ in Lot 4 Activity 8 be corrected to ‘Istanbul Airport Station’ and that the revised BOQ be issued. | Confirmed. The reference to ‘Sabiha Gökçen Station’ in the Lot 4 Summary Price Table / Activity 8 is a typographical error. The station within Lot 4 is Istanbul Airport Station. The relevant Schedule/Summary Price Table is corrected by Addendum No. 2, Amendment No. 35. | Yes
885 | Section IX – Particular Conditions / Part A – Contract Data / Sub-Clauses 1.1.86 and 1.1.95 – Time for Completion and Milestones; Addendum | The Time for Completion has been stated as the same for all four Lots. Could you please confirm this? | Confirmed. The Time for Completion is 1826 days for each of the four Lots, as stated in Contract Data Sub-Clause 1.1.86. The contractual Milestones applicable to each Lot shall be achieved within the periods stated in Contract Data Sub-Clause 1.1.95, as amended by the applicable Addendum No. 2, Amendment No. 3. | No
886 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Proposal Submission Deadline; Section I – ITP 8 – Amendment of RFP Document | Due to the comprehensive technical and financial requirements of the tender, we require additional time to prepare our proposal and compile all necessary official documents. In order to prepare a high-quality, competitive, and fully compliant bid, we kindly request the Employer to grant a 2-month extension for the final bid submission deadline. | Please refer to Addendum No. 1 regarding the revised Proposal submission deadline under PDS ITP 23.1. | No
887 | Section II – Proposal Data Sheet (PDS) / ITP 23.1 – Proposal Submission Deadline; Section I – ITP 8 – Amendment of RFP Document | Considering the Design and Build nature of the Contract under the FIDIC Plant and Design-Build Contract (Yellow Book), the preparation of a fully compliant and technically sound Tender requires substantial engineering, design development and coordination activities in addition to the preparation of the commercial proposal. Furthermore, due to the complexity and multidisciplinary nature of the Works, adequate time is required to coordinate the technical inputs, verify quantities and assumptions, assess interface requirements, and ensure that the proposed design and construction methodology are fully aligned with the Employer’s Requirements and the Tender Documents. In this regard, we believe that allowing an additional two (2) months would provide all prospective Tenderers with sufficient time to prepare complete, technically robust and competitive Tenders and would contribute to a more comprehensive and effective tender evaluation process. | Please refer to Addendum No. 1 regarding the revised Proposal submission deadline under PDS ITP 23.1. | No
888 | Section I – Instructions to Proposers (ITP), ITP 18.2(d); Section IX – Particular Conditions (PC) / Contract Data, Sub-Clause 6.1; Section VII – Employer’s Requirements, Clause 11.7.2 – Local Employment and Local Workforce Development; Section IV – Local Labour Method Statement | Subject: Definition of “local labour” (ITP 18.2(d), Sub-Clause 6.1) ITP 18.2(d) and Sub-Clause 6.1 of the Particular Conditions require that not less than 30% of the total labour cost be allocated to local labour, and state only that “local labour excludes Contractor’s foreign personnel”. Section 11.7.2 of the Employer’s Requirements states that, “for the purposes of this Contract”, local means “individuals residing within the Project’s area of influence or surrounding districts”. Based on these provisions, we understand that, for the 30% requirement, “local labour” means Contractor’s Personnel residing within the Project’s area of influence or surrounding districts, excluding foreign personnel. Please confirm whether this understanding is correct, or whether “local labour” for this requirement refers to all Contractor’s Personnel other than foreign personnel, regardless of their place of residence in Türkiye, with the definition in Section 11.7.2 applying only to the local employment priority and KPIs under that Section. | Confirmed. For the minimum 30% allocation of total labour cost required under ITP 18.2(d) and Contract Data Sub-Clause 6.1, “local labour” shall be understood in accordance with Employer’s Requirements Clause 11.7.2, i.e. individuals residing within the Project’s area of influence or surrounding districts, excluding Contractor’s foreign personnel. It does not mean all Turkish/non-foreign personnel irrespective of residence. KPI E3 is a separate KPI based on Turkish nationality and shall be applied in accordance with the KPI Schedule. | No
889 | Section III – Evaluation and Qualification Criteria, A. Technical Part, Factor 8 – Social Aspects & Local Economic Impact, Sub-factor 8.2.1; Section VII – Employer’s Requirements, Clause 11.7.2 | Subject: Definition of “local subcontractors and suppliers” Sub-factor 8.2.1 of Section III (Evaluation and Qualification Criteria) refers to “targets for engaging local subcontractors and suppliers”. The RFP does not define “local” for subcontractors and suppliers; Section 11.7.2 of the Employer’s Requirements defines “local” only for individuals, by place of residence. Please clarify how “local subcontractors and suppliers” should be define. | For purposes of Sub-factor 8.2.1, “local subcontractors and suppliers” means subcontractors and suppliers having an established operational/business presence within Türkiye and contributing goods or services from the local economy. The Proposer should identify the basis on which the proposed entities are considered local and state its engagement targets and monitoring approach. Please refer to Addendum No. 2, Amendment No. 43. | Yes
890 | Section VII – Employer’s Requirements, Clause 5.3.2 – Special System Works; Clause 10.9.4 – Fire Detection and Fire Suppression Systems; Annex K – Tunnel Electromechanical Works Technical Specification | Clause 5.3.2 of the Employer's Requirements includes the design, supply, installation, testing and commissioning of water mist fire suppression systems for tunnels along the railway line and within station areas. i. Please clarify whether this requirement applies to all tunnels along their full length and to all station areas, or only to specified locations. ii. Please identify the relevant tunnels, tunnel sections, station areas and Lots, and provide the applicable coverage limits and design/performance criteria. | Please refer to Answer 819. The water-mist fire-suppression system is expressly required and is included in the Contractor’s scope. The exact installation areas, zoning/coverage, hydraulic design, equipment selection, interfaces and performance criteria shall be established through the approved Detailed Design, fire-life-safety strategy, applicable national/international standards and authority approvals. The absence of a separate prescriptive water-mist annex does not remove the requirement. | No
891 | Section VII – Employer’s Requirements, Clauses 1.2 and 5.8.2 – Istanbul Airport Station; Annex A – Drawings AYGM-INR-ALG-PLP-033 and AYGM-INR-ARC-IST-001 | The following drawings indicate different total lengths for Istanbul Airport Station: AYGM-INR-ALG-PLP-033: 630.852 m. AYGM-INR-ARC-IST-001: 616.550 m. Please confirm the station length and drawing to be adopted as the basis for tendering and design. Please also clarify the reason for the discrepancy and provide revised drawings, if applicable. | The cited drawings are tender-stage/conceptual documents prepared for different design purposes and shall be read together with the Employer’s Requirements and the document-precedence provisions. Neither stated length constitutes a guaranteed final quantity or a fixed station length for the Design-Build Contract. The final station geometry and length shall be developed by the Contractor through the approved Detailed Design, taking account of all functional, structural, operational, interface, safety and authority requirements. No revised drawing is issued through this clarification. | No
892 | Section VII – Employer’s Requirements, Clauses 9 and 10 – Fire/Life Safety, Testing and Commissioning; Annex E1 – Design Technical Specification; Annex K – Tunnel Electromechanical Works Technical Specification; TSI SRT | In alignment.dwg, tunnels longer than 5 km are shown, but the associated intermediate evacuation and rescue point (ERP) arrangements are not clear. i. Please confirm the passenger rolling-stock fire safety category to be adopted for the project (Category A or Category B) under TSI SRT. ii. Please identify the intended ERP locations, including any stations to be used as ERPs, and clarify the applicable maximum spacing and access arrangements. iii. Where additional ERP facilities or access shafts are required, please confirm whether their design and construction are included in the Contractor's scope. | The fire-safety category of the rolling stock and the evacuation/rescue strategy shall comply with the applicable TSI SRT requirements and the final approved rolling-stock and operational parameters. The RFP does not prescribe, through the cited conceptual alignment drawings, a separate fixed Category A or Category B classification. Evacuation and rescue points, safe areas, spacing and access arrangements shall be developed in the Contractor’s detailed fire-life-safety and evacuation design, taking account of stations and tunnel geometry, and shall be subject to Engineer and competent-authority approval. Any additional ERP, access shaft or associated facility required to achieve contractual and regulatory compliance is included in the Contractor’s Design-Build scope unless expressly allocated otherwise in the Contract. | No
893 | Section VII – Employer’s Requirements, Clauses 5.8.2, 9 and 10 – Station and Fire/Life Safety Requirements; Annex A – Drawing AYGM-INR-ARC-SGA-006; Annex E1; Annex K; applicable TSI SRT and Turkish fire-safety requirements | Drawing AYGM-INR-ARC-SGA-006 indicates a platform depth of approximately 50 m at Sabiha Gökçen Airport Station. A dedicated firefighting lift and enclosed escape stairs are not clearly identified in the drawing. i. Please confirm whether the station is intended to serve as an evacuation and rescue point (ERP) for the adjoining tunnels. ii. Please clarify the required emergency access and evacuation arrangements, including whether a dedicated firefighting lift providing direct access between the surface and platform level and enclosed escape stairs are required. iii. Please confirm whether these facilities and any associated modifications are included in the Contractor's scope, and specify the applicable design criteria. | The tender-stage drawing does not constitute an exhaustive fire-life-safety design. Sabiha Gökçen Airport Station shall be incorporated into the overall evacuation and rescue strategy for the adjoining tunnels. Its status and function as an evacuation/rescue point, and the required firefighting access, firefighting lift, protected/enclosed escape routes and other emergency facilities, shall be established through the approved Detailed Design in accordance with the Employer’s Requirements, applicable TSI SRT, Turkish fire-safety requirements and competent-authority approvals. All facilities required for compliance are included in the Contractor’s scope unless the Contract expressly allocates them otherwise. | No
894 | Section VII – Employer’s Requirements, Clauses 4.8 and 5.3.2 – Interfaces / Electrification; Annex A – YSS Bridge Typical Sections; Annex J2 – Catenary Systems Technical Specification | Please clarify the foundation type for the overhead contact line system and confirm whether provisions for overhead contact line foundations have already been incorporated into the YSS Bridge. | The Contractor shall verify the existing YSS Bridge geometry, structural provisions and interface constraints and shall design all OCS supports, foundations, attachments and associated works required for the INRAIL electrification system. The RFP does not warrant that ready-to-use OCS foundations have already been incorporated into the existing bridge. Any existing provisions may be used only after verification and approval. The final solution shall be coordinated with the Engineer, KGM/YSS Bridge operator and other relevant interface parties and shall comply with the structural and electrification requirements of the Contract. | No
895 | Section VII – Employer’s Requirements, Clause 1.2 – Document Precedence; Annex K – Tunnel Electromechanical Works Technical Specification, Clause 2.2; Annex B1 – Conceptual Design Report, Clause 8.3; applicable TSI SRT / NFPA 130 requirements | According to Clause 8.3 of ANNEX B1, mechanical ventilation systems are required for tunnels longer than 1,000 m. However, Clause 7.1.2.2 of NFPA130D requires mechanical ventilation systems for tunnels longer than 1,000 ft (305 m). Please clarify whether the tunnel length threshold for requiring mechanical ventilation is 1,000 m or 1,000 ft. | Please refer to Addendum No. 2, Amendment No. 10, and the corresponding amendment to ER Clause 9.3.1. The project-specific requirements in Annex K shall be applied with SRT-TSI for alignment structures, including mainline railway tunnels. NFPA 130 shall remain applicable to underground station structures and station-specific fire/life-safety requirements. The applicable tunnel ventilation and fire-fighting requirements shall be read consistently within these respective scopes; the standards are not interchangeable across the whole project. | Yes
896 | Section VII – Employer’s Requirements, Clauses 4.5–4.8 – Interface Management / Third-Party Interfaces; Annex E4 – Railway Bridge Design Technical Specification; applicable KGM/TCDD/authority requirements | Where long-span structures are required to cross roads, railways or other facilities, what structural forms and construction methods are commonly adopted? For example, if a continuous girder structure is adopted, is cantilever construction using form travellers or bridge rotation construction commonly used? Is construction using form travellers permitted above roads or railways while traffic remains in operation below? Are there any relevant requirements? | The RFP does not prescribe a single structural form or erection method for long-span crossings. Under the Design-Build arrangement, the Contractor shall select and substantiate the structural system and construction methodology that satisfy the Employer’s Requirements, Site/interface constraints, safety requirements and competent-authority approvals. Cantilever construction using form travellers, rotation/launching methods or other methods may be proposed where technically suitable. Construction above live road or railway traffic is permitted only where the relevant authority/operator accepts the method and all required possessions, traffic management, protection, monitoring and safety measures are implemented. No right to work above live traffic without such approval is granted. | No
897 | Section VII – Employer’s Requirements, Annex J2 – Catenary Systems Technical Specification, Clauses 2.2 and 10.1.1; ADDENDUM – Amendment 7 | Question: Clause 10.1.1 specifies that design documents must be submitted based on a speed of 250 km/h + 10%, which is inconsistent with Clause 2.2. Please clarify which speed standard should be used to complete the design. | Please refer to Addendum No. 2, Amendment No. 7. The governing catenary design/operational speed for the INRAIL works is 200 km/h + 10%, where the additional 10% margin is required by the applicable design/testing provisions. The conflicting reference to 250 km/h + 10% in Annex J2 is superseded by the Addendum. | Yes
898 | Section VII – Employer’s Requirements, Annex E1 – Design Technical Specification, Clause 7.6.13.5.1 – Lighting in Tunnels and Viaducts | Question: Please confirm that all railway viaducts on the main lines of this project that are longer than 400 meters must have lighting systems designed and installed within the effective length of these bridges. | Confirmed. Where Annex E1 Clause 7.6.13.5.1 applies, railway viaducts longer than 400 m shall be provided with the required lighting system. The detailed extent, arrangement, power supply, controls, emergency provisions and interfaces shall be developed in the approved Detailed Design in accordance with the Contract requirements and applicable standards. | No
899 | Section IX – Particular Conditions (PC), Sub-Clauses 21.1 and 21.6; ADDENDUM – Amendment 20 | With respect to INRAIL_RFP at pdf page 30 footnote which reads as: “An individual firm is considered a domestic Proposer for purposes of the margin of preference if it is registered in the country of the Employer, has more than 50 percent ownership by nationals of the country of the Employer, and if it does not subcontract more than 10 percent of the contract price, excluding provisional sums, to foreign contractors. JVs are considered as domestic Proposer and eligible for domestic preference only if the individual member firms are registered in the country of the Employer or have more than 50 percent ownership by nationals of the country of the Employer, and the JV shall be registered in the country of the Borrower. The JV shall not subcontract more than 10 percent of the contract price, excluding provisional sums, to foreign firms. JVs between foreign and national firms will not be eligible for domestic preference.” Could the Employer please confirm that Where the Contractor is a joint venture comprising both Turkish and foreign member whether it would be classified as a “foreign Contractor”. | Please refer to Answer 198 and Addendum No. 2, Amendment No. 20. For the purposes of Sub-Clauses 21.1 and 21.6, a joint venture having at least one foreign member shall be treated as a foreign Contractor. All JV-member nationalities shall be taken into account for the DAAB nationality requirement. | Yes
900 | Section VIII – General Conditions (GC), Sub-Clause 4.1 – Contractor’s General Obligations / Fitness for Purpose; Section IX – Particular Conditions (PC) / Contract Data, Sub-Clause 1.15 – Limitation of Liability | Please clarify that the Contractor’s fitness-for-purpose obligation is limited to the purposes expressly identified in the Contract and shall be satisfied where the Works comply with the Employer’s Requirements, approved design, applicable standards and contractual performance requirements. Please also confirm that any liability arising from the fitness-for-purpose obligation shall remain subject to the overall limitation of liability under Sub-Clause 1.15, except for the expressly agreed carve-outs. | The fitness-for-purpose obligation applies to the purposes for which the Works are intended as stated or reasonably ascertainable from the Contract, including the Employer’s Requirements and contractual performance/function requirements. Compliance with an approved design or a stated standard does not, by itself, relieve the Contractor from the fitness-for-purpose obligation if the completed Works do not satisfy those contractual purposes. Any liability arising under the Contract remains subject to Sub-Clause 1.15 to the extent applicable, including the exclusions/carve-outs expressly stated in the Contract. | No
901 | Section VIII – General Conditions (GC), Sub-Clause 4.12 – Unforeseeable Physical Conditions; Section VII – Employer’s Requirements / Geotechnical and Site Information; Section IX – Particular Conditions (PC) | Please confirm that the disclaimers, disclosed hazards and deemed-foreseeability provisions in the Employer’s Requirements do not exclude or restrict the Contractor’s entitlement under Sub-Clause 4.12 in respect of physical conditions that: •a re materially different in nature, extent, severity or locaon from the condions disclosed in the Contract; and • could not reasonably have been foreseen by an experienced contractor by the Base Date. For clarity, please confirm that the Employer’s Requirements do not override Sub-Clause 4.12 except where expressly stated in the Particular Conditions. | Please refer to Answer 765. The disclosed hazards, geotechnical information, Site data and risk allocations form part of the contractual basis to be considered when assessing foreseeability. They do not delete Sub-Clause 4.12 except to the extent the Contract expressly modifies or allocates the relevant risk. A physical condition may be dealt with under Sub-Clause 4.12 only where the requirements of that Sub-Clause are satisfied, including that the condition was not reasonably foreseeable by an experienced contractor by the Base Date and is not otherwise allocated to the Contractor. Any entitlement is subject to the applicable notice, substantiation and determination provisions. | No
902 | Section VII – Employer’s Requirements / Annex C – Geotechnical Data Report (GDR); Section IV – Schedule of Priced Activities and Sub-activities – Basis of Lump Sum Prices | Please confirm whether Annex C (Geotechnical Data Report) will be issued to bidders before the Proposal submission deadline. | Annex C / the Geotechnical Data Report is identified in the RFP as an Employer-furnished reference document. Proposers shall use the version made available as part of the tender documentation. No additional or revised GDR is committed through this clarification. | No
903 | Section IX – Particular Conditions (PC), Sub-Clause 21.6 – Arbitration; Contract Data, Sub-Clause 21.6 | If a mixed-nationality JV is classified as a foreign Contractor, please specify and agree the neutral place and juridical seat of arbitration in the Contract Data before Contract award. We suggest Paris, France, or Geneva, Switzerland. If the Contractor is classified as domestic, please identify: •t he applicable arbitral instuon; •t he arbitraon rules; •t he number and method of appointment of arbitrators; •t he juridical seat and city of arbitraon; and •t he language of arbitraon. | Please refer to Answers 198 and 199 and Addendum No. 2, Amendment No. 20. For a foreign Contractor, disputes shall be finally settled under the ICC Rules by one or three arbitrators, and the neutral place of arbitration will be indicated at the time of award in accordance with Contract Data Sub-Clause 21.6; the request to pre-fix Paris or Geneva is not accepted. For a domestic Contractor, arbitration shall be conducted in accordance with the laws of Türkiye as stated in PC Sub-Clause 21.6(b). The RFP does not prescribe an additional arbitral institution, rules or seat for the domestic case beyond that provision. The arbitration language is governed by Sub-Clause 1.4. | Yes
904 | Section IX – Particular Conditions (PC), Sub-Clause 21.1 – Constitution of the DAAB; Section I – ITP 12.5; ADDENDUM – Amendment 20 | Please confirm that, where a mixed-nationality JV is classified as a foreign Contractor, the DAAB members shall comply with the nationality requirements under PC Sub-Clause 21.1 and shall not have the same nationality as either the Employer or the Contractor. Accordingly, please confirm that, if the Contractor is classified as a foreign Contractor, the Employer’s currently proposed Turkish candidates shall not be eligible for appointment to the DAAB and shall be replaced by compliant candidates. Please also disclose the names, nationalities and CVs of the replacement candidates sufficiently in advance to allow the Contractor to assess their qualifications, independence and impartiality before appointment. | Please refer to Addendum No. 2, Amendment No. 20. Where the successful Contractor is a foreign Contractor, a DAAB member shall not have the same nationality as the Employer or as any member of the Contractor’s JV. The names proposed in the RFP are potential candidates only and remain subject to the contractual eligibility requirements and the Bank’s No-objection. A candidate who does not satisfy the applicable nationality requirement cannot be appointed. The appointment process, supporting CVs and consideration of candidate qualifications/independence shall follow ITP 12.5 and Sub-Clause 21.1; no replacement list is issued through this clarification. | Yes
905 | Section I – Instructions to Proposers (ITP), ITP 7 and ITP 8 – Clarification and Amendment of RFP; Section VIII/IX – Conditions of Contract, Sub-Clause 1.5 – Priority of Documents | Please confirm that all Employer responses materially affecting the technical, commercial or contractual basis of the Proposal will: • be issued through a formal addendum; • form part of the RFP Documents and, following award, the Contract; • be issued before the Proposal submission deadline; and • be accompanied by a reasonable extension of the submission deadline where necessary to allow Proposers to incorporate the response into their Proposals. Please also clarify the order of precedence of such addenda and clarification responses under Sub-Clause 1.5. | Please refer to Answer 556. Clarification responses explain the RFP but do not amend its terms. Where an Employer response requires a modification of the RFP, the modification will be made only by Addendum pursuant to ITP 8. An Addendum forms part of the RFP Documents and, upon award, the contractual documents as applicable. Clarification responses that do not amend the RFP do not have separate precedence over the Contract. Any extension of the Proposal submission deadline will be decided and notified by the Employer in accordance with ITP 8.3 and ITP 23.2; it is not automatic for every clarification. | No
906 | Section VII – Employer’s Requirements, Clause 10.10.13 – O&M Supervision Period; Annex P – Testing and Commissioning Technical Specification; Section VIII/IX – Conditions of Contract, Clause 11 and Sub-Clause 1.15 | Please consider clarifying that, following Taking-Over, the Contractor’s continuing obligations shall be limited to the completion of outstanding work and remedying defects for which it is responsible under Clause 11. Any additional requirement during the 24-month O&M Supervision Period (Employer Requirement 10.10.13) including supervision of revenue service, operational support, performance monitoring, additional staffing or response to system failures shall be instructed and valued as a Variation, with the corresponding adjustment to the Contract Price and, where applicable, EOT. Please also confirm that the final-two-month performance baseline shall apply prospectively only, without creating retrospective or uncapped liability, and that all related liability shall remain subject to Sub-Clause 1.15 | Please refer to Answers 747 and 812. The 24-month O&M Supervision Period is an express contractual obligation and is not limited to defect-remedy activities under Clause 11. The O&M Supervision Period and the 730-day Defects Notification Period are separate obligations and may run concurrently after Taking-Over. Staffing, supervision, operational support, monitoring and response obligations already required by the Contract are included in the Contract Price and are not Variations merely because they occur after Taking-Over. Work instructed outside the contractual scope shall be dealt with under Clause 13. Any liability is governed by the Contract, including Sub-Clause 1.15 where applicable. | No
907 | Section VIII – General Conditions (GC), Sub-Clause 14.5 – Plant and Materials Intended for the Works; Section IX – Contract Data; Section IV – Schedule of Priced Activities | As no Plant or Materials appear to be identified in the Contract Data for the purposes of Sub-Clause 14.5, please allow Proposers to identify in their Proposals the categories of Plant and Materials for which interim payment will apply when shipped or delivered. Please also confirm that qualifying Plant and Materials will be certified at not less than 80% of their supported value in accordance with Sub-Clause 14.5, without an aggregate percentage cap against the Accepted Contract Amount. | Please refer to Answers 288 and 816. No Contract Data entry identifies Plant or Materials, categories or percentages eligible for payment under Sub-Clause 14.5; therefore that pre-incorporation payment mechanism is not activated for this Contract. Proposers may not activate it by identifying categories in their Proposals. Payments shall be assessed through the Schedule of Priced Activities and Sub-activities and the applicable provisions of Clause 14. | No
908 | Section VII – Employer’s Requirements, Clause 7.6 – Third-Party Approval Obligations; Section VIII/IX – Conditions of Contract, Sub-Clauses 1.13, 2.2, 8.5, 8.6, 13.6 and 20.2 | With respect to ER Section 7.6, Please consider deleting the wording extending the Contractor’s responsibility to authorities and approval requirements not identified in the Contract. The Contractor’s responsibility should be limited to approvals expressly allocated to it under Sub-Clause 1.13 and identified or reasonably foreseeable from the Contract and applicable Laws at the Base Date. Please also confirm that ER Section 7.6 shall not override or restrict the Contractor’s rights and relief under the Conditions of Contract, including Employer assistance under Sub-Clause 2.2, EOT for unforeseeable delays caused by authorities under Sub-Clauses 8.5 and 8.6, and relief for Changes in Laws under Sub-Clause 13.6. Any additional or unforeseeable approval requirement should therefore entitle the Contractor to the corresponding EOT and adjustment to the Contract Price, as applicable. | The request to delete or limit Employer’s Requirements Clause 7.6 is not accepted. The Contractor shall identify, pursue and obtain the approvals allocated to it by the Contract, including approvals of the relevant authorities and interface parties. Clause 7.6 does not, however, extinguish an express contractual entitlement available under the Conditions of Contract where the requirements of the relevant Sub-Clause are satisfied. Any claim for Employer assistance, EOT and/or Cost must therefore be assessed under the applicable contractual provision on its facts, including causation, critical-path effect, foreseeability/risk allocation, notice and substantiation. No automatic EOT or Cost entitlement arises merely because an approval or authority was not individually listed in the RFP. | No
909 | Section IX – Particular Conditions (PC), Sub-Clauses 14.6.2, 14.6.3 and 1.15 – KPI Withholding / Limitation of Liability | Please consider amending the Contract to confirm that KPI Performance Withholding under Sub-Clause 14.6.3 shall constitute the Employer’s sole and exclusive financial remedy for failure to achieve the relevant KPI. The same factual breach or event shall not give rise to duplicate or cumulative withholding, damages, deductions or other financial claims under Sub-Clauses 14.6.2 and 14.6.3 or otherwise under the Contract or applicable law. In particular, where an ES, local labour, cybersecurity or other compliance issue also affects KPI performance, withholding shall be applied only once unless genuinely distinct obligations and separately identifiable losses or consequences are established. Please also confirm that all amounts withheld or forfeited under the KPI regime shall count toward the Contractor’s overall limitation of liability under Sub-Clause 1.15. | The request to make KPI Performance Withholding the Employer’s sole and exclusive financial remedy is not accepted. PC Sub-Clause 14.6.3 already provides that the same factual breach shall not be subject to duplicate financial withholding under Sub-Clauses 14.6.2 and 14.6.3, except where the Engineer determines that separate contractual obligations have been breached. That provision does not waive other rights or remedies arising from a genuinely distinct breach, loss or contractual obligation. Sub-Clause 1.15 applies according to its terms and stated exclusions; no additional deeming provision is introduced to recharacterize all KPI withholdings/forfeitures as amounts counted toward the liability cap. | No
910 | Section IX – Particular Conditions (PC), Sub-Clauses 15.1, 15.2.1 and 15.2.2 – Contractor Default / Termination; ADDENDUM – Amendment 26 | GC Sub-Clause 15.2.1 contains termination grounds numbered (a) to (h), including the existing sub-paragraph (g) relating to insolvency. PC Sub-Clause 15.2.1 introduces an additional KPI-related termination ground also identified as sub-paragraph “(g),” without renumbering the existing provisions, and replaces sub-paragraph (h) with the fraud and corruption termination ground. As Sub-Clause 15.2.2 permits immediate termination for grounds under sub-paragraphs (g) and (h), the duplicate numbering creates uncertainty as to whether immediate termination is intended to apply to the newly introduced KPI-related ground. Please clarify the intended numbering of the additional KPI-related termination ground and confirm that termination on the KPI grounds in the new sub-paragraph (g) is subject to the 14-day notice procedure in GC Sub-Clause 15.2.2 and not to immediate termination. | Please refer to Addendum No. 2, Amendment No. 26. The KPI-related additional ground for default is renumbered as Sub-Clause 15.2.1(i), removing the duplicate use of sub-paragraph (g). Accordingly, the immediate-termination treatment associated with the original sub-paragraphs (g) and (h) does not apply merely by reason of the former duplicate numbering. In addition, before termination on the Critical-KPI threshold under Sub-Clause 15.2.1(i)(ii), the Particular Conditions expressly require a Notice to Correct and a 28-day period for permanent corrective measures, followed by the stated two consecutive reporting periods of maintained compliance. The remaining termination procedure in Sub-Clause 15.2.2 applies according to its terms. | Yes
911 | Section IX – Particular Conditions (PC) / Contract Data, Sub-Clauses 14.6.3 and 14.6.5 – KPI Procedures; ADDENDUM – Amendment 37 | Please define “Working Days” as used in PC Sub-Clauses 14.6.3 and 14.6.5 and the KPI Schedule. | Please refer to Addendum No. 2, Amendment No. 37. For purposes of Sub-Clauses 14.6.3 and 14.6.5 and the KPI Schedule, “Working Day” means any day that is an official working day in Türkiye, excluding Saturdays, Sundays and official public holidays in Türkiye. | Yes
912 | Section IX – Particular Conditions (PC) / Contract Data, Sub-Clause 1.15 – Limitation of Liability | Please confirm that “100%” in CD Sub-Clause 1.15 refers to 100% of the Accepted Contract Amount. | Confirmed. The “100%” stated in Contract Data Sub-Clause 1.15 means 100% of the Accepted Contract Amount, subject to the scope of the limitation and the exclusions/carve-outs stated in Sub-Clause 1.15. | No
913 | Section IX – Particular Conditions (PC), Sub-Clauses 14.6.3, 14.6.5 and 15.2.1(i) – Critical KPI Breaches; ADDENDUM – Amendment 26 | As per PC 15.2.1(g)(ii) , three verified breaches of any Critical KPI or two verified breaches of the same Critical KPI within six months give a ground for default. The term “Verified” is undefined, so breaches still under dispute may count. Please confirm whether a Critical KPI breach that is the subject of a pending objection or dispute under PC Sub-Clauses 14.6.3 or 14.6.5 counts as a “verified breach” for the purposes of PC Sub-Clause 15.2.1(g)(ii). | For purposes of the Critical-KPI termination threshold, a breach is not treated as verified while a timely objection under Sub-Clause 14.6.3 remains pending before the Engineer’s final determination. Once the Engineer has issued the written final determination following the applicable KPI assessment/objection process, the breach may be treated as verified for contract administration, subject to any suspension, revision or decision made under the KPI data-dispute procedure or by the DAAB. A subsequent referral of the matter does not create an automatic suspension unless the Contract, the Engineer or the DAAB provides otherwise. The KPI termination ground is Sub-Clause 15.2.1(i) as corrected by Addendum No. 2, Amendment No. 26. | Yes
914 | Section IV – Proposal Forms, Code of Conduct for Contractor’s Personnel (ES), pp.147–150; Section III – Evaluation and Qualification Criteria, A. Technical Part, 1.4 Key Personnel; Section II – PDS ITP 12.2(k) | We kindly request the Employer's clarification regarding the relationship between the “Contractor’s Social Expert” referred to in the Code of Conduct and the Key Personnel positions, as well as the associated submission requirements. Is the “Contractor’s Social Expert” intended to refer to either the Social Specialist or the Gender and SEA/SH Specialist included in the Key Personnel list? If it refers to a lot-specific Key Personnel position, should a different person be designated for each Lot where the Proposer submits a Proposal for more than one Lot? Alternatively, may the Contractor designate another suitably experienced person within its organization, outside the PER-1/PER-2 Key Personnel, and use the same person for multiple Lots? Please also confirm whether this person is required to be nominated as Key Personnel. Please confirm our understanding that, at the proposal stage, a separate complete copy of the Code of Conduct, including Attachment 1, must be completed and signed for each Key Personnel submitted with the Proposal. | The “Contractor’s Social Expert” in the Code of Conduct is the Contractor’s designated contact for SEA/SH-related concerns and is not, solely by that wording, a separate mandatory Key Personnel position. The function may be assigned to the proposed Social Specialist or Gender and SEA/SH Specialist where suitably qualified; if a listed Key Personnel is used, the lot-specific Key Personnel requirements, including the requirement for different persons for multiple Lots, apply. The Contractor may alternatively designate another suitably experienced person outside PER-1/PER-2, in which case that person is not required to be nominated as Key Personnel and the multiple-Lot Key Personnel restriction does not apply to that non-Key role. At Proposal stage, the Proposer shall submit the organizational Code of Conduct required by PDS ITP 12.2(k); a separate individually signed complete copy for each proposed Key Personnel is not required at Proposal stage. Individual acknowledgement/signature by Contractor’s Personnel applies during implementation. | No
915 | Section VII – Employer’s Requirements / Annex C1 – Geotechnical Data; Annex F – Tunnelling; Section VIII – GC Sub-Clause 4.12 – Unforeseeable Physical Conditions | Please confirm whether the Employer's investigations identified gas-bearing strata, abandoned mine workings or contaminated ground along the Lot 2 corridor, whether the Contractor is required to price gas monitoring and explosion-protected equipment during tunnelling, and whether contaminated material disposal, if encountered, is treated under GC Sub-Clause 4.12. | Please refer to Answer 765. The Employer makes no additional representation concerning gas-bearing strata, abandoned mine workings or contaminated ground beyond the geotechnical, environmental and Site information issued with the RFP. The Contractor shall carry out the investigations, monitoring, ventilation/gas-safety measures, explosion-protected installations and material handling/disposal reasonably required by the disclosed risks, applicable Laws, E&S requirements and its approved design, and shall price the corresponding contractual scope. If an actual physical condition is genuinely unforeseeable within the meaning of Sub-Clause 4.12 and is not otherwise allocated to the Contractor, it shall be dealt with under Sub-Clause 4.12 and the applicable claim procedure. Encountering contaminated material does not automatically establish an entitlement under Sub-Clause 4.12. | No
916 | Section VII – Employer’s Requirements, Clause 11.13 – Cultural Heritage; Section VIII/IX – Conditions of Contract, Sub-Clause 4.23 – Archaeological and Geological Findings; ESIA / CHMP | Please confirm whether archaeological surveys have been completed, whether museum supervision of excavations is required and at whose cost, and confirm that delays and costs arising from archaeological findings are treated under GC Sub-Clause 4.23. | Please refer to Answers 190 and 499. The Contractor shall comply with the cultural-heritage/chance-find requirements, applicable Laws, museum/competent-authority requirements and the ESIA/CHMP, including protection, coordination, monitoring and any supervision required by the authority. The RFP does not warrant that archaeological investigations are complete or that no additional finding will occur. Ordinary compliance and coordination obligations are included in the Contract Price. Any time and/or Cost entitlement arising from a specific archaeological/geological finding shall be determined under Sub-Clause 4.23 and the applicable notice, causation and determination provisions; it is not automatic. | No
917 | Section VII – Employer’s Requirements, Clause 10.10.13 – O&M Supervision Period; Annex P – Testing and Commissioning; Section IX – Contract Data – Defects Notification Period; Section IV – Schedule of Priced Activities | Annex P refers to a 24-month operation and maintenance supervision period after Taking-Over, a sample timetable at 2-minute headway and compensation of 60 times the maintenance cost. Please confirm whether these provisions apply, define the Contractor's obligations, staffing and deliverables during that period, state the relationship with the 730-day Defects Notification Period and Activity 11.3, and confirm whether the related costs are deemed included in the Contract Price. | Please refer to Answers 747 and 812. The 24-month O&M Supervision Period is an express post-Taking-Over contractual obligation and is separate from, although it may run concurrently with, the 730-day Defects Notification Period. The Contractor shall provide the staffing, supervision, monitoring, maintenance support and deliverables required by Clause 10.10.13 and Annex P for the systems within its scope; those obligations are included in the Contract Price and relevant priced activities. Operational examples and performance provisions in Annex P apply only to the extent relevant to the Contractor’s systems and the approved Operations/Testing and Commissioning arrangements. Work outside the contractual scope, if instructed, shall be dealt with under Clause 13. | No
918 | Section VII – Employer’s Requirements, Clauses 9–10 – Testing, Commissioning and Trial Operation; Annex P | Please confirm which party provides and pays for the test trains, locomotives, measuring vehicles, drivers and traction energy for static and dynamic tests, for the catenary tests after energisation, and for the 30-day or 5,000 train-km trial operation, and whether the electricity consumed through the TEİAŞ connection during testing and trial operation is paid by the Employer. | Please refer to Answer 818. Unless the Contract expressly allocates a particular resource to the Employer, the Contractor shall provide or arrange and pay for all resources necessary for its static/dynamic tests, catenary tests, trial running and trial operation, including test trains/locomotives or measuring vehicles, operating personnel/drivers, traction energy and the required operating/access arrangements. The detailed resources and interfaces shall be coordinated through the approved Testing and Commissioning Master Plan with TCDD/Railway Operator, the Engineer and other Contractors. No Employer commitment to supply rolling stock or to bear traction-energy costs is made through this clarification. | No
919 | Section VII – Employer’s Requirements / Annex P – Testing and Commissioning, common/integrated test cost provisions | Annex P states that test costs shall be shared equally among the contractors. Please identify the tests concerned, the contractors among which the costs are shared (Lot 1, Lot 2, Package 2) and the mechanism of settlement, or confirm that each contractor bears only the cost of its own tests. | Please refer to Answer 817. Equal cost sharing applies only to common Project-wide testing/commissioning costs for which the Contract expressly provides a shared allocation and which are not attributable to a particular Contractor. Where a test must be repeated because of a defect, non-conformance, incomplete work or non-readiness attributable to a particular Contractor, the resulting re-test and associated costs shall be borne by that responsible Contractor. The participating Contractors and settlement mechanism shall be established in the approved integrated Testing and Commissioning arrangements in accordance with Annex P. | No
920 | Section VII – Employer’s Requirements, Clauses 5.3.4–5.3.5 and 10; Annex P; Section IX – Contract Data – Milestone 4; ADDENDUM – Amendment 3 | Annex P contains chapters on 1500 V DC systems, platform screen doors, TBM equipment and ETCS/GSM-R signalling and refers to approximately 100 km of high speed line. Please confirm which chapters apply to which Lot Contractor, provide the integrated testing and commissioning programme showing the sequencing with Package 2 and Lot Contractors, the availability dates of the Maltepe control and SCADA centres, and the expected duration of Milestone 4. | Only the provisions of Annex P that are relevant to the INRAIL systems, the relevant Lot scope and the contractual interfaces apply to the Lot Contractor. References in Annex P to systems or equipment allocated to Package 2 or otherwise outside a Lot Contractor’s scope do not transfer those systems into the Lot Contract. The integrated Testing and Commissioning Master Plan, including sequencing among the Lot Contractors and Package 2, shall be developed and approved during implementation; the RFP does not provide separate fixed availability dates for the Maltepe control/SCADA centres beyond the contractual programme and interface requirements. For Milestone 4, please refer to Addendum, Amendment No. 3: the milestone period is 60 months cumulatively from the Commencement Date. Please refer to Addendum No. 2, Amendment No. 3. | Yes
921 | Section VII – Employer’s Requirements, Clauses 9–10; Annex E1; Annex P – Certification / Testing and Commissioning; Section IV – Testing and Commissioning Activities | Please confirm the certification and authorisation regime: whether TSI conformity assessment by a Notified Body, Designated Body assessment against national rules, an Independent Safety Assessor under CSM-RA and the authorisation for placing in service by the Ministry are required, which party appoints and pays each body, and the deliverables expected from the Contractor. | Please refer to Answers 76 and 697. The Contractor shall obtain the conformity/safety assessments and certificates required for its contractual scope under the applicable EU/TSI, CSM-RA, national and authorization framework, including engagement of NoBo, AsBo and, where legally/applicably required, DeBo/other independent assessment bodies. Such bodies shall be appointed and paid by the Contractor unless the Contract expressly allocates a body or assessment to another Contractor/Package. The Ministry/competent railway authority performs the regulatory authorization function. The Contractor shall deliver all design dossiers, assessment evidence, verification certificates, safety-assessment reports and authorization-supporting documents required for Taking-Over and placing into service. | No
922 | Section VII – Employer’s Requirements, Clause 10.6.2 – Taking-Over; Annex P – Integrated Testing; Section VIII/IX – Conditions of Contract, Clause 10 and Clause 13 | Please confirm the Taking-Over criteria for the each Lot Contractor Works if Package 2 or other lots are not complete when the a particular lot is ready for completion, and whether Taking-Over of each lot may be issued on the basis of the relevant lot’s tests alone, with integrated tests performed later under a separate instruction and the Contractor's attendance paid as a Variation. | Taking-Over is assessed for the relevant Contract/Lot under Clause 10 and Employer’s Requirements Clause 10.6.2. A Lot may be Taken Over only when the contractual Taking-Over conditions for that Lot have been satisfied, including the tests, interfaces, documentation, certification and safe-operability requirements that are conditions of Taking-Over. The fact that another Lot or Package 2 has separate outstanding work does not by itself prevent Taking-Over, but any integrated test/interface that is required for the subject Lot must be satisfactorily completed or otherwise dealt with in accordance with the Contract. Attendance/cooperation in later integrated activities already required by the Contract is not automatically a Variation; an Engineer-instructed change outside the contractual scope is dealt with under Clause 13. | No
923 | Section IX – Contract Data, Sub-Clauses 1.1.86 and 1.1.95 – Time for Completion / Milestones; ADDENDUM – Amendment 3 | The Contract Data defines the Time for Completion as 1,826 days, whereas the sum of the Milestone durations (12, 36, 12 and 24 months) is 84 months. Please confirm which governs, the date from which each Milestone is measured, and whether the Milestones are sequential or overlapping. | Please refer to Answer No. 5. Please refer to Addendum No. 2, Amendment No. 3. | Yes
924 | Section IX – Contract Data, Clause 19 – Insurance; Section VIII – General Conditions, Clause 19 | Please confirm the insurance requirements, minimum amounts and deductibles (contractor's all risks, third party liability, professional indemnity, employer's liability), whether the Employer holds any project insurance, and whether the Contractor's insurance must cover the Employer's and the other contractors' adjacent works, the motorway and the YSS Bridge. | The insurance requirements are those stated in Clause 19 and Contract Data. Maximum deductibles are: Works and Plant – USD 1,000,000 per occurrence; third-party liability – USD 500,000 per occurrence; professional indemnity – USD 1,000,000 per claim. Goods shall be insured for 110% of CIF value. Professional-duty liability insurance shall be not less than 20% of the Accepted Contract Amount and shall be maintained for the period stated in the Contract as amended for the Defects Notification Period. Insurance for injury to persons and damage to property shall be EUR 5,000,000 per occurrence with a maximum aggregate limit of EUR 20,000,000. The Contractor shall also maintain insurances required by Turkish law/local practice. The RFP does not state that the Employer maintains a project-wide policy relieving the Contractor of these obligations. Coverage of the Employer, third parties, adjacent works, the motorway and YSS Bridge shall be provided to the extent required by Clause 19 and the Contractor’s contractual liabilities/exposures. | No
925 | Section VIII/IX – Conditions of Contract, Sub-Clause 2.1 – Right of Access to the Site and Sub-Clause 20.2 – Claims; Section VII – Employer’s Requirements, Clauses 10.1.10(j) and 11.15.8 | Please confirm that the Contractor's entitlement to extension of time and Cost under GC Sub-Clause 2.1 remains fully applicable where land access to any section is delayed by expropriation, RP/LRP implementation, sectional Completion Reports, PIOC review or the World Bank's no-objection, and that the exclusion in ER 10.1.10 (j) does not apply to such delays. | Please refer to Answers 75 and 520. Where the Employer is contractually required to give access to a part of the Site, any entitlement arising from delayed access is assessed under Sub-Clause 2.1 and the applicable claim procedure, subject to the facts, causation, critical-path impact, notice and substantiation. Employer’s Requirements Clause 11.15.8 establishes E&S/land-acquisition conditions that must be satisfied before access to affected areas can be granted; it does not, by itself, delete an express entitlement under the Conditions of Contract. Clause 10.1.10(j) does not override an entitlement expressly provided elsewhere in the Contract. | No
926 | Section VII – Employer’s Requirements, Clauses 11.6.3 and 11.10.1 – Land / Project Facilities; Section VIII/IX – Conditions of Contract, Sub-Clause 2.1 | Please confirm whether temporary working areas inside the expropriation corridor (laydown, site offices, batching plants, stockpiles) may be used by the Contractor without further land access procedures, and which Project Facilities the Employer expects to be located outside the Site. | Being located within the planned/expropriation corridor does not by itself constitute handover or authorization for use. The Contractor may use temporary working areas within the Site only after the relevant area has been made available and the applicable E&S, land and approval requirements have been satisfied. The RFP does not pre-designate every camp, batching plant, laydown area, stockpile, spoil area or similar temporary facility as an Employer-provided Project Facility. Temporary/additional areas required by the Contractor’s construction methodology and located outside the Site are to be secured and managed by the Contractor in accordance with the Contract. | No
927 | Section VII – Employer’s Requirements, Clauses 11.6.3, 11.10.1 and 11.11 – Additional/Temporary Land and ESS5; Section IV – Provisional Sum P.2 | For additional facilities outside the Site (camps, batching plants, spoil disposal areas, borrow areas, access roads) secured by the Contractor through lease or agreement, please confirm the scope and expected duration of the Employer's land access review and ESS5 clearance, and whether supplementary livelihood measures for such areas are reimbursable from Provisional Sum P.2. | For camps, batching plants, spoil/disposal areas, borrow areas, access roads and other additional facilities outside the Site, the Contractor shall secure the necessary land rights/agreements and comply with the applicable E&S/ESS5 screening, approval and management requirements before use. The RFP does not prescribe a fixed Employer/ESS5 review duration; the Contractor shall allow for the review/approval process in its programme. Provisional Sum P.2 is not an automatic reimbursement mechanism for livelihood measures arising from land or facilities voluntarily selected/secured by the Contractor; it may be used only for eligible livelihood-support measures instructed/authorized under the Contract. | No
928 | Section VII – Employer’s Requirements, Clauses 7.6 and 11.10.1 – Permits / Land; Section VIII/IX – Conditions of Contract, applicable EOT/claim provisions | Please confirm which party applies for and bears the fees of permanent and temporary forest permits, pasture status changes and treasury or public land allocations required for the alignment, portals, substations, access roads and temporary facilities, and whether delays in these permits entitle the Contractor to extension of time. | Please refer to Answers 184 and 734. Permanent land rights, allocations or acquisition required for the Permanent Works are handled through the Employer’s Project land-acquisition/allocation process, with the Contractor providing the design and technical information required. Temporary land, temporary facilities, access arrangements and permits arising from the Contractor’s construction methodology remain the Contractor’s responsibility unless expressly stated otherwise. Statutory permits and authority coordination allocated to the Contractor shall be pursued under Clause 7.6. Delay does not automatically entitle the Contractor to EOT; any entitlement shall be assessed under the applicable Contract provisions on the facts, including responsibility, foreseeability, critical-path impact, notice and substantiation. | No
929 | Section VII – Employer’s Requirements, Clauses 4.8 and 7.6 – KGM / YSS Bridge Interfaces and Authority Approvals; Site Information | Please provide the protocol between the Employer and KGM governing the use of the North Marmara Motorway right-of-way, confirm whether land within the motorway corridor will be available without expropriation from the Commencement Date, and state the permit procedure, lane closure restrictions, fees and protection measures required by KGM and the YSS Bridge operator for works adjacent to the live motorway. | No additional KGM/YSS protocol is issued through this clarification. The Contractor shall comply with Employer’s Requirements Clauses 4.8 and 7.6 and shall coordinate all works affecting the North Marmara Motorway/YSS Bridge with KGM, the bridge/motorway operator, the Engineer and other interface parties. The RFP does not guarantee that every area within the motorway corridor will be available for unrestricted use from the Commencement Date. Site access shall follow the contractual handover/access arrangements. Required permits, lane/traffic restrictions, possessions, protection, monitoring, safety measures and authority coordination shall be developed and priced by the Contractor in accordance with the approvals of the relevant authority/operator. | No
930 | Section VII – Employer’s Requirements, Clause 5.3.3 – Power Supply Design / TEİAŞ Interface; Annex J1; land-access provisions | Please confirm whether the design, land acquisition, construction and energisation of the 154 kV connection line between the TEİAŞ network and the traction substation, together with the TEİAŞ connection and system usage agreements and their fees, fall within the Lot 2 Contract Price, and confirm that the exclusion of claims in ER 5.3.3 relates to the TEİAŞ approval process only and not to land acquisition for the substation and the line. | Please refer to Answers 733 and 734. Under Employer’s Requirements Clause 5.3.3, Lots 2 and 4 shall perform the system-wide power simulations, identify/propose TEİAŞ 154 kV connection points, obtain the required TEİAŞ/energy-authority approvals at their own cost, and develop the detailed power-supply/transmission/distribution solution within their contractual boundaries. The Contractor of the Lot containing an approved transformer centre is responsible for its design and the associated contractual power-supply works and interfaces. Permanent land rights required for approved Project substations/transmission facilities are dealt with under the Project land provisions; the Contractor shall provide the design/technical information needed for that process. TEİAŞ coordination, connection/approval requirements and costs allocated by the Contract are included in the Contract Price. The express no-claim wording in Clause 5.3.3 concerns the approval process; any other asserted entitlement must satisfy the relevant Contract provision and is not automatic. | No
931 | Section II – PDS ITP 12.2(k) – E&S Instruments / Project Disclosure Channel; Section VII – Employer’s Requirements, Clause 11 | Please confirm whether the Employer will provide the Resettlement Framework Annex 3 parcel data for Lot 2, the current ESIA, ESMP, SEP and LMP versions, the Cultural Heritage Management Plan and the status of the ESS5 cut-off date, and state which versions will form part of the Contract. | The Proposer shall use the environmental and social instruments disclosed through the official Project disclosure channel and incorporated/referred to by the RFP, including the applicable ESIA, ESMP, SEP, LMP, Resettlement Framework/Plans and cultural-heritage instruments. The applicable tender-stage versions are those issued/disclosed by the Employer by the Proposal submission deadline, including any Addenda. Approved updates made during implementation shall be complied with in accordance with the Contract/ESCP. No additional Lot 2 parcel dataset, separate CHMP or ESS5 cut-off-date document beyond the documents officially disclosed/issued is committed through this clarification. | No
932 | Section I – ITP 18.2(d); Section IX – Contract Data, Sub-Clause 6.1; Section VII – Employer’s Requirements, Clause 11.7.2 and KPI E3 | In ER Section 11.7.2, “local labor” refers to residence within the Project area of influence or surrounding districts, while as per KPI E3 it refers to Turkish nationals. Please clarify the definition of local labour applicable to the minimum 30% of total labour cost requirement. Also, please confirm whether KPI E3 will be measured for each lot alone. | Confirmed. For the minimum 30% allocation of total labour cost under ITP 18.2(d) and Contract Data Sub-Clause 6.1, “local labour” means individuals residing within the Project’s area of influence or surrounding districts in accordance with Employer’s Requirements Clause 11.7.2, excluding Contractor’s foreign personnel. KPI E3 is a separate metric based on Turkish nationality. For a Lot Contract, the Contractor’s compliance with KPI E3 is measured using the workforce (direct and subcontracted) employed under that Contract/Lot; the Employer may aggregate data across Lots for Project-level reporting, but another Contractor’s workforce is not used to determine the subject Contractor’s compliance. | No
933 | Section I – ITP 12.4; Section II – PDS ITP 12.3(e); Section III – Evaluation of Technical Part, Factors 2.2.2, 5.2.2 and 8.1.2 | In Section III — Evaluation and Qualification Criteria, Clause 2, particularly criteria 2.2.2, 5.2.2 and 8.1.2; the rated criteria require information on cash-flow projections, resource allocation and budgets. However, ITP 12.4 and PDS ITP 12.3(e) restrict the inclusion of financial information relating to the Proposal price in the Technical Part. Please clarify the minimum information and supporting evidence expected for evaluating such criteria, and the permitted presentation format consistent with these restrictions. | Please refer to Answer 811. The Technical Part shall not disclose the Proposal price or material financial information from which the Proposal price can be derived. For rated criteria concerning resource/cash-flow/budget adequacy, the Proposer may present non-price information such as normalized cash-flow curves, percentages, timing profiles, resource histograms, staffing/equipment allocations, qualitative or indexed budget/resource controls and evidence from comparable projects. The presentation must demonstrate the required management approach without disclosing the Proposal Price or priced Financial Part. | No
934 | Section VII – Employer’s Requirements, Clauses 4.5.2 and 5.3.5 – Package 1 / Package 2 Interface; Annex L6 | Please clarify the contractual boundary for the signalling and telecommunication technical buildings shown on the Annex L wayside layout within Lot 2 (approximately km 33+300, 39+100 and 45+580): whether the buildings, foundations, site works, HVAC and power connections are Package 2 scope (ER 5.3.5 item 14) or civil contractor scope as "equipment rooms" (ER 4.5.2), and whether their land is within the expropriation corridor. | Employer’s Requirements Clause 4.5.2 defines the minimum Package 1 civil prerequisites for Package 2. Accordingly, the Lot Contractor shall construct the signalling/telecommunication equipment rooms and the associated civil/building provisions within its Lot, including the required dimensions, structural/floor provisions, finishes, power termination points, earthing bars, HVAC and cable-entry provisions, and shall hand them over clean, weathertight and energized. Package 2 is responsible for the S&T systems/equipment and its Package 2 technical-system scope under Clause 5.3.5. Permanent land required for Project facilities is dealt with under the Project land-acquisition provisions; the final building locations and boundaries shall be confirmed through the approved interface/detailed design. | No
935 | Section VII – Employer’s Requirements, Clauses 4.5.2 and 5.3.5 – Power Supply / S&T Interface; Annex J2 and Annex L5 | Please confirm which party supplies and installs the 25/0.23 kV catenary auxiliary service transformers and their 25 kV connections, fuses and protection (Annex J2 lists them as catenary gantry equipment while Annex L5 specifies them under the signalling contract), and whether Lot 2 provides only the gantry structure, earthing and cabling. | The higher-level Employer’s Requirements in Clauses 4.5.2 and 5.3.5 govern the Package 1/Package 2 interface. Equipment whose function is the dedicated power supply of signalling/telecommunication systems is within the Package 2 system scope, while the Lot Contractor shall provide the civil/electrification prerequisites and interfaces required by Clause 4.5.2, including the available 25 kV source/termination interface where applicable, supporting/gantry provisions, earthing/bonding, cable routes and coordinated protection interfaces. Any 25/0.23 kV transformer identified in Annex L5 as part of the signalling power-supply system shall therefore be supplied/installed by Package 2; the Lot Contractor shall provide the corresponding civil and electrical interface provisions. The final interface shall be confirmed in the approved Interface Control Documents. | No
936 | Section IV – Proposal Forms, Lot 2 – Schedule of Priced Activities, Activity 8.1 – Existing Track Removal | Activity 8.1 of the Lot 2 Schedule of Priced Activities refers to "existing track removal works, all locations within Lot 2". Please identify the existing track concerned or confirm that the item is not applicable to Lot 2. | No separate inventory or guaranteed quantity of existing track to be removed within Lot 2 is provided by the RFP. Activity 8.1 covers any existing-track removal that proves necessary within the Lot 2 contractual scope, including at interfaces/tie-ins, as established by the Contractor’s Site verification and approved Detailed Design. The item does not constitute a representation that a specific measurable quantity of existing track exists, and the lump-sum Design-Build pricing basis remains applicable. | No
937 | Section VII – Employer’s Requirements, Clause 5.3.3 – Power Supply Design; Annex J1/J2; Section VIII/IX – Clause 13 – Variations | Please confirm the traction power feeding scheme to be priced (1x25 kV or 2x25 kV autotransformer), the number and locations of traction substations and switching posts assumed for Lot 2 pricing, and how changes resulting from the Employer's final decision after the power supply simulations (ER 5.3.3) will be treated in terms of price and time. | Please refer to Answer No. 118. | No
938 | Section VII – Employer’s Requirements / Annex B2 – Operations Plan; Annex E1 – Design Technical Specification; Railway Safety Plan; fire-life-safety requirements | Please confirm the design train capacity and length to be used for tunnel evacuation and station fire safety design (Annex B2 indicates 400 passengers per trainset while the Railway Safety Plan uses 584), and the design train lengths (400 m passenger, 1,000 m freight per Annex E1). | Please refer to Answer 90. No single fixed passenger-load value is established through this clarification. Tunnel evacuation and station fire-life-safety design shall use the final approved rolling-stock configuration, Operations Plan and the credible/worst-case occupancy required by the applicable standards and authority approvals. The passenger and freight train lengths stated in the governing Employer’s Requirements/Annex E1 remain applicable design parameters unless amended; conceptual or safety-plan passenger figures do not by themselves override the approved contractual design basis. | No
939 | Section VII – Employer’s Requirements, Clauses 1.2 and 9.3 – Document Precedence / Fire-Life Safety; Annex E1, Annex K, Annex M2 and Annex I2 | For the tunnel fire life safety systems please confirm: (a) the scenario start logic (ER 9.3 requires automatic activation without manual intervention, Annex E1 and M2 require operator approval with automatic start after a time set by the Authority); (b) emergency lighting autonomy (Annex K 90 minutes, Annex E1 2 and 3 hours); (c) generator rating and fuel (Annex K prime, 8 hours; Annex E1 standby, 6 hours); (d) hydrant and fire cabinet spacing and pipe jointing (Annex E1 45 m and 245 m, threaded above 2.5 inch; Annex K cabinets at 120 m, grooved above 60 mm); (e) manual lighting switch spacing (250 m in Annex E1 and K, 100 m in Annex I2); (f) emergency telephone cable pairs (Annex E1 four pairs, Annex M2 two pairs). | For item (a), the higher-ranked Employer’s Requirement in Clause 9.3 shall govern: required emergency/fire-life-safety actions shall not be made dependent on manual approval where the Employer’s Requirements require automatic activation. For items (b)–(f), the cited provisions are contained in technical annexes of the same document-precedence level. Where the provisions can be complied with cumulatively, the Detailed Design shall satisfy all applicable requirements. Where they are genuinely irreconcilable for the same function, the Contractor shall identify the conflict through the design/interface process and obtain the Engineer’s determination in accordance with Employer’s Requirements Clause 1.2; the Contractor shall not unilaterally adopt the less onerous value. The final fire-life-safety design is also subject to the applicable TSI SRT, Turkish fire-safety requirements and competent-authority approvals. No numerical requirement is deleted or relaxed through this clarification. | No
940 | Section VII – Employer’s Requirements, Clause 1.2; Annex E1, Annex G1, Annex G15 and Annex G19 – Track Works; ADDENDUM – Amendment 25 | For track works please confirm: (a) the ultrasonic inspection coverage of rail welds (Annex G15 sampling versus Annex G15 5.4 and G19 full coverage); (b) track gauge and sleeper spacing (Annex E1 1435 plus or minus 3 mm, Annex G1 1436 mm and 60 cm, Railway Safety Plan 620 mm); (c) whether drilling of rails for return current and IRJ connections is permitted (Annex E1 prohibition versus Annex G15 hole spacing rules); (d) the governing final track position tolerances where Annex G1 is internally inconsistent. | For (a), please refer to Answer 261: ultrasonic testing of rail welds shall be 100% where required by the governing rail-welding requirements; sampling provisions do not reduce the full-coverage requirement. For (b), please refer to Addendum No. 2, Amendment No. 25 and Answer 91: the nominal track gauge is 1,435 mm, and the 1,437 mm/other mould dimensions shall not be treated as a different nominal gauge; for sleeper spacing the governing track technical specification requirement applies rather than the lower-priority conceptual/safety-plan value. For (c), the prohibition on rail drilling shall be observed except where a drilling/connection is expressly required and approved for a defined electrical/IRJ purpose; in that case the applicable detailed drilling requirements in the rail technical specification govern the approved connection. For (d), where Annex G1 contains an irreconcilable internal conflict at the same precedence level, it shall be referred to the Engineer for determination under Employer’s Requirements Clause 1.2 and resolved in the approved Detailed Design/acceptance criteria. | Yes
941 | Section VII – Employer’s Requirements, Clause 1.2 – Document Precedence; Clauses 9 and 10.1.10; Annex E1 / Annex E4; applicable Turkish Laws, Eurocodes, TSI SRT, NFPA 130, BYKHY and KGM requirements | Please confirm the hierarchy of design codes where they differ: Eurocodes and the Turkish Building Earthquake Code (TBDY 2018) for structures, TSI SRT, NFPA 130 and BYKHY for tunnel fire safety, and KGM specifications for road structures, and confirm that the "more onerous requirement" rule of ER 10.1.10 is limited to testing and commissioning. | The governing document hierarchy remains the one stated in ER Clause 1.2, together with mandatory Turkish laws and regulatory requirements. For clarity, NFPA 130 shall apply to underground station structures and station-specific emergency ventilation, passenger evacuation and safety requirements; SRT-TSI shall apply to alignment structures, including mainline railway tunnels and cross-passages; BYKHY remains applicable where required by Turkish law; and KGM specifications apply to road structures within their stated scope. Please refer to Addendum No. 2, Amendment No. 10 and the corresponding amendment to ER Clause 9.3.1. The “more onerous requirement” rule under ER Clause 10.1.10 remains limited to the testing and commissioning scope stated in that clause. | No

## ADDENDUM
İSTANBUL NORTH RAIL CROSSING PROJECT (INRAIL)
Loan No. IBRD-99430
Design and Construction of Infrastructure & Superstructure Works including Electrification – Lots 1, 2, 3 and 4
RFP No. AYGM-INRAIL-2025-YAP 01/1-2-3-4
ADDENDUM
The provisions of this Addendum modify or amend the Request for Proposals (RFP) Document. Except as expressly amended below, all provisions of the RFP Document remain unchanged.
Amendment No. | RFP Document Page No. | RFP Document Reference / Clause | Provisions in Original RFP document | Amended Provisions
1 | 134 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities (Lot 4), Activity 7, Items 7.3 and 7.4 | 7.3 NATM Tunnel 19-C Type-5 NATM Turnout Tunnel Construction (Complete, all support classes, per Employer's Requirements) L.S. 7.4 NATM Tunnel 19-C Type-5 NATM Turnout Tunnel Construction (Complete, all support classes, per Employer's Requirements) L.S. | Item 7.4 is deleted. Items 7.5–7.12 are renumbered as 7.4–7.11.
2 | 137 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities (Lot 4), Activity 13 – DAAB | TOTAL ACTIVITY 12 | TOTAL ACTIVITY 13
3 | 389–390 | Section IX – Particular Conditions, Part A – Contract Data, Sub-Clause 1.1.95 – Milestones | Milestone 1 – Detailed Design Completion 12 months from the Commencement Date Milestone 2 – Infrastructure Works Completion 36 months from the completion date of Major Milestone 1 Milestone 3 – Superstructure Completion 12 months from the completion date of Major Milestone 2 Milestone 4 – Testing and Commissioning Completion 24 months from the completion date of Major Milestone 3 | Sub-Clause 1.1.95 – Milestones is amended as follows (all periods measured from the Commencement Date in accordance with ER Sub-Clause 4.26): Milestone 1 – Detailed Design Completion: by Month 12. Milestone 2 – Infrastructure Works Completion: by Month 46 (34 months after Milestone 1). Milestone 3 – Superstructure Completion: by Month 58 (12 months after Milestone 2). Milestone 4 – Testing and Commissioning Completion: by Month 60 (2 months after Milestone 3). The Time for Completion under Sub-Clause 1.1.86 remains 1,826 days (approximately 60 months) from the Commencement Date. The Contractor's programme, delay damages under Sub-Clause 8.8 and KPI assessment under ER Clause 12.4 shall be read consistently with these milestone due dates and ER Clause 4.9.4. Testing of completed sections may commence before Milestone 3; the period from Month 58 to Month 60 provides the defined system-wide testing, trial-running, integrated commissioning and safety certification window, without limiting earlier testing required by the Contract.
4 | 217 | Section VII – Employer’s Requirements, Clause 5.1 – General | Unless otherwise stated, the design period shall commence from the Effective Date of the Contract, with the Contractor required to achieve substantial completion of the design deliverables necessary for the execution of the Works within twelve (12) months thereof. The construction period shall be completed within sixty (60) months from the Effective Date of the Contract, and the Defects Notification Period shall be twenty-four (24) months from Taking-Over. | “Effective Date of the Contract” is replaced by “Commencement Date” in both sentences.
5 | 103, 111, 120, 130 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities (Lots 1–4), Activity 1 – Design Completion | Lot 1: 1.7 As-Built Documentation — All Disciplines (submission and acceptance) Lot 2: 1.6 As-Built Documentation — All Disciplines (submission and acceptance) Lot 3: 1.6 As-Built Documentation — All Disciplines (submission and acceptance) Lot 4: 1.7 As-Built Documentation — All Disciplines (submission and acceptance) | The following As-Built Documentation items are deleted from Activity 1 – Design Completion of the respective Lot schedules: Lot 1 Item 1.7; Lots 2 and 3 Item 1.6; and Lot 4 Item 1.7.
6 | 87 | Section IV – Proposal Forms / Table of Forms | Daywork Schedule Schedule of Daywork Rates: 1. Labor Schedule of Daywork Rates: 2. Materials Schedule of Daywork Rates: 3. Contractor’s Equipment Daywork Summary | These entries are deleted from the Table of Forms.
7 | Annex J2 | Section VII – Employer’s Requirements / Annex J2 – Catenary Systems Technical Specification / Design Speed | 250 km/h | 250 km/h is replaced by 200 km/h for electrification and signalling systems.
8 | 79–85 | Section III – Evaluation and Qualification Criteria / Item 4.2(b) and Footnotes 9, 11, 13 and 15 | “Volume, number, or rate of production of any key activity can be demonstrated in one or more contracts combined if executed during same time period.” | The following sentence is deleted in its entirety wherever it appears in Section III, Item 4.2(b), including Footnotes 9, 11, 13 and 15: “Volume, number, or rate of production of any key activity can be demonstrated in one or more contracts combined if executed during same time period.” For every Key Activity expressly requiring experience under a single contract, the full specified quantity/length/output shall be demonstrated in a single contract. The same contract may satisfy more than one Key Activity, or separate qualifying single contracts may be used for different Key Activities. Aggregation of contracts to meet an individual single-contract criterion is not permitted.
9 | 247 | Section VII – Employer’s Requirements / Clause 5.8.2 – Key Works and Structures / Istanbul Airport Station | As-built information relating to the completed station structure shall be made available as part of the tender dossier. | This sentence is deleted.
10 | 272 | Section VII – Employer’s Requirements / Clause 9.3.4 – Emergency Egress and Cross-Passage Requirements | For all twin-bore TBM tunnels, cross-passages connecting the two running bores shall be provided at a maximum spacing of 250 metres, measured along the track alignment, in accordance with NFPA 130. Cross-passage spacing, dimensions, and fire door specifications shall be confirmed through the Contractor's detailed design and consented by the Engineer before tunnel boring commences on the relevant section, in accordance with Section 5.9.2 of these Employer's Requirements. All emergency egress routes — including cross-passages, escape tunnels, station emergency exits, and stairwells — shall remain smoke-free and accessible throughout the evacuation period and shall comply with the pressurisation and smoke control requirements of NFPA 130 and BYKHY. Emergency lighting, wayfinding, and communication systems shall be designed as integral components of the egress system. | Section VII – ER Clause 9.3.4 is amended so that, for twin-bore mainline TBM railway tunnels (alignment structures), cross-passages connecting the running bores shall be spaced at no more than 500 m, measured along the track alignment, in accordance with the applicable EU SRT-TSI. Cross-passage details and related evacuation provisions are to be substantiated in the detailed fire/life-safety design and consented by the Engineer. ER Clause 9.3.1 is amended to distinguish the governing fire/life-safety standards: NFPA 130 shall apply to underground station structures, including station evacuation and smoke-control design; SRT-TSI shall apply to alignment structures including mainline railway tunnels and tunnel cross-passages. Applicable Turkish legislation (including BYKHY) shall also be complied with. Station design provisions developed under NFPA 130 remain applicable. The standards shall not be mixed so as to reduce any mandatory requirement for a particular structure.
11 | Annex F | Section VII – Employer’s Requirements / Annex F – Civil Works (Infrastructure) Technical Specification / Clause 2.21.10.3 – Quality Control | The 28-day compressive strength, measured in a 100 mm cube, shall be a minimum of 8 MPa. | “8 MPa” is replaced by “2.0 MPa”. The 50 kPa requirement under Clause 2.21.12 remains unchanged.
12 | 140 | Section IV – Proposal Forms / Schedule of Payments | Schedule of Payments | The existing blank Schedule of Payments in Section IV shall be retained and populated with the following provision: “Payments in respect of each Activity shall be based on the lump-sum prices quoted by the Proposer for the individual Deliverables/Sub-activities set out in the Schedule of Priced Activities and Sub-activities, including up to three (3) additional Deliverables/Sub-activities proposed and priced by the Proposer under each Activity where permitted. Subject to the applicable certification requirements of Clause 14, the amount for a Deliverable/Sub-activity becomes payable upon its completion and acceptance by the Engineer. No partial or percentage-based payment for incomplete Deliverables/Sub-activities shall be certified on the basis of measured progress. Periodic statements and Interim Payment Certificates shall continue to be prepared certified under Clause 14.''
13 | Annex A1 / Annex E1 / Annex G10 | Section VII – Employer’s Requirements / Mass-Spring System (MSS) | Not included in the RFP Documents. | Mass-Spring System Technical Specification is added.
14 | Annex E1 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / TBM Tunnel Diameter | The tunnel design commonly used in railway systems comprises a structure consisting of six segments, each 1.50 metres long, with an inner ring diameter of 5.7 metres and a tunnel lining thickness of 30 centimetres. Four of these segments are arranged in parallel, whilst the other two are designed in a trapezoidal shape (one being the key segment and the other the counter-key segment). | The tunnel design commonly used in railway systems comprises a structure consisting of six segments, each 1.50 metres long, with an inner ring diameter of 8.60 metres and a tunnel lining thickness of 30 centimetres. Four of these segments are arranged in parallel, whilst the other two are designed in a trapezoidal shape (one being the key segment and the other the counter-key segment).
15 | Annex B1 / Annex G10 | Section VII – Employer’s Requirements / Track Superstructure on Bridges and Viaducts | Not included in the RFP Documents. | Ballasted/Ballastless Track Itinerary is added.
16 | Annex G3 | Section VII – Employer’s Requirements / Annex G3 – Ballast Technical Specification / Clauses 1 and 2.2.1 | “HT/YHT, conventional, connecting and shunting lines” “Following the collection of samples from the quarry, the Bidders shall deliver the relevant ballast samples to the laboratory prior to the tender date and shall submit the delivery records for the samples they have delivered, together with receipts confirming payment of the testing fees, along with their tenders.” | HT/YHT acceptance criteria shall apply. The pre-tender ballast sample delivery and testing-fee receipt requirement in Clause 2.2.1 is deleted.
17 | Annex B1 / Annex E4 | Section VII – Employer’s Requirements / AYGM Rail Expansion Gasket (REG) Technical Specification | Not included in the RFP Documents. | AYGM Rail Expansion Gasket (REG) Technical Specification is added.
18 | Annex Q | Section VII – Employer’s Requirements / Annex Q – Quality Management / Project Quality Requirements / Clauses 5, 12 and 13 | 5. PROJECT PROJECT QUALITY PLAN (PQP) 12. Non-Conformance and Corrective Action Management 13. Non-Conformance and Corrective Action Management | Clause 5 heading is corrected to “PROJECT QUALITY PLAN (PQP)”. Clause 13 heading is corrected to “QUALITY AUDIT PROGRAMME”.
19 | Annex Q | Section VII – Employer’s Requirements / Annex Q – Quality Management / Project Quality Requirements / Clause 14 | 14. REFERENCES AND APPLICABLE STANDARDS [unnumbered table of reference standards] 14.3 Priority of Standards | The standards table is numbered 14.1 “Applicable Standards”. Existing 14.3 is renumbered 14.2 “Priority of Standards”.
20 | Section IX | Section IX – Particular Conditions / Sub-Clauses 21.1 and 21.6 | Not stated. | A JV with at least one member incorporated outside Türkiye shall be treated as a foreign Contractor for Sub-Clause 21.6. For DAAB nationality, the nationalities of all JV members shall be considered.
21 | 389; 397; Annex D | Section IX – Contract Data / Sub-Clauses 1.1.27 and 19.2.3; Section VII – Employer’s Requirements / Clause 10.6.4; Annex D – Warranty | Defects Notification Period 1.1.27: 730 days (two years) 10.6.4 Defects Liability Period “The Defects Liability Period (DLP) shall commence upon issuance of the Taking-Over Certificate and shall continue for the period defined in the Contract.” 19.2.3: Until end of Defects Liability Period “Warranty Period shall be 60 (sixty) months starting from the date of Final Acceptance.” | In Clause 10.6.4, “Defects Liability Period (DLP)” is replaced by “Defects Notification Period (DNP)”. The DNP is 730 days from Taking-Over. In Sub-Clause 19.2.3, “Until end of Defects Liability Period” is replaced by “Until the end of the Defects Notification Period”. The 60-month Warranty Period remains a separate obligation starting from Final Acceptance.
22 | 231 | Section VII – Employer’s Requirements / Clause 5.3.3 – Power Supply Design – Cross-Lot Obligations; Clause 5.5.1 – Overview | Clause 5.5.1 states: “As the Anatolian end-section contractor, the Lot 1 Contractor carries specific system-wide obligations for power supply simulation and CTC Center connection as set out in Sections 5.2.3 and 5.2.4.” | The sentence is revised as follows: “The system-wide train operation / power-supply simulation obligations shall be as set out in Clause 5.3.3 and shall be undertaken independently by the Contractors for Lots 2 and 4. The references to Sections 5.2.3 and 5.2.4 in this context are deleted.”
23 | Annex E4 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Clause 3.5.3.2 – α Classification Factor | 0.75, 0.83, 0.91, 1.00, 1.10, 1.21, 1.33 and 1.46 | For INRAIL bridges, the applicable α classification factor shall be 1.33.
24 | Annex B1 | Section VII – Employer’s Requirements / Annex B1 – Conceptual Design Report / Rail and Turnout Types | The narrative states: “On the main line, S-type turnouts with a ratio of 1/24,5 and a radius of R = 1500 m … are used.” The quantity breakdown refers to “1/24 R = 1500 m”. | All references to main-line turnouts with R = 1,500 m shall be read as 1/24.5. The conceptual quantities remain indicative; final quantities, locations and distribution by Lot shall be confirmed through the Contractor’s Detailed Design.
25 | Annex E1 / Annex G5 / Annex G | Section VII – Employer’s Requirements / Track Gauge, Sleepers and Fastenings |  | The nominal track gauge governing the Works shall be 1,435 mm. The 1,437 mm dimension in Annex G5 shall be understood as the applicable sleeper/mould manufacturing dimension and shall not change the nominal track gauge. For the ballasted main line, the B07 sleeper with W21 fastening system shall apply.
26 | 439–440 | Section IX – Particular Conditions / Sub-Clause 15.2 and Sub-Clause 15.2.1 – Contractor Default / KPI-related Termination | Sub-Clause 15.2 Add Sub-Clause 15.2.1 (g) as an additional ground for default as follows: (i) the Contractor remains in sustained breach of more than three (3) KPIs for three (3) consecutive reporting periods; (ii) the Contractor has three verified breaches of any Critical KPI, or two verified breaches of the same Critical KPI, within any rolling six-month period; (iii) the Contractor persistently fails to submit, implement, or complete Corrective Action Plans required under the Employer's Requirements or Sub-Clause 14.6.3, where such failure has continued across two (2) or more consecutive reporting periods following a Notice to Correct issued by the Employer under Sub-Clause 15.1, and the Contractor has not demonstrated to the Engineer's satisfaction that adequate remedial measures have been taken. Before exercising the right to terminate under sub-paragraph (g)(ii), the Employer shall give the Contractor a Notice to Correct under Sub-Clause 15.1, requiring the Contractor to implement permanent corrective measures within twenty-eight (28) days. If the Contractor demonstrates, to the Engineer’s satisfaction, that such permanent corrective measures have been implemented within that period and thereafter maintains compliance with the relevant Critical KPI for two (2) consecutive reporting periods, the Employer’s right to terminate on the basis of the relevant Critical KPI breaches shall lapse, without prejudice to any KPI Performance Withholding or other rights accrued prior to such lapse. For the avoidance of doubt, the existence of KPI Performance withholdings under Sub-Clause 14.6.3 shall not prevent the Employer from exercising any right under this Sub-Clause where the Contractor’s underperformance constitutes a default under the Contract. | Sub-Clause 15.2 Add Sub-Clause 15.2.1 (i) as an additional ground for default as follows: (i) the Contractor remains in sustained breach of more than three (3) KPIs for three (3) consecutive reporting periods; (ii) the Contractor has three verified breaches of any Critical KPI, or two verified breaches of the same Critical KPI, within any rolling six-month period; (iii) the Contractor persistently fails to submit, implement, or complete Corrective Action Plans required under the Employer's Requirements or Sub-Clause 14.6.3, where such failure has continued across two (2) or more consecutive reporting periods following a Notice to Correct issued by the Employer under Sub-Clause 15.1, and the Contractor has not demonstrated to the Engineer's satisfaction that adequate remedial measures have been taken. Before exercising the right to terminate under sub-paragraph (i)(ii), the Employer shall give the Contractor a Notice to Correct under Sub-Clause 15.1, requiring the Contractor to implement permanent corrective measures within twenty-eight (28) days. If the Contractor demonstrates, to the Engineer’s satisfaction, that such permanent corrective measures have been implemented within that period and thereafter maintains compliance with the relevant Critical KPI for two (2) consecutive reporting periods, the Employer’s right to terminate on the basis of the relevant Critical KPI breaches shall lapse, without prejudice to any KPI Performance Withholding or other rights accrued prior to such lapse. For the avoidance of doubt, the existence of KPI Performance withholdings under Sub-Clause 14.6.3 shall not prevent the Employer from exercising any right under this Sub-Clause where the Contractor’s underperformance constitutes a default under the Contract. All references in the Particular Conditions and the Employer’s Requirements to the KPI-related additional ground under Sub-Clause 15.2.1(g) shall be read as references to Sub-Clause 15.2.1(i).
27 | 265 / Annex O | Section VII – Employer’s Requirements / Clause 7.7 – BIM Obligations at Design Stage; Annex O – BIM Technical Specification / Clause 6.1 – BIM Execution Plan | Annex O – BIM Technical Specification, Clause 6.1: “The BIM Execution Plan shall be submitted within 30 working days following the relevant Site handover.” Employer’s Requirements, Clause 7.7: “The BIM Execution Plan (BEP) is a mandatory design-stage deliverable. The Contractor shall submit the BEP to the Engineer for review and consent within 28 days of contract award. The BEP shall be approved before the commencement of any Detailed Design activities and shall remain a live document throughout the duration of the Contract.” | In Annex O – BIM Technical Specification, Clause 6.1, replace the first submission-deadline sentence with the following to align with ER Clause 7.7: “The BIM Execution Plan (BEP) is a mandatory design-stage deliverable. The Contractor shall submit the BEP to the Engineer for review and consent within twenty-eight (28) days of Contract award. The BEP shall be approved before the commencement of any Detailed Design activities and shall remain a live document throughout the duration of the Contract.” ER Clause 7.7 remains the governing provision and is unchanged by this amendment.
28 | Annex E4 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Clauses 3.5.4.5 and 3.3 – Dynamic Factor and LM71 Fatigue | Annex E4, Clause 3.5.4.5 – Dynamic Factor: Φ2 applies for lines where maintenance is carried out with care and diligence. Φ3 applies for lines with standard maintenance. The dynamic factor is determined using the applicable determinant length LΦ. Annex E4, Clause 3.3: the LM71-based fatigue check refers to Φ2. | Annex E4, Clause 3.5.4.5 and the corresponding LM71 fatigue-check provision in Clause 3.3 are amended as follows: “The dynamic factor Φ3, applicable to lines with standard maintenance, shall be used for Load Models LM71, SW/0 and SW/2 in accordance with Annex E4 and the applicable standard. The factor shall be calculated using the applicable determinant length LΦ. Where dynamic analysis is required by Annex E4, the dynamic-analysis requirements shall also apply, with the corresponding track-irregularity effects based on standard maintenance. The factor Φ2 specified in Annex E4 Clause 3.3 for the LM71-based fatigue check shall be replaced by Φ3. The specific provisions for separate fatigue-train models shall remain applicable.”
29 | Annex E4 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Authority-specified parameters | Annex E4 contains provisions requiring the following project-specific values to be specified by the Authority: • the increased height of application ht of the centrifugal force above 1.80 m for specific vehicle types; • additional requirements applicable to heavy traffic at speeds exceeding 120 km/h; • additional requirements for braking effects where the loaded track length exceeds 300 m; • the load to be applied to cantilevers longer than 0.5 m carrying rail traffic; • the permissible difference in transverse deflection between adjacent decks and additional limits on deck-end rotations adjacent to switches and expansion joints; and • passenger-comfort requirements for temporary bridges. | For the purpose of applying the Authority-specified provisions of Annex E4 at Proposal stage, the following matters shall be addressed on a common basis: Specified or standard-based matters (as set out in the Tender Documents and applicable standards): (1) The LM71 classification factor α = 1.33, as already specified for the Project. (2) Design and operating speeds: the speeds specified for the relevant alignment sections in the Tender Documents, including Annex B1 and the applicable alignment drawings, shall be used for railway-bridge centrifugal-force calculations, dynamic effects and other speed-related checks under Annex E4 and EN 1991-2. Annex B1, Clause 4.1.4.6, Table 5 shows illustrative alignment data for S18 and S20/S38 at 160 km/h and S27/S28 at 120 km/h. These examples are section-specific and shall not be treated as a single governing speed for the entire alignment. The Contractor shall substantiate the speeds and alignment parameters adopted for each bridge in accordance with the governing Tender Documents. (3) Real-train models for dynamic analysis: the applicable EN 1991-2 requirements shall govern; the Proposer shall identify and substantiate the adopted models for its design. (4) Railway traffic in seismic design: the applicable TKDY-2020 requirements, including the specified 20% railway live-load allowance where applicable, shall govern. (5) Braking effects for loaded lengths above 300 m: the relevant EN 1991-2 provisions apply; no additional project-specific braking requirement is prescribed here. (6) Ballastless-track deformation, bridge-end rotations, relative transverse displacement between adjacent decks and additional rail stresses shall be assessed in accordance with the applicable EN requirements and the characteristics of the selected track system.The Contractor shall demonstrate compatibility with the proposed track, fastening, turnout, rail expansion joint and bridge expansion arrangements, including compliance with the applicable limits for relative movements and rotations. Where the relevant limits depend on the selected system or structural arrangement, they shall be established and substantiated as part of the Contractor's design. No additional universal project-specific numerical limit is prescribed. (7) Horizontal rotation and changes in track curvature (Annex E4 Table 2.4.3.4.1: α1–α3 and r1–r6): the applicable standard values, including recommended values where expressly adopted by the relevant EN standard, shall be used unless the RFP expressly states a different project requirement. (8) Design water levels: the applicable hydraulic and project requirements stated elsewhere in the Employer's Requirements remain applicable. (9) Application of Load Model SW/2 Load Model SW/2 shall be considered throughout the entire railway alignment, in accordance with the applicable provisions of Annex E4 and EN 1991-2. The applicable design speeds shall be those specified in the Tender Documents for the relevant sections. The use of SW/2 shall not exclude consideration of other applicable railway load models and load combinations. (10) Height of Application of Centrifugal Force The application height of ht = 1.80 m above rail level shall be adopted for centrifugal forces. No increased project-specific application height is required. (11) Additional Requirements for Heavy Traffic at Speeds Exceeding 120 km/h No additional project-specific requirements are prescribed for heavy freight traffic at speeds exceeding 120 km/h.Where such traffic is applicable, the Contractor shall comply with the relevant EN 1991-2 requirements, including any limitations on the applicability of the standard centrifugal-force provisions, and shall substantiate the adopted loading assumptions based on the specified railway operating conditions. (12) Loads on Cantilevers Longer than 0.5 m Carrying Railway Traffic Cantilevers longer than 0.5 m supporting railway traffic shall be designed for all applicable railway loads and load effects in accordance with the governing standards, specified railway load models and load combinations, and the Employer's Requirements. Specific dynamic analysis shall be performed where required under EN 1991-2, including Clause 8.4.6, as applicable. The Contractor shall establish and substantiate the relevant design actions for its proposed structural arrangement. No separate project-specific numerical loading value is prescribed. (13) Passenger Comfort on Temporary Railway Bridges The Employer does not require any temporary railway bridge as a mandatory element of the Works. Where a temporary railway bridge carrying operational railway traffic is required by the Contractor's proposed construction methodology, it shall be designed and verified in accordance with the applicable railway bridge design standards and railway operating requirements, including the relevant passenger-comfort criteria. The design, construction and associated approvals of such temporary works shall remain the Contractor's responsibility. No additional project-specific passenger-comfort criterion is prescribed. The above provisions establish the common basis for Proposal preparation. No further project-specific numerical values are required for the matters identified above, except where expressly specified elsewhere in the Tender Documents. The Contractor remains responsible for demonstrating compliance with all applicable design, safety, operational and performance requirements.
30 | Annex E4 | Section VII – Employer’s Requirements / Annex E4 – Railway Bridge Design Technical Specification / Clauses 5.1 and 6.1 – Structural Resistance Codes | Annex E4, Clause 5.1: TS EN 1992-1:2004; TS EN 1992-2:2004; ACI 318M-05; TS 500-2000. Annex E4, Clause 6.1: TS EN 1993-1-1:2005; TS EN 1993-1-8:2005; TS EN 1993-1-9:2005; prEN 1993-2:2003; AASHTO LRFD Bridge Design Specifications 2017. | For structural resistance verification of reinforced/prestressed concrete and steel railway bridges, the AASHTO LRFD Bridge Design Specifications, 9th Edition (2020), shall govern. References to “the latest edition in force” shall not apply to this resistance-verification basis. Inconsistent edition references concerning this basis in Annex E4 shall be read as 9th Edition (2020). The load factors and load combinations in Annex E4 Table 3.3.1 remain applicable. Other standards listed in Annex E4 Clauses 5.1 and 6.1 may be used for supplementary matters not addressed by the governing framework and shall not alter the applicable resistance or load-factor basis.
31 | Annex E1 / Annex B1 | Section VII – Employer's Requirements / Annex E1 – Design Technical Specification (entire Annex, including Clauses 3.1.1 and 3.2.3); Annex B1, Clause 4.1.4.1 | Annex E1, Clause 3.2.3: Minimum main-line curve radius: 2,500 m; 2,000 m in exceptional cases. The same clause also states that a minimum radius of 450 m is recommended and that 300 m may be used in exceptional circumstances. Annex B1, Clause 4.1.4.1: the conceptual design states a general main-line minimum horizontal curve radius of 1,500 m. Existing Annex E1 – Design Technical Specification (entire annex as issued with the RFP). | REPLACEMENT OF ANNEX E1 IN ITS ENTIRETY The existing Section VII, Annex E1 – Design Technical Specification, including all clauses, tables and figures, is deleted and replaced in its entirety by the revised Annex E1 – Design Technical Specification attached to this Addendum No. 2. The attached revised Annex E1 constitutes the complete amended text and shall be used for Proposal preparation and subsequent design. The superseded Annex E1 shall not be used. References to Annex E1 in clarification replies shall be understood as references to the revised Annex E1 attached to this Addendum, unless an express different amendment is stated. SEPARATE AMENDMENT TO ANNEX B1, CLAUSE 4.1.4.1 Original provision: a general main-line minimum horizontal curve radius of 1,500 m. Revised provision: 'The minimum horizontal curve radius of each section shall comply with the applicable design speed and geometric design requirements stated in the revised Annex E1 – Design Technical Specification. The reference/conceptual alignment shall be verified and developed in accordance with those requirements during Detailed Design.' This replacement of Annex E1 does not, by itself, amend Annex E4 or any other Annex; any such changes are made only where expressly stated in this Addendum. The revised Annex E1 attached to this Addendum shows all changes against the superseded Annex E1 in tracked changes and in bold font, so that Proposers can identify every revision. Only changes shown in this way are amendments to Annex E1. Any text that is not so marked remains unchanged from the superseded Annex E1. As this addendum is issued before Proposal submission, alignment adjustments required to comply with the amended radius requirements shall be included in the ​Proposers' design scope, with their implications accounted for in the Proposal price and implementation programme
32 | Annex E1 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clauses 3.2.1 and 3.2.4 – Cant and Cant Deficiency | Annex E1, Clause 3.2.1: Maximum cant: 130 mm. Maximum cant deficiency: 150 mm. Annex E1, Clause 3.2.4: Maximum permissible cant: 150 mm. Unbalanced cant shall not exceed 100 mm, or 130 mm in exceptional cases. | Original provisions: the maximum cant and cant-deficiency criteria in Annex E1 Clauses 3.2.1 and 3.2.4 are set out in the 'Provisions in Original RFP document' column. Amended provisions: These original Annex E1 provisions and associated tables are superseded by the revised Annex E1 – Design Technical Specification attached to this Addendum No. 2 (Amendment No. 31). The corresponding cant, cant-deficiency, cant-excess and related design criteria shall be those expressly specified in the revised Annex E1. This amendment does not itself replace or amend the text of Annex B1.The revised Annex E1 attached to this Addendum shows all changes against the superseded Annex E1 in tracked changes and in bold font, so that Proposers can identify every revision. Only changes shown in this way are amendments to Annex E1. Any text that is not so marked remains unchanged from the superseded Annex E1. As this addendum is issued before Proposal submission, alignment adjustments required to comply with the amended radius requirements shall be included in the ​Proposers' design scope, with their implications accounted for in the Proposal price and implementation programme
33 | Annex E1 / Annex B1 | Section VII – Employer’s Requirements / Annex E1 Clause 3.2.5, Table 3.7; Annex B1 Clauses 4.1.4.5–4.1.4.6 and Table 5 – Cant Ramp Gradient | Annex E1, Clause 3.2.5, Table 3.7: Cant ramp gradient: 2.00 mm/m; absolute maximum: 2.50 mm/m. Annex B1, Clause 4.1.4.5: The corresponding value shall not exceed 35 mm/m. Annex B1 Table 5: general gradient values 0.25% (suggested), 0.33% (maximum); the corrected table shows 0.20% and 0.25%. | ANNEX E1 – ORIGINAL/REVISED PROVISIONS Original: Clause 3.2.5 and Table 3.7 as reproduced in the 'Provisions in Original RFP document' column. Revised: These clauses and the associated table are superseded by the revised Annex E1 – Design Technical Specification attached to this Addendum No. 2 (Amendment No. 31). The applicable cant-transition requirements shall be as stated in that revised Annex E1. ANNEX B1 – EXPRESS AMENDMENTS (NOT REPLACED BY ANNEX E1) (i) In Annex B1 Clause 4.1.4.5, delete the original statement that the cant ramp gradient shall not exceed 35 mm/m. The spatial cant-ramp gradient dd/ds (mm/m or %) shall not be confused with the cant and cant-deficiency time rates dd/dt and dI/dt (mm/s). (ii) In Annex B1 Table 5, replace the original general cant-ramp-gradient limits of 0.25% (suggested) and 0.33% (maximum) with 0.20% and 0.25%, respectively. The revised Table 5 of Annex B1, Clause 4.1.4.6, is the corrected table. The examples S18, S20/S38 and S27/S28 (dd/ds 0.033%, 0.044% and 0.075%) are calculated examples, not alternative design limits.The revised Annex E1 attached to this Addendum shows all changes against the superseded Annex E1 in tracked changes and in bold font, so that Proposers can identify every revision. Only changes shown in this way are amendments to Annex E1. Any text that is not so marked remains unchanged from the superseded Annex E1. As this addendum is issued before Proposal submission, alignment adjustments required to comply with the amended radius requirements shall be included in the ​Proposers' design scope, with their implications accounted for in the Proposal price and implementation programme
34 | Annex E1 / Annex B1 | Section VII – Employer’s Requirements / Annex E1 – Design Technical Specification / Clause 3.3.2; Annex B1 – Conceptual Design Report / Clause 4.2.1 – Minimum Length of Constant Gradient | Annex E1, Clause 3.3.2: The minimum length of a constant gradient shall be 0.56 × V, where V is the design speed in km/h. Annex B1, Clause 4.2.1: Minimum length of constant gradient: 50 m. Annex E1 also contains an exceptional 20 m minimum; Bank requested an express applicability decision and conditions. | ANNEX E1 – ORIGINAL/REVISED PROVISIONS Original: Clause 3.3.2, as reproduced in the 'Provisions in Original RFP document' column, including its exceptional case. Revised: Clause 3.3.2 and the related criteria are superseded by the revised Annex E1 – Design Technical Specification attached to this Addendum No. 2 (Amendment No. 31). The minimum length of a constant gradient, including any permitted exceptions and conditions, shall be as stated in that revised Annex E1 for the applicable design speed. ANNEX B1 – EXPRESS AMENDMENT In Annex B1 Clause 4.2.1, the original provision 'Minimum length of constant gradient: 50 m' is deleted and replaced by: 'The minimum length of a constant gradient shall comply with Clause 3.3.2 of the revised Annex E1 – Design Technical Specification, taking account of the applicable approved design speed.' The revised Annex E1 attached to this Addendum shows all changes against the superseded Annex E1 in tracked changes and in bold font, so that Proposers can identify every revision. Only changes shown in this way are amendments to Annex E1. Any text that is not so marked remains unchanged from the superseded Annex E1. As this addendum is issued before Proposal submission, alignment adjustments required to comply with the amended radius requirements shall be included in the ​Proposers' design scope, with their implications accounted for in the Proposal price and implementation programme
35 | 137 | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities (Lot 4) / Lot 4 Summary Price Table, Activity 8 | 8 Station works Sabiha Gökçen Station | In Section IV, Lot 4 Summary Price Table, Activity 8, “Station works Sabiha Gökçen Station” is replaced by “Station works İstanbul Airport Station”. The station-design and commissioning references for Lot 4 (including Items 1.6 and 11.5) refer to İstanbul Airport Station. No mention of Sabiha Gökçen Station shall be retained in the Lot 4 schedule other than an explicitly identified cross-lot interface. No mention of Sabiha Gökçen Station shall be retained in the Lot 2 and 3 schedules other than an explicitly identified cross-lot interface.
36 | 75; 79–85 | Section III – Evaluation and Qualification Criteria / Item 3.2 – Average Annual Construction Turnover; Item 4.1(a) – General Construction Experience; Item 4.2(b) – Construction Experience in Key Activities (Lots 1–4) | Item 3.2 – Average Annual Construction Turnover: Under the Joint Venture “Each Member” column: “Must meet 20 % (twenty) of the requirement.” Item 4.1(a) – General Construction Experience: “Experience of more than 15 (fifteen) years prior to the bid submission deadline under any type of construction contracts in the role of prime contractor, JV member, Subcontractor, or management contractor.” Under the Joint Venture “Each Member” column: “Must meet requirement.” Item 4.2(b) – Construction Experience in Key Activities: For Lots 1–4, the requirement includes experience in the design of railway systems (including tunnels) with a route length of at least 20 km under a single contract. Joint Venture compliance columns: “All Members Combined” – “Must meet requirements”; “Each Member” – “N/A”; “One Member” – “N/A”. | Under Section III, Item 3.2, in the column “Each Member”, add: “Where a member of a Joint Venture is proposed to perform design services under this Contract, the Average Annual Construction Turnover requirement shall not apply to that JV member proposed for design services.” Under Section III, Item 4.1(a), in the column “Each Member”, add: “Where a member of a Joint Venture is proposed to perform design services under this Contract, the requirement for fifteen (15) years of experience under construction contracts shall not apply to that JV member. Instead, a JV member proposed for design services shall demonstrate at least ten (10) years of experience in design of works under railway projects.” The qualification criteria in Item 4.2(b) remain applicable to the Proposer as a Single Entity or in case of JV to All members combined, and cannot be satisfied by a Specialized Subcontractor's experience.
37 | Section IX | Section IX – Contract Data, Sub-Clauses 14.6.3 and 14.6.5 / KPI Schedule – Definition of Working Day | “Working Day” is not expressly defined for the KPI procedures. | For the purposes of Sub-Clauses 14.6.3 and 14.6.5 and the KPI Schedule, “Working Day” means any day that is an official working day in Türkiye, excluding Saturdays, Sundays and official public holidays in Türkiye.
38 | Section IV | Section IV – Proposal Forms / Schedule of Priced Activities and Sub-activities, Lots 1–4 / Table column headings | The prefatory text uses “Activities and Sub-Activities”, while schedule tables use the heading “Deliverable” / “Deliverables”. | In all Section IV Schedule of Priced Activities and Sub-activities tables for Lots 1–4, the column heading “Deliverable” or “Deliverables”, as applicable, is replaced by “Deliverables/Sub-activities”. The prefatory text and the lump-sum pricing basis remain unchanged.
39 | Section VII | Section VII – Employer’s Requirements / Clauses 5.3.3 and 4.6.2–4.6.4 – Power-supply simulations, reconciliation and revisions | Lots 2 and 4 prepare independent system-wide simulations; the Engineer issues directions under ER Clause 5.3.3, coordinated with ER Clauses 4.6.2–4.6.4. No reconciliation decision deadline is specified. | Add the following clarification to ER Clause 5.3.3, read with Clauses 4.6.2–4.6.4: “Each of the Lot 2 and Lot 4 Contractors shall independently submit the system-wide train operation/power-supply simulation for the full corridor. The Engineer shall reconcile the submissions and issue its written system-wide power-requirements direction following receipt of both complete, compliant simulations, and in any event no later than the end of the Detailed Design phase. The Engineer shall document and communicate the technical basis of any inconsistency and the attribution of responsibility after reviewing the assumptions, interfaces, input data and compliance of both simulations. Revision costs arising from a Contractor's non-compliant inputs or design assumptions shall be borne by the responsible Contractor(s) in accordance with ER Clause 4.6.2, after an evidenced determination by the Engineer; responsibility shall not be assigned merely because an Engineer's direction requires a change. Where no Contractor non-compliance is identified, the contractual consequences of a change shall be dealt with under the applicable Conditions of Contract. ER Clause 4.6.4 applies to normal coordination and harmonisation obligations, subject to the Conditions of Contract.”
40 | Annex E1 / Annex E4 | Section VII – ER / Annex E1 Clause 5.12.1 – Railway Bridges and Viaducts / Alignment with Annex E4 | Annex E1 Clause 5.12.1 sets railway-bridge loading and action values inconsistent with the specific railway-bridge design requirements of Annex E4. | ANNEX E1 – ORIGINAL/REVISED PROVISIONS Original: The railway-bridge-specific loading, actions and fixed numerical values in Annex E1 Clause 5.12.1 (see the 'Provisions in Original RFP document' column). Revised: The original Annex E1 is replaced in its entirety by the revised Annex E1 attached to Addendum No. 2, Amendment No. 31. The superseded text of Clause 5.12.1 does not continue to apply. ANNEX E4 – APPLICABLE, SEPARATELY PRESERVED REQUIREMENTS For railway bridges and viaducts, the discipline-specific design provisions of Annex E4 continue to govern, including railway vertical loads (Clause 3.5.3), dynamic effects (Clause 3.5.4.5 and Amendment No. 28), centrifugal/nosing/traction and braking actions (Clauses 3.5.5.1–3.5.5.3), derailment actions (Clause 3.12), and railway bridge load combinations and factors (Clause 3.3, Table 3.3.1). This amendment does not change Annex E4 or Amendment No. 30.
41 | 100 / Section IV | Section IV – Proposal Forms / Table C – Provisional Sums, Lots 1–4 | The Table C row “Provisional sums expressed in local currency” includes only Provisional Sum P.1, excluding P.2 (Livelihood support). | In Section IV, Table C, the row “Provisional sums expressed in local currency” shall include the sum of P.1 and P.2 for each Lot, replacing the amounts currently shown: Lot 1: P.1 TRY 736,000,000.00 + P.2 TRY 800,000,000.00 = TRY 1,536,000,000.00. Lot 2: P.1 TRY 433,000,000.00 + P.2 TRY 450,000,000.00 = TRY 883,000,000.00. Lot 3: P.1 TRY 403,000,000.00 + P.2 TRY 450,000,000.00 = TRY 853,000,000.00. Lot 4: P.1 TRY 702,000,000.00 + P.2 TRY 750,000,000.00 = TRY 1,452,000,000.00. Both P.1 and P.2 shall be excluded from the local/foreign-currency percentage calculation in Table C; P.2 is denominated in TRY and administered under Sub-Clause 13.4, with price adjustment only if allowed by Sub-Clause 13.7.
42 | 104 / Section IV | Section IV – Proposal Forms / Lot 1, Activity 3 – Alignment Infrastructure and Slope Stabilization / Items 3.1, 3.3 and 3.5 | Items 3.1, 3.3 and 3.5 each commence with “Project Start” in the issued Schedule of Priced Activities. | In Section IV – Schedule of Priced Activities and Sub-activities, Lot 1, Activity 3, Item 3.1 retains “Project Start” as its starting reference. For Items 3.3 and 3.5, the repeated reference to “Project Start” is deleted; the start and end limits of these items shall correspond to the respective alignment segments shown in Annex A1. The remaining scope descriptions of Items 3.1, 3.3 and 3.5 remain unchanged.
43 | Section III / Section VII | Section III – Evaluation and Qualification Criteria, Technical Part / Sub-factor 8.2.1; ER Clause 11.7.2 – Local suppliers and subcontractors | The definition of “local” for subcontractors and suppliers in Technical Sub-factor 8.2.1 is not stated; ER 11.7.2 defines local individuals. | For the purpose of Technical Evaluation Sub-factor 8.2.1 only, “local subcontractors and suppliers” means subcontractors and suppliers with an established operational/business presence in Türkiye that provide goods or services contributing to the local economy. Each Proposer shall identify the basis for classifying a proposed subcontractor or supplier as local and describe its targets and monitoring method. The residency-based definition for local individual workers in ER Clause 11.7.2 remains unchanged and applies only to individuals.
44 | Section VII | Section VII – Employer’s Requirements / Annex E1 – Special Systems; Annex L – Signalling and Telecommunication / Cross-package interfaces | The RFP refers to Early Earthquake Warning, Climate-Based Limited Operation and Mass-Spring systems without a single scope-allocation statement across Package 2 and the civil-works Lots. | For the purpose of defining the scope and pricing of Special Systems, functions that form part of signalling, telecommunication and supporting systems—including signalling-integrated early-earthquake-warning and climate-based limited-operation functions—are allocated to Package 2. The relevant Lots 1–4 Contractor(s) remain responsible for all civil, structural, foundations, power, passive safety, interface and other enabling works expressly included in their Lot scope. The Mass-Spring System, wherever required by the approved track/civil design, remains within the relevant Lot Contractor's scope and is governed by the added Mass-Spring System Technical Specification (Amendment 13). These allocations do not relieve any Contractor from coordination and interface obligations under Section VII.