## REPLIES TO QUERIES No.2
PROJECT NAME AND LOAN NO:
RAIL LOGISTICS IMPROVEMENT PROJECT - 91450 TR
TITLE OF WORKS AND RFB NO:
Construction Works for Branching Railway Lines to the industrial facilities at the Cukurova Region, Yumurtalik Free Zone and the Ports at the Iskenderun Bay AYGM-YAP-2023-WB 02
Replies to Queries and Clarifications No.2
The provisions of this "Replies to Queries and Clarifications" are being issued to provide necessary clarifications on certain aspects of the Request for Bidding document in response to the queries or clarification requests raised by Bidders
No. | RFB Document Page no. | RFB Document Reference Clause | Querry or Clarification Requested by the Bidder | Reply of the Employer | Amendment in the RFP document is required
1 | 62-63 | Section III - Evaluation and Qualification Criteria A.Qualification, 4.2(c) | With the reference of Item 4.2.(c), please confirm our understanding is correct as following. Any kind type of contract, which is being implemented according to the environmental and social management plan to prove the experience in managing ES risks and impacts, can be acceptable to fulfil the requested criteria | Any kind type of contract, which is being implemented according to the environmental and social management plan to prove the experience in managing ES risks and impacts, shall fulfil the requested criteria | No
2 | 62-63 | Section III - Evaluation and Qualification Criteria A.Qualification, 4.2(c) | With the reference of Item 4.2.(c), please confirm our understanding is correct as following.We are asking your kind confirmation any type of contract which is procured and being implemented under World Bank regulations can be acceptable. | Implementing environmental and social management plan in any kind of projects shall fullfil the requested criteria regardless of source of financing. | No
3 | 62-63 | Section III - Evaluation and Qualification Criteria A.Qualification, 4.2(c) | With the reference of Item 4.2.(c), please confirm our understanding is correct as following.Regarding the reference project(s) which is substantially completed/under implementation, any kind of proof documentation which is showing that project is being implemented according to the environmental and social management plan and is confirmed by the Employer can be acceptable to fulfil the requested criteria. | Any kind of proof documentation supported by the employer’s letter confirming satisfactory completion of environmental and social management plan is acceptable and will fulfil the criteria. | No
4 | - | - | We obtained the alignment drawings and structural drawings are missmatching with each other. The structure chainages are not same as alignment drawings, types and size of structures are different. Could you please clarify. | Please refer to Addendum No. 1/Amendment No.5 | No
5 | 150 | Section IX - Particular Conditions of Contract Part A - Contract Data, 14.3(iii) | We respectfully request that the Client considers accepting a bank letter (also known as a letter of guarantee) instead of the traditional retention money holdback. This option would provide you with a guaranteed financial security against any potential non-performance on our part, while simultaneously improving our cash flow and facilitating smoother project execution. | The related sub-clause shall remain unchanged. | No
6 | - | - | What is the status of site expropriation plan? Will the contractor able to access to site for the project in whole route? | The mentioned studies are currently in progress. Client is coordinating closely with the relevant authorities to ensure timely completion. Please also refer to Item A.2.2.43 of the General Technical Specification. | No
7 | 40 | Section II - Bid Data Sheet ITB 7.4 | The date of the meeting needs to be corrected. Please clarify. | The date of the meeting has been rearranged, Please refer to Addendum No.1 | No
8 | - | - | The release conditions of the ES Performance Security are not defined in the tender documents. Please clarify. | As stated in Section IX - Particular Conditions of the Contract, Part B - Special Conditions Sub-Clause 4.2," the term “Performance Security” is replaced with: “Performance Security and, if applicable, an Environmental and Social (ES) Performance Security”. Therefore, the return of ES Performance Security shall be according to Sub-Clause 4.2.3. | No
9 | - | - | It is stated in tender documents that payment is allowed in multiple currencies. However, it is not clear how different currencies will be shown in the Bill of Quantities and consequently presented in the bidder's offer. Please advise. | Bills shall be inputed in Turkish Lira(TL) only. Consequently, bidder's offer shall be in TL only. However, the bidders shall state the currency(ies), percentage(s) and rates of exchange in Appendix to Bid - Table C. Each payment will be done according to the type, percentage and rate of exchange that is stated by the bidder. Please also revisit ITB 15.1. | No
10 | - | - | In addition to the lines shown in the ITB, the following lines are present in the project filed: c.Yukarıburnaz-Port Line (~6 km) d.Yukarıburnaz-OIZ Line (~8 km) Please confirm that the current scope of the project comprises of the following 4 lines: a.Erzin Station - Tayseb Station Connection Line (~16.79 km) b.OIZ - Port Connection (~13.05 km) c.Yukarıburnaz-Port Line (~6 km) d.Yukarıburnaz-OIZ Line (~8 km) | Due to the stakeholder requests, the mainlines are updated within the context of revised design. The project comprises of the following 4 lines: a.Erzin Station - Tayseb Station Connection Line (~16.79 km) b.OIZ - Port Connection (~13.05 km) c.Yukarıburnaz-Port Line (~6 km) d.Yukarıburnaz-OIZ Line (~8 km) | No
11 | 60 | Section III - Evaluation and Qualification Criteria A.Qualification, 3.2 | In Section III (Evaluation and Qualification Criteria) according to 3.2 Average Annual Construction Turnover, "Minimum average annual construction turnover of US$ 130,000,000 (one hundred and thirty million) calculated as total certified payments received for contracts in progress and/or completed within the last 5 years (i.e. 2018, 2019, 2020, 2021, 2022) starting 1st January 2018, divided by years", which date exchange rate should we use for converting to USD for the turnover issued in Turkish Lira? | Date of exchange rate is 30th June or the latest business day before the given date of respective calendar year as it is stated in Section III - Evaluation and Qualification Criteria page 47. | No
12 | 43 | Section II - BDS ITB 22.1 & 25.1 | As per your announcement, the tenderer need to submit their proposals no later than 27th March 2024, 14.30. Whereas the time for preparation of proposals is very limited in order to prepare and submit appropriate bids, it would be highly appreciated to accept an extension at least 1(one) month to make the tenderers able to prepare and submit the comprehensive and competitive proposals, to be conform compeletly to the project specifications and the employer criteria's. | Please refer to Addendum No.3 | Addendum No.3 Amendment No 2&3
13 | - | - | In case of JV, should all partners of the JV purchase the tender document? Is it sufficient for one partner to buy? Please confirm. | It is sufficient for one partner to buy. | No
14 | - | Section VII - Works' Requirements Drawings | The DWG and PDF drawings of the same structures shared within the context of art works do not match. When pricing, which one should be considered correct, DWG or PDF? | Please refer to Addendum No. 1/Amendment No.5 | No
15 | - | Section VII - Works' Requirements Drawings | In the shared project 01_ILTISAK\12+337.090, missing pages have been observed. Please complete the pages. | There are 3 files for the culvert 12+337.090, which consists of; 1- General Layout Plan 2- Wingwall Reinforcement Plan 3- Strip Reinforcement Plan In the folder, 01_ILTISAK the scanned file for number 3 is missing. The file can be viewed as dwg in SANAT YAPILARI\MENFEZ\ILTISAK_HATTI\12+337_2.0x2.0 | No
16 | - | - | Can all materials extracted from the basalt barrow pit located 50 meters to the right of OSB - Station (1) Line at km = 0+500 be used as fill material? If the DSI 6th Regional Directorate does not approve the use of this quarry, can you suggest an alternative quarry to meet the filling requirement? | Employer will not suggest any quarry. Availibity of mentioned or any other alternative quarry shall be surveyed by the bidders. | No
17 | - | - | Looking at the presentation date of the EIA Report, we see it as May 14, 2020. In the aformentioned section 3.2.4.3. on Stone Quarries and Barrow Pits, it is stated that "There is more than 1,000,000 m3 of reserves in Yılankale Quarry. The quarry is located on state land and is licensed on behalf of the 5th Regional Directorate of Highways, operated by a private company. "Similarly, it is stated in the same section, "In Badıllı Stone Quarry, quarry material will be crushed and screened to be suitable for use as ballast material. There is more than 1,000,000 m3 of reserves in the quarry. The quarry is licensed on behalf of a private company, and quarry operations are still ongoing.". Assuming current usage, can you confirm that the same amount of material remains in these same quarries as of today (March 6, 2024)? | Employer will not suggest any quarry. Current situation of the mentioned quarry is not in concern of the Employer. Bidders shall carry out their own study related to potential quarries. | No
18 | - | Sectiın IV - Bidding Forms | At “Section III-Evaluation and Qualification Criteria”, “Item 1.5 Equipment”, it is stated that “The Bidder shall provide further detail of proposed items of equipment using the relevant Form in Section IV, Bidding Forms”, however we couldn’t see any relevant Equipment Form. Please provide that form. | Please refer to Addendum No.3 | Addendum No.3 Amendment No. 5
19 | 50 | Section III - Evaluation and Qualification Criteria 1.4 Contractor's Representative and Key Personnel | At “Section III-Evaluation and Qualification Criteria”, “Item 1.4 Contractor’s Representative and Key Personnel” “Min. 5 years relevant experience and Min. 8 years overall Experience” is stated. Are the Social Lead and Archaeologist mentioned in the article required to have 5 years of experience in a similar project (Railway, Metro, etc.) or in a similar position? | Social Lead and Archaeologist shall have 5 years of experience in any construction work to fulfil the requirement. | No
20 | 43 | Section II - BDS ITB 22.1 & 25.1 | We kindly would like to request 4 (four) weeks of extension for the submission of aforementioned project. We assure you that the requested time extension for the submission will enable us to provide you with a well-surrounded, comprehensive, and more competitive proposal | Please refer to Addendum No.3 | Addendum No.3 Amendment No 2&3
21 | - | - | We were expecting the receive a draft contract which is “ Conditions of Contract for Construction for Building and Engineering Works Designed by the Employer (“Redbook”) Second edition 2017, reprinted 2022 with amendments ” published by the (FIDIC) as stated in the Section VIII of the ITT. Could you kindly confirm that the document you shared is the only tender document, please? | Due to the copyrights, it must be obtained from FIDIC itself or other organizations authorized by FIDIC. | No
22 | 40 | Section II - Bid Data Sheet ITB 7.4 | As per ITB 7.4 of ITT, pre-bid meeting shall take place on 05.07.2024 which is after the deadline of the tender. Deadline of the tender is 27.03.2024 as per ITB 22.1. Could you confirm the pre-bid meeting date, please? | Please refer to Addendum No.1 | Yes
23 | 190 | Section IX – Particular Conditions of Contract Part B - Special Provisions 21.6 | Referring to Section IX – Particular Conditions of Contract, Sub-Clause 21.6 Arbitration Please clarify for a JV bidder, is the Place for Arbitration decided based on origin of leading partner of the JV bidder? | Place of arbitration shall be decided considering origin of all JV members. | No
24 | 43 | Section II - BDS ITB 22.1 & 25.1 | A very meticulous and coordinated work is being carried out by us in order to make a more competitive bid and to make proper calculations in terms of engineering. In order to finalize these studies, we request that you grant an extension of time of not less than 6 weeks. | Please refer to Addendum No.3 | Yes
25 | - | Section VII - Works' Requirements Specifications | "5.43. TCDD's building gauge shall be unconditionally provided for the placement of equipment along the road. Where necessary, signal bridge carrier console will be used." According to the relevant article, Could you please indicate and clarify where and how many Signal Bridge Carrier to be used? | Although signal bridge construction is not currently planned, as clearly stated in items 9.28 and 9.39 of the Technical Specification for Construction of Signalization Systems, in case of insufficient clearance according to the track conditions, required number of signal bridges will need to be constructed by the Contractor as additional work in accordance with the Contract. | No
26 | - | Section VII - Works' Requirements Specifications | • Temporary speed restrictions should be assignable from 5 km/h to 195 km/h in 5 km/h speed floors. According to the relevant article, The speed criterion of all other articles regarding the speed requirement of the specification is 160 km/h. We assume that the speed criterion in this article should be up to 160 km/h, please confirm. | Temporary speed restriction criterion in the article of item 14.20 of Technical Specification for Construction of Signalization Systems will be up to 155 km/h. | No
27 | - | Section VII - Works' Requirements Specifications | 15.2. Automatic train stopping systems will operate smoothly and safely at train speeds up to 160 km/h. 15.11. Each crossing signal on the Project line will be equipped with automatic train stop crossing systems. In addition, automatic train stopping crossing systems will be installed at a distance of 300 meters approaching each entrance signal and 40 km/h signs indicating that the section in question will be crossed at a maximum speed of 40 km/h and will be easily visible from the engineer's cab. SIN-107.2.2 Type D ATS wayside Equipment (including cable, roadside cave, all connection equipment, 40 km speed sign and design). According to the relevant article, Could you please clarify what will be operating speed with ATS? | Technical specification is clear. Relationship between the signal notification (block, entrance and exit signals) and the response of the relevant ATS magnet based on this signal notification is given item 15.12 of Technical Specification for Construction of Signalization Systems. Maximum train speed allowed by ATS system based on the signal notification is also given in the item of 15.12 of Technical Specification for Construction of Signalization Systems. The maximum operating speed at which automatic train stopping systems will operate smoothly and safely is also clearly stated in 15.2 of Technical Specification for Construction of Signalization Systems. | No
28 | - | Section VII - Works' Requirements Drawings | In the tender documents we found geological drawings of the railway route, however we couldn’t see neither geological report nor borehole logs. Could you please provide report and logs for a better undestanding of the soil conditions. | The geological reports and borehole logs are presented in the Employers Design (dated 2019) folder. The data can be found in \JEOTEKNIK RAPOR. The revised project (dated 2023) are designed accordingly and no additonal boreholes are drilled on the site for this project. | No

## ADDENDUM No.3
PROJECT NAME AND LOAN NO:
RAIL LOGISTICS IMPROVEMENT PROJECT - 91450 TR
TITLE OF WORKS AND RFB NO:
Construction Works for Branching Railway Lines to the industrial facilities at the Cukurova Region, Yumurtalik Free Zone and the Ports at the Iskenderun Bay AYGM-YAP-2023-WB 02
ADDENDUM NO: 3
The provisions of this Addendum are being issued to modify or amend certain provisions of the Request for Bid (RFB) document as a result of changing circumstances or additional information being available from the Employer or in response to the queries raised by the Bidders.The RFB document is hereby amended as below:
Amendment No. | RFB Document Page No. | RFB Document Reference Clause | Clause in the Original RFB Document | Amended Clause
1 | 42 | Section II - Bid Data Sheet ITB 18.1 | The Bid shall be valid until: 23.08.2024 | The Bid shall be valid until:13.09.2024
2 | 43 | Section II - Bid Data Sheet ITB 22.1 | The deadline for Bid submission is: Date: 27.03.2024 Time: 14:30 | The deadline for Bid submission is: Date: 17.04.2024 Time: 14:30
3 | 43 | Section II - Bid Data Sheet ITB 25.1 | The Bid opening shall take place at: Street Address: Hakkı Turayliç Caddesi No:5/B Emek Floor/ Room number: Floor: Ground Floor, Room: Conference Room City: Ankara Country: Türkiye Date: 27.03.2024 Time: 14:30 | The Bid opening shall take place at: Street Address: Hakkı Turayliç Caddesi No:5/B Emek Floor/ Room number: Floor: Ground Floor, Room: Conference Room City: Ankara Country: Türkiye Date: 17.04.2024 Time: 14:30
4 | 45 | Section II - Bid Data Sheet ITB 36.1 | The date for the exchange rate shall be: 13.03.2024 (at 15:30 o’clock) | The date for the exchange rate shall be: 03.04.2024 (at 15:30 o’clock)
5 | - | - |  | Form EQU: Contractor's Equipment has been added to Section IV: Bidding Forms which shall be used for Section III - Evaluation and Qualification Criteria, Equipment.