## REPLIES TO QUERIES
PROJECT NAME AND LOAN NO:
RAIL LOGISTICS IMPROVEMENT PROJECT - 91450 TR
TITLE OF WORKS AND RFB NO:
Construction Works for Branching Railway Lines to the industrial facilities at the Cukurova Region, Yumurtalik Free Zone and the Ports at the Iskenderun Bay AYGM-YAP-2023-WB 02
Replies to Queries and Clarifications
The provisions of this "Replies to Queries and Clarifications" are being issued to provide necessary clarifications on certain aspects of the Request for Bidding document in response to the queries or clarification requests raised by Bidders
No. | RFB Document Page no. | RFB Document Reference Clause | Querry or Clarification Requested by the Bidder | Clarification of the Employer | Amendment in the RFP document is required
1 | 43 | Section II - Bid Data Sheet BDS 22.1 & 25.1 | We kindly request and request that the relevant tender be postponed to 05.06.2024, as we are in the process of registering the work completions of our project partners, Chinese company Covec CO, to EKAP. | Please refer to Addendum No.6. Please kindly note that the prospective bidders are not required to register to EKAP or any other platform at the bidding stage to submit their bids. | No
2 | - | - | Considering the progress thus far and based on the design drawings provided by your esteemed authority during tender stage, although the tender appears to be referenced under the FIDIC Red Book, it is understood that the project's design drawings will be re-produced by the contractor with existing revisions and corrections. Please confirmed. | Design drawings have already been shared with the bidders. These designs can be subject to further refinement "as deemed necessary" to ensure accuracy and compliance with project requirements. | No
3 | - | Section IV - Bidding Forms Bill of Quantities | As part of the Clarifications No. 3, Addendum No. 4 Document which has been published on 16.04.2024 by your esteemed administration, the following question has been addressed: “At typical drawings of Stations, we see Landscaping and Asphalt Areas images. Please clarify the scope of “Lump Sum Station Works” in details. We are confused if the Landscaping, Asphalt works at parking area, loading/unloading areas of containers, truck maneuver area and the soil improvements of these areas are included or not? If these are included in the scope , please provide us the related drawings and specifications of Landscaping , Asphalt works at parking area, loading/unloading areas of containers, truck maneuver area and the soil improvements of these areas.” This question has been answered in Response No. 101 as follows: “The mentioned works are not included in the scope.” In addition, as part of the Clarifications No. 4, Addendum No.6 Document which has been published on 08.05.2024, the following question on a similar topic has been addressed: “We undertstand that the construction of the Station Buildings includes all passenger, loading & unloading platforms from the Unit Price Preamble of the Station, but we cannot understand if landscaping and car parking areas are in scope or not. Please Clarify” This question has been answered in Response No. 137 as follows: “Please refer to station projects folder included in the Tender documents. Please also refer to unit price description / specifications regarding stations included in preamble, General Technical Specifications and Station Buildings Specifications. Another question has been addressed as part of Clarifications No. 4, which is as follows: “For the construction of Station Buildings, as per Preamble to Bill of Quantities – Unit Price Definitions for Station Buildings, Item No. SB-100; It is stated that “All kinds of equipment, materials, labor, and transportation costs for the construction of the work are included in the unit price and there is no cost not included in the unit price.” Could you kindly clarify if soil improvement, excavation, back filling, and concrete works of the entire station platforms and station buildings are included in the set prices? If they are not included, please advise if above mentioned civil works are going to be reimbursed from the relevant unit prices defined in “Bill No.1_Infrastructure Works”.” This question has been answered in Response No. 4 as follows: “Soil improvement, excavation, back filling, concrete works of the entire station platforms and station buildings and any other works stated in the specification section(costs included in the unit price/costs not included in the unit price/payment) of Unit Prices Item No SB-100, and Technical Specifications of Station Buildings are included.” In light of the above questions and answers, we assume that the reply from Clarifications No. 3 do not directly align with the replies from Clarifications No.4., and Clarifications No. 4 document does not directly express the same judgement from Clarifications No.3. However, as the Clarifications No. 3 document directly states that the landscaping, asphalt works, parking area works and the soil improvement works in these areas are out of scope we conclude that this response shall prevail. We kindly request the clarification of the above matter from your esteemed administration as to which works are out of scope from the Bill of Quantities Item No. SB-100. | Considering the logic put forward by all the Employer's answers referred to in your question, it is clear that there is no contradiction. These responses primarily focus on the 'Item Definition' and specification content of the relevant Price Items under the 'Station Buildings section' within the context of the 'Preamble Document'. Therefore, your confirmation request regarding the landscaping, asphalt works, parking area works, and soil improvement works being out of scope, as stated in the last part of your question, is confirmed and aligns with the previous answers. | No
4 | - | Section VII - Employer's Requirements Drawings | In your Q&A_No.4 / Answer 22, you wrote that the Buffer Stops is not included in the scope of work. However, in Q&A_No.3 / Answer 35, you wrote that the Buffer Stops is included in the relevant unit price. In the unit price descriptions, there is no work item that includes the Buffer Stops. Please clarify. | Answer 22 of Clarifications No. 4 in your inquiry pertains to Kurtpınarı Station, while Answer 35 of Clarifications No. 3 relates to certification. | No
5 | - | Section IV - Bidding Forms Bill of Quantities | According to Q&A_No.3 / Question 101 ; - Asphalt works - Landscape Works - Ground Improvement Works Aren’t included in "Turnkey(set)" Station Buildings work item (SB-100). However, in Q&A_No.4 / Answer 4, it’s stated that the unit price of Station Buildings (SB-100) is include these works. Which one is true? Please clarify this situation. | Please refer to answer no. 3 | No
6 | - | Section IV - Bidding Forms Bill of Quantities | In Q&A_No.4 / Answer 69, you wrote to look at the station projects, SB-100 pose unit price description and Station Technical Specifications regarding our previous question. However, there is no explanation about asphalt and ground improvement works in the unit price description and station projects. In addition, there are only architectural, mechanical and electrical works technical specifications for the station buildings there is no more specification ex. Civil works, substructure of stations etc. Please clarify this situation and publish specification and projects for calculating turnkey price. | Please refer to answer no. 3 | No
7 | - | Section IV - Bidding Forms Bill of Quantities | Station Buildings and Loading/Unloading Platforms; - Ground Improvement Works - Asphalt Works, - Landscape Works - Excavation Works - Filling Works Please clearly indicate from which pose in the BOQ they will be paid. Will these productions be paid from the SB-100 unit price? Or will they be paid from the relevant poses in BOQ Infrastructure Works? If these will be paid under unit SB-100 we need detailed certain projects for calculating. | Please refer to answer no. 3 | No
8 | - | - | In Q&A_No.4 / Answer 48 you wrote that 3 new stations will be built. In previous answers, you wrote that 4 new stations will be built. We think there is a mistake. From the projects; - OIZ Station - Tayseb Station - Yukarıburnaz Station - Port Station , We see that 4 stations will be built. Please confirm. | There is a typo in Clarification No. 4 / Answer No. 48. The answer shall be "There are five stations included in the project, four of which are to be newly constructed. The railway line project begins from Erzin Station. In Erzin Station, there will be no works in the station buildings, only the platforms will be enlarged." | No
9 | - | - | In Q&A_No.4 / Answer 33, you stated that line dismantling works are included in the cost of unit prices. However, there is no work item to include line dismantling works. Please explain. | There is no unique pose for dismantling works. The line dismantling works shall be accepted as general expense. No additional payment will be made for this work. | No
10 | - | - | In Q&A_No.4 / Answer 52, you stated that only the platforms will be extended at Erzin station and ground improvement works are not necessary. However, we think that ground improvement may be necessary according to the size of the expansion. Please specify how much the platforms will be extended. | The mentioned platform in Clarifications No.4 / Answer 48 & 52 to be enlarged, is a railway platform, so there will be no expansion station or loading platform of Erzin Station. | No
11 | - | - | In Q&A_No.4 / Answer 87, you stated that the trees to be cut / transported within the expropriation area are within the overhead cost and in Answer 57, you stated that the permits for tree transport / cutting works are the responsibility of the contractor. There are quite a lot of trees on the lands that have been/will be expropriated and the size of the work to be done cannot be evaluated within the general expense. For this reason, in order to make the necessary calculation, it is necessary to clarify the situations in which these trees will be cut or moved and the number of trees should be shared with us. | The project site is easily accessible, enabling the contractor to conduct thorough surveys and gather essential data. Contractors experienced in the sector can submit competitive tenders based on their past experience in similar scopes/projects | No
12 | - | Section VII - Employer's Requirements Drawings | There is no difference between the shared as revised geological itinerary and the previous project. Please indicate the change made. | Please refer to Addendum No.7, Serial No.1 | Yes
13 | 151 | Section IX – Particular Conditions of Contract Part A - Contract Data, Sub Clause 14.5(c)(i), Plant and Materials | In Q&A No.4 / Answer 191, you stated that in order to avoid confusion, Rail, Traverses etc. material payments will be made as specified in the relevant item. However, in Addendum No.6 / Amendment No.6, only the percentages of Rail, Traverses, Slab Tracks materials have been deleted. In this way, it is understood that 100% of the materials will be paid. Please explain. | The payment shall be done as determined in the General and Particular Conditions of the Contract, and the Preamble. | No
14 | 117 | Section IV - Bidding Forms Table of Adjustment Data, Table B: Foreign Currency (FC) | In the description of Table B standard form, it is written that it will be used if payments are allowed to be made in foreign currency. However, the BDS states that the bid currency and payment currency will be in Turkish Lira. In this case, we understand that Table B will not be used. However, within the scope of Q&A, we constantly refer to the use of Table B. We think that there is a mistake. Please explain this situation and how to use the tables. | The bidders shall quote the Bill of Quantity in Turkish Lira. However, progress payments to contractor shall be made in the proportion of currency(ies) with requested exchange rate that is determined in Table C by the bidder. Table C shall be filled by the bidder. Table B shall be used if bidder requested any foreign currency in Table C. Table B shall be filled for each different type of foreign currency requested by the bidder. Please also refer to Clarification No.4, Answer No. 95, 167, 181 and 194. | No
15 | - | Section VII - Employer's Requirements Drawings | In many previous answers, you stated that calculations should be made according to the 2023 route projects. However, in Q&A No.4 / Answer 110, you wrote that the 2023 route projects will also be redesigned. In the route project sheets, the projects are shown as "Final". Please clarify this situation. | All relevant calculations should be made according to the 2023 designs.These designs can be subject to further refinement "as deemed necessary" to ensure accuracy and compliance with project requirements. | No
16 | - | Section VII - Employer's Requirements Drawings | In Q&A No.4 / Answer 135, you answered that the empty areas mentioned in the question can be used for loading and par areas like other stations. Please clarify the word " can be considered". | It means that "it shall be considered". | No
17 | - | Section IV - Bidding Forms Bill of Quantities | Will the asphalt pavements to be made in the parking/loading areas of the station buildings be included in the SB-100 set price of the station works? (You stated in Q&A No.3 / Answer No.101 that it is not included in the Station Works.) Or will it be paid from the asphalt works poses included in the infrastructure works? Please explain this situation. If it will be included in the station set price, please clearly indicate the areas to be paved with asphalt. Since this production will be carried out in a very large area, it affects our cost to a great extent. | Please refer to Answer no. 3 | No
18 | - | Section IV - Bidding Forms Bill of Quantities | Is the area included in pose SB-100 only Station Building, Loading/Unloading platforms? (Approximately 19.500 m²/for per station) or else approximately 15.000 m² (for per station) maneuver area, car parking area, landscaping area included in the SB-100 Station Building pose? This information is required for the calculation of the ground improvement cost included in the SB-100 pose. Please explain. | Please refer to Answer no. 3 | No
19 | 152 | Section IX - Particular Conditions of Contract Part A. Contract Data, Sub-Clause 19.2.4 | Regarding below amended clause (Section IX - Particular Conditions of Contract Part A. Contract Data, Sub-Clause 19.1) kindly confirm if "maximum cumulative deductible" means the maximum insurance deductible for each and every loss for each insurance policy. Since the number of losses to be incurred during project / insurance period cannot be predicted from the start of a project and insurance policy, it is not possible to determine a cumultaive deductible amount for all losses. Sectin IX - Particular Conditions of Contract Part A. Contract Data, Sub-Clause 19.1 "The maximum cumulative amount for deductibles of each insurance shall not exceed 3% of the Contract Amount" | Please refer to Addendum No.6, Amendment #13. The contractor can offer deducutibles for each insurance provided. 'The maximum cumulative amount for deductibles of each insurance shall not exceed 3% of the Contract Amount. | No
20 | - | Section IV - Bidding Forms Bill of Quantities | As part of Addendum No.6 Serial No.18, 19 and 20, the Work Items No: SIN-108.1 and SIN-108.2 have been removed from the Bill of Quantities and Unit Price definitions. The cable channels for the signalling and telecommunication systems cables have been defined within the Technical Specification, Signal&Telecom, 4 - Cable Construction Technical Specifications under Article 9.1. We understand that the price for the cable channels as explained within the Article 9.1 of the Signalling & Telecom Systems Technical Specifications, 4-Cable Construction Technical Specifications, will be indicated and paid under the unit price item 76.110.3401 of the infrastructure works. Please confirm. | It is confirmed. | No
21 | - | Section IV - Bidding Forms Bill of Quantities | The first sentence of unit price definition for the unit price item "76.110.3401 Construction of Precast Cable Ducts and Covers (All Inclusive)" contains a description such as "In accordance with the principles and conditions specified in the Project design and Technical Specifications, conforming to the instructions to be given by the Engineer, construction and placement of precast cable ducts and covers, precast covers in engineering structures and drainage covers in the tunnels." Precast covers of engineering structures and drainage covers are not defined within the technical specifications of the Cable ducts (Article 9.1 of the Signalling & Telecom Systems Technical Specifications, 4 - Cable Construction Technical Specifications). Please confirm that this unit price definition is only for the "Construction of Precast Cable Ducts and Covers" and does not include the construction of covers for the drainage system or covers for other engineering structures. | The item 76.110.3401 contains only the construction of cable ducts and their covers. Precast covers of engineering structures and drainage covers will be paid from item 76.110.2851. | No
22 | - | Section IV - Bidding Forms Bill of Quantities | Regarding unit price description of Item No: 76.110.2801; it is understood that reinforcement rebar is excluded in this item. Please confirm the reinforcement rebars of prestressed bridge beams will be paid in Item No: 76.110.2101-R | It is confirmed. | No
23 | - | - | Is there a designated area for the borrow pit? | Clarification No.4, Answer No. 11 has been updated as below: Please refer to respective provisions of the ESIA and ESMP included in the bidding package for the selection of borrow pits. | No
24 | 160 | Section IX – Particular Conditions of Contract Part B – Special Provisions Sub-Clause 4.1 | ……… “The Contractor shall provide relevant contract-related information, as the Employer and/or Engineer may reasonably request to conduct Stakeholder engagements. “Stakeholder” refers to individuals or groups who: (i) are affected or likely to be affected by the Contract; and (ii) may have an interest in the Contract. The Contractor shall also directly participate in Stakeholder engagements, as the Employer and/or Engineer may reasonably request. …... a) Please clarify the scope and extent of Stakeholder engagements and what exactly will be the role of the Contractor in “participating the Stakeholder engagaments”. b) We also request the Employer to clarify how will the likely additional time and cost incurred by the Contractor for complying with such stakeholder engagements be reimbursed. | Clarification No.4, Answer No. 106 has been updated as below: Please refer to project's SEP (heading "5. STAKEHOLDER ENGAGEMENT PROGRAM AND METHODS" and heading "6. ROLES AND RESPONSIBILITIES FOR IMPLEMENTING STAKEHOLDER ENGAGEMENT ACTIVITIES". The Contractor shall consult regularly with the project affected communities about grievance mechanism, construction works and schedule, community health and safety. In addition, the Contractor shall carry out day-to-day liaison activities. During the course of ongoing operations conducted by the Contractor, a Social Expert and Comunity Liaison Officers to be employed in the project remain actively engaged in monitoring and evaluating social impacts and outcomes. | No
25 | 160 | Section IX - Particular Conditions of the Contract Part - B Spcial Provisions, Sub-Clause 4.1 Clarification No.3 Addendum No.4 Amendment No.26 | The Employer is kindly requested to clarify whether he has already applied for the permit for the existing railway alignment design from DSI with regard to the Burnaz Springs Protected Area, and from the Ministry of Culture with regard to cultural heritage sites - ancient City of Issos, Isus waterway and historical Erzin train station. If yes, what is the estimated timeline for recovery of such permit ? | Clarification No.4, Answer No. 187 has been updated as below: The Employer has successfully submitted applications for both permits and has made significant progress. As a result of consultations with the permitting authorities, it was determined that the disclosure of technical details is necessary to facilitate the acquisition of permits. In order to finalize and obtain the necessary permits, the Employer will follow up with DSI to seek its agreement with the currently proposed design of the section crossing the Burnaz Springs protected area. The start of mobilizaiton and civil works will be subject of availability of such permit/agreement from DSI. | No
26 | - | - | Kindly confirm whether the depot area shown in the below image is free of charge or not. | Clarification No.4, Answer No. 189 has been updated as below: Bidders shall carry out their own study related to potential depot/logistic areas, in accordance with the provisions of the ESIA, ESMP and sub-management plans included in the bidding documents. | No

## ADDENDUM No.7
PROJECT NAME AND LOAN NO:
RAIL LOGISTICS IMPROVEMENT PROJECT - 91450 TR
TITLE OF WORKS AND RFB NO:
Construction Works for Branching Railway Lines to the industrial facilities at the Cukurova Region, Yumurtalik Free Zone and the Ports at the Iskenderun Bay AYGM-YAP-2023-WB 02
ADDENDUM NO: 7
The provisions of this Addendum and its attachments are being issued to modify or amend certain provisions of the Request for Bids (RFB) document as a result of changing circumstances or additional information being available from the Employer or in response to the queries raised by the Bidders.The RFB document is hereby amended as below:
Serial No. | RFB Document Page No. | RFB Document Reference Clause | Clause in the Original RFB Document | Amended Clause
1 | - | Section VII - Employer's Requirements Specification Drawings | CKR-AYGM-JEO-GZG-001-K-00 & CKR-AYGM-JEO-GZG-002-K-00 | The drawings are replaced with the updated drawings listed below and attached to this CKR-AYGM-JEO-GZG-002-K-00: Geological and Geotechnical Plan Itenary CKR-AYGM-JEO-GZG-002-K-00 : Geolojik Geoteknik Plan Itenerer